## README
Toowoomba to Warwick Pipeline — Master Asset Register
Consolidated from three source registers. Chainage is the primary key: every record is positioned by Chainage Start (m).
Source registers
Source file | Sheet used | Chainage field(s) | Valid records loaded
Thrust Block Register - T2W_PIPELINE 24-8.xlsm | Master Register - LandPartners | KP | 255
Trench Type Register - T2W_PIPELINE.xlsm | Master Register Trench Type | KP (START) / KP (END) | 207
Trench&Bulkheads- T2W_PIPELINE.xlsm | Master Register - LandPartners | KP | 452
Forreign service raw data.xlsx | Sheet1 | KP | 334
PHw_PWG_Creek_Crossings.xlsx | PHw + PWG | Start Chainage (m) / End Chainage (m) | 32
T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | PHW + PWG | Start Ch. (m) / End Ch. (m) | 489
T2W - Tree Removal TakeOff (V.1).xlsx | Sheet1 | Start Chainage / End Chainage (km) | 91
TOTAL |  |  | 1450
Sheets in this workbook
Master Register | All records in one table, sorted by Pipeline Section then Chainage Start (m). One row per source row.
Edit Log | Changes made through the HTML editor, appended automatically with who, when and the previous value.
Data Quality | Every edit made during consolidation and every anomaly found, with the source row it came from.
Chainage Index | Record counts per 1 km chainage bin per register — live COUNTIFS over Master Register.
Trench Type Summary | Total length and section count by trench type, carried across from the Trench Type Register.
Src - Thrust Block | Unmodified source rows (Thrust Block Register).
Src - Trench Type | Unmodified source rows (Trench Type Register).
Src - Trench Stop & BH | Unmodified source rows (Trench & Bulkheads Register).
Src - Creek Crossings | Trenched creek crossing rows, PHw and PWG tables combined.
Src - Road & Rail Xings | Road, rail, carpark and protected-tree crossings from schedule T2WRWP-05304-PTW-PPG-SCH-00002 Rev 0.
Src - Foreign Service | Foreign service rows with the derived Utility Type / Operator / Size / Info Source columns beside the raw description.
Progress Control | The two fronts. Pipe chainage is typed here and nowhere else; trench chainage is derived from Cost Tracker - Linear. Everything chainage-driven in the workbook reads this sheet.
Cost Tracker - Pipe | One row per pipe segment, all 409. Laid metres, percentage, budget and earned value derived from the pipe front. Nothing on it is typed.
Rate Library | Every unit rate in one place — trench $/m by pipeline section and trench type, pipe $/m per pipe asset, point assets $/item. The only sheet where a rate is typed.
Plant and Labour Rates | Hourly cost, and optional dayworks charge, for every resource recorded at end of day.
Cost Tracker - Linear | One row per trench section. Trench and pipe progress entered in metres; budget and earned value calculated from Rate Library.
Cost Dashboard | Live roll-up of budget, earned value and remaining cost — by section and trench type, by pipe asset, and for point assets.
Thrust Block Costing | Every thrust block by section and type: counts, rate, budget, blocks complete and earned value. All live from the Master Register and Rate Library.
Daily Progress | One row per section per day from the End of day page: chainage reached, metres for the day, assets ticked, earned value, weather, downtime, notes. Append only.
Daily Plant and Labour | One row per resource per day: type, description, number, worked hours, standby hours.
Daily Safety | One row per day: toolbox talk and topic, personnel on site, incident class and detail, lost time.
Daily Hold Points | One row per hold point movement: reference, description, status, and the record it belongs to.
Daily Profit | One row per day: earned, direct cost, plant and labour, profit and margin.
Daily Progress | One row per section per day from the End of day page: chainage reached, metres for the day, assets ticked, earned value, weather, downtime, notes. Append only.
Asset ID codes assigned by this consolidation
Format {SECTION}-{TYPE}-{NNNN}, matching the existing PHW-TS / PHW-BS / PPH-TB convention. Numbering restarts at 0001 for each section and each type, ascending by chainage; where several records share a chainage the original source row order is preserved. These IDs are NEW - they do not appear in the source files.
Code | Meaning | Register | Assigned
EL | Electricity | Foreign Service | 98
CM | Communications | Foreign Service | 104
WA | Water | Foreign Service | 39
RW | Water - recycled | Foreign Service | 1
SW | Sewer | Foreign Service | 17
DR | Drainage | Foreign Service | 6
GA | Gas | Foreign Service | 5
OI | Oil | Foreign Service | 1
FN | Fence | Foreign Service | 56
CC | Trenched creek crossing | Creek Crossing | 32
RD | Road crossing (major or minor) | Road & Rail Crossing | 33
RL | Rail crossing | Road & Rail Crossing | 3
CP | Carpark / side lane | Road & Rail Crossing | 4
PT | Significant protected trees | Road & Rail Crossing | 2
- | Survey level - no ID assigned | Foreign Service | 7
TOTAL ASSIGNED |  |  | 241
Assumptions and treatment of source data
• | Header row is row 5 in every source sheet; data starts at row 6. Confirmed in all three files.
• | A record is kept only where the chainage-start cell holds a number. This excludes the colour legend / dropdown block that sits below the data (rows 294-304) in the Thrust Block and Trench Type sheets.
• | Chainage is in METRES in all three registers despite the "KP" column label (observed ranges 0-27,012). No unit conversion applied.
• | Pipeline Section is derived from the Asset ID prefix (PHW / PWG / PPH / RHF). Where there is no Asset ID, the source Pipeline Section cell is used if it holds one of those codes; otherwise the record is marked UNASSIGNED. The original cell value is preserved in "Section Ref (source)".
• | In the Trench & Bulkheads register the "Pipeline Section" cell holds a drawing-sheet reference (1.1, 9.1 ...), not a section code. It is kept in "Section Ref (source)" only.
• | Trench Type records carry a chainage range (start and end); Thrust Block, Trench Stop and Bulkhead records are point assets and have a start only, so their Length (m) is blank.
• | Length (m) is calculated (End - Start), not copied. "Source Length (m)" holds the value stated in the Trench Type Register so the two can be compared.
• | "Comments" merges the source Comments column with the "Notes , Not on Plan" column from the Trench & Bulkheads register.
• | The RHF section of the Thrust Block Register (13 records, RHF-TB-001 to RHF-TB-013) has no chainage entered in the source. Those records are retained and sort to the end of the Master Register with a blank Chainage Start. See the Data Quality sheet.
• | ASSET IDs ASSIGNED: the foreign service source file carried no asset identifier, so 327 IDs were generated on the convention set out above. They are NEW, created here, and are not present in the source file. The 7 survey-level records were deliberately left without an ID. No generated ID collides with an existing PHW-TS, PHW-BS, PPH-TB or RHF-TB identifier.
• | FOREIGN SERVICES: the raw file gives only Pipeline, Drawing Number, KP, Utility Description, Included in Current Plan and Comments. Utility Description is free text, so four columns are DERIVED from it and are not source data: Asset Type (utility category), Operator (asset owner), Size (mm) (parsed from the DN value) and Info Source (the BYDA / PUP prefix). The raw description is kept verbatim in Utility Description so every derivation can be checked.
• | Operator for foreign services is read from the description and, where the description is silent, from the Comments text — the three APA Group gas records are identified that way. Spelling variants in the source (BDYA, BYD, TELSTA, TELSTRACOMMS, TELSTRA COMS) are treated as BYDA and Telstra respectively; the misspellings are left untouched in the raw description and listed on the Data Quality sheet.
• | Foreign services are point crossings and carry a chainage start only, so their Length (m) is blank. Their chainage is a whole number of metres in the source.
• | RECORD KEY is the stable identifier for every row and the field the HTML editor and the Edit Log address. 974 keys are the Asset IDs already in the source registers; 214 were generated because the source had none - 102 PHW and 105 PWG trench sections (TT) and 7 survey levels (SL). No generated key collides with an existing identifier. Asset ID itself is unchanged and is still blank on those 214.
• | Source File and Source Row on every record point back to the exact originating cell range, so nothing here is untraceable.
• | The source workbooks are macro-enabled (.xlsm). This consolidation is a plain .xlsx; no macros were carried across.
• | RESIDUAL DATA REMOVED: all three source files are built on a template from the Jemena Port Kembla pipeline (revision BRRK7728-NCP-8-4, dated 03-Dec-2022) and still contain 8-9 rows of that project's survey data. Its coordinates sit near Port Kembla NSW (E 301,270-301,434 / N 6,184,121-6,184,177), not the T2W corridor. In the Thrust Block Register (rows 305-312) the whole row was foreign and has been removed. In the Trench & Bulkheads Register (rows 309-318) the residue sat in columns E-L on top of nine genuine T2W trench-stop records, so only those cells were cleared and the assets kept. Every instance is itemised on the Data Quality sheet.
• | CONSEQUENCE: the survey block (Located, C&G, TRENCH, Surveyors PtNo, E, N, Z, Survey Code, Actual Chainage) holds NO genuine T2W data in any of the three registers. Those columns are retained but empty, ready for as-built survey to be entered.
Rev 2 — 24 Aug 2026
• | The Trench & Bulkheads source was reissued 2026-08-17. 37 new PWG records (PWG-TS-0001 to PWG-TS-0036 and PWG-BS-0001) were loaded; no existing record changed and none was removed. Src - Trench Stop & BH now reflects the 2026-08-17 source; the previous load is preserved in _backups.
• | TREE REMOVAL added as a seventh register, code VG, Register = "Vegetation". 91 of the takeoff's 222 records were loaded — the PHW (70) and PWG (21) sections. PAE, PLG, PLE and PEL are not sections of this register and were held back; all 222 rows are on Src - Tree Removal.
• | Tree chainage is stated in KILOMETRES in the takeoff and has been converted to metres, the unit used everywhere else in this workbook. Two columns were added to the Master Register for this register: Area (m2) and Timber Density (HEAVY / LIGHT / TRIM).
• | Tree record keys are NEW, assigned here on the {SECTION}-VG-{NNNN} convention ascending by source row. The takeoff's own Pipe ID (VEG_PHW001 ...) is kept in Asset ID.
Rev 3 — 24 Aug 2026
• | The Thrust Block Register was reissued 24-8 with 134 further thrust blocks: PWG-TB-026 to PWG-TB-134 and PHW-TB-077 to PHW-TB-101. None of the 121 records already held changed. Src - Thrust Block now reflects the 24-8 source; the previous load is preserved in _backups.
• | THRUST BLOCK CATEGORY is a new column in that source and a new column here. It classifies every thrust block as Bend, Tee, Isolation Valve, Pigging Station, In-Line or Facility (RHF). It was populated for all 255 thrust blocks, so the 121 already held gained a value they did not have before.
• | The 13 RHF thrust blocks are now identified as "Facility (RHF) - not in pipeline index". Their blank chainage is correct, not missing: they sit in the Regional Header Facility and are not positioned on the pipeline. The gap flagged at baseline is closed.
Rev 4 — 24 Aug 2026
• | UNIT RATES. Unit Rate ($), Quantity, Unit and Total Cost ($) added to the Master Register. Total Cost is a formula, not a typed number.
• | Rated so far: trench stops $1,112.50 each (442) and concrete bulkheads $20,507.00 each (47), $1,455,554.00 in total. Rates supplied by J. Krasnoff-Hnatjuk, 24 Aug 2026; item detail on C-DWG-PTW-105.1 Rev 1, Issued for Construction.
• | The $1,112.50 rate is PER TRENCH STOP, not per metre of trench. Read as a metre rate it would price the 46,169 m of trench at $51.4M instead of $491,725.
• | 961 records carry no rate and are blank, not zero. Any total from this register is therefore partial until the remaining rates are supplied.
Rev 5 — 26 Aug 2026
• | COST TRACKING. Three sheets added: Rate Library, Cost Tracker - Linear and Cost Dashboard. No value on the Master Register was changed and no column was added to it.
• | The Master Register and all seven Src - sheets are now PROTECTED. They read, filter and sort as before but cannot be typed into, which makes the Master Register a lookup source: Cost Tracker - Linear finds each record by Record Key and reads its chainage, length and trench type. To edit the register: Review > Unprotect Sheet (no password), make the change, log it, protect it again.
• | Cost Tracker - Linear carries all 207 trench sections. Progress is entered as METRES COMPLETE against the section length — separately for trench and for pipe, because they are different activities at different rates over the same chainage. Percentage complete is derived from the metres, never typed.
• | TRENCH RATES ARE SPLIT BY PIPELINE SECTION: 22 rate lines, the 11 trench types in PHW and the same 11 in PWG, because the construction differs between the two. A rate against PHW 1A does not affect PWG 1A. One of the 22 combinations, PHW 4&6, has no trench sections in the register and needs no rate; the other 21 do. Sections in register on Rate Library shows the count for each.
• | PIPE IS FOUR SEPARATE ASSETS, held individually because the diameters differ: PHW DICL DN600, PHW MSCL OD660, PWG DICL DN375, PWG MSCL OD457. Descriptions are taken from Pipe Description on the Master Register. Pipe Type is chosen per trench section from a dropdown; a blank Pipe Type prices no pipe, and the unassigned length is reported on Cost Dashboard.
• | These four pipe lines are TEST ENTRIES: the structure is real and proven, but no pipe rate has been supplied, so every rate cell is blank.
• | Rates live only on Rate Library. Change a rate there and every budget, earned value and dashboard figure that uses it recalculates. No rate is typed on the tracker.
• | No trench or pipe rate has been supplied yet, so all linear budgets read blank rather than zero. The numbers needed to price the whole 46,169 m are 21 live trench live trench section/type rates and 4 pipe rates.
• | Point assets stay where they are: priced per item on the Master Register in Unit Rate ($) / Quantity / Total Cost ($), and rolled up separately on Cost Dashboard so no cost is counted twice. The $1,112.50 trench stop and $20,507.00 bulkhead rates from Rev 4 are restated on Rate Library Table 3 for visibility only.
Rev 5.2 — 27 Aug 2026
• | THRUST BLOCKS PRICED PER TYPE. Rate Library Table 4 added: every thrust block type in each pipeline section gets its own rate per block, because a Type 7 bend and a Type 12 isolation valve block are not the same item.
• | New sheet Thrust Block Costing: PHW and PWG shown separately, each type with its record count, block count, rate, budget, blocks complete and earned value. PPH and RHF are listed apart as off-alignment.
• | On the Master Register, all 255 thrust block records now carry Quantity (blocks), Unit (each), a Unit Rate formula reading Rate Library Table 4, and the standard Total Cost formula — the same pattern as trench stops.
• | A record reading "2 x Type 12" holds Quantity 2. There are 255 thrust block records but 260 blocks.
• | No rate has been supplied yet, so every thrust block budget reads blank rather than zero.
Rev 5.3 — 27 Aug 2026
• | THRUST BLOCKS POPULATED FROM THE INDEX DRAWINGS. S-DWG-PTW-115, 116, 117 and 118 (Issued for Construction) were read and matched to the register on pipeline section and chainage. All 242 on-alignment thrust blocks matched exactly — no chainage differed by so much as a millimetre.
• | CORRECTION: 72 of those 242 records held the wrong thrust block type. In PHW the column was shifted by one row, so a record carried the type belonging to the next block down the line. Types now come from the drawings. Every change is in the Edit Log with its before and after.
• | Eight columns added at the end of the Master Register: Fitting Type, Type of Bend, Fitting Material, Fitting DN (mm), Max Test Pressure (kPa), Allowable Lateral Bearing (kPa), Thrust Block Item and Design Source. Nothing to the left of them moved.
• | Rate Library Table 4 rebuilt and split: grouped by thrust block type, with a line for each fitting within it — 31 lines in PHW, 24 in PWG. A Type 4 on a 45 deg DICL bend prices apart from a Type 4 on a mitred MSCL bend.
• | Thrust Block Costing rebuilt to match, PHW and PWG separately, grouped by type.
• | The 13 RHF thrust blocks are not in the index — note 4 on the drawings excludes facilities packages — so they carry no type or fitting and are counted separately.
• | The index also lists 5 PPH thrust blocks (2 tees, 2 isolation valves, 1 more) that are NOT in this register. PPH is a separate package; raise it if they should be here.
Rev 5.4 — 27 Aug 2026
• | DAILY PROGRESS sheet added, with an End of day page in the front end that writes to it. One row per section per day: chainage reached for trench and pipe, metres for the day, point assets ticked, earned value, weather, downtime and notes.
• | Append only. A day is a statement of what was reported, so a correction is a later row, not an overtype. The same save also updates Cost Tracker - Linear and the Complete column on the Master Register, so the cost position and the day log never disagree.
• | The End of day page carries yesterday forward: the chainage each section had reached is shown, and only the new figure is typed. Point assets between the two chainages are listed for ticking.
Rev 5.4 — 27 Aug 2026
• | DAILY PROGRESS sheet added, with an End of day page in the front end that writes to it. One row per section per day: chainage reached for trench and pipe, metres for the day, point assets ticked, earned value, weather, downtime and notes.
• | Append only. A day is a statement of what was reported, so a correction is a later row, not an overtype. The same save also updates Cost Tracker - Linear and the Complete column on the Master Register, so the cost position and the day log never disagree.
• | The End of day page carries yesterday forward: the chainage each section had reached is shown, and only the new figure is typed. Point assets between the two chainages are listed for ticking.
Rev 5.5 — 27 Aug 2026
• | THREE SHEETS ADDED for the End of day page: Daily Plant and Labour, Daily Safety and Daily Hold Points. All append only, all written by the same save as Daily Progress.
• | Plant and labour is carried forward day to day. Yesterday’s crew and plant appear already filled in with their hours, so a day the same as the one before takes no typing.
• | Hold points left Outstanding carry forward too, and keep appearing until a day records them Released.
• | The End of day page can also print the day as a one-page report, or copy it as text to paste into an email.
Rev 5.6 — 27 Aug 2026
• | FIX: rates typed as "=114663" were constants written as formulas. Excel showed them correctly, but every other tool reads cached values, and a cached value is dropped whenever the file is rewritten by anything but Excel — so the front end saw those 44 thrust block rates as blank. They are now plain numbers. Genuine formulas were left untouched.
• | FIX: the Cost Dashboard point-asset budget returned a VALUE error in Excel, and took PROJECT TOTAL with it. The formula used SUMPRODUCT(N(range)...), and N() will not accept an array holding text — which is what Unit Rate became once thrust blocks were priced by formula. It now sums Total Cost, which already guards itself. LibreOffice tolerated the old formula, which is why it was not caught earlier.
• | SETTINGS sheet added, so the workbook carries what the front end remembers rather than the browser alone. Recorded By, the default shift and weather, the default shift hours, the file and backup folder names, the pipe type per section, and a standing plant and labour list.
• | Opening the workbook reads it; saving writes back the parts the page owns. Move the file to another machine and the page starts configured.
• | The project folder cannot be remembered in the file — a browser only accepts a folder a person picks, never a path read from a document. The folder name is recorded as a reminder of which one to choose.
Rev 5.7 — 27 Aug 2026
• | COST BESIDE CHARGE. Every rate table on Rate Library now carries a Cost Rate next to its Rate, with Margin and Margin % calculated beside it. Rate is what the client is charged; Cost Rate is what it costs us. 148 rate lines across trench, pipe, point assets and thrust blocks.
• | PLANT AND LABOUR RATES sheet added: an hourly cost for every resource the End of day page records, plus an optional charge rate for dayworks. The day’s plant and labour cost is worked out from these.
• | DAILY PROGRESS gained Our Cost Today and Gross Margin Today, so a section row shows its own margin before plant and labour.
• | DAILY PROFIT sheet added: one row per day with Earned, Direct Cost, Plant and Labour, Total Cost, Profit and Margin %. Profit = Earned minus Direct Cost minus Plant and Labour.
• | The End of day page shows the same figures live as the day is entered, so the profit is visible before the day is saved rather than after.
Rev 5.8 — 28 Aug 2026
• | FIX — STALE LOOKUP RANGES. Every cost formula addressed Master Register rows 2:1638. Adding the pipe, bend and valve registers took the register to row 2200, and because the new records were inserted in chainage order rather than appended, 562 existing records were pushed past the end of every range. 52 of the 207 trench sections (PWG-TT-0054 onward) returned a failed MATCH and carried no length, rate or budget at all — 18,546.7 m and about $7.13M of trench. 29 trench stops and 103 thrust blocks were also outside their ranges. All Master Register ranges now run to row 2600, leaving room for another 400 records.
• | FIX — DRAWING LOOKUP. The Drawing (Start) array formula searched rows 2:1451 for the trench section covering a chainage, so 223 of the newly added PWG records (173 pipe, 30 bend, 20 valve) returned no-match errors. Same stale-range fault, same fix: the ranges now run to 2600 and every cell resolves.
• | CONSEQUENCE OF THOSE TWO FIXES: Cost Dashboard PROJECT TOTAL was reading $18,118,086. It now reads $36,858,200 — $20.71M trench (was $13.58M), $10.80M pipe (was $0.16M) and $5.35M point assets (was $4.38M). Nothing was re-rated; the money was always there, the formulas just could not see it.
• | PROGRESS CONTROL sheet added. It holds the two fronts that drive the whole register, one row per pipeline section. The PIPE front is the only progress figure typed anywhere in this workbook. The TRENCH front is not typed at all — it is derived from Trench Complete (m) on Cost Tracker - Linear as the front of CONTINUOUS completed trench, so a section finished out of sequence does not move it and a gap left behind holds it back.
• | The pipe register is what makes this work. It is continuous: PHW runs 0 to 19,156.739 m across 200 segments and PWG 0 to 27,012.465 m across 209, with no gaps, no overlaps, and the same end chainage as the trench register. One number per section therefore determines every segment and every asset behind it.
• | COST TRACKER - PIPE sheet added: all 409 pipe segments, one row each, in chainage order. Nothing on it is typed. Laid (m) is MIN(MAX(front - segment start, 0), segment length), so a segment wholly behind the front reads 100%, the segment the front sits inside reads part, and everything ahead reads zero.
• | Pipe Type is now read from each segment’s own Pipe Description rather than chosen by hand against a trench section. Every metre of the 46,169 m is therefore priced against the right pipe, and the "trench length with no pipe type chosen" gap is closed. This is why the pipe budget moved from $158,761 to $10,799,585.
• | AUTO COMPLETE. Four columns added at the end of the Master Register: Completion Driver, Front Chainage (m), Auto Complete and Auto Complete As At. Completion Driver is PIPE for the Bend and Valve registers and TRENCH for thrust blocks, trench stops, bulkheads, creek crossings, road and rail crossings and vegetation. Auto Complete reads YES once the driving front has passed the record’s chainage. Type one chainage and every asset behind it follows.
• | Bends and valves follow the PIPE front on Jerry’s instruction, 27 Aug 2026: a bend or a valve is installed as part of pipelay, not with the trench. Everything else keeps the TRENCH front it already had, so no existing behaviour changed.
• | Auto Complete does NOT overwrite Complete (BR) or Completion Date (BS). Those stay the manual, front-end-written fields. Auto Complete is the derived view beside them, so the two can be compared and a genuine exception — an asset the front has passed but which is not actually finished — stays visible instead of being papered over.
• | RATE LIBRARY TABLE 5 — BENDS. 10 rate lines, 5 per pipeline section, covering all 211 bends. DICL bends are the three standard design angles (11.25, 22.5 and 45 deg); every other angle is a mitred MSCL bend priced by CUT COUNT, which is how the schedule of rates already prices them (the ...10a / 10b / 10c items each cover a band of angles). The cut boundary is 12 deg: Table 4 records 1 cut for every mitred bend up to 10.6 deg and 2 cuts for every one from 13.9 deg up, so 12 sits inside the gap and no existing block is reclassified.
• | FITTING MATERIAL AND FITTING DN DERIVED for all 211 bends on that same standard-angle rule, and checked against the 155 bends that sit at the exact chainage of a thrust block: 138 of 138 standard-angle bends are DICL there and 14 of 14 non-standard are MSCL, with no exceptions. DN follows the section: DICL 600 in PHW and 375 in PWG, MSCL 650 and 450.
• | RATE LIBRARY TABLE 6 — VALVES. 20 rate lines, section by valve class by valve type, covering all 129 valves.
• | DOUBLE-COUNT WARNING, recorded because it is easy to trip over. Isolation valves and pigging stations ALSO carry a thrust block on Table 4, one for one: 5 PHW and 6 PWG isolation valves and 2 PHW and 3 PWG pigging stations, matching exactly. 145 of the 211 bends likewise sit at the exact chainage of a bend thrust block. Jerry confirmed 27 Aug 2026 that the Table 4 rate is the block only and does not include the fitting, so both are billed — but if a rate is ever supplied that covers the whole assembly, enter it once and leave the other line blank.
• | NO BEND OR VALVE RATE HAS BEEN SUPPLIED, so all 30 new rate lines are blank and every bend and valve budget reads blank rather than zero, exactly as an unpriced trench type does. Air valves (69) and scour valves (44) are the two that were carrying no cost anywhere in the workbook at all.
• | On the Master Register all 211 bends and 129 valves now carry Quantity 1, Unit "each", a Unit Rate formula reading Table 5 or Table 6, and the standard Total Cost formula — the same pattern as trench stops and thrust blocks.
• | COST DASHBOARD. Pipe now reads Cost Tracker - Pipe instead of the pipe columns on Cost Tracker - Linear. The point-asset table gained a Driver column, a Complete column and an Earned column, plus lines for bends and valves; those two are counted on Register rather than Asset Type, because a bend is HOR, VERT or COMPOUND and a valve is AV, SCV, IV or PIG.
• | The pipe columns on Cost Tracker - Linear (N to S) are SUPERSEDED. They are left in place so the End of day page keeps working unchanged, but they no longer feed any total on Cost Dashboard.
• | STILL TO DO: the End of day page lists point assets from a fixed list of nine asset types and drives all of them off the trench chainage. It does not yet know about bends or valves and does not yet read the pipe front. Until it is updated, book the pipe front on Progress Control and the page will keep behaving as it did.

## Document Control
Document Control
This workbook is the controlled master asset register for the Toowoomba to Warwick pipeline. It is a living document: it is updated in place and never re-created from scratch.
Register identity
Document title | T2W Pipeline Master Asset Register
File name | T2W Pipeline Master Asset Register.xlsx
Controlled location | C:\Users\J.Krasnoff-Hnatjuk\Desktop\T2W_PL\CLAUDE FOLDER\Rev 2
Document owner | Jerry Krasnoff-Hnatjuk (j.krasnoff-hnatjuk@nacap.com.au)
Current revision | Rev 5.7
Revision date | 27 Aug 2026
Status | Live — under continuous update
Records in Master Register | 1450
Backups | _backups\ — dated copy written before every editing session
How this register is kept up to date
1. Single file | There is one canonical file, at the controlled location above. It is opened, edited and saved in place. Nothing is copied to a new name or a new folder.
2. Backup first | Before any editing session a dated copy of the current file is written to _backups\. Any change can be rolled back to the previous state.
3. Edits by record key | Every change is addressed by Record Key, the stable identifier on every row of the Master Register. Asset ID is not used to address rows because 214 rows have none.
4. Every change logged | Each field change writes one row to the Edit Log: timestamp, who made it, record key, asset ID, field, previous value, new value and the sheet cell touched. No change is made without a log entry.
5. Source sheets frozen | The six Src - sheets are never edited. They remain the verbatim record of what each source file said, so any Master Register value can always be checked against origin.
6. Revision on close | At the end of a session in which the data changed, the revision number above is bumped and a line is added to the revision history below summarising what changed.
7. Derived fields | Length (m), Pipeline Section, Asset Type, Operator, Size (mm) and Info Source are derived, not source data. If a driving value is edited, the derived field is recalculated with it.
8. New records | New assets are appended with a Record Key following the {SECTION}-{TYPE}-{NNNN} convention, the next free number for that section and type. Source File is set to the file or instruction that introduced the record so it stays traceable.
9. Rates in one place | Unit rates are entered on Rate Library and nowhere else. A cost figure is never typed over: if it is wrong, the rate or the metres complete behind it is corrected. Trench rates are held per pipeline section and pipe rates per pipe asset, so a rate is never applied to work it was not priced for. Every rate carries who supplied it and when.
Revision history
Revision | Date | Description of change | Records affected | Issued by
Rev 1 | 24 Aug 2026 | Register placed under document control. Baseline consolidation of six source registers (1,188 records). No data values changed. | 1188 (baseline) | J. Krasnoff-Hnatjuk
Rev 2 | 24 Aug 2026 | Trench & Bulkheads source reissued 2026-08-17: 37 new PWG trench stops and bulkheads loaded. Tree Removal TakeOff (V.1) added as a new Vegetation register: 91 PHW and PWG records, chainage converted from km to m. Two columns added (Area (m2), Timber Density). No existing value changed. | 128 added (1,188 to 1,316) | J. Krasnoff-Hnatjuk
Rev 3 | 24 Aug 2026 | Thrust Block Register reissued 24-8: 134 new thrust blocks loaded (109 PWG, 25 PHW). New source column Thrust Block Category added and populated for all 255 thrust blocks, including 121 backfilled onto records already held. The 13 RHF records are confirmed as facility blocks with no pipeline chainage. No previously held value was overwritten. | 134 added (1,316 to 1450); 121 enriched | J. Krasnoff-Hnatjuk
Rev 4 | 24 Aug 2026 | Unit rates introduced. Four columns added: Unit Rate ($), Quantity, Unit and Total Cost ($). 442 trench stops rated at $1,112.50 each and 47 bulkheads at $20,507.00 each, $1,455,554.00 in total. All other assets left blank pending rates. No existing value changed. | 489 rated, 961 left blank | J. Krasnoff-Hnatjuk
Rev 5 | 26 Aug 2026 | Cost tracking introduced. Rate Library, Cost Tracker - Linear (207 trench sections, trench and pipe progress in metres) and Cost Dashboard added. Trench rates split by pipeline section (22 lines) and pipe set up as four individual assets (PHW DICL DN600, PHW MSCL OD660, PWG DICL DN375, PWG MSCL OD457). Master Register and all Src - sheets protected so the register serves as a locked lookup source. No Master Register value changed; no column added to it. No trench or pipe rate supplied yet — all blank. | 207 trench sections tracked; 4 pipe assets defined; 0 rated | J. Krasnoff-Hnatjuk
Rev 5.2 | 27 Aug 2026 | Thrust blocks priced per type. Rate Library Table 4 added (section x type, rate per block); new Thrust Block Costing sheet splitting PHW and PWG; all 255 thrust block records given Quantity, Unit, a Unit Rate lookup and the Total Cost formula. 260 blocks across 255 records. No rate supplied yet. | 255 records / 260 blocks; 0 rated | J. Krasnoff-Hnatjuk
Rev 5.3 | 27 Aug 2026 | Thrust blocks populated from index drawings S-DWG-PTW-115 to 118: fitting type, bend angle, material, DN, test pressure and bearing capacity added (8 new columns at the end). 72 thrust block types corrected against the drawings and logged. Rate Library Table 4 split by type and fitting; Thrust Block Costing rebuilt. | 242 populated, 72 corrected, 55 rate lines | J. Krasnoff-Hnatjuk
Rev 5.4 | 27 Aug 2026 | Daily Progress sheet added (append only) and an End of day page added to the front end that writes to it, alongside the existing writes to Cost Tracker - Linear and the Master Register Complete column. No existing value changed. | 1 sheet added | J. Krasnoff-Hnatjuk
Rev 5.4 | 27 Aug 2026 | Daily Progress sheet added (append only) and an End of day page added to the front end that writes to it, alongside the existing writes to Cost Tracker - Linear and the Master Register Complete column. No existing value changed. | 1 sheet added | J. Krasnoff-Hnatjuk
Rev 5.5 | 27 Aug 2026 | Daily Plant and Labour, Daily Safety and Daily Hold Points sheets added (append only) and the End of day page extended to capture them, with a printable daily report. No existing value changed. | 3 sheets added | J. Krasnoff-Hnatjuk
Rev 5.6 | 27 Aug 2026 | Settings sheet added so the front end reads its own configuration from the workbook: Recorded By, day defaults, file and backup folder names, pipe types and a standing plant and labour list. No existing value changed. | 1 sheet added | J. Krasnoff-Hnatjuk
Rev 5.7 | 27 Aug 2026 | Cost rates added beside charge rates on every Rate Library table, with margin calculated. Plant and Labour Rates sheet added. Daily Progress gained Our Cost and Gross Margin. Daily Profit sheet added for the day-level bottom line. No existing rate changed. | 2 sheets added, 148 cost lines | J. Krasnoff-Hnatjuk

## Settings
Settings
What the front end remembers. It reads this sheet when the workbook is opened, so a new machine or a fresh browser starts where the last one left off instead of blank.
EDIT ONLY THE YELLOW CELLS. The page writes back to them when you save, so a value typed here and a value set on the page end up the same either way.
Preferences
Setting | Value | What it does
Recorded By | Jerry KH | Fills in your name on the End of day page and in the Edit Log, so it is not typed every day.
Default Shift | Day | Which shift the End of day page starts on.
Default Weather | Fine | Which weather the End of day page starts on.
Default Shift Hours | 10 | The hours a new plant or labour row starts with.
Workbook File Name | T2W_Pipeline_Master_Asset_Register.xlsx | The file the page saves back into when a project folder is set.
Backups Folder | backups | The folder inside the project folder that timestamped copies go into.
Project Folder (last used) | t2w-asset-register_rev2 | A note of where the register was last opened from. A browser cannot be handed a path for security, so the folder still has to be picked once per browser — this is a reminder of which one.
Pipe Type PHW | DICL | Which pipe the cost view prices PHW against until a section says otherwise.
Pipe Type PWG | DICL | Which pipe the cost view prices PWG against until a section says otherwise.
Standing plant and labour
The crew and plant a day starts with when there is no previous day to carry forward. The End of day page can write the current list back here, so the standing list keeps up with the job.
Type | Description | Number | Default Hours | Notes
Labour | Supervisor | 1 | 10
Labour | Pipe crew | 6 | 10
Plant | Excavator 30t | 1 | 9
Plant | Sideboom | 1 | 9
How this is used
[5 empty] | • | Opening the workbook reads this sheet. A blank Recorded By is left alone rather than overwriting a name already typed into the page.
[5 empty] | • | Saving writes back Recorded By, the two default pipe types and, if you asked for it on the End of day page, the standing plant and labour list.
[5 empty] | • | The project folder itself cannot be stored — a browser will not accept a path from a file, only a folder you pick. The name here is a note to tell you which folder to pick.

## Progress Control
Progress Control — the two fronts that drive everything else
The pipe front is the ONLY progress figure typed on this workbook. Type the chainage the pipelay crew reached and every pipe segment, bend and valve behind it follows.
The trench front is NOT typed. It is derived from Trench Complete (m) on Cost Tracker - Linear as the front of continuous completed trench, so a gap left behind holds it back.
EDIT ONLY THE YELLOW CELLS. Everything else on this sheet, and everything that reads it, is a formula.
Fronts by pipeline section
| Pipeline Section | Section extent (m) | PIPE | TRENCH | As At Date | Updated By | Pipe % | Trench % | Pipe m today | Check
| PHW | 19156.739 | 0 | 0 | 2026-08-28 | Jerry | 0% | 0% | 0 | ok
| PWG | 27012.465 | 0 | 0 | 2026-08-28 | Jerry | 0% | 0% | 0 | ok
| TOTAL | 46169.204 | 0 | 0 |  |  | 0% | 0%
What those fronts have completed
Counted live off Auto Complete on the Master Register. A record is complete when the front named in Completion Driver has passed its chainage.
| Register | Driver | Complete | In register | Complete (%) | Value complete ($)
| Pipe segments | PIPE | 0 | 409 | 0% | 0
| Bends | PIPE | 0 | 211 | 0% | 0
| Valves | PIPE | 0 | 129 | 0% | 0
| Thrust blocks | TRENCH | 0 | 255 | 0% | 0
| Trench stops & bulkheads | TRENCH | 0 | 489 | 0% | 0
| Creek crossings | TRENCH | 0 | 32 | 0% | 0
| Road & rail crossings | TRENCH | 0 | 42 | 0% | 0
| TOTAL |  | 0 | 1567 | 0% | 0
How to book a day
1. Type the chainage the pipelay crew reached into the yellow PIPE cell for that section. Nothing else.
2. Every pipe segment behind it splits itself on Cost Tracker - Pipe: whole segments go to 100%, the one the front sits inside goes to part.
3. Every bend and valve behind it reads YES in Auto Complete on the Master Register, and its value lands in the table above.
4. Thrust blocks, trench stops, bulkheads and crossings stay on the TRENCH front, which is derived from Cost Tracker - Linear and is not typed here.
5. Check reads ok while the pipe front sits at or behind the trench front. Pipe cannot be laid in a trench that is not recorded as dug.

## Master Register
Record Key | Chainage Start (m) | Chainage End (m) | Length (m) | Pipeline Section | Register | Asset Type | Asset ID | Trench Type | Source Length (m) | Drawing (Start) | Drawing (End) | Drawing (superseded) | Info Source | Included in Current Plan | Section Ref (source) | Feature Name | Utility Description | Surface | Pipeline DN | Embankment Treatment | Creek Bed Treatment | Pipe Description | Type 6 (m) | Type 7 (m) | Type 4 & 7 (m) | Type 4 & 6 (m) | Operator | Location | Material | Size (mm) | ID | Actual Chainage (surveyed) | Located | C&G Code | Trench Code | Surveyors PtNo | E | N | Z | Survey Code | Proven to Underside of Service | Test Point | Proposed Crossing Method | Parallel or Crossed | Design Drawing | DBYD SEQ | Separation (m) | Asset DOC (m) | Pipeline DOC (m) | Depth to Underside of Asset (m) | Crossover | Within | Excavation Permit Required? | Excavation Permit Date | Crossing Permit Required? | Crossing Permit Date | Comments | Source File | Source Row | Area (m2) | Timber Density | Thrust Block Category | Installed | Install Date | Installed By | Test Document No | Test Status | Test Date | Complete | Completion Date | Progress Notes | Unit Rate ($) | Quantity | Unit | Total Cost ($) | Fitting Type | Type of Bend | Fitting Material | Fitting DN (mm) | Max Test Pressure (kPa) | Allowable Lateral Bearing (kPa) | Thrust Block Item | Design Source | Valve Type | Crossing Type | Crew | Bend Rate Class | Completion Driver | Front Chainage (m) | Auto Complete | Auto Complete As At
PHW-TT-0001 | 0 | 327.039 | 327.039 | PHW | Trench Type | TRENCH SECTION |  | 1A | 327.039 | D-DWG-PHW-001.2 | D-DWG-PHW-001.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 6
PHW-PIPE-0001 | 0 | 150 | 150 | PHW | Pipe | PIPE | PHW-PIPE-0001 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-VG-0001 | 10 | 20 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW001 | [49 empty] | 1 LARGE TREE, MULTIPLE SMALL TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 18 | 195 | HEAVY | [7 empty] | Yes | 2026-08-28 | [17 empty] | TRENCH | 0 | NO
PHW-FN-0001 | 15 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0001 |  |  | D-DWG-PHW-001.2 |  | D-DWG-PHW-001_C |  | Yes | PHW |  | FENCE LINE NO POSTS | [40 empty] | Forreign service raw data.xlsx | 2
PHW-TB-001 | 18.832 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-001 | [7 empty] | PHW |  | Type 5 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 13 |  |  | Bend | [6 empty] | Yes | 2026-08-28 |  | 15214 | 1 | each | 15214 | Bend | 22.5+11.25 | DICL | 600 | 1376 | 150 | Bend; 22.5+11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-001 | 18.832 |  |  | PHW | Bend | HOR | PHW-BND-001 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PHW | [53 empty] | Yes | 2026-08-28 |  |  | 1 | each |  | Bend | 22.5° | DICL | 600 | [7 empty] | 22.5 | PIPE | 0 | NO
PHW-CM-0001 | 38 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0001 |  |  | D-DWG-PHW-001.2 |  | D-DWG-PHW-001_C | BYDA | Yes | PHW |  | BYDA TELSTRA COMMSTUD | [9 empty] | Telstra | [30 empty] | Forreign service raw data.xlsx | 3
PHW-CM-0002 | 44 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0002 |  |  | D-DWG-PHW-001.2 |  | D-DWG-PHW-001_C | BYDA | Yes | PHW |  | BYDA TELSTRA COMMSTUD | [9 empty] | Telstra | [30 empty] | Forreign service raw data.xlsx | 4
PHW-VG-0002 | 60 | 200 | 140 | PHW | Vegetation | TREE REMOVAL | VEG_PHW002 | [49 empty] | MULTIPLE SMALL TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 19 | 658 | LIGHT | [7 empty] | Yes | 2026-08-28 | [17 empty] | TRENCH | 0 | NO
PHW-PIPE-0002 | 150 | 225.345 | 75.345 | PHW | Pipe | PIPE | PHW-PIPE-0002 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-AV-001 | 156.3 |  |  | PHW | Valve | AV | PHW-AV-001 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PHW | [53 empty] | Yes | 2026-08-28 |  |  | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-TS-0001 | 188 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0001 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 6 | [9 empty] | Yes | 2026-08-28 |  | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0002 | 197.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0002 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 7 | [9 empty] | Yes | 2026-08-28 |  | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0003 | 206.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0003 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 8 | [9 empty] | Yes | 2026-08-28 |  | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0004 | 216.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0004 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 9 | [9 empty] | Yes | 2026-08-28 |  | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0003 | 225.345 | 236.345 | 11 | PHW | Pipe | PIPE | PHW-PIPE-0003 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Special Crossings
PHW-TS-0005 | 225.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0005 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 10 | [9 empty] | Yes | 2026-08-28 |  | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0006 | 235 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0006 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 11 | [9 empty] | Yes | 2026-08-28 |  | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0004 | 236.345 | 321.539 | 85.194 | PHW | Pipe | PIPE | PHW-PIPE-0004 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-TS-0007 | 244.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0007 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 12 | [9 empty] | Yes | 2026-08-28 |  | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0003 | 250 | 270 | 20 | PHW | Vegetation | TREE REMOVAL | VEG_PHW003 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 20 | 110 | HEAVY | [7 empty] | Yes | 2026-08-28 | [17 empty] | TRENCH | 0 | NO
PHW-TS-0008 | 253.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0008 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 13 | [9 empty] | Yes | 2026-08-28 |  | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0009 | 259 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0009 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 14 | [9 empty] | Yes | 2026-08-28 |  | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0010 | 266.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0010 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 15 | [9 empty] | Yes | 2026-08-28 |  | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0011 | 274 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0011 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 16 | [9 empty] | Yes | 2026-08-28 |  | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0012 | 281.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0012 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 17 | [9 empty] | Yes | 2026-08-28 |  | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0013 | 289 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0013 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 18 | [9 empty] | Yes | 2026-08-28 |  | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0014 | 296.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0014 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 19 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0015 | 304 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0015 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 20 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0016 | 311.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0016 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 21 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0017 | 319 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0017 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 22 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0005 | 321.539 | 327.039 | 5.5 | PHW | Pipe | PIPE | PHW-PIPE-0005 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Trenchless entry | Special Crossings
PHW-TS-0018 | 326.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0018 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 23 | [9 empty] | Yes | 2026-08-28 |  | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PT-0001 | 327.039 | 404.867 | 77.828 | PHW | Road & Rail Crossing | SIGNIFICANT PROTECTED TREES | PHW-PT-0001 |  | 77.828 | [5 empty] | PHW | Trees - Kieman Road |  | N/A | 600 |  |  | OD660x6WT MSCL Sintalock Type 2 PN35 Carrier & OD813x12WT MS Enveloper |  |  |  |  | TRC | [15 empty] | Thrust Boring | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 6 | [28 empty] | TRENCH | 0 | NO
PHW-TT-0002 | 327.039 | 404.862 | 77.823 | PHW | Trench Type | TRENCH SECTION |  | 8A | 77.823 | D-DWG-PHW-001.2 | D-DWG-PHW-001.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 7
PHW-PIPE-0006 | 327.039 | 404.862 | 77.823 | PHW | Pipe | PIPE | PHW-PIPE-0006 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 + OD813 12WT MS Enveloper | [6 empty] | MSCL | 660 | [54 empty] | Trenchless Crossing | Trenchless
PHW-VG-0004 | 330 | 370 | 40 | PHW | Vegetation | TREE REMOVAL | VEG_PHW004 | [49 empty] | 2 LARGE TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 21 | 486 | HEAVY | [7 empty] | Yes | 2026-08-28 | [17 empty] | TRENCH | 0 | NO
PHW-CM-0003 | 361 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0003 |  |  | D-DWG-PHW-001.2 |  | D-DWG-PHW-001_C | BYDA | Yes | PHW |  | BYDA TELSTRA COMMSTUD | [9 empty] | Telstra | [30 empty] | Forreign service raw data.xlsx | 5
PHW-EL-0001 | 364 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0001 |  |  | D-DWG-PHW-001.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 6
PHW-VG-0005 | 380 | 410 | 30 | PHW | Vegetation | TREE REMOVAL | VEG_PHW005 | [49 empty] | 2 LARGE TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 22 | 145 | HEAVY | [7 empty] | Yes | 2026-08-28 | [17 empty] | TRENCH | 0 | NO
PHW-TT-0003 | 404.862 | 426.39 | 21.528 | PHW | Trench Type | TRENCH SECTION |  | 4 | 21.528 | D-DWG-PHW-001.2 | D-DWG-PHW-001.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 8
PHW-PIPE-0007 | 404.862 | 426.39 | 21.528 | PHW | Pipe | PIPE | PHW-PIPE-0007 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-TT-0004 | 426.39 | 878.592 | 452.202 | PHW | Trench Type | TRENCH SECTION |  | 1A | 452.202 | D-DWG-PHW-001.2 | D-DWG-PHW-002.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 9
PHW-PIPE-0008 | 426.39 | 654.13 | 227.74 | PHW | Pipe | PIPE | PHW-PIPE-0008 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-TS-0019 | 448 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0019 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.2 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 24 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0006 | 450 | 460 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW006 | [49 empty] | BRANCHES HANGING OVER PIPE | T2W - Tree Removal TakeOff (V.1).xlsx | 23 | 18.7 | TRIM | [7 empty] | Yes | 2026-08-28 | [17 empty] | TRENCH | 0 | NO
PHW-TS-0020 | 463 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0020 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.3 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 25 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0021 | 471.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0021 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.3 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 26 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0022 | 479.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0022 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.3 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 27 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0023 | 486.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0023 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.4 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 28 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0001 | 492.5 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0001 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.4 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 29 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0024 | 498.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0024 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.4 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 30 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0025 | 505.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0025 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.4 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 31 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0007 | 510 | 530 | 20 | PHW | Vegetation | TREE REMOVAL | VEG_PHW007 | [49 empty] | 3 SMALL TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 24 | 85.9 | TRIM | [26 empty] | TRENCH | 0 | NO
PHW-TS-0026 | 511.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0026 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.4 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 32 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0002 | 518.1 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0002 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.4 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 33 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0027 | 524.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0027 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.4 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 34 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0028 | 531.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0028 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 35 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0003 | 536.1 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0003 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 36 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0008 | 540 | 560 | 20 | PHW | Vegetation | TREE REMOVAL | VEG_PHW008 | [49 empty] | 2 LARGE TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 25 | 147 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-TS-0029 | 541 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0029 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 37 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0030 | 545.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0030 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 38 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0031 | 550.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0031 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 39 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0004 | 553.25 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0004 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 40 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0032 | 555.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0032 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 41 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0033 | 560.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0033 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 42 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0034 | 565.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0034 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 43 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0005 | 570.4 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0005 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 44 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0035 | 575.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0035 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 45 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0036 | 577 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0036 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.6 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 46 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0037 | 582.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0037 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.6 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 47 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0038 | 588.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0038 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.6 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 48 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0039 | 608.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0039 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.7 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 49 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0040 | 618.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0040 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.7 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 50 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0009 | 620 | 640 | 20 | PHW | Vegetation | TREE REMOVAL | VEG_PHW009 | [49 empty] | 1 LARGE TREE, 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 26 | 108 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-TS-0041 | 628.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0041 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.7 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 51 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0042 | 635.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0042 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.8 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 52 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0043 | 642.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0043 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.8 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 53 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0044 | 649.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0044 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.8 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 54 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0009 | 654.13 | 670.63 | 16.5 | PHW | Pipe | PIPE | PHW-PIPE-0009 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Special Crossings
PHW-TS-0045 | 655.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0045 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.8 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 55 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0046 | 662 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0046 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.9 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 56 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0006 | 666.3 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0006 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.9 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 57 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0010 | 670 | 690 | 20 | PHW | Vegetation | TREE REMOVAL | VEG_PHW010 | [49 empty] | 2 LARGE TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 27 | 110 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-TS-0047 | 670.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0047 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.9 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 58 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0010 | 670.63 | 878.592 | 207.962 | PHW | Pipe | PIPE | PHW-PIPE-0010 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-FN-0002 | 671 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0002 |  |  | D-DWG-PHW-001.2 |  | D-DWG-PHW-001_C |  | Yes | PHW |  | FENCE LINE NO POSTS | [40 empty] | Forreign service raw data.xlsx | 7
PHW-TS-0048 | 674.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0048 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.9 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 59 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0049 | 679.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0049 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.9 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 60 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0007 | 681.35 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0007 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.9 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 61 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0050 | 683.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0050 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.9 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 62 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0051 | 687.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0051 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.9 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 63 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0052 | 692.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0052 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.9 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 64 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0053 | 696.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0053 |  |  | D-DWG-PHW-001 |  |  |  |  | 1.9 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 65 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0008 | 700.7 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0008 |  |  | D-DWG-PHW-002 |  |  |  |  | 1.9 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 66 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0054 | 705 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0054 |  |  | D-DWG-PHW-002 |  |  |  |  | 1.9 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 67 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0055 | 709.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0055 |  |  | D-DWG-PHW-002 |  |  |  |  | 1.9 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 68 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0056 | 713.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0056 |  |  | D-DWG-PHW-002 |  |  |  |  | 1.9 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 69 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0009 | 717.9 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0009 |  |  | D-DWG-PHW-002 |  |  |  |  | 1.9 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 70 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0057 | 722.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0057 |  |  | D-DWG-PHW-002 |  |  |  |  | 1.9 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 71 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0058 | 729 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0058 |  |  | D-DWG-PHW-002 |  |  |  |  | 2.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 72 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0011 | 730 | 740 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW011 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 28 | 62.9 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-BS-0010 | 731.5 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0010 |  |  | D-DWG-PHW-002 |  |  |  |  | 2.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 73 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0059 | 734 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0059 |  |  | D-DWG-PHW-002 |  |  |  |  | 2.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 74 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0060 | 742 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0060 |  |  | D-DWG-PHW-002 |  |  |  |  | 2.3 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 75 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0061 | 749 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0061 |  |  | D-DWG-PHW-002 |  |  |  |  | 2.3 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 76 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0012 | 770 | 800 | 30 | PHW | Vegetation | TREE REMOVAL | VEG_PHW012 | [49 empty] | 3 LARGE TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 29 | 262 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-IV-001 | 842.6 |  |  | PHW | Valve | IV | PHW-IV-001 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PHW | [55 empty] | Supplied |  | 1 | each | [9 empty] | RHS |  |  |  | PIPE | 0 | NO
PHW-TB-093 | 842.62 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-093 | [7 empty] | PHW |  | Type 12 | [12 empty] | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 252 |  |  | Isolation Valve | [10 empty] | 1 | each |  | Isolation Valve |  |  | 600 | 2130 | 240 | Isolation valve | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TB-002 | 848.792 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-002 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 14 |  |  | Bend | [9 empty] | 14150 | 1 | each | 14150 | Bend | 11.25 | DICL | 600 | 2131 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-002 | 848.792 |  |  | PHW | Bend | HOR | PHW-BND-002 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-AV-002 | 851.8 |  |  | PHW | Valve | AV | PHW-AV-002 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-TT-0005 | 878.592 | 886.749 | 8.157 | PHW | Trench Type | TRENCH SECTION |  | 4 | 8.157 | D-DWG-PHW-002.2 | D-DWG-PHW-002.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 10
PHW-PIPE-0011 | 878.592 | 886.749 | 8.157 | PHW | Pipe | PIPE | PHW-PIPE-0011 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Open trench Access track crossing | Special Crossings
PHW-RD-0001 | 886 | 1135 | 249 | PHW | Road & Rail Crossing | MINOR ROAD CROSSING | PHW-RD-0001 |  | 249 | [5 empty] | PHW | Access Track - Kieman Road |  | Unsealed | 600 |  |  | DN600 PN35 DICL RRJ |  | 219.2 | 29.8 |  | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 7 | [28 empty] | TRENCH | 0 | NO
PHW-TT-0006 | 886.749 | 955.896 | 69.147 | PHW | Trench Type | TRENCH SECTION |  | 7 | 69.147 | D-DWG-PHW-002.2 | D-DWG-PHW-002.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 11
PHW-PIPE-0012 | 886.749 | 955.896 | 69.147 | PHW | Pipe | PIPE | PHW-PIPE-0012 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-VG-0013 | 890 | 900 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW013 | [49 empty] | 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 30 | 24.2 | LIGHT | [26 empty] | TRENCH | 0 | NO
PHW-TS-0062 | 892 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0062 |  |  | D-DWG-PHW-002 |  |  |  |  | 2.4 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 77 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0063 | 899 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0063 |  |  | D-DWG-PHW-002 |  |  |  |  | 2.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 78 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TB-003 | 899.995 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-003 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 15 |  |  | Bend | [9 empty] | 14150 | 1 | each | 14150 | Bend | 11.25 | DICL | 600 | 2144 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TS-0064 | 903.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0064 |  |  | D-DWG-PHW-002 |  |  |  |  | 2.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 79 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0011 | 908.2 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0011 |  |  | D-DWG-PHW-002 |  |  |  |  | 2.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 80 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0065 | 912.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0065 |  |  | D-DWG-PHW-002 |  |  |  |  | 2.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 81 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0066 | 917.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0066 |  |  | D-DWG-PHW-002 |  |  |  |  | 2.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 82 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0014 | 920 | 930 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW014 | [49 empty] | 2 LARGE TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 31 | 66.5 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-TS-0067 | 922 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0067 |  |  | D-DWG-PHW-002 |  |  |  |  | 2.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 83 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0012 | 926.6 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0012 |  |  | D-DWG-PHW-002 |  |  |  |  | 2.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 84 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0068 | 931.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0068 |  |  | D-DWG-PHW-002 |  |  |  |  | 2.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 85 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0069 | 935.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0069 |  |  | D-DWG-PHW-002 |  |  |  |  | 2.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 86 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0070 | 940.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0070 |  |  | D-DWG-PHW-002 |  |  |  |  | 2.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 87 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0013 | 945 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0013 |  |  | D-DWG-PHW-002 |  |  |  |  | 2.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 88 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0071 | 949.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0071 |  |  | D-DWG-PHW-002 |  |  |  |  | 2.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 89 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0015 | 950 | 950 | 0 | PHW | Vegetation | TREE REMOVAL | VEG_PHW015 | [49 empty] | 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 32 | 9.64 | LIGHT | [26 empty] | TRENCH | 0 | NO
PHW-TS-0072 | 954.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0072 |  |  | D-DWG-PHW-002 |  |  |  |  | 2.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 90 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TT-0007 | 955.896 | 960.896 | 5 | PHW | Trench Type | TRENCH SECTION |  | 4&7 | 5 | D-DWG-PHW-002.2 | D-DWG-PHW-002.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 12
PHW-PIPE-0013 | 955.896 | 960.896 | 5 | PHW | Pipe | PIPE | PHW-PIPE-0013 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Open trench Access track crossing | Special Crossings
PHW-VG-0016 | 960 | 980 | 20 | PHW | Vegetation | TREE REMOVAL | VEG_PHW016 | [49 empty] | 2 LARGE TREES, TRIMMING NEEDED | T2W - Tree Removal TakeOff (V.1).xlsx | 33 | 123 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-TT-0008 | 960.896 | 1092.896 | 132 | PHW | Trench Type | TRENCH SECTION |  | 7 | 132 | D-DWG-PHW-002.2 | D-DWG-PHW-002.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 13
PHW-PIPE-0014 | 960.896 | 1092.896 | 132 | PHW | Pipe | PIPE | PHW-PIPE-0014 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-TS-0073 | 964 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0073 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 91 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0074 | 967.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0074 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 92 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0014 | 971.2 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0014 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 93 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0075 | 974.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0075 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 94 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0076 | 978.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0076 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 95 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0077 | 982 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0077 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 96 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0015 | 985.6 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0015 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 97 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0078 | 989.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0078 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 98 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0079 | 992.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0079 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 99 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0017 | 1000 | 1010 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW017 | [49 empty] | BRANCHES HANGING OVER PIPE | T2W - Tree Removal TakeOff (V.1).xlsx | 34 | 55.6 | TRIM | [26 empty] | TRENCH | 0 | NO
PHW-TS-0080 | 1000.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0080 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 100 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0081 | 1005 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0081 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 101 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0016 | 1007.25 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0016 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 102 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0082 | 1009.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0082 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 103 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0018 | 1010 | 1020 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW018 | [49 empty] | 2 LARGE TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 35 | 57.9 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-TS-0083 | 1014 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0083 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 104 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0084 | 1020.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0084 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 105 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0085 | 1024.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0085 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 106 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0017 | 1029.3 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0017 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 107 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0086 | 1033.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0086 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 108 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0087 | 1038.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0087 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 109 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0019 | 1040 | 1050 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW019 | [49 empty] | 2 SMALL TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 36 | 23 | LIGHT | [26 empty] | TRENCH | 0 | NO
PHW-TS-0088 | 1042.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0088 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 110 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0018 | 1046.9 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0018 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 111 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0089 | 1051.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0089 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 112 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0090 | 1055.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0090 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 113 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0091 | 1060 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0091 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 114 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0019 | 1065 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0019 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 115 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0092 | 1070 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0092 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 116 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0020 | 1070 | 1080 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW020 | [49 empty] | 2 LARGE TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 37 | 85.4 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-TS-0093 | 1075 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0093 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 117 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0094 | 1080 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0094 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 118 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0020 | 1085 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0020 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 119 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TB-004 | 1086.423 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-004 | [7 empty] | PHW |  | Type 6 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 16 |  |  | Bend | [9 empty] | 14743 | 1 | each | 14743 | Bend | 11.25 | DICL | 600 | 2505 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TT-0009 | 1092.896 | 1116.806 | 23.91 | PHW | Trench Type | TRENCH SECTION |  | 4&7 | 23.91 | D-DWG-PHW-002.2 | D-DWG-PHW-002.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 14
PHW-PIPE-0015 | 1092.896 | 1116.896 | 24 | PHW | Pipe | PIPE | PHW-PIPE-0015 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Special Crossings
PHW-BND-003 | 1092.986 |  |  | PHW | Bend | HOR | PHW-BND-003 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-VG-0021 | 1100 | 1130 | 30 | PHW | Vegetation | TREE REMOVAL | VEG_PHW021 | [49 empty] | 3 LARGE TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 38 | 117 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-DR-0001 | 1105 |  |  | PHW | Foreign Service | DRAINAGE | PHW-DR-0001 |  |  | D-DWG-PHW-002.2 |  |  | PUP | Yes | PHW |  | PUP DRAINAGE DN375 | [12 empty] | 375 | [27 empty] | Forreign service raw data.xlsx | 8
PHW-TT-0010 | 1116.806 | 1135.078 | 18.272 | PHW | Trench Type | TRENCH SECTION |  | 7 | 18.272 | D-DWG-PHW-002.2 | D-DWG-PHW-002.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 15
PHW-PIPE-0016 | 1116.896 | 1135.078 | 18.182 | PHW | Pipe | PIPE | PHW-PIPE-0016 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Special Crossings
PHW-TT-0011 | 1135.078 | 1142.896 | 7.818 | PHW | Trench Type | TRENCH SECTION |  | 1A | 7.818 | D-DWG-PHW-002.2 | D-DWG-PHW-002.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 16
PHW-PIPE-0017 | 1135.078 | 1142.896 | 7.818 | PHW | Pipe | PIPE | PHW-PIPE-0017 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Special Crossings
PHW-TB-005 | 1137.626 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-005 | [7 empty] | PHW |  | Type 6 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 17 |  |  | Bend | [9 empty] | 14743 | 1 | each | 14743 | Bend | 11.25 | DICL | 600 | 2534 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-VG-0022 | 1140 | 1150 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW022 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 39 | 82 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-TT-0012 | 1142.896 | 1182.245 | 39.349 | PHW | Trench Type | TRENCH SECTION |  | 4 | 39.349 | D-DWG-PHW-002.2 | D-DWG-PHW-002.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 17
PHW-PIPE-0018 | 1142.896 | 1182.245 | 39.349 | PHW | Pipe | PIPE | PHW-PIPE-0018 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Special Crossings
PHW-VG-0023 | 1170 | 1190 | 20 | PHW | Vegetation | TREE REMOVAL | VEG_PHW023 | [49 empty] | BRANCHES HANGING OVER PIPE | T2W - Tree Removal TakeOff (V.1).xlsx | 40 | 46.3 | TRIM | [26 empty] | TRENCH | 0 | NO
PHW-TT-0013 | 1182.245 | 1217.093 | 34.848 | PHW | Trench Type | TRENCH SECTION |  | 1A | 34.848 | D-DWG-PHW-002.2 | D-DWG-PHW-002.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 18
PHW-PIPE-0019 | 1182.245 | 1217.093 | 34.848 | PHW | Pipe | PIPE | PHW-PIPE-0019 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Special Crossings
PHW-TS-0095 | 1185 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0095 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 120 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0096 | 1192 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0096 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 121 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0097 | 1199 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0097 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 122 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0098 | 1206 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0098 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 123 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0024 | 1210 | 1220 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW024 | [49 empty] | BRANCHES HANGING OVER PIPE | T2W - Tree Removal TakeOff (V.1).xlsx | 41 | 12.4 | TRIM | [26 empty] | TRENCH | 0 | NO
PHW-TS-0099 | 1211 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0099 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 124 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0021 | 1212.55 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0021 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 125 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0100 | 1214.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0100 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 126 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TT-0014 | 1217.093 | 1232.924 | 15.831 | PHW | Trench Type | TRENCH SECTION |  | 4 | 15.831 | D-DWG-PHW-002.2 | D-DWG-PHW-002.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 19
PHW-PIPE-0020 | 1217.093 | 1232.924 | 15.831 | PHW | Pipe | PIPE | PHW-PIPE-0020 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Special Crossings
PHW-RD-0002 | 1232.924 | 1255.696 | 22.772 | PHW | Road & Rail Crossing | MAJOR ROAD CROSSING | PHW-RD-0002 |  | 22.772 | [5 empty] | PHW | Old Goombungee Road |  | Sealed | 600 |  |  | OD660x6WT MSCL Sintalock Type 2 PN35 Carrier & OD813x12WT MS Enveloper |  |  |  |  | TRC | [15 empty] | Thrust Boring | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 8 | [28 empty] | TRENCH | 0 | NO
PHW-TT-0015 | 1232.924 | 1255.696 | 22.772 | PHW | Trench Type | TRENCH SECTION |  | 8A | 22.772 | D-DWG-PHW-002.2 | D-DWG-PHW-002.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 20
PHW-PIPE-0021 | 1232.924 | 1255.696 | 22.772 | PHW | Pipe | PIPE | PHW-PIPE-0021 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 + OD813 12WT MS Enveloper | [6 empty] | MSCL | 660 | [54 empty] | Old Goombungee Road | Trenchless
PHW-SW-0001 | 1242 |  |  | PHW | Foreign Service | SEWER | PHW-SW-0001 |  |  | D-DWG-PHW-002.2 |  | D-DWG-PHW-002_C | BYDA | Yes | PHW |  | BYDA TRC SEWER | [9 empty] | Toowoomba Regional Council | [29 empty] | DEPTH OF DUAL SEWER MAINS NOT KNOWN AT EXACT CROSSING LOCATION. CONTRACTOR TO CONFIRM PRIOR TO D&C DESIGN. | Forreign service raw data.xlsx | 9
PHW-SW-0002 | 1243 |  |  | PHW | Foreign Service | SEWER | PHW-SW-0002 |  |  | D-DWG-PHW-002.2 |  |  | PUP | Yes | PHW |  | PUP SEWER DN375 | [12 empty] | 375 | [26 empty] | DEPTH OF DUAL SEWER MAINS NOT KNOWN AT EXACT CROSSING LOCATION. CONTRACTOR TO CONFIRM PRIOR TO D&C DESIGN. | Forreign service raw data.xlsx | 10
PHW-VG-0025 | 1250 | 1250 | 0 | PHW | Vegetation | TREE REMOVAL | VEG_PHW025 | [49 empty] | 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 42 | 54 | LIGHT | [26 empty] | TRENCH | 0 | NO
PHW-TT-0016 | 1255.696 | 1733.958 | 478.262 | PHW | Trench Type | TRENCH SECTION |  | 1A | 478.262 | D-DWG-PHW-002.2 | D-DWG-PHW-003.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 21
PHW-PIPE-0022 | 1255.696 | 1294.197 | 38.501 | PHW | Pipe | PIPE | PHW-PIPE-0022 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-TB-006 | 1256.696 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-006 | [7 empty] | PHW |  | Type 3 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 18 |  |  | Bend | [9 empty] | 16755 | 1 | each | 16755 | Bend | 45 | DICL | 600 | 2663 | 150 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-004 | 1256.696 |  |  | PHW | Bend | HOR | PHW-BND-004 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 45° | DICL | 600 | [7 empty] | 45 | PIPE | 0 | NO
PHW-TB-077 | 1261.832 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-077 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 236 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN600xDN150 DIFBE SCOUR TEE |  | 150 | 2663 | 150 | Tee; DN600XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-SCV-001 | 1265 |  |  | PHW | Valve | SCV | PHW-SCV-001 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PHW-TB-007 | 1265.039 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-007 | [7 empty] | PHW |  | Type 3 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 19 |  |  | Bend | [9 empty] | 16755 | 1 | each | 16755 | Bend | 45 | DICL | 600 | 2662 | 150 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-005 | 1265.039 |  |  | PHW | Bend | HOR | PHW-BND-005 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 45° | DICL | 600 | [7 empty] | 45 | PIPE | 0 | NO
PHW-PIPE-0023 | 1294.197 | 1350.152 | 55.955 | PHW | Pipe | PIPE | PHW-PIPE-0023 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-TS-0101 | 1302 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0101 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 127 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0102 | 1317.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0102 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 128 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0026 | 1320 | 1330 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW026 | [49 empty] | 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 43 | 66 | LIGHT | [26 empty] | TRENCH | 0 | NO
PHW-TS-0103 | 1332.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0103 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 129 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0104 | 1347.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0104 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 130 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0024 | 1350.152 | 1370.58 | 20.428 | PHW | Pipe | PIPE | PHW-PIPE-0024 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Special Crossings
PHW-TS-0105 | 1363.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0105 |  |  | D-DWG-PHW-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 131 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0025 | 1370.58 | 1615.899 | 245.319 | PHW | Pipe | PIPE | PHW-PIPE-0025 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-AV-003 | 1420 |  |  | PHW | Valve | AV | PHW-AV-003 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-TB-008 | 1451.029 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-008 | [7 empty] | PHW |  | Type 1 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 20 |  |  | Bend | [9 empty] | 114663 | 1 | each | 114663 | Bend | 45 | DICL | 600 | 2596 | 50 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-006 | 1451.029 |  |  | PHW | Bend | HOR | PHW-BND-006 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 45° | DICL | 600 | [7 empty] | 45 | PIPE | 0 | NO
PHW-EL-0002 | 1459 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0002 |  |  | D-DWG-PHW-003.2 |  | D-DWG-PHW-003_C | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 11
PHW-FN-0003 | 1462 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0003 |  |  | D-DWG-PHW-003.2 |  | D-DWG-PHW-003_C |  | Yes | PHW |  | FENCE LINE NO POSTS | [40 empty] | Forreign service raw data.xlsx | 12
PHW-TB-009 | 1471.052 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-009 | [7 empty] | PHW |  | Type 1 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 21 |  |  | Bend | [9 empty] | 114663 | 1 | each | 114663 | Bend | 45 | DICL | 600 | 2613 | 50 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-007 | 1471.052 |  |  | PHW | Bend | HOR | PHW-BND-007 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 45° | DICL | 600 | [7 empty] | 45 | PIPE | 0 | NO
PHW-TS-0106 | 1484.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0106 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 132 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0107 | 1488.25 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0107 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 133 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0108 | 1493 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0108 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 134 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0109 | 1497.15 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0109 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 135 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0110 | 1501.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0110 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 136 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0111 | 1506.05 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0111 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 137 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0112 | 1509.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0112 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 138 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0113 | 1517.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0113 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 139 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0114 | 1526.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0114 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 140 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-FN-0004 | 1534 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0004 |  |  | D-DWG-PHW-003.2 |  | D-DWG-PHW-003_C |  | Yes | PHW |  | FENCE LINE NO POSTS | [40 empty] | Forreign service raw data.xlsx | 13
PHW-TS-0115 | 1534.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0115 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 141 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0116 | 1542.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0116 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 142 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0117 | 1551.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0117 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 143 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0118 | 1559.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0118 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 144 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0119 | 1567.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0119 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 145 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0120 | 1576 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0120 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 146 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0121 | 1584.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0121 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 147 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0122 | 1592.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0122 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 148 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0123 | 1600.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0123 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 149 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0124 | 1615 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0124 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 150 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0026 | 1615.899 | 1733.958 | 118.059 | PHW | Pipe | PIPE | PHW-PIPE-0026 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-TS-0125 | 1621.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0125 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 151 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0126 | 1628.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0126 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 152 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0127 | 1635.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0127 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 153 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0128 | 1643.25 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0128 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 154 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0022 | 1647.95 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0022 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 155 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0129 | 1652.65 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0129 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 156 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0130 | 1657.35 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0130 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 157 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0131 | 1662.05 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0131 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 158 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0023 | 1666.75 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0023 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 159 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0132 | 1671.45 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0132 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 160 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TB-010 | 1675.935 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-010 | [7 empty] | PHW |  | Type 8 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 22 |  |  | Bend | [9 empty] | 14024 | 1 | each | 14024 | Bend | 11.25 | DICL | 600 | 2857 | 50 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-008 | 1675.935 |  |  | PHW | Bend | VERT | PHW-BND-008 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-TS-0133 | 1679.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0133 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 161 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0134 | 1688.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0134 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 162 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TB-078 | 1727.817 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-078 | [7 empty] | PHW |  | Type 6 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 237 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN600xDN150 DIFBE SCOUR TEE |  | 150 | 2880 | 50 | Tee; DN600XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-SCV-002 | 1728 |  |  | PHW | Valve | SCV | PHW-SCV-002 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1E |  |  |  | PIPE | 0 | NO
PHW-AV-004 | 1730 |  |  | PHW | Valve | AV | PHW-AV-004 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 2 |  |  |  | PIPE | 0 | NO
PHW-TB-011 | 1733.958 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-011 | [7 empty] | PHW |  | Type 10 | [11 empty] | MSCL | 650 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 23 |  |  | Bend | [9 empty] | 49509 | 1 | each | 49509 | Bend | 7.5 | MSCL | 650 | 2882 | 50 | Bend; MS - 7.5° | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TT-0017 | 1733.958 | 1787.137 | 53.179 | PHW | Trench Type | TRENCH SECTION |  | 5 | 53.179 | D-DWG-PHW-003.2 | D-DWG-PHW-003.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 22
PHW-BND-009 | 1733.958 |  |  | PHW | Bend | VERT | PHW-BND-009 |  |  | D-DWG-PHW-003.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 7.5° | MSCL | 650 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PHW-PIPE-0027 | 1733.958 | 1787.137 | 53.179 | PHW | Pipe | PIPE | PHW-PIPE-0027 |  |  | D-DWG-PHW-003.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Major Creek Crossing | Special Crossings
PHW-CC-0001 | 1734 | 1787 | 53 | PHW | Creek Crossing | TRENCHED CREEK CROSSING | PHW-CC-0001 | [7 empty] | PHW | GOWRIE CREEK |  |  |  | LOOSE ROCK | C | [36 empty] | PHw_PWG_Creek_Crossings.xlsx | 3 | [28 empty] | TRENCH | 0 | NO
PHW-FN-0005 | 1736 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0005 |  |  | D-DWG-PHW-003.2 |  | D-DWG-PHW-003_C |  | Yes | PHW |  | FENCE LINE NO POSTS | [40 empty] | Forreign service raw data.xlsx | 14
PHW-VG-0027 | 1740 | 1780 | 40 | PHW | Vegetation | TREE REMOVAL | VEG_PHW027 | [49 empty] | 2 LARGE TREES, 2 SMALL TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 44 | 402 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-BND-010 | 1749.478 |  |  | PHW | Bend | VERT | PHW-BND-010 |  |  | D-DWG-PHW-003.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 14.3° | MSCL | 650 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PHW-BND-011 | 1756.406 |  |  | PHW | Bend | VERT | PHW-BND-011 |  |  | D-DWG-PHW-003.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 28.5° | MSCL | 650 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PHW-TT-0018 | 1787.137 | 2036.932 | 249.795 | PHW | Trench Type | TRENCH SECTION |  | 1A | 249.795 | D-DWG-PHW-003.2 | D-DWG-PHW-003.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 23
PHW-PIPE-0028 | 1787.137 | 1822.818 | 35.681 | PHW | Pipe | PIPE | PHW-PIPE-0028 |  |  | D-DWG-PHW-003.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-TS-0135 | 1788 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0135 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 163 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0136 | 1791.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0136 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 164 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0024 | 1792.8 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0024 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 165 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0137 | 1794.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0137 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 166 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0138 | 1797.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0138 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 167 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TB-012 | 1802.818 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-012 | [7 empty] | PHW |  | Type 10 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 24 |  |  | Bend | [9 empty] | 44440 | 1 | each | 44440 | Bend | 11.25 | DICL | 600 | 2859 | 50 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-012 | 1802.818 |  |  | PHW | Bend | VERT | PHW-BND-012 |  |  | D-DWG-PHW-003.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-AV-005 | 1805 |  |  | PHW | Valve | AV | PHW-AV-005 |  |  | D-DWG-PHW-003.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 2 |  |  |  | PIPE | 0 | NO
PHW-TS-0139 | 1809 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0139 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 168 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0028 | 1810 | 1830 | 20 | PHW | Vegetation | TREE REMOVAL | VEG_PHW028 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 45 | 271 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-TS-0140 | 1819 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0140 |  |  | D-DWG-PHW-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 169 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-FN-0006 | 1820 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0006 |  |  | D-DWG-PHW-003.2 |  | D-DWG-PHW-003_C |  | Yes | PHW |  | FENCE CHAINWIRE | [40 empty] | Forreign service raw data.xlsx | 15
PHW-PIPE-0029 | 1822.818 | 2036.932 | 214.114 | PHW | Pipe | PIPE | PHW-PIPE-0029 |  |  | D-DWG-PHW-003.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Special Crossings
PHW-FN-0007 | 1868 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0007 |  |  | D-DWG-PHW-003.2 |  | D-DWG-PHW-003_C |  | Yes | PHW |  | FENCE LINE NO POSTS | [40 empty] | Forreign service raw data.xlsx | 16
PHW-TB-013 | 1870.316 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-013 | [7 empty] | PHW |  | Type 1 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 25 |  |  | Bend | [9 empty] | 114663 | 1 | each | 114663 | Bend | 45 | DICL | 600 | 2822 | 50 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-013 | 1870.316 |  |  | PHW | Bend | HOR | PHW-BND-013 |  |  | D-DWG-PHW-003.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 45° | DICL | 600 | [7 empty] | 45 | PIPE | 0 | NO
PHW-TB-014 | 1878.593 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-014 | [7 empty] | PHW |  | Type 2 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 26 |  |  | Bend | [9 empty] | 99539 | 1 | each | 99539 | Bend | 22.5 | DICL | 600 | 2818 | 50 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-014 | 1878.593 |  |  | PHW | Bend | HOR | PHW-BND-014 |  |  | D-DWG-PHW-003.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 600 | [7 empty] | 22.5 | PIPE | 0 | NO
PHW-FN-0008 | 1897 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0008 |  |  | D-DWG-PHW-003.2 |  | D-DWG-PHW-003_C |  | Yes | PHW |  | FENCE LINE NO POSTS | [40 empty] | Forreign service raw data.xlsx | 17
PHW-FN-0009 | 1915 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0009 |  |  | D-DWG-PHW-003.2 |  | D-DWG-PHW-003_C |  | Yes | PHW |  | FENCE LINE NO POSTS | [39 empty] | Not Included in Rev 2 | Forreign service raw data.xlsx | 18
PHW-VG-0029 | 1980 | 2010 | 30 | PHW | Vegetation | TREE REMOVAL | VEG_PHW029 | [49 empty] | 1 LARGE TREE, 2 SMALL TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 46 | 380 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-IV-002 | 2019 |  |  | PHW | Valve | IV | PHW-IV-002 |  |  | D-DWG-PHW-003.2 |  |  |  |  | PHW | [55 empty] | Supplied |  | 1 | each | [9 empty] | 3 |  |  |  | PIPE | 0 | NO
PHW-AV-006 | 2019 |  |  | PHW | Valve | AV | PHW-AV-006 |  |  | D-DWG-PHW-003.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PHW-TB-094 | 2019.495 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-094 | [7 empty] | PHW |  | Type 12 | [12 empty] | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 253 |  |  | Isolation Valve | [10 empty] | 1 | each |  | Isolation Valve |  |  | 600 | 2804 | 150 | Isolation valve | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TB-015 | 2029.495 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-015 | [7 empty] | PHW |  | Type 3 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 27 |  |  | Bend | [9 empty] | 16755 | 1 | each | 16755 | Bend | 45 | DICL | 600 | 2803 | 150 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-015 | 2029.495 |  |  | PHW | Bend | HOR | PHW-BND-015 |  |  | D-DWG-PHW-003.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 45° | DICL | 600 | [7 empty] | 45 | PIPE | 0 | NO
PHW-VG-0030 | 2030 | 2040 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW030 | [49 empty] | 2 SMALL TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 47 | 99 | LIGHT | [26 empty] | TRENCH | 0 | NO
PHW-TB-016 | 2036.932 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-016 | [7 empty] | PHW |  | Type 3 | [11 empty] | MSCL | 650 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 28 |  |  | Bend | [9 empty] | 26944 | 1 | each | 26944 | Bend | 47.1 | MSCL | 650 | 2801 | 150 | Bend; MS - 47.1° | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TT-0019 | 2036.932 | 2038.507 | 1.575 | PHW | Trench Type | TRENCH SECTION |  | 4 | 1.575 | D-DWG-PHW-003.2 | D-DWG-PHW-003.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 24
PHW-BND-016 | 2036.932 |  |  | PHW | Bend | HOR | PHW-BND-016 |  |  | D-DWG-PHW-003.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 47.1° | MSCL | 650 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PHW-PIPE-0030 | 2036.932 | 2110.24 | 73.308 | PHW | Pipe | PIPE | PHW-PIPE-0030 |  |  | D-DWG-PHW-003.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 + OD813 15WT MS Enveloper | [6 empty] | MSCL | 660 | [54 empty] | Railway Crossing | Trenchless
PHW-RL-0001 | 2038.507 | 2110.24 | 71.733 | PHW | Road & Rail Crossing | MAJOR RAIL CROSSING | PHW-RL-0001 |  | 71.733 | [5 empty] | PHW | West Moreton System |  | Rail | 600 |  |  | OD660x6WT MSCL Sintalock Type 2 PN35 Carrier & OD813x15WT MS Enveloper |  |  |  |  | QLD Rail | [15 empty] | Thrust Boring | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 9 | [28 empty] | TRENCH | 0 | NO
PHW-TT-0020 | 2038.507 | 2110.24 | 71.733 | PHW | Trench Type | TRENCH SECTION |  | 8A | 71.733 | D-DWG-PHW-003.2 | D-DWG-PHW-004.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 25
PHW-FN-0010 | 2062 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0010 |  |  | D-DWG-PHW-003.2 |  | D-DWG-PHW-003_C |  | Yes | PHW |  | FENCE CHAINWIRE | [40 empty] | Forreign service raw data.xlsx | 19
PHW-FN-0011 | 2062 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0011 |  |  | D-DWG-PHW-003.2 |  | D-DWG-PHW-003_C |  | Yes | PHW |  | FENCE LINE NO POSTS | [40 empty] | Forreign service raw data.xlsx | 20
PHW-CM-0004 | 2093 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0004 |  |  | D-DWG-PHW-003.2 |  | D-DWG-PHW-003_C | BYDA | Yes | PHW |  | BYDA TELSTRA COMMSTUD | [9 empty] | Telstra | [30 empty] | Forreign service raw data.xlsx | 21
PHW-RW-0001 | 2104 |  |  | PHW | Foreign Service | WATER - RECYCLED | PHW-RW-0001 |  |  | D-DWG-PHW-004.2 |  |  | BYDA | Yes | PHW |  | BYDA RECYCLED WATER | [40 empty] | Forreign service raw data.xlsx | 22
PHW-CM-0005 | 2108 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0005 |  |  | D-DWG-PHW-004.2 |  | D-DWG-PHW-004_C | BYDA | Yes | PHW |  | BYDA TELSTRA COMMSTUD | [9 empty] | Telstra | [30 empty] | Forreign service raw data.xlsx | 23
PHW-TT-0021 | 2110.24 | 2122.834 | 12.594 | PHW | Trench Type | TRENCH SECTION |  | 4 | 12.594 | D-DWG-PHW-004.2 | D-DWG-PHW-004.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 26
PHW-PIPE-0031 | 2110.24 | 2122.834 | 12.594 | PHW | Pipe | PIPE | PHW-PIPE-0031 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-BND-017 | 2112.701 |  |  | PHW | Bend | HOR | PHW-BND-017 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 16.9° | MSCL | 650 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PHW-TT-0022 | 2122.834 | 2468.34 | 345.506 | PHW | Trench Type | TRENCH SECTION |  | 1A | 345.506 | D-DWG-PHW-004.2 | D-DWG-PHW-004.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 27
PHW-PIPE-0032 | 2122.834 | 2468.34 | 345.506 | PHW | Pipe | PIPE | PHW-PIPE-0032 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-FN-0012 | 2123 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0012 |  |  | D-DWG-PHW-004.2 |  |  |  | Yes | PHW |  | FENCE CHAINWIRE | [40 empty] | Forreign service raw data.xlsx | 24
PHW-TS-0141 | 2125 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0141 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 170 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0142 | 2131 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0142 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 171 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-IV-003 | 2140 |  |  | PHW | Valve | IV | PHW-IV-003 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PHW | [55 empty] | Supplied |  | 1 | each | [9 empty] | 3 |  |  |  | PIPE | 0 | NO
PHW-SCV-003 | 2140 |  |  | PHW | Valve | SCV | PHW-SCV-003 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PHW-TB-095 | 2140.173 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-095 | [7 empty] | PHW |  | Type 12 | [12 empty] | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 254 |  |  | Isolation Valve | [10 empty] | 1 | each |  | Isolation Valve |  |  | 600 | 2735 | 50 | Isolation valve | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TS-0143 | 2146 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0143 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 172 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0144 | 2157.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0144 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 173 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0145 | 2169 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0145 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 174 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0146 | 2180.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0146 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 175 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0147 | 2192 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0147 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 176 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0148 | 2203.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0148 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 177 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0149 | 2215 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0149 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 178 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0150 | 2226.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0150 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 179 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0151 | 2238 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0151 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 180 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0152 | 2249.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0152 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 181 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0153 | 2261 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0153 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 182 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0154 | 2272.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0154 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 183 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0155 | 2284 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0155 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 184 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0156 | 2295.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0156 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 185 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0157 | 2307 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0157 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 186 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0158 | 2318.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0158 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 187 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0031 | 2320 | 2330 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW031 | [49 empty] | 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 48 | 44.8 | LIGHT | [26 empty] | TRENCH | 0 | NO
PHW-TS-0159 | 2330 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0159 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 188 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TB-017 | 2336.958 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-017 | [7 empty] | PHW |  | Type 2 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 29 |  |  | Bend | [9 empty] | 99969 | 1 | each | 99969 | Bend | 22.5+11.25 | DICL | 600 | 2588 | 50 | Bend; 22.5+11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-018 | 2336.958 |  |  | PHW | Bend | HOR | PHW-BND-018 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 600 | [7 empty] | 22.5 | PIPE | 0 | NO
PHW-TS-0160 | 2339.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0160 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 189 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-WA-0001 | 2340 |  |  | PHW | Foreign Service | WATER | PHW-WA-0001 |  |  | D-DWG-PHW-004.2 |  |  | BYDA | Yes | PHW |  | BYDA WATER | [40 empty] | Forreign service raw data.xlsx | 25
PHW-TS-0161 | 2350.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0161 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 190 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0032 | 2360 | 2380 | 20 | PHW | Vegetation | TREE REMOVAL | VEG_PHW032 | [49 empty] | 1 LARGE TREE, 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 49 | 141 | TRIM | [26 empty] | TRENCH | 0 | NO
PHW-VG-0033 | 2360 | 2370 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW033 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 50 | 94 | TRIM | [26 empty] | TRENCH | 0 | NO
PHW-TS-0162 | 2360.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0162 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 191 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0163 | 2371.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0163 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 192 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0164 | 2381.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0164 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 193 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0165 | 2392.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0165 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 194 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0034 | 2400 | 2420 | 20 | PHW | Vegetation | TREE REMOVAL | VEG_PHW034 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 51 | 138 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-TS-0166 | 2402.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0166 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 195 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0167 | 2413.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0167 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 196 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0168 | 2423.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0168 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 197 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0169 | 2434.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0169 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 198 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0170 | 2444.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0170 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 199 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0035 | 2460 | 2480 | 20 | PHW | Vegetation | TREE REMOVAL | VEG_PHW035 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 52 | 132 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-TT-0023 | 2468.34 | 2500.706 | 32.366 | PHW | Trench Type | TRENCH SECTION |  | 4 | 32.366 | D-DWG-PHW-004.2 | D-DWG-PHW-004.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 28
PHW-PIPE-0033 | 2468.34 | 2500.706 | 32.366 | PHW | Pipe | PIPE | PHW-PIPE-0033 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-VG-0036 | 2480 | 2490 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW036 | [49 empty] | 2 SMALL TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 53 | 37.7 | LIGHT | [26 empty] | TRENCH | 0 | NO
PHW-VG-0037 | 2500 | 2510 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW037 | [49 empty] | 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 54 | 17 | LIGHT | [26 empty] | TRENCH | 0 | NO
PHW-TB-018 | 2500.706 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-018 | [7 empty] | PHW |  | Type 2 | [11 empty] | MSCL | 650 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 30 |  |  | Bend | [9 empty] | 104391 | 1 | each | 104391 | Bend | 38.2 | MSCL | 650 | 2489 | 50 | Bend; MS - 38.2° | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TT-0024 | 2500.706 | 2791.911 | 291.205 | PHW | Trench Type | TRENCH SECTION |  | 1A | 291.205 | D-DWG-PHW-004.2 | D-DWG-PHW-004.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 29
PHW-BND-019 | 2500.706 |  |  | PHW | Bend | HOR | PHW-BND-019 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 38.2° | MSCL | 650 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PHW-PIPE-0034 | 2500.706 | 2561.973 | 61.267 | PHW | Pipe | PIPE | PHW-PIPE-0034 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Open trenched - foreign service | Special Crossings
PHW-CM-0006 | 2506 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0006 |  |  | D-DWG-PHW-004.2 |  |  | BYDA | Yes | PHW |  | BYDA COMMS DN35 | [12 empty] | 35 | [27 empty] | Forreign service raw data.xlsx | 26
PHW-WA-0002 | 2507 |  |  | PHW | Foreign Service | WATER | PHW-WA-0002 |  |  | D-DWG-PHW-004.2 |  | D-DWG-PHW-004_C | BYDA | Yes | PHW |  | BYDA WATER | [40 empty] | Forreign service raw data.xlsx | 27
PHW-TS-0171 | 2521.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0171 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 200 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TB-019 | 2536.539 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-019 | [7 empty] | PHW |  | Type 6 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 31 |  |  | Bend | [9 empty] | 14743 | 1 | each | 14743 | Bend | 11.25 | DICL | 600 | 2473 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-020 | 2536.539 |  |  | PHW | Bend | HOR | PHW-BND-020 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-TS-0172 | 2537 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0172 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 201 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0173 | 2552.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0173 |  |  | D-DWG-PHW-004 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 202 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-CM-0007 | 2560 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0007 |  |  | D-DWG-PHW-004.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMSTUD | [9 empty] | Telstra | [30 empty] | Forreign service raw data.xlsx | 28
PHW-VG-0038 | 2560 | 2580 | 20 | PHW | Vegetation | TREE REMOVAL | VEG_PHW038 | [49 empty] | 2 LARGE TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 55 | 117 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-PIPE-0035 | 2561.973 | 2791.911 | 229.938 | PHW | Pipe | PIPE | PHW-PIPE-0035 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-AV-007 | 2572 |  |  | PHW | Valve | AV | PHW-AV-007 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-VG-0039 | 2620 | 2620 | 0 | PHW | Vegetation | TREE REMOVAL | VEG_PHW039 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 56 | 29 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-TB-020 | 2667.545 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-020 | [7 empty] | PHW |  | Type 5 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 32 |  |  | Bend | [9 empty] | 14784 | 1 | each | 14784 | Bend | 22.5 | DICL | 600 | 2481 | 150 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-021 | 2667.545 |  |  | PHW | Bend | HOR | PHW-BND-021 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 600 | [7 empty] | 22.5 | PIPE | 0 | NO
PHW-TB-021 | 2679.259 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-021 | [7 empty] | PHW |  | Type 4 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 33 |  |  | Bend | [9 empty] | 18443 | 1 | each | 18443 | Bend | 22.5+11.25 | DICL | 600 | 2485 | 150 | Bend; 22.5+11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-022 | 2679.259 |  |  | PHW | Bend | HOR | PHW-BND-022 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 600 | [7 empty] | 22.5 | PIPE | 0 | NO
PHW-VG-0040 | 2710 | 2720 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW040 | [49 empty] | 3 SMALL TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 57 | 43.3 | LIGHT | [26 empty] | TRENCH | 0 | NO
PHW-SCV-004 | 2746 |  |  | PHW | Valve | SCV | PHW-SCV-004 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PHW-TB-079 | 2746.277 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-079 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 238 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN600xDN150 DIFBE SCOUR TEE |  | 150 | 2488 | 150 | Tee; DN600XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-VG-0041 | 2750 | 2750 | 0 | PHW | Vegetation | TREE REMOVAL | VEG_PHW041 | [49 empty] | BRANCHES HANGING OVER PIPE | T2W - Tree Removal TakeOff (V.1).xlsx | 58 | 32.5 | TRIM | [26 empty] | TRENCH | 0 | NO
PHW-VG-0042 | 2770 | 2790 | 20 | PHW | Vegetation | TREE REMOVAL | VEG_PHW042 | [49 empty] | 1 LARGE TREE, 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 59 | 86.4 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-TT-0025 | 2791.911 | 2813.28 | 21.369 | PHW | Trench Type | TRENCH SECTION |  | 4 | 21.369 | D-DWG-PHW-004.2 | D-DWG-PHW-005.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 30
PHW-PIPE-0036 | 2791.911 | 2813.28 | 21.369 | PHW | Pipe | PIPE | PHW-PIPE-0036 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Open trenched - foreign service | Special Crossings
PHW-EL-0003 | 2792 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0003 | [5 empty] | BYDA | Yes | PHW |  | BYDA ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 335
PHW-WA-0003 | 2793 |  |  | PHW | Foreign Service | WATER | PHW-WA-0003 |  |  | D-DWG-PHW-004.2 |  |  | BYDA | Yes | PHW |  | BYDA WATER | [40 empty] | Forreign service raw data.xlsx | 29
PHW-WA-0004 | 2793 |  |  | PHW | Foreign Service | WATER | PHW-WA-0004 |  |  | D-DWG-PHW-004.2 |  |  | BYDA | Yes | PHW |  | BYDA WATER | [40 empty] | Forreign service raw data.xlsx | 30
PHW-TB-022 | 2793.96 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-022 | [7 empty] | PHW |  | Type 7 | [11 empty] | MSCL | 650 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 34 |  |  | Bend | [9 empty] | 19220 | 1 | each | 19220 | Bend | 9.1 | MSCL | 650 | 2476 | 150 | Bend; MS - 9.1° | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-023 | 2793.96 |  |  | PHW | Bend | HOR | PHW-BND-023 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 9.9° | MSCL | 650 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PHW-FN-0013 | 2796 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0013 |  |  | D-DWG-PHW-004.2 |  |  |  | Yes | PHW |  | FENCE CHAINWIRE | [40 empty] | Forreign service raw data.xlsx | 31
PHW-AV-008 | 2801 |  |  | PHW | Valve | AV | PHW-AV-008 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PHW-TB-023 | 2802.89 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-023 | [7 empty] | PHW |  | Type 4 | [11 empty] | MSCL | 650 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 35 |  |  | Bend | [9 empty] | 20678 | 1 | each | 20678 | Bend | 30 | MSCL | 650 | 2474 | 150 | Bend; MS - 30° | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-WA-0005 | 2810 |  |  | PHW | Foreign Service | WATER | PHW-WA-0005 |  |  | D-DWG-PHW-005.2 |  |  | BYDA | Yes | PHW |  | BYDA WATER | [40 empty] | Forreign service raw data.xlsx | 32
PHW-VG-0043 | 2810 | 2810 | 0 | PHW | Vegetation | TREE REMOVAL | VEG_PHW043 | [49 empty] | 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 60 | 41.4 | LIGHT | [26 empty] | TRENCH | 0 | NO
PHW-CM-0008 | 2813 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0008 |  |  | D-DWG-PHW-005.2 |  |  | BYDA | Yes | PHW |  | BYDA COMMS DN15 | [12 empty] | 15 | [27 empty] | Forreign service raw data.xlsx | 34
PHW-WA-0006 | 2813 |  |  | PHW | Foreign Service | WATER | PHW-WA-0006 |  |  | D-DWG-PHW-005.2 |  |  | BYDA | Yes | PHW |  | BYDA WATER DN450 | [12 empty] | 450 | [27 empty] | Forreign service raw data.xlsx | 33
PHW-TT-0026 | 2813.28 | 2846.195 | 32.915 | PHW | Trench Type | TRENCH SECTION |  | 1A | 32.915 | D-DWG-PHW-005.2 | D-DWG-PHW-005.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 31
PHW-PIPE-0037 | 2813.28 | 2846.195 | 32.915 | PHW | Pipe | PIPE | PHW-PIPE-0037 |  |  | D-DWG-PHW-005.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TB-024 | 2819.519 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-024 | [7 empty] | PHW |  | Type 5 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 36 |  |  | Bend | [9 empty] | 14784 | 1 | each | 14784 | Bend | 22.5 | DICL | 600 | 2479 | 150 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-024 | 2819.519 |  |  | PHW | Bend | HOR | PHW-BND-024 |  |  | D-DWG-PHW-005.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 600 | [7 empty] | 22.5 | PIPE | 0 | NO
PHW-TT-0027 | 2846.195 | 2881.928 | 35.733 | PHW | Trench Type | TRENCH SECTION |  | 4 | 35.733 | D-DWG-PHW-005.2 | D-DWG-PHW-005.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 32
PHW-PIPE-0038 | 2846.195 | 2881.928 | 35.733 | PHW | Pipe | PIPE | PHW-PIPE-0038 |  |  | D-DWG-PHW-005.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Driveway crossings | Special Crossings
PHW-TT-0028 | 2881.928 | 3534.937 | 653.009 | PHW | Trench Type | TRENCH SECTION |  | 1A | 653.009 | D-DWG-PHW-005.2 | D-DWG-PHW-006.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 33
PHW-PIPE-0039 | 2881.928 | 3457.556 | 575.628 | PHW | Pipe | PIPE | PHW-PIPE-0039 |  |  | D-DWG-PHW-005.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Trenchless
PHW-FN-0014 | 2923 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0014 |  |  | D-DWG-PHW-005.2 |  | D-DWG-PHW-005_C |  | Yes | PHW |  | FENCE CHAINWIRE | [40 empty] | Forreign service raw data.xlsx | 35
PHW-FN-0015 | 2923 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0015 |  |  | D-DWG-PHW-005.2 |  | D-DWG-PHW-005_C |  | Yes | PHW |  | FENCE LINE NO POSTS | [40 empty] | Forreign service raw data.xlsx | 36
PHW-TS-0174 | 2930 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0174 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 203 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0175 | 2945.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0175 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 204 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0176 | 2961 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0176 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 205 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0177 | 2976.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0177 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 206 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0178 | 2988.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0178 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 207 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-EL-0004 | 3000 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0004 |  |  | D-DWG-PHW-005.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [9 empty] | Ergon Energy | [29 empty] | POWER POLE TO BE RELOCATED BY OTHERS (ERGON) PRIOR TO CONSTRUCTION | Forreign service raw data.xlsx | 37
PHW-TS-0179 | 3000.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0179 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 208 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0180 | 3011.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0180 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 209 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0181 | 3023.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0181 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 210 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0182 | 3035 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0182 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 211 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0183 | 3046.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0183 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 212 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0184 | 3058.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0184 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 213 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0185 | 3069.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0185 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 214 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0186 | 3081.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0186 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 215 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0187 | 3093 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0187 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 216 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0188 | 3104.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0188 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 217 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0189 | 3116.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0189 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 218 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0190 | 3127.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0190 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 219 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0191 | 3139.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0191 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 220 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0192 | 3151 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0192 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 221 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0193 | 3162.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0193 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 222 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0194 | 3174.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0194 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 223 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0195 | 3185.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0195 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 224 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0196 | 3197.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0196 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 225 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-EL-0005 | 3350 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0005 |  |  | D-DWG-PHW-005.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [9 empty] | Ergon Energy | [29 empty] | POWER POLE TO BE RELOCATED BY OTHERS (ERGON) PRIOR TO CONSTRUCTION | Forreign service raw data.xlsx | 38
PHW-TB-025 | 3354.973 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-025 | [7 empty] | PHW |  | Type 6 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 37 |  |  | Bend | [9 empty] | 14743 | 1 | each | 14743 | Bend | 11.25 | DICL | 600 | 2800 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-025 | 3354.973 |  |  | PHW | Bend | HOR | PHW-BND-025 |  |  | D-DWG-PHW-005.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-TS-0197 | 3432.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0197 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 226 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0198 | 3449.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0198 |  |  | D-DWG-PHW-005 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 227 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-CC-0002 | 3457 | 3489 | 32 | PHW | Creek Crossing | TRENCHED CREEK CROSSING | PHW-CC-0002 | [7 empty] | PHW |  |  |  |  | FABRIC/VEGETATION | [37 empty] | PHw_PWG_Creek_Crossings.xlsx | 4 | [28 empty] | TRENCH | 0 | NO
PHW-PIPE-0040 | 3457.556 | 3487.105 | 29.549 | PHW | Pipe | PIPE | PHW-PIPE-0040 |  |  | D-DWG-PHW-005.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Open trench minor creek crossing | Pipelay Crew
PHW-PIPE-0041 | 3487.105 | 3534.937 | 47.832 | PHW | Pipe | PIPE | PHW-PIPE-0041 |  |  | D-DWG-PHW-005.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TB-026 | 3534.937 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-026 | [7 empty] | PHW |  | Type 3 | [11 empty] | MSCL | 650 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 38 |  |  | Bend | [9 empty] | 26944 | 1 | each | 26944 | Bend | 43.2 | MSCL | 650 | 2859 | 150 | Bend; MS - 43.2° | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TT-0029 | 3534.937 | 3547.077 | 12.14 | PHW | Trench Type | TRENCH SECTION |  | 4 | 12.14 | D-DWG-PHW-006.2 | D-DWG-PHW-006.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 34
PHW-BND-026 | 3534.937 |  |  | PHW | Bend | HOR | PHW-BND-026 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 43.2° | MSCL | 650 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PHW-PIPE-0042 | 3534.937 | 3547.079 | 12.142 | PHW | Pipe | PIPE | PHW-PIPE-0042 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Open trenched - foreign service | Special Crossings
PHW-WA-0007 | 3537 |  |  | PHW | Foreign Service | WATER | PHW-WA-0007 |  |  | D-DWG-PHW-005.2 |  |  | BYDA | Yes | PHW |  | BYDA WATER DN450 | [12 empty] | 450 | [27 empty] | Forreign service raw data.xlsx | 39
PHW-WA-0008 | 3538 |  |  | PHW | Foreign Service | WATER | PHW-WA-0008 |  |  | D-DWG-PHW-006.2 |  |  | BYDA | Yes | PHW |  | BYDA WATER DN450 | [12 empty] | 450 | [27 empty] | Forreign service raw data.xlsx | 42
PHW-WA-0009 | 3544 |  |  | PHW | Foreign Service | WATER | PHW-WA-0009 |  |  | D-DWG-PHW-005.2 |  |  | BYDA | Yes | PHW |  | BYDA WATER DN450 | [12 empty] | 450 | [27 empty] | Forreign service raw data.xlsx | 40
PHW-CM-0009 | 3545 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0009 |  |  | D-DWG-PHW-005.2 |  |  | BYDA | Yes | PHW |  | BYDA COMMS DN15 | [12 empty] | 15 | [27 empty] | Forreign service raw data.xlsx | 41
PHW-WA-0010 | 3545 |  |  | PHW | Foreign Service | WATER | PHW-WA-0010 |  |  | D-DWG-PHW-006.2 |  |  | BYDA | Yes | PHW |  | BYDA WATER DN450 | [12 empty] | 450 | [27 empty] | Forreign service raw data.xlsx | 43
PHW-CM-0010 | 3546 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0010 |  |  | D-DWG-PHW-006.2 |  |  | BYDA | Yes | PHW |  | BYDA COMMS DN15 | [12 empty] | 15 | [27 empty] | Forreign service raw data.xlsx | 44
PHW-TT-0030 | 3547.077 | 4416.742 | 869.665 | PHW | Trench Type | TRENCH SECTION |  | 1A | 869.665 | D-DWG-PHW-006.2 | D-DWG-PHW-007.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 35
PHW-PIPE-0043 | 3547.079 | 3785 | 237.921 | PHW | Pipe | PIPE | PHW-PIPE-0043 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TB-027 | 3549.714 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-027 | [7 empty] | PHW |  | Type 4 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 39 |  |  | Bend | [9 empty] | 16211 | 1 | each | 16211 | Bend | 45 | DICL | 600 | 2862 | 240 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-027 | 3549.714 |  |  | PHW | Bend | HOR | PHW-BND-027 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 45° | DICL | 600 | [7 empty] | 45 | PIPE | 0 | NO
PHW-SCV-005 | 3558 |  |  | PHW | Valve | SCV | PHW-SCV-005 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PHW-TB-080 | 3558.423 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-080 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 239 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN600xDN150 DIFBE SCOUR TEE |  | 150 | 2854 | 240 | Tee; DN600XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-EL-0006 | 3559 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0006 |  |  | D-DWG-PHW-006.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 45
PHW-EL-0007 | 3560 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0007 |  |  | D-DWG-PHW-006.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 46
PHW-AV-009 | 3569 |  |  | PHW | Valve | AV | PHW-AV-009 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-CM-0011 | 3762 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0011 |  |  | D-DWG-PHW-006.2 |  | D-DWG-PHW-006_C | BYDA | Yes | PHW |  | BYDA TELSTRA COMMSTUD | [9 empty] | Telstra | [30 empty] | Forreign service raw data.xlsx | 47
PHW-EL-0008 | 3762 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0008 |  |  | D-DWG-PHW-006.2 |  | D-DWG-PHW-006_C | BYDA | Yes | PHW |  | BYDA ELECTRICITY LV | [40 empty] | Forreign service raw data.xlsx | 48
PHW-PIPE-0044 | 3785 | 3832.98 | 47.98 | PHW | Pipe | PIPE | PHW-PIPE-0044 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Special Crossings
PHW-PIPE-0045 | 3832.98 | 3859.762 | 26.782 | PHW | Pipe | PIPE | PHW-PIPE-0045 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TB-028 | 3833.98 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-028 | [7 empty] | PHW |  | Type 5 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 40 |  |  | Bend | [9 empty] | 14784 | 1 | each | 14784 | Bend | 22.5 | DICL | 600 | 2922 | 240 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-028 | 3833.98 |  |  | PHW | Bend | HOR | PHW-BND-028 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 600 | [7 empty] | 22.5 | PIPE | 0 | NO
PHW-TS-0199 | 3836.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0199 |  |  | D-DWG-PHW-006 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 228 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0200 | 3841.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0200 |  |  | D-DWG-PHW-006 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 229 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TB-029 | 3843.886 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-029 | [7 empty] | PHW |  | Type 9 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 41 |  |  | Bend | [9 empty] | 14347 | 1 | each | 14347 | Bend | 11.25 | DICL | 600 | 2933 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-029 | 3843.886 |  |  | PHW | Bend | VERT | PHW-BND-029 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-CM-0012 | 3845 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0012 |  |  | D-DWG-PHW-006.2 |  |  | BYDA | Yes | PHW |  | BYDA COMMS DN15 | [12 empty] | 15 | [27 empty] | Forreign service raw data.xlsx | 49
PHW-WA-0011 | 3847 |  |  | PHW | Foreign Service | WATER | PHW-WA-0011 |  |  | D-DWG-PHW-006.2 |  |  | BYDA | Yes | PHW |  | BYDA WATER DN450 | [12 empty] | 450 | [27 empty] | Forreign service raw data.xlsx | 50
PHW-WA-0012 | 3855 |  |  | PHW | Foreign Service | WATER | PHW-WA-0012 |  |  | D-DWG-PHW-006.2 |  |  | BYDA | Yes | PHW |  | BYDA WATER DN450 | [12 empty] | 450 | [27 empty] | Forreign service raw data.xlsx | 51
PHW-TB-030 | 3858.762 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-030 | [7 empty] | PHW |  | Type 5 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 42 |  |  | Bend | [9 empty] | 14784 | 1 | each | 14784 | Bend | 22.5 | DICL | 600 | 2935 | 240 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-030 | 3858.762 |  |  | PHW | Bend | HOR | PHW-BND-030 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 600 | [7 empty] | 22.5 | PIPE | 0 | NO
PHW-PIPE-0046 | 3859.762 | 4085 | 225.238 | PHW | Pipe | PIPE | PHW-PIPE-0046 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-VG-0044 | 3930 | 3940 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW044 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 61 | 283 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-VG-0045 | 3950 | 3960 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW045 | [49 empty] | 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 62 | 99 | LIGHT | [26 empty] | TRENCH | 0 | NO
PHW-PIPE-0047 | 4085 | 4100.183 | 15.183 | PHW | Pipe | PIPE | PHW-PIPE-0047 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Special Crossings
PHW-PIPE-0048 | 4100.183 | 4111.325 | 11.142 | PHW | Pipe | PIPE | PHW-PIPE-0048 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-EL-0009 | 4102 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0009 |  |  | D-DWG-PHW-006.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 52
PHW-TS-0201 | 4105.75 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0201 |  |  | D-DWG-PHW-006 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 230 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0049 | 4111.325 | 4314.51 | 203.185 | PHW | Pipe | PIPE | PHW-PIPE-0049 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-WA-0013 | 4119 |  |  | PHW | Foreign Service | WATER | PHW-WA-0013 |  |  | D-DWG-PHW-006.2 |  |  | BYDA | Yes | PHW |  | BYDA WATER | [40 empty] | Forreign service raw data.xlsx | 53
PHW-CM-0013 | 4178 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0013 |  |  | D-DWG-PHW-006.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMS DN35 | [9 empty] | Telstra |  |  | 35 | [27 empty] | Forreign service raw data.xlsx | 54
PHW-EL-0010 | 4178 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0010 |  |  | D-DWG-PHW-006.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 55
PHW-AV-010 | 4269 |  |  | PHW | Valve | AV | PHW-AV-010 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-TB-031 | 4304.94 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-031 | [7 empty] | PHW |  | Type 6 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 43 |  |  | Bend | [9 empty] | 14743 | 1 | each | 14743 | Bend | 11.25 | DICL | 600 | 3029 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-031 | 4304.94 |  |  | PHW | Bend | HOR | PHW-BND-031 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-PIPE-0050 | 4314.51 | 4339.807 | 25.297 | PHW | Pipe | PIPE | PHW-PIPE-0050 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-EL-0011 | 4317 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0011 |  |  | D-DWG-PHW-007.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 56
PHW-TS-0202 | 4318.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0202 |  |  | D-DWG-PHW-007 |  |  |  |  | 7.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 231 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0203 | 4327.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0203 |  |  | D-DWG-PHW-007 |  |  |  |  | 7.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 232 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0204 | 4335.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0204 |  |  | D-DWG-PHW-007 |  |  |  |  | 7.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 233 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0051 | 4339.807 | 4416.742 | 76.935 | PHW | Pipe | PIPE | PHW-PIPE-0051 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TB-032 | 4409.494 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-032 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 44 |  |  | Bend | [9 empty] | 14150 | 1 | each | 14150 | Bend | 11.25 | DICL | 600 | 3077 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-032 | 4409.494 |  |  | PHW | Bend | HOR | PHW-BND-032 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-TB-033 | 4413.12 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-033 | [7 empty] | PHW |  | Type 4 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 45 |  |  | Bend | [9 empty] | 16211 | 1 | each | 16211 | Bend | 45 | DICL | 600 | 3078 | 240 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-033 | 4413.12 |  |  | PHW | Bend | HOR | PHW-BND-033 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 45° | DICL | 600 | [7 empty] | 45 | PIPE | 0 | NO
PHW-TT-0031 | 4416.742 | 4455.042 | 38.3 | PHW | Trench Type | TRENCH SECTION |  | 8A | 38.3 | D-DWG-PHW-007.2 | D-DWG-PHW-007.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 36
PHW-PIPE-0052 | 4416.742 | 4455.042 | 38.3 | PHW | Pipe | PIPE | PHW-PIPE-0052 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 + OD813 12WT MS Enveloper | [6 empty] | MSCL | 660 | [54 empty] | Morris Road | Trenchless
PHW-RD-0003 | 4416.743 | 4455.043 | 38.3 | PHW | Road & Rail Crossing | MINOR ROAD CROSSING | PHW-RD-0003 |  | 38.3 | [5 empty] | PHW | Morris Road |  | Sealed | 600 |  |  | OD660x6WT MSCL Sintalock Type 2 PN35 Carrier & OD813x12WT MS Enveloper |  |  |  |  | TRC | [15 empty] | Thrust Boring | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 10 | [28 empty] | TRENCH | 0 | NO
PHW-CM-0014 | 4417 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0014 |  |  | D-DWG-PHW-007.2 |  |  | BYDA | Yes | PHW |  | BYDA COMMS DN15 | [12 empty] | 15 | [27 empty] | Forreign service raw data.xlsx | 58
PHW-WA-0014 | 4417 |  |  | PHW | Foreign Service | WATER | PHW-WA-0014 |  |  | D-DWG-PHW-007.2 |  |  | BYDA | Yes | PHW |  | BYDA WATER DN450 | [12 empty] | 450 | [27 empty] | Forreign service raw data.xlsx | 57
PHW-CM-0015 | 4435 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0015 |  |  | D-DWG-PHW-007.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMS DN20 | [9 empty] | Telstra |  |  | 20 | [27 empty] | Forreign service raw data.xlsx | 59
PHW-CM-0016 | 4437 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0016 |  |  | D-DWG-PHW-007.2 |  | D-DWG-PHW-007_C | BYDA | Yes | PHW |  | BYDA TELSTRA COMMSTUD | [9 empty] | Telstra | [30 empty] | Forreign service raw data.xlsx | 60
PHW-SW-0003 | 4448 |  |  | PHW | Foreign Service | SEWER | PHW-SW-0003 |  |  | D-DWG-PHW-007.2 |  | D-DWG-PHW-007_C | BYDA | Yes | PHW |  | BYDA TRC SEWER | [9 empty] | Toowoomba Regional Council | [30 empty] | Forreign service raw data.xlsx | 61
PHW-TT-0032 | 4455.042 | 4534.979 | 79.937 | PHW | Trench Type | TRENCH SECTION |  | 4 | 79.937 | D-DWG-PHW-007.2 | D-DWG-PHW-007.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 37
PHW-PIPE-0053 | 4455.042 | 4534.797 | 79.755 | PHW | Pipe | PIPE | PHW-PIPE-0053 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TB-081 | 4470 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-081 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 240 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN600xDN150 DIFBE SCOUR TEE |  | 150 | 3082 | 240 | Tee; DN600XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-SCV-006 | 4470 |  |  | PHW | Valve | SCV | PHW-SCV-006 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PHW-BND-034 | 4486.634 |  |  | PHW | Bend | HOR | PHW-BND-034 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-PIPE-0054 | 4534.797 | 4663.144 | 128.347 | PHW | Pipe | PIPE | PHW-PIPE-0054 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TT-0033 | 4534.979 | 4663.144 | 128.165 | PHW | Trench Type | TRENCH SECTION |  | 1A | 128.165 | D-DWG-PHW-007.2 | D-DWG-PHW-007.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 38
PHW-AV-011 | 4605 |  |  | PHW | Valve | AV | PHW-AV-011 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-TS-0205 | 4613.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0205 |  |  | D-DWG-PHW-007 |  |  |  |  | 7.2 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 234 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0206 | 4629.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0206 |  |  | D-DWG-PHW-007 |  |  |  |  | 7.2 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 235 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-SCV-007 | 4661 |  |  | PHW | Valve | SCV | PHW-SCV-007 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PHW-TB-082 | 4661.417 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-082 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 241 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN600xDN150 DIFBE SCOUR TEE |  | 150 | 3087 | 240 | Tee; DN600XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-CC-0003 | 4663 | 4696 | 33 | PHW | Creek Crossing | TRENCHED CREEK CROSSING | PHW-CC-0003 | [7 empty] | PHW |  |  |  |  | LOOSE ROCK | A | [36 empty] | PHw_PWG_Creek_Crossings.xlsx | 5 | [28 empty] | TRENCH | 0 | NO
PHW-TT-0034 | 4663.144 | 4695.751 | 32.607 | PHW | Trench Type | TRENCH SECTION |  | 5 | 32.607 | D-DWG-PHW-007.2 | D-DWG-PHW-007.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 39
PHW-PIPE-0055 | 4663.144 | 4695.751 | 32.607 | PHW | Pipe | PIPE | PHW-PIPE-0055 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Open Trenched Creek Crossings | Pipelay Crew
PHW-BND-035 | 4680.222 |  |  | PHW | Bend | VERT | PHW-BND-035 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 9.5° | MSCL | 650 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PHW-TT-0035 | 4695.751 | 4712.804 | 17.053 | PHW | Trench Type | TRENCH SECTION |  | 2 | 17.053 | D-DWG-PHW-007.2 | D-DWG-PHW-007.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 40
PHW-PIPE-0056 | 4695.751 | 4712.804 | 17.053 | PHW | Pipe | PIPE | PHW-PIPE-0056 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TT-0036 | 4712.804 | 4758.731 | 45.927 | PHW | Trench Type | TRENCH SECTION |  | 1A/1B/1C | 45.927 | D-DWG-PHW-007.2 | D-DWG-PHW-007.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 41
PHW-PIPE-0057 | 4712.804 | 4758.731 | 45.927 | PHW | Pipe | PIPE | PHW-PIPE-0057 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TT-0037 | 4758.731 | 5731.564 | 972.833 | PHW | Trench Type | TRENCH SECTION |  | 1A | 972.833 | D-DWG-PHW-007.2 | D-DWG-PHW-009.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 42
PHW-PIPE-0058 | 4758.731 | 4857.072 | 98.341 | PHW | Pipe | PIPE | PHW-PIPE-0058 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-PIPE-0059 | 4857.072 | 4971.37 | 114.298 | PHW | Pipe | PIPE | PHW-PIPE-0059 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Pipelay Crew
PHW-TS-0207 | 4859.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0207 |  |  | D-DWG-PHW-007 |  |  |  |  | 7.3 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 236 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BND-036 | 4859.321 |  |  | PHW | Bend | VERT | PHW-BND-036 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-TB-034 | 4859.322 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-034 | [7 empty] | PHW |  | Type 9 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 46 |  |  | Bend | [9 empty] | 14347 | 1 | each | 14347 | Bend | 11.25 | DICL | 600 | 3026 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TS-0208 | 4864.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0208 |  |  | D-DWG-PHW-007 |  |  |  |  | 7.3 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 237 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0209 | 4869.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0209 |  |  | D-DWG-PHW-007 |  |  |  |  | 7.3 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 238 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0210 | 4876.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0210 |  |  | D-DWG-PHW-007 |  |  |  |  | 7.3 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 239 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0211 | 4886.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0211 |  |  | D-DWG-PHW-007 |  |  |  |  | 7.3 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 240 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0212 | 4895.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0212 |  |  | D-DWG-PHW-007 |  |  |  |  | 7.3 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 241 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0046 | 4900 | 4910 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW046 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 63 | 309 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-TS-0213 | 4905.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0213 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 242 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0214 | 4914.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0214 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 243 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-AV-012 | 4920 |  |  | PHW | Valve | AV | PHW-AV-012 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-TS-0215 | 4954.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0215 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 244 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-SCV -001 | 4961 |  |  | PHW | Valve | SCV | PHW-SCV -001 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PHW-TB-083 | 4961.176 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-083 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 242 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN600xDN150 DIFBE SCOUR TEE |  | 150 | 2999 | 240 | Tee; DN600XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-PIPE-0060 | 4971.37 | 5175.571 | 204.201 | PHW | Pipe | PIPE | PHW-PIPE-0060 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-PIPE-0061 | 5175.571 | 5323.75 | 148.179 | PHW | Pipe | PIPE | PHW-PIPE-0061 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TS-0216 | 5182.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0216 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 245 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0217 | 5195.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0217 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 246 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0218 | 5209.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0218 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 247 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0219 | 5222.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0219 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 248 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0220 | 5236.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0220 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 249 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0221 | 5249.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0221 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 250 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0222 | 5263.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0222 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 251 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-AV-013 | 5270 |  |  | PHW | Valve | AV | PHW-AV-013 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-PIPE-0062 | 5323.75 | 5600 | 276.25 | PHW | Pipe | PIPE | PHW-PIPE-0062 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-BND-037 | 5356.118 |  |  | PHW | Bend | HOR | PHW-BND-037 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 600 | [7 empty] | 22.5 | PIPE | 0 | NO
PHW-TB-035 | 5356.119 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-035 | [7 empty] | PHW |  | Type 5 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 47 |  |  | Bend | [9 empty] | 14784 | 1 | each | 14784 | Bend | 22.5 | DICL | 600 | 2863 | 240 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TS-0223 | 5359.75 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0223 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 252 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0224 | 5367.35 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0224 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 253 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0225 | 5374.95 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0225 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 254 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0226 | 5382.55 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0226 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 255 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TB-036 | 5386.241 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-036 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 48 |  |  | Bend | [9 empty] | 14150 | 1 | each | 14150 | Bend | 11.25 | DICL | 600 | 2828 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-038 | 5386.241 |  |  | PHW | Bend | HOR | PHW-BND-038 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-VG-0047 | 5390 | 5410 | 20 | PHW | Vegetation | TREE REMOVAL | VEG_PHW047 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 64 | 142 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-TS-0227 | 5390.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0227 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 256 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0228 | 5401 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0228 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 257 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0229 | 5411.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0229 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 258 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0230 | 5421.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0230 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 259 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0231 | 5431.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0231 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 260 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0232 | 5442.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0232 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 261 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0233 | 5452.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0233 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 262 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0234 | 5462.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0234 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 263 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0235 | 5473.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0235 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 264 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0236 | 5483.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0236 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 265 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0237 | 5493.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0237 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 266 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-CM-0017 | 5494 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0017 |  |  | D-DWG-PHW-008.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMS | [9 empty] | Telstra | [30 empty] | Forreign service raw data.xlsx | 62
PHW-CM-0018 | 5494 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0018 |  |  | D-DWG-PHW-008.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMS | [9 empty] | Telstra | [30 empty] | Forreign service raw data.xlsx | 63
PHW-TB-037 | 5498.469 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-037 | [7 empty] | PHW |  | Type 5 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 49 |  |  | Bend | [9 empty] | 14784 | 1 | each | 14784 | Bend | 22.5 | DICL | 600 | 2731 | 240 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-039 | 5498.469 |  |  | PHW | Bend | HOR | PHW-BND-039 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 600 | [7 empty] | 22.5 | PIPE | 0 | NO
PHW-TS-0238 | 5501.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0238 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 267 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0239 | 5508.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0239 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 268 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0240 | 5515.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0240 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 269 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0241 | 5522 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0241 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 270 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0242 | 5527.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0242 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 271 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0243 | 5536 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0243 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 272 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0244 | 5544.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0244 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 273 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0245 | 5552.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0245 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 274 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0246 | 5561.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0246 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 275 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0247 | 5569.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0247 |  |  | D-DWG-PHW-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 276 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0063 | 5600 | 5731.564 | 131.564 | PHW | Pipe | PIPE | PHW-PIPE-0063 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Pipelay Crew
PHW-TB-038 | 5641.654 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-038 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 50 |  |  | Bend | [9 empty] | 14150 | 1 | each | 14150 | Bend | 11.25 | DICL | 600 | 2615 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-040 | 5641.654 |  |  | PHW | Bend | HOR | PHW-BND-040 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-TS-0248 | 5671.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0248 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 277 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0249 | 5682.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0249 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 278 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0250 | 5694.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0250 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 279 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0251 | 5705.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0251 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 280 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0252 | 5717.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0252 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 281 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TB-039 | 5719.91 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-039 | [7 empty] | PHW |  | Type 9 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 51 |  |  | Bend | [9 empty] | 14347 | 1 | each | 14347 | Bend | 11.25 | DICL | 600 | 2563 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-041 | 5719.91 |  |  | PHW | Bend | VERT | PHW-BND-041 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-TS-0253 | 5723.75 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0253 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.2 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 282 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0025 | 5726.4 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0025 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.2 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 283 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0254 | 5729.05 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0254 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.2 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 284 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TT-0038 | 5731.564 | 5754.45 | 22.886 | PHW | Trench Type | TRENCH SECTION |  | 4 | 22.886 | D-DWG-PHW-009.2 | D-DWG-PHW-009.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 43
PHW-PIPE-0064 | 5731.564 | 5754.45 | 22.886 | PHW | Pipe | PIPE | PHW-PIPE-0064 |  |  | D-DWG-PHW-009.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-BS-0026 | 5733 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0026 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.3 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 285 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0027 | 5736 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0027 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.3 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 286 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0028 | 5739 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0028 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.3 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 287 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0029 | 5742 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0029 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.3 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 288 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0030 | 5745 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0030 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.3 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 289 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0031 | 5748 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0031 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.3 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 290 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0032 | 5751 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0032 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.3 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 291 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0033 | 5754 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0033 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.3 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 292 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TT-0039 | 5754.45 | 6114.476 | 360.026 | PHW | Trench Type | TRENCH SECTION |  | 1A | 360.026 | D-DWG-PHW-009.2 | D-DWG-PHW-009.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 44
PHW-PIPE-0065 | 5754.45 | 5897.237 | 142.787 | PHW | Pipe | PIPE | PHW-PIPE-0065 |  |  | D-DWG-PHW-009.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TS-0255 | 5756.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0255 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.4 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 293 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0256 | 5761 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0256 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.4 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 294 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0257 | 5765.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0257 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.4 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 295 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0258 | 5769.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0258 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.4 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 296 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0259 | 5775.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0259 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 297 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0260 | 5783.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0260 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 298 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0261 | 5791.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0261 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 299 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0262 | 5799.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0262 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 300 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0263 | 5808.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0263 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 301 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0264 | 5816.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0264 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.5 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 302 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BND-042 | 5823.56 |  |  | PHW | Bend | HOR | PHW-BND-042 |  |  | D-DWG-PHW-009.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-TB-040 | 5823.561 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-040 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 52 |  |  | Bend | [9 empty] | 14150 | 1 | each | 14150 | Bend | 11.25 | DICL | 600 | 2381 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TS-0265 | 5825.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0265 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.6 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 303 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0266 | 5835.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0266 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.6 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 304 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0048 | 5840 | 5850 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW048 | [49 empty] | 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 65 | 85.2 | LIGHT | [26 empty] | TRENCH | 0 | NO
PHW-TS-0267 | 5845.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0267 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.6 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 305 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BND-043 | 5849.629 |  |  | PHW | Bend | VERT | PHW-BND-043 |  |  | D-DWG-PHW-009.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-TB-041 | 5851.91 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-041 | [7 empty] | PHW |  | Type 9 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 53 |  |  | Bend | [9 empty] | 14347 | 1 | each | 14347 | Bend | 11.25 | DICL | 600 | 2360 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TS-0268 | 5852.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0268 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.7 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 306 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0269 | 5855.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0269 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.7 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 307 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0034 | 5857.25 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0034 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.7 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 308 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0270 | 5858.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0270 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.7 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 309 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0271 | 5862.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0271 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.7 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 310 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0272 | 5870 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0272 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.8 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 311 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0273 | 5875 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0273 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.8 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 312 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0035 | 5877.5 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0035 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.8 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 313 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0274 | 5880 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0274 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.8 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 314 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0275 | 5885 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0275 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.8 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 315 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0276 | 5893.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0276 |  |  | D-DWG-PHW-009 |  |  |  |  | 9,9 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 316 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0066 | 5897.237 | 6114.476 | 217.239 | PHW | Pipe | PIPE | PHW-PIPE-0066 |  |  | D-DWG-PHW-009.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-AV-014 | 5906 |  |  | PHW | Valve | AV | PHW-AV-014 |  |  | D-DWG-PHW-009.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-TB-042 | 5909.993 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-042 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 54 |  |  | Bend | [9 empty] | 14150 | 1 | each | 14150 | Bend | 11.25 | DICL | 600 | 2280 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TS-0277 | 5914.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0277 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.9.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 317 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0278 | 5952.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0278 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 318 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0279 | 5959.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0279 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 319 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0280 | 5966.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0280 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 320 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0049 | 5970 | 5990 | 20 | PHW | Vegetation | TREE REMOVAL | VEG_PHW049 | [49 empty] | 2 LARGE TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 66 | 212 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-TS-0281 | 5973.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0281 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 321 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0282 | 5980.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0282 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 322 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0283 | 5987.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0283 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 323 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0284 | 5994.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0284 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 324 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0285 | 6002 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0285 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 325 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0286 | 6009.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0286 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 326 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0287 | 6016.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0287 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 327 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0288 | 6023.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0288 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 328 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0289 | 6030.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0289 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 329 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0290 | 6037.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0290 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.1 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 330 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0291 | 6042.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0291 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.11 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 331 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0292 | 6048.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0292 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.11 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 332 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0036 | 6053.7 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0036 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.11 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 333 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0293 | 6059.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0293 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.11 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 334 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0294 | 6064.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0294 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.11 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 335 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0037 | 6070.5 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0037 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.11 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 336 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0295 | 6076.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0295 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.11 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 337 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0296 | 6081.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0296 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.11 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 338 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0038 | 6087.3 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0038 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.11 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 339 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0297 | 6092.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0297 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.11 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 340 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0298 | 6098.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0298 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.11 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 341 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TB-043 | 6101.187 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-043 | [7 empty] | PHW |  | Type 5 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 55 |  |  | Bend | [9 empty] | 14784 | 1 | each | 14784 | Bend | 22.5 | DICL | 600 | 2498 | 150 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TS-0299 | 6104 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0299 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.12 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 342 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0300 | 6111.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0300 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.12 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 343 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TT-0040 | 6114.476 | 6160.84 | 46.364 | PHW | Trench Type | TRENCH SECTION |  | 4 | 46.364 | D-DWG-PHW-009.2 | D-DWG-PHW-009.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 45
PHW-PIPE-0067 | 6114.476 | 6160.84 | 46.364 | PHW | Pipe | PIPE | PHW-PIPE-0067 |  |  | D-DWG-PHW-009.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Open trenched - foreign service | Special Crossings
PHW-GA-0001 | 6125 |  |  | PHW | Foreign Service | GAS | PHW-GA-0001 |  |  | D-DWG-PHW-009.2 |  |  | BYDA | Yes | PHW |  | BYDA GAS DN400 | [9 empty] | APA Group |  |  | 400 | [26 empty] | LOCATION/DEPTH OF DUAL APA GAS MAINS NOT KNOWN. CONTRACTOR TO CONFIRM PRIOR TO CONSTRUCTION. | Forreign service raw data.xlsx | 64
PHW-GA-0002 | 6141 |  |  | PHW | Foreign Service | GAS | PHW-GA-0002 |  |  | D-DWG-PHW-009.2 |  |  | BYDA | Yes | PHW |  | BYDA GAS DN400 | [12 empty] | 400 | [27 empty] | Forreign service raw data.xlsx | 65
PHW-TS-0301 | 6160.84 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0301 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.13 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 344 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TT-0041 | 6160.84 | 6368.309 | 207.469 | PHW | Trench Type | TRENCH SECTION |  | 1A | 207.469 | D-DWG-PHW-009.2 | D-DWG-PHW-010.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 46
PHW-PIPE-0068 | 6160.84 | 6203.719 | 42.879 | PHW | Pipe | PIPE | PHW-PIPE-0068 |  |  | D-DWG-PHW-009.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TS-0302 | 6169.24 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0302 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.13 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 345 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0303 | 6177.64 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0303 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.13 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 346 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TB-044 | 6181.401 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-044 | [7 empty] | PHW |  | Type 7 | [11 empty] | MSCL | 650 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 56 |  |  | Bend | [9 empty] | 19220 | 1 | each | 19220 | Bend | 7.7 | MSCL | 650 | 2567 | 150 | Bend; MS - 7.7° | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TS-0304 | 6186.04 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0304 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.13 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 347 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-GA-0003 | 6194 |  |  | PHW | Foreign Service | GAS | PHW-GA-0003 |  |  | D-DWG-PHW-009.2 |  |  | BYDA | Yes | PHW |  | BYDA GAS DN400 | [12 empty] | 400 | [27 empty] | Forreign service raw data.xlsx | 66
PHW-TS-0305 | 6194.44 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0305 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.13 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 348 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0306 | 6202.84 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0306 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.13 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 349 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0069 | 6203.719 | 6225 | 21.281 | PHW | Pipe | PIPE | PHW-PIPE-0069 |  |  | D-DWG-PHW-009.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Special Crossings
PHW-TS-0307 | 6211.24 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0307 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.13 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 350 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0308 | 6219.64 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0308 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.13 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 351 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0070 | 6225 | 6260 | 35 | PHW | Pipe | PIPE | PHW-PIPE-0070 |  |  | D-DWG-PHW-009.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-TS-0309 | 6228.04 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0309 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.13 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 352 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0310 | 6236.44 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0310 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.13 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 353 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-EL-0012 | 6237 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0012 |  |  | D-DWG-PHW-009.2 |  | D-DWG-PHW-009_C | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 67
PHW-TS-0311 | 6244.84 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0311 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.13 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 354 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0312 | 6253.24 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0312 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.13 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 355 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0071 | 6260 | 6270 | 10 | PHW | Pipe | PIPE | PHW-PIPE-0071 |  |  | D-DWG-PHW-009.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Special Crossings
PHW-TS-0313 | 6261.64 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0313 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.13 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 356 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0072 | 6270 | 6368.309 | 98.309 | PHW | Pipe | PIPE | PHW-PIPE-0072 |  |  | D-DWG-PHW-009.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-TS-0314 | 6270.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0314 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.14 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 357 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0315 | 6287.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0315 |  |  | D-DWG-PHW-009 |  |  |  |  | 9.14 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 358 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0316 | 6303.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0316 |  |  | D-DWG-PHW-010 |  |  |  |  | 9.14 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 359 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0317 | 6320.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0317 |  |  | D-DWG-PHW-010 |  |  |  |  | 9.14 | [42 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 360 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0318 | 6337 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0318 |  |  | D-DWG-PHW-010 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 361 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0319 | 6350.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0319 |  |  | D-DWG-PHW-010 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 362 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0320 | 6366.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0320 |  |  | D-DWG-PHW-010 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 363 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-RD-0004 | 6368.309 | 6385.309 | 17 | PHW | Road & Rail Crossing | MINOR ROAD CROSSING | PHW-RD-0004 |  | 17 | [5 empty] | PHW | Ganzer Road |  | Sealed | 600 |  |  | DN600 PN35 DICL RRJ | 17 |  |  |  | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 11 | [28 empty] | TRENCH | 0 | NO
PHW-TT-0042 | 6368.309 | 6392.653 | 24.344 | PHW | Trench Type | TRENCH SECTION |  | 6 | 24.344 | D-DWG-PHW-010.2 | D-DWG-PHW-010.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 47
PHW-PIPE-0073 | 6368.309 | 6392.653 | 24.344 | PHW | Pipe | PIPE | PHW-PIPE-0073 |  |  | D-DWG-PHW-010.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Open Trench Minor road crossing | Special Crossings
PHW-TS-0321 | 6381.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0321 |  |  | D-DWG-PHW-010 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 364 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TT-0043 | 6392.653 | 6481.011 | 88.358 | PHW | Trench Type | TRENCH SECTION |  | 1A | 88.358 | D-DWG-PHW-010.2 | D-DWG-PHW-010.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 48
PHW-PIPE-0074 | 6392.653 | 6477.516 | 84.863 | PHW | Pipe | PIPE | PHW-PIPE-0074 |  |  | D-DWG-PHW-010.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TS-0322 | 6397.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0322 |  |  | D-DWG-PHW-010 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 365 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0323 | 6419.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0323 |  |  | D-DWG-PHW-010 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 366 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0324 | 6426.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0324 |  |  | D-DWG-PHW-010 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 367 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0039 | 6429.35 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0039 |  |  | D-DWG-PHW-010 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 368 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0325 | 6432.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0325 |  |  | D-DWG-PHW-010 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 369 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0326 | 6452.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0326 |  |  | D-DWG-PHW-010 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 370 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0327 | 6459.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0327 |  |  | D-DWG-PHW-010 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 371 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0328 | 6466.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0328 |  |  | D-DWG-PHW-010 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 372 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0040 | 6474 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0040 |  |  | D-DWG-PHW-010 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 373 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0075 | 6477.516 | 6506.275 | 28.759 | PHW | Pipe | PIPE | PHW-PIPE-0075 |  |  | D-DWG-PHW-010.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Open Trenched Creek Crossings | Special Crossings
PHW-TT-0044 | 6481.011 | 6506.275 | 25.264 | PHW | Trench Type | TRENCH SECTION |  | 4 | 25.264 | D-DWG-PHW-010.2 | D-DWG-PHW-010.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 49
PHW-FN-0016 | 6486 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0016 |  |  | D-DWG-PHW-010.2 |  |  |  | Yes | PHW |  | FENCE LINE NO POST - WIRE ONLY | [40 empty] | Forreign service raw data.xlsx | 68
PHW-GA-0004 | 6488 |  |  | PHW | Foreign Service | GAS | PHW-GA-0004 |  |  | D-DWG-PHW-010.2 |  |  | PUP | Yes | PHW |  | PUP GAS DN250 | [9 empty] | APA Group |  |  | 250 | [26 empty] | LOCATION/DEPTH OF DUAL APA GAS MAINS NOT KNOWN. CONTRACTOR TO CONFIRM PRIOR TO CONSTRUCTION. | Forreign service raw data.xlsx | 69
PHW-GA-0005 | 6494 |  |  | PHW | Foreign Service | GAS | PHW-GA-0005 |  |  | D-DWG-PHW-010.2 |  |  | PUP | Yes | PHW |  | PUP GAS DN400 | [9 empty] | APA Group |  |  | 400 | [26 empty] | LOCATION/DEPTH OF DUAL APA GAS MAINS NOT KNOWN. CONTRACTOR TO CONFIRM PRIOR TO CONSTRUCTION. | Forreign service raw data.xlsx | 70
PHW-TT-0045 | 6506.275 | 6772.73 | 266.455 | PHW | Trench Type | TRENCH SECTION |  | 1A | 266.455 | D-DWG-PHW-010.2 | D-DWG-PHW-010.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 50
PHW-PIPE-0076 | 6506.275 | 6772.73 | 266.455 | PHW | Pipe | PIPE | PHW-PIPE-0076 |  |  | D-DWG-PHW-010.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TS-0329 | 6525.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0329 |  |  | D-DWG-PHW-010 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 374 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0330 | 6545.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0330 |  |  | D-DWG-PHW-010 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 375 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0331 | 6564.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0331 |  |  | D-DWG-PHW-010 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 376 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-AV-015 | 6573 |  |  | PHW | Valve | AV | PHW-AV-015 |  |  | D-DWG-PHW-010.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-VG-0050 | 6620 | 6630 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW050 | [49 empty] | 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 67 | 27 | LIGHT | [26 empty] | TRENCH | 0 | NO
PHW-TT-0046 | 6772.73 | 6792.875 | 20.145 | PHW | Trench Type | TRENCH SECTION |  | 5 | 20.145 | D-DWG-PHW-010.2 | D-DWG-PHW-010.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 51
PHW-PIPE-0077 | 6772.73 | 6792.875 | 20.145 | PHW | Pipe | PIPE | PHW-PIPE-0077 |  |  | D-DWG-PHW-010.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Open trench minor creek crossing | Special Crossings
PHW-CC-0004 | 6773 | 6793 | 20 | PHW | Creek Crossing | TRENCHED CREEK CROSSING | PHW-CC-0004 | [7 empty] | PHW |  |  |  |  | LOOSE ROCK | A | [36 empty] | PHw_PWG_Creek_Crossings.xlsx | 6 | [28 empty] | TRENCH | 0 | NO
PHW-BND-044 | 6786.183 |  |  | PHW | Bend | VERT | PHW-BND-044 |  |  | D-DWG-PHW-010.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 19.1° | MSCL | 650 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PHW-TT-0047 | 6792.875 | 6886.695 | 93.82 | PHW | Trench Type | TRENCH SECTION |  | 1A | 93.82 | D-DWG-PHW-010.2 | D-DWG-PHW-010.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 52
PHW-PIPE-0078 | 6792.875 | 6886.695 | 93.82 | PHW | Pipe | PIPE | PHW-PIPE-0078 |  |  | D-DWG-PHW-010.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TB-084 | 6796.976 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-084 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 243 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN600xDN150 DIFBE SCOUR TEE |  | 150 | 2958 | 200 | Tee; DN600XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-SCV-008 | 6797 |  |  | PHW | Valve | SCV | PHW-SCV-008 |  |  | D-DWG-PHW-010.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PHW-TT-0048 | 6886.695 | 6934.724 | 48.029 | PHW | Trench Type | TRENCH SECTION |  | 5 | 48.029 | D-DWG-PHW-010.2 | D-DWG-PHW-010.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 53
PHW-PIPE-0079 | 6886.695 | 6934.724 | 48.029 | PHW | Pipe | PIPE | PHW-PIPE-0079 |  |  | D-DWG-PHW-010.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-CC-0005 | 6887 | 6935 | 48 | PHW | Creek Crossing | TRENCHED CREEK CROSSING | PHW-CC-0005 | [7 empty] | PHW |  |  |  |  | LOOSE ROCK | A | [36 empty] | PHw_PWG_Creek_Crossings.xlsx | 7 | [28 empty] | TRENCH | 0 | NO
PHW-AV-016 | 6887 |  |  | PHW | Valve | AV | PHW-AV-016 |  |  | D-DWG-PHW-010.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-TT-0049 | 6934.724 | 6980.09 | 45.366 | PHW | Trench Type | TRENCH SECTION |  | 1A | 45.366 | D-DWG-PHW-010.2 | D-DWG-PHW-010.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 54
PHW-PIPE-0080 | 6934.724 | 6980.09 | 45.366 | PHW | Pipe | PIPE | PHW-PIPE-0080 |  |  | D-DWG-PHW-010.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TS-0332 | 6937.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0332 |  |  | D-DWG-PHW-010 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 377 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0333 | 6947.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0333 |  |  | D-DWG-PHW-010 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 378 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0334 | 6956.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0334 |  |  | D-DWG-PHW-010 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 379 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0335 | 6965.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0335 |  |  | D-DWG-PHW-010 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 380 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-RD-0005 | 6980.09 | 7035.325 | 55.235 | PHW | Road & Rail Crossing | MAJOR ROAD CROSSING | PHW-RD-0005 |  | 55.235 | [5 empty] | PHW | Gowrie Junction road |  | Sealed | 600 |  |  | OD660x6WT MSCL Sintalock Type 2 PN35 Carrier & OD813x12WT MS Enveloper |  |  |  |  | TRC | [15 empty] | Thrust Boring | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 12 | [28 empty] | TRENCH | 0 | NO
PHW-TT-0050 | 6980.09 | 7035.325 | 55.235 | PHW | Trench Type | TRENCH SECTION |  | 8A | 55.235 | D-DWG-PHW-010.2 | D-DWG-PHW-011.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 55
PHW-PIPE-0081 | 6980.09 | 7035.325 | 55.235 | PHW | Pipe | PIPE | PHW-PIPE-0081 |  |  | D-DWG-PHW-010.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 + OD813 12WT MS Enveloper | [6 empty] | MSCL | 660 | [54 empty] | Gowrie Junction road | Trenchless
PHW-FN-0017 | 6993 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0017 |  |  | D-DWG-PHW-010.2 |  |  |  | Yes | PHW |  | FENCE LINE NO POSTS | [40 empty] | Forreign service raw data.xlsx | 71
PHW-FN-0018 | 6993 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0018 |  |  | D-DWG-PHW-010.2 |  |  |  | Yes | PHW |  | FENCE LINE NO POSTS | [40 empty] | Forreign service raw data.xlsx | 72
PHW-CM-0019 | 6995 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0019 |  |  | D-DWG-PHW-010.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMSTUD | [9 empty] | Telstra | [30 empty] | Forreign service raw data.xlsx | 73
PHW-CM-0020 | 6996 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0020 |  |  | D-DWG-PHW-010.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMSTUD | [9 empty] | Telstra | [30 empty] | Forreign service raw data.xlsx | 74
PHW-CM-0021 | 6996 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0021 |  |  | D-DWG-PHW-010.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMSTUD | [9 empty] | Telstra | [30 empty] | Forreign service raw data.xlsx | 75
PHW-CM-0022 | 6997 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0022 |  |  | D-DWG-PHW-010.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMSTUD | [9 empty] | Telstra | [30 empty] | Forreign service raw data.xlsx | 76
PHW-CM-0023 | 6998 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0023 |  |  | D-DWG-PHW-010.2 |  |  | BYDA | Yes | PHW |  | BYDA NEXTGEN | [9 empty] | Nextgen | [30 empty] | Forreign service raw data.xlsx | 77
PHW-CM-0024 | 7021 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0024 |  |  | D-DWG-PHW-011.2 |  | D-DWG-PHW-011_C | BYDA | Yes | PHW |  | BYDA NBN COMMS | [9 empty] | NBN Co | [30 empty] | Forreign service raw data.xlsx | 78
PHW-CM-0025 | 7021 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0025 |  |  | D-DWG-PHW-011.2 |  | D-DWG-PHW-011_C | BYDA | Yes | PHW |  | BYDA NBN COMMS | [9 empty] | NBN Co | [30 empty] | Forreign service raw data.xlsx | 79
PHW-WA-0015 | 7030 |  |  | PHW | Foreign Service | WATER | PHW-WA-0015 |  |  | D-DWG-PHW-011.2 |  | D-DWG-PHW-011_C | BYDA | Yes | PHW |  | BYDA TRC WATER | [9 empty] | Toowoomba Regional Council | [30 empty] | Forreign service raw data.xlsx | 80
PHW-EL-0013 | 7032 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0013 |  |  | D-DWG-PHW-011.2 |  | D-DWG-PHW-011_C | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 81
PHW-CM-0026 | 7033 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0026 |  |  | D-DWG-PHW-011.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMS | [9 empty] | Telstra | [30 empty] | Forreign service raw data.xlsx | 82
PHW-TT-0051 | 7035.325 | 7046.827 | 11.502 | PHW | Trench Type | TRENCH SECTION |  | 4 | 11.502 | D-DWG-PHW-011.2 | D-DWG-PHW-011.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 56
PHW-PIPE-0082 | 7035.325 | 7046.827 | 11.502 | PHW | Pipe | PIPE | PHW-PIPE-0082 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-TT-0052 | 7046.827 | 7819.18 | 772.353 | PHW | Trench Type | TRENCH SECTION |  | 1A | 772.353 | D-DWG-PHW-011.2 | D-DWG-PHW-012.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 57
PHW-PIPE-0083 | 7046.827 | 7328.079 | 281.252 | PHW | Pipe | PIPE | PHW-PIPE-0083 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-PIPE-0084 | 7328.079 | 7338.213 | 10.134 | PHW | Pipe | PIPE | PHW-PIPE-0084 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-IV-004 | 7335 |  |  | PHW | Valve | IV | PHW-IV-004 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PHW | [55 empty] | Supplied |  | 1 | each | [9 empty] | SPECIAL |  |  |  | PIPE | 0 | NO
PHW-TB-096 | 7335.153 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-096 | [7 empty] | PHW |  | Type 12 | [12 empty] | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 255 |  |  | Isolation Valve | [10 empty] | 1 | each |  | Isolation Valve |  |  | 600 | 2796 | 200 | Isolation valve | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-PIPE-0085 | 7338.213 | 7795.276 | 457.063 | PHW | Pipe | PIPE | PHW-PIPE-0085 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-EL-0014 | 7481 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0014 |  |  | D-DWG-PHW-011.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 83
PHW-AV-017 | 7777 |  |  | PHW | Valve | AV | PHW-AV-017 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-TB-045 | 7780.848 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-045 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 57 |  |  | Bend | [9 empty] | 14150 | 1 | each | 14150 | Bend | 11.25 | DICL | 600 | 2848 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-045 | 7780.848 |  |  | PHW | Bend | HOR | PHW-BND-045 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-PIPE-0086 | 7795.276 | 7845 | 49.724 | PHW | Pipe | PIPE | PHW-PIPE-0086 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-RD-0006 | 7811.422 | 7833.422 | 22 | PHW | Road & Rail Crossing | MINOR ROAD CROSSING | PHW-RD-0006 |  | 22 | [5 empty] | PHW | Holmes Road |  | Unsealed | 600 |  |  | DN600 PN35 DICL RRJ |  | 22 |  |  | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 13 | [28 empty] | TRENCH | 0 | NO
PHW-TT-0053 | 7819.18 | 7833.422 | 14.242 | PHW | Trench Type | TRENCH SECTION |  | 7 | 14.242 | D-DWG-PHW-012.2 | D-DWG-PHW-012.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 58
PHW-TT-0054 | 7833.422 | 8192.409 | 358.987 | PHW | Trench Type | TRENCH SECTION |  | 1A | 358.987 | D-DWG-PHW-012.2 | D-DWG-PHW-012.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 59
PHW-TS-0336 | 7839.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0336 |  |  | D-DWG-PHW-012 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 381 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0087 | 7845 | 7882.79 | 37.79 | PHW | Pipe | PIPE | PHW-PIPE-0087 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TS-0337 | 7851.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0337 |  |  | D-DWG-PHW-012 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 382 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-CM-0027 | 7860 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0027 |  |  | D-DWG-PHW-012.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMS DN50 | [9 empty] | Telstra |  |  | 50 | [27 empty] | Forreign service raw data.xlsx | 84
PHW-TS-0338 | 7864.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0338 |  |  | D-DWG-PHW-012 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 383 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-EL-0015 | 7867 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0015 |  |  | D-DWG-PHW-012.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 85
PHW-TS-0339 | 7876.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0339 |  |  | D-DWG-PHW-012 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 384 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-WA-0016 | 7882 |  |  | PHW | Foreign Service | WATER | PHW-WA-0016 |  |  | D-DWG-PHW-012.2 |  |  | BYDA | Yes | PHW |  | BYDA TRC WATER DN 375 | [9 empty] | Toowoomba Regional Council |  |  | 375 | [26 empty] | LOCATION/DEPTH OF WATER SERVICE NOT KNOWN. CONTRACTOR TO CONFIRM PRIOR TO CONSTRUCTION | Forreign service raw data.xlsx | 86
PHW-PIPE-0088 | 7882.79 | 7972.409 | 89.619 | PHW | Pipe | PIPE | PHW-PIPE-0088 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-CM-0028 | 7903 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0028 |  |  | D-DWG-PHW-012.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMS | [9 empty] | Telstra | [30 empty] | Forreign service raw data.xlsx | 87
PHW-TB-046 | 7936.403 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-046 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 58 |  |  | Bend | [9 empty] | 14150 | 1 | each | 14150 | Bend | 11.25 | DICL | 600 | 2912 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TS-0340 | 7937.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0340 |  |  | D-DWG-PHW-012 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 385 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0341 | 7948.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0341 |  |  | D-DWG-PHW-012 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 386 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0342 | 7959.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0342 |  |  | D-DWG-PHW-012 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 387 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0343 | 7970.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0343 |  |  | D-DWG-PHW-012 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 388 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0089 | 7972.409 | 8192.409 | 220 | PHW | Pipe | PIPE | PHW-PIPE-0089 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-CC-0006 | 8187 | 8212 | 25 | PHW | Creek Crossing | TRENCHED CREEK CROSSING | PHW-CC-0006 | [7 empty] | PHW |  |  |  |  | FABRIC/VEGETATION | [37 empty] | PHw_PWG_Creek_Crossings.xlsx | 8 | [28 empty] | TRENCH | 0 | NO
PHW-TS-0344 | 8192.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0344 |  |  | D-DWG-PHW-012 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 389 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TT-0055 | 8192.409 | 8250.538 | 58.129 | PHW | Trench Type | TRENCH SECTION |  | 1B/1C | 58.129 | D-DWG-PHW-012.2 | D-DWG-PHW-012.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 60
PHW-PIPE-0090 | 8192.409 | 8250.538 | 58.129 | PHW | Pipe | PIPE | PHW-PIPE-0090 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Open trench minor creek crossing | Special Crossings
PHW-TB-085 | 8197.671 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-085 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 244 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN600xDN150 DIFBE SCOUR TEE |  | 150 | 3049 | 240 | Tee; DN600XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-SCV-009 | 8198 |  |  | PHW | Valve | SCV | PHW-SCV-009 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PHW-TS-0345 | 8210 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0345 |  |  | D-DWG-PHW-012 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 390 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TT-0056 | 8250.538 | 9069.736 | 819.198 | PHW | Trench Type | TRENCH SECTION |  | 1A | 819.198 | D-DWG-PHW-012.2 | D-DWG-PHW-013.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 61
PHW-PIPE-0091 | 8250.538 | 8375.652 | 125.114 | PHW | Pipe | PIPE | PHW-PIPE-0091 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TS-0346 | 8285.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0346 |  |  | D-DWG-PHW-012 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 391 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0347 | 8296.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0347 |  |  | D-DWG-PHW-012 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 392 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0348 | 8307.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0348 |  |  | D-DWG-PHW-012 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 393 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0051 | 8310 | 8320 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW051 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 68 | 188 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-TS-0349 | 8317.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0349 |  |  | D-DWG-PHW-012 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 394 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0350 | 8328.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0350 |  |  | D-DWG-PHW-012 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 395 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0351 | 8338.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0351 |  |  | D-DWG-PHW-012 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 396 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-BND-046 | 8345.314 |  |  | PHW | Bend | HOR | PHW-BND-046 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 45° | DICL | 600 | [7 empty] | 45 | PIPE | 0 | NO
PHW-TB-047 | 8345.315 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-047 | [7 empty] | PHW |  | Type 4 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 59 |  |  | Bend | [9 empty] | 16211 | 1 | each | 16211 | Bend | 45 | DICL | 600 | 2990 | 240 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TS-0352 | 8349.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0352 |  |  | D-DWG-PHW-012 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 397 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0052 | 8350 | 8360 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW052 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 69 | 54.8 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-TB-048 | 8350.305 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-048 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 60 |  |  | Bend | [9 empty] | 14150 | 1 | each | 14150 | Bend | 11.25 | DICL | 600 | 2986 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TS-0353 | 8360.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0353 |  |  | D-DWG-PHW-012 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 398 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0354 | 8370.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0354 |  |  | D-DWG-PHW-012 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 399 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0092 | 8375.652 | 8857.962 | 482.31 | PHW | Pipe | PIPE | PHW-PIPE-0092 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-VG-0053 | 8460 | 8470 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW053 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 70 | 56 | TRIM | [26 empty] | TRENCH | 0 | NO
PHW-TB-049 | 8676.185 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-049 | [7 empty] | PHW |  | Type 5 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 61 |  |  | Bend | [9 empty] | 14784 | 1 | each | 14784 | Bend | 22.5 | DICL | 600 | 2868 | 240 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-047 | 8676.185 |  |  | PHW | Bend | HOR | PHW-BND-047 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 600 | [7 empty] | 22.5 | PIPE | 0 | NO
PHW-TB-050 | 8768.417 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-050 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 62 |  |  | Bend | [9 empty] | 14150 | 1 | each | 14150 | Bend | 11.25 | DICL | 600 | 2853 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-048 | 8768.417 |  |  | PHW | Bend | HOR | PHW-BND-048 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-AV-018 | 8772 |  |  | PHW | Valve | AV | PHW-AV-018 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 2 |  |  |  | PIPE | 0 | NO
PHW-PIPE-0093 | 8857.962 | 9053.682 | 195.72 | PHW | Pipe | PIPE | PHW-PIPE-0093 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-VG-0054 | 8950 | 8960 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW054 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 71 | 88.8 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-VG-0055 | 8970 | 8980 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW055 | [49 empty] | 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 72 | 5 | LIGHT | [26 empty] | TRENCH | 0 | NO
PHW-PIPE-0094 | 9053.682 | 9069.736 | 16.054 | PHW | Pipe | PIPE | PHW-PIPE-0094 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-BND-049 | 9056.493 |  |  | PHW | Bend | HOR | PHW-BND-049 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 600 | [7 empty] | 22.5 | PIPE | 0 | NO
PHW-TB-051 | 9056.494 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-051 | [7 empty] | PHW |  | Type 5 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 63 |  |  | Bend | [9 empty] | 15214 | 1 | each | 15214 | Bend | 22.5+11.25 | DICL | 600 | 2895 | 240 | Bend; 22.5+11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TS-0355 | 9059.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0355 |  |  | D-DWG-PHW-013 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 400 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0356 | 9067.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0356 |  |  | D-DWG-PHW-013 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 401 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TT-0057 | 9069.736 | 9078.356 | 8.62 | PHW | Trench Type | TRENCH SECTION |  | 4 | 8.62 | D-DWG-PHW-013.2 | D-DWG-PHW-013.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 62
PHW-PIPE-0095 | 9069.736 | 9078.356 | 8.62 | PHW | Pipe | PIPE | PHW-PIPE-0095 |  |  | D-DWG-PHW-013.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TS-0357 | 9075.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0357 |  |  | D-DWG-PHW-013 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 402 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TT-0058 | 9078.356 | 9087.51 | 9.154 | PHW | Trench Type | TRENCH SECTION |  | 1A | 9.154 | D-DWG-PHW-013.2 | D-DWG-PHW-013.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 63
PHW-PIPE-0096 | 9078.356 | 9087.51 | 9.154 | PHW | Pipe | PIPE | PHW-PIPE-0096 |  |  | D-DWG-PHW-013.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TT-0059 | 9087.51 | 9105.7 | 18.19 | PHW | Trench Type | TRENCH SECTION |  | 4 | 18.19 | D-DWG-PHW-013.2 | D-DWG-PHW-014.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 64
PHW-PIPE-0097 | 9087.51 | 9105.7 | 18.19 | PHW | Pipe | PIPE | PHW-PIPE-0097 |  |  | D-DWG-PHW-013.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TT-0060 | 9105.7 | 9330.84 | 225.14 | PHW | Trench Type | TRENCH SECTION |  | 1A | 225.14 | D-DWG-PHW-014.2 | D-DWG-PHW-014.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 65
PHW-PIPE-0098 | 9105.7 | 9330.884 | 225.184 | PHW | Pipe | PIPE | PHW-PIPE-0098 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TS-0358 | 9126.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0358 |  |  | D-DWG-PHW-014 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 403 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0359 | 9138.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0359 |  |  | D-DWG-PHW-014 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 404 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0056 | 9140 | 9150 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW056 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 73 | 164 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-BND-050 | 9146.643 |  |  | PHW | Bend | HOR | PHW-BND-050 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 600 | [7 empty] | 22.5 | PIPE | 0 | NO
PHW-TB-052 | 9146.86 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-052 | [7 empty] | PHW |  | Type 5 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 64 |  |  | Bend | [9 empty] | 14784 | 1 | each | 14784 | Bend | 22.5 | DICL | 600 | 2937 | 240 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TS-0360 | 9150.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0360 |  |  | D-DWG-PHW-014 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 405 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0361 | 9162 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0361 |  |  | D-DWG-PHW-014 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 406 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0362 | 9173.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0362 |  |  | D-DWG-PHW-014 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 407 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0363 | 9185.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0363 |  |  | D-DWG-PHW-014 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 408 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0364 | 9197.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0364 |  |  | D-DWG-PHW-014 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 409 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0365 | 9209.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0365 |  |  | D-DWG-PHW-014 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 410 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0057 | 9220 | 9230 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW057 | [49 empty] | 3 SMALL TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 74 | 40 | LIGHT | [26 empty] | TRENCH | 0 | NO
PHW-TS-0366 | 9221 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0366 |  |  | D-DWG-PHW-014 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 411 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0367 | 9232.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0367 |  |  | D-DWG-PHW-014 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 412 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0368 | 9244.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0368 |  |  | D-DWG-PHW-014 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 413 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0369 | 9256.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0369 |  |  | D-DWG-PHW-014 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 414 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-CC-0007 | 9258 | 9438 | 180 | PHW | Creek Crossing | TRENCHED CREEK CROSSING | PHW-CC-0007 | [7 empty] | PHW |  |  |  |  | FABRIC/VEGETATION | [37 empty] | PHw_PWG_Creek_Crossings.xlsx | 9 | [28 empty] | TRENCH | 0 | NO
PHW-TT-0061 | 9330.84 | 9333.706 | 2.866 | PHW | Trench Type | TRENCH SECTION |  | 2 | 2.866 | D-DWG-PHW-014.2 | D-DWG-PHW-014.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 66
PHW-PIPE-0099 | 9330.884 | 9333.706 | 2.822 | PHW | Pipe | PIPE | PHW-PIPE-0099 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Open trench minor creek crossing | Special Crossings
PHW-TT-0062 | 9333.706 | 9341.679 | 7.973 | PHW | Trench Type | TRENCH SECTION |  | 1A/1B/1C | 7.973 | D-DWG-PHW-014.2 | D-DWG-PHW-014.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 67
PHW-PIPE-0100 | 9333.706 | 9341.679 | 7.973 | PHW | Pipe | PIPE | PHW-PIPE-0100 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Open trench minor creek crossing | Special Crossings
PHW-TT-0063 | 9341.679 | 9431.212 | 89.533 | PHW | Trench Type | TRENCH SECTION |  | 1A | 89.533 | D-DWG-PHW-014.2 | D-DWG-PHW-014.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 68
PHW-PIPE-0101 | 9341.679 | 9431.212 | 89.533 | PHW | Pipe | PIPE | PHW-PIPE-0101 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-SCV-010 | 9410 |  |  | PHW | Valve | SCV | PHW-SCV-010 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 2 |  |  |  | PIPE | 0 | NO
PHW-TB-053 | 9411.852 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-053 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 65 |  |  | Bend | [9 empty] | 14150 | 1 | each | 14150 | Bend | 11.25 | DICL | 600 | 3059 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TB-054 | 9422.385 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-054 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 66 |  |  | Bend | [9 empty] | 14150 | 1 | each | 14150 | Bend | 11.25 | DICL | 600 | 3058 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TT-0064 | 9431.212 | 9437.047 | 5.835 | PHW | Trench Type | TRENCH SECTION |  | 2 | 5.835 | D-DWG-PHW-014.2 | D-DWG-PHW-014.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 69
PHW-PIPE-0102 | 9431.212 | 9437.047 | 5.835 | PHW | Pipe | PIPE | PHW-PIPE-0102 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Open trench minor creek crossing | Special Crossings
PHW-TT-0065 | 9437.047 | 9446.253 | 9.206 | PHW | Trench Type | TRENCH SECTION |  | 1A/1B/1C | 9.206 | D-DWG-PHW-014.2 | D-DWG-PHW-014.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 70
PHW-PIPE-0103 | 9437.047 | 9446.253 | 9.206 | PHW | Pipe | PIPE | PHW-PIPE-0103 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Open trench minor creek crossing | Special Crossings
PHW-TS-0370 | 9441.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0370 |  |  | D-DWG-PHW-014 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 415 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TT-0066 | 9446.253 | 10080.68 | 634.427 | PHW | Trench Type | TRENCH SECTION |  | 1A | 634.427 | D-DWG-PHW-014.2 | D-DWG-PHW-015.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 71
PHW-PIPE-0104 | 9446.253 | 9510.598 | 64.345 | PHW | Pipe | PIPE | PHW-PIPE-0104 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TS-0371 | 9452 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0371 |  |  | D-DWG-PHW-014 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 416 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0058 | 9460 | 9470 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW058 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 75 | 48 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-TS-0372 | 9462.8 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0372 |  |  | D-DWG-PHW-014 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 417 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0373 | 9473.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0373 |  |  | D-DWG-PHW-014 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 418 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-CM-0029 | 9476 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0029 |  |  | D-DWG-PHW-014.2 |  |  | BYDA | Yes | PHW |  | BYDA COMMS DN50 | [12 empty] | 50 | [27 empty] | Forreign service raw data.xlsx | 88
PHW-TS-0374 | 9484.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0374 |  |  | D-DWG-PHW-014 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 419 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0375 | 9495.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0375 |  |  | D-DWG-PHW-014 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 420 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0376 | 9506 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0376 |  |  | D-DWG-PHW-014 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 421 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0105 | 9510.598 | 9698.209 | 187.611 | PHW | Pipe | PIPE | PHW-PIPE-0105 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-VG-0059 | 9590 | 9600 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW059 | [49 empty] | 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 76 | 29 | LIGHT | [26 empty] | TRENCH | 0 | NO
PHW-BND-051 | 9605.527 |  |  | PHW | Bend | HOR | PHW-BND-051 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-AV-019 | 9658 |  |  | PHW | Valve | AV | PHW-AV-019 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 2 |  |  |  | PIPE | 0 | NO
PHW-CM-0030 | 9698 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0030 |  |  | D-DWG-PHW-014.2 |  |  | BYDA | Yes | PHW |  | BYDA COMMS DN50 | [12 empty] | 50 | [27 empty] | Forreign service raw data.xlsx | 89
PHW-BND-052 | 9698.209 |  |  | PHW | Bend | HOR | PHW-BND-052 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-PIPE-0106 | 9698.209 | 9793.567 | 95.358 | PHW | Pipe | PIPE | PHW-PIPE-0106 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-BND-053 | 9727.431 |  |  | PHW | Bend | HOR | PHW-BND-053 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-CC-0008 | 9781 | 9809 | 28 | PHW | Creek Crossing | TRENCHED CREEK CROSSING | PHW-CC-0008 | [7 empty] | PHW |  |  |  |  | FABRIC/VEGETATION | [37 empty] | PHw_PWG_Creek_Crossings.xlsx | 10 | [28 empty] | TRENCH | 0 | NO
PHW-PIPE-0107 | 9793.567 | 9808.864 | 15.297 | PHW | Pipe | PIPE | PHW-PIPE-0107 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Open trench minor creek crossing | Special Crossings
PHW-PIG-001 | 9801 |  |  | PHW | Valve | PIG | PHW-PIG-001 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [13 empty] | PIPE | 0 | NO
PHW-TB-100 | 9801.143 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-100 | [7 empty] | PHW |  | 2 x Type 12 | [12 empty] | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 259 |  |  | Pigging Station | [10 empty] | 2 | each |  | Pigging Station |  |  | 600 | 2972 | 150 | Pigging station | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-PIPE-0108 | 9808.864 | 9960.086 | 151.222 | PHW | Pipe | PIPE | PHW-PIPE-0108 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TS-0377 | 9840.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0377 |  |  | D-DWG-PHW-015 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 422 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0378 | 9852.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0378 |  |  | D-DWG-PHW-015 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 423 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TB-055 | 9885.483 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-055 | [7 empty] | PHW |  | Type 4 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 67 |  |  | Bend | [9 empty] | 18443 | 1 | each | 18443 | Bend | 22.5+11.25 | DICL | 600 | 2933 | 150 | Bend; 22.5+11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-054 | 9885.484 |  |  | PHW | Bend | HOR | PHW-BND-054 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 600 | [7 empty] | 22.5 | PIPE | 0 | NO
PHW-AV-020 | 9960 |  |  | PHW | Valve | AV | PHW-AV-020 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 2 |  |  |  | PIPE | 0 | NO
PHW-PIPE-0109 | 9960.086 | 9997.286 | 37.2 | PHW | Pipe | PIPE | PHW-PIPE-0109 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TB-056 | 9979.18 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-056 | [7 empty] | PHW |  | Type 10 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 68 |  |  | Bend | [9 empty] | 44440 | 1 | each | 44440 | Bend | 11.25 | DICL | 600 | 2925 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-055 | 9979.181 |  |  | PHW | Bend | VERT | PHW-BND-055 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-TS-0379 | 9981.4 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0379 |  |  | D-DWG-PHW-015 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 424 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TB-057 | 9984.731 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-057 | [7 empty] | PHW |  | Type 6 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 69 |  |  | Bend | [9 empty] | 14743 | 1 | each | 14743 | Bend | 11.25 | DICL | 600 | 2932 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-056 | 9984.731 |  |  | PHW | Bend | HOR | PHW-BND-056 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-TS-0380 | 9987.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0380 |  |  | D-DWG-PHW-015 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 425 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0381 | 9993.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0381 |  |  | D-DWG-PHW-015 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 426 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0110 | 9997.286 | 10080.68 | 83.394 | PHW | Pipe | PIPE | PHW-PIPE-0110 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TT-0067 | 10080.68 | 10101.635 | 20.955 | PHW | Trench Type | TRENCH SECTION |  | 5 | 20.955 | D-DWG-PHW-015.2 | D-DWG-PHW-015.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 72
PHW-PIPE-0111 | 10080.68 | 10101.635 | 20.955 | PHW | Pipe | PIPE | PHW-PIPE-0111 |  |  | D-DWG-PHW-015.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Open trench minor creek crossing | Special Crossings
PHW-CC-0009 | 10081 | 10102 | 21 | PHW | Creek Crossing | TRENCHED CREEK CROSSING | PHW-CC-0009 | [7 empty] | PHW |  |  |  |  | LOOSE ROCK | A | [36 empty] | PHw_PWG_Creek_Crossings.xlsx | 11 | [28 empty] | TRENCH | 0 | NO
PHW-TT-0068 | 10101.635 | 10347.95 | 246.315 | PHW | Trench Type | TRENCH SECTION |  | 1A | 246.315 | D-DWG-PHW-015.2 | D-DWG-PHW-015.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 73
PHW-PIPE-0112 | 10101.635 | 10344.417 | 242.782 | PHW | Pipe | PIPE | PHW-PIPE-0112 |  |  | D-DWG-PHW-015.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Open Trenched Creek Crossings | Pipelay Crew
PHW-TB-086 | 10103.635 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-086 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 245 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN600xDN150 DIFBE SCOUR TEE |  | 150 | 2983 | 150 | Tee; DN600XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-SCV-011 | 10104 |  |  | PHW | Valve | SCV | PHW-SCV-011 |  |  | D-DWG-PHW-015.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PHW-TB-058 | 10177.634 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-058 | [7 empty] | PHW |  | Type 4 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 70 |  |  | Bend | [9 empty] | 15780 | 1 | each | 15780 | Bend | 22.5 | DICL | 600 | 2965 | 150 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-057 | 10177.634 |  |  | PHW | Bend | HOR | PHW-BND-057 |  |  | D-DWG-PHW-015.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 600 | [7 empty] | 22.5 | PIPE | 0 | NO
PHW-TB-059 | 10319.973 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-059 | [7 empty] | PHW |  | Type 4 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 71 |  |  | Bend | [9 empty] | 15780 | 1 | each | 15780 | Bend | 22.5 | DICL | 600 | 2919 | 150 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-058 | 10319.973 |  |  | PHW | Bend | HOR | PHW-BND-058 |  |  | D-DWG-PHW-015.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 600 | [7 empty] | 22.5 | PIPE | 0 | NO
PHW-VG-0060 | 10320 | 10330 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW060 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 77 | 65.7 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-TB-060 | 10337.161 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-060 | [7 empty] | PHW |  | Type 4 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 72 |  |  | Bend | [9 empty] | 15780 | 1 | each | 15780 | Bend | 22.5 | DICL | 600 | 2917 | 150 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-059 | 10337.161 |  |  | PHW | Bend | HOR | PHW-BND-059 |  |  | D-DWG-PHW-015.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 600 | [7 empty] | 22.5 | PIPE | 0 | NO
PHW-RD-0007 | 10342 | 10364 | 22 | PHW | Road & Rail Crossing | MINOR ROAD CROSSING | PHW-RD-0007 |  | 22 | [5 empty] | PHW | Khurt Court |  | Sealed | 600 |  |  | DN600 PN35 DICL RRJ | 22 |  |  |  | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 14 | [28 empty] | TRENCH | 0 | NO
PHW-PIPE-0113 | 10344.417 | 10367.669 | 23.252 | PHW | Pipe | PIPE | PHW-PIPE-0113 |  |  | D-DWG-PHW-015.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Open trench minor road Crossing | Special Crossings
PHW-TT-0069 | 10347.95 | 10367.669 | 19.719 | PHW | Trench Type | TRENCH SECTION |  | 6 | 19.719 | D-DWG-PHW-015.2 | D-DWG-PHW-015.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 74
PHW-TT-0070 | 10367.669 | 10531.389 | 163.72 | PHW | Trench Type | TRENCH SECTION |  | 1A | 163.72 | D-DWG-PHW-015.2 | D-DWG-PHW-016.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 75
PHW-PIPE-0114 | 10367.669 | 10378.599 | 10.93 | PHW | Pipe | PIPE | PHW-PIPE-0114 |  |  | D-DWG-PHW-015.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TS-0382 | 10373.15 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0382 |  |  | D-DWG-PHW-015 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 427 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TB-061 | 10378.599 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-061 | [7 empty] | PHW |  | Type 6 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 73 |  |  | Bend | [9 empty] | 14743 | 1 | each | 14743 | Bend | 11.25 | DICL | 600 | 2904 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-060 | 10378.599 |  |  | PHW | Bend | HOR | PHW-BND-060 |  |  | D-DWG-PHW-015.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-PIPE-0115 | 10378.599 | 10531.389 | 152.79 | PHW | Pipe | PIPE | PHW-PIPE-0115 |  |  | D-DWG-PHW-015.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TB-062 | 10459.505 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-062 | [7 empty] | PHW |  | Type 4 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 74 |  |  | Bend | [9 empty] | 15780 | 1 | each | 15780 | Bend | 22.5 | DICL | 600 | 2889 | 150 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-061 | 10459.506 |  |  | PHW | Bend | HOR | PHW-BND-061 |  |  | D-DWG-PHW-015.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 600 | [7 empty] | 22.5 | PIPE | 0 | NO
PHW-AV-021 | 10517 |  |  | PHW | Valve | AV | PHW-AV-021 |  |  | D-DWG-PHW-015.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-TT-0071 | 10531.389 | 10582.353 | 50.964 | PHW | Trench Type | TRENCH SECTION |  | 4 | 50.964 | D-DWG-PHW-016.2 | D-DWG-PHW-016.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 76
PHW-PIPE-0116 | 10531.389 | 10582.353 | 50.964 | PHW | Pipe | PIPE | PHW-PIPE-0116 |  |  | D-DWG-PHW-016.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-BND-062 | 10581.354 |  |  | PHW | Bend | HOR | PHW-BND-062 |  |  | D-DWG-PHW-016.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 37.1° | MSCL | 650 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PHW-RD-0008 | 10582.353 | 10645.383 | 63.03 | PHW | Road & Rail Crossing | MAJOR ROAD CROSSING | PHW-RD-0008 |  | 63.03 | [5 empty] | PHW | Toowoomba Connection Road / Warrego Highway |  | Sealed | 600 |  |  | OD660x6WT MSCL Sintalock Type 2 PN35 Carrier & OD813x12WT MS Enveloper |  |  |  |  | TMR | [15 empty] | Thrust Boring | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 15 | [28 empty] | TRENCH | 0 | NO
PHW-TT-0072 | 10582.353 | 10645.383 | 63.03 | PHW | Trench Type | TRENCH SECTION |  | 8A | 63.03 | D-DWG-PHW-016.2 | D-DWG-PHW-016.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 77
PHW-PIPE-0117 | 10582.353 | 10654.383 | 72.03 | PHW | Pipe | PIPE | PHW-PIPE-0117 |  |  | D-DWG-PHW-016.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 + OD813 12WT MS Enveloper | [6 empty] | MSCL | 660 | [54 empty] | Warrego Highway | Trenchless
PHW-SL-0001 | 10595 |  |  | PHW | Foreign Service | SURVEY LEVEL |  |  |  | D-DWG-PHW-016.2 |  |  |  | Yes | PHW |  | EUD LEVEL | [39 empty] | UNKOWN ASSET | Forreign service raw data.xlsx | 90
PHW-SL-0002 | 10597 |  |  | PHW | Foreign Service | SURVEY LEVEL |  |  |  | D-DWG-PHW-016.2 |  |  |  | Yes | PHW |  | DG LEVEL | [39 empty] | UNKOWN ASSET | Forreign service raw data.xlsx | 91
PHW-SL-0003 | 10598 |  |  | PHW | Foreign Service | SURVEY LEVEL |  |  |  | D-DWG-PHW-016.2 |  |  |  | Yes | PHW |  | DG LEVEL | [39 empty] | UNKOWN ASSET | Forreign service raw data.xlsx | 92
PHW-SL-0004 | 10599 |  |  | PHW | Foreign Service | SURVEY LEVEL |  |  |  | D-DWG-PHW-016.2 |  |  |  | Yes | PHW |  | DG LEVEL | [39 empty] | UNKOWN ASSET | Forreign service raw data.xlsx | 93
PHW-SL-0005 | 10609 |  |  | PHW | Foreign Service | SURVEY LEVEL |  |  |  | D-DWG-PHW-016.2 |  |  |  | Yes | PHW |  | EUD LEVEL | [39 empty] | UNKOWN ASSET | Forreign service raw data.xlsx | 94
PHW-SL-0006 | 10610 |  |  | PHW | Foreign Service | SURVEY LEVEL |  |  |  | D-DWG-PHW-016.2 |  |  |  | Yes | PHW |  | DG LEVEL | [39 empty] | UNKOWN ASSET | Forreign service raw data.xlsx | 95
PHW-SL-0007 | 10632 |  |  | PHW | Foreign Service | SURVEY LEVEL |  |  |  | D-DWG-PHW-016.2 |  |  |  | Yes | PHW |  | EUD LEVEL | [39 empty] | UNKOWN ASSET | Forreign service raw data.xlsx | 96
PHW-CM-0031 | 10642 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0031 |  |  | D-DWG-PHW-016.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMS DN100 | [9 empty] | Telstra |  |  | 100 | [27 empty] | Forreign service raw data.xlsx | 97
PHW-TT-0073 | 10645.383 | 10684.369 | 38.986 | PHW | Trench Type | TRENCH SECTION |  | 4 | 38.986 | D-DWG-PHW-016.2 | D-DWG-PHW-016.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 78
PHW-PIPE-0118 | 10654.383 | 10684.369 | 29.986 | PHW | Pipe | PIPE | PHW-PIPE-0118 |  |  | D-DWG-PHW-016.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-BND-063 | 10670.434 |  |  | PHW | Bend | HOR | PHW-BND-063 |  |  | D-DWG-PHW-016.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 43.4° | MSCL | 650 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PHW-EL-0016 | 10676 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0016 |  |  | D-DWG-PHW-016.2 |  | D-DWG-PHW-016_C | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 98
PHW-TT-0074 | 10684.369 | 11171.188 | 486.819 | PHW | Trench Type | TRENCH SECTION |  | 1A | 486.819 | D-DWG-PHW-016.2 | D-DWG-PHW-016.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 79
PHW-PIPE-0119 | 10684.369 | 10752.637 | 68.268 | PHW | Pipe | PIPE | PHW-PIPE-0119 |  |  | D-DWG-PHW-016.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-EL-0017 | 10691 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0017 |  |  | D-DWG-PHW-016.2 |  | D-DWG-PHW-016_C | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 99
PHW-CM-0032 | 10692 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0032 |  |  | D-DWG-PHW-016.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMS | [9 empty] | Telstra | [30 empty] | Forreign service raw data.xlsx | 100
PHW-TB-063 | 10699.881 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-063 | [7 empty] | PHW |  | Type 1 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 75 |  |  | Bend | [9 empty] | 114663 | 1 | each | 114663 | Bend | 45 | DICL | 600 | 2906 | 100 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-064 | 10699.881 |  |  | PHW | Bend | HOR | PHW-BND-064 |  |  | D-DWG-PHW-016.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 45° | DICL | 600 | [7 empty] | 45 | PIPE | 0 | NO
PHW-PIPE-0120 | 10752.637 | 10795 | 42.363 | PHW | Pipe | PIPE | PHW-PIPE-0120 |  |  | D-DWG-PHW-016.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-CM-0033 | 10775 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0033 |  |  | D-DWG-PHW-016.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMS DN50 | [9 empty] | Telstra |  |  | 50 | [27 empty] | Forreign service raw data.xlsx | 101
PHW-EL-0018 | 10793 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0018 |  |  | D-DWG-PHW-016.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 102
PHW-PIPE-0121 | 10795 | 10805 | 10 | PHW | Pipe | PIPE | PHW-PIPE-0121 |  |  | D-DWG-PHW-016.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-PIPE-0122 | 10805 | 10892.518 | 87.518 | PHW | Pipe | PIPE | PHW-PIPE-0122 |  |  | D-DWG-PHW-016.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-AV-022 | 10835 |  |  | PHW | Valve | AV | PHW-AV-022 |  |  | D-DWG-PHW-016.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PHW-PIPE-0123 | 10892.518 | 10902.518 | 10 | PHW | Pipe | PIPE | PHW-PIPE-0123 |  |  | D-DWG-PHW-016.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Open trench minor road Crossing | Special Crossings
PHW-PIPE-0124 | 10902.518 | 11171.188 | 268.67 | PHW | Pipe | PIPE | PHW-PIPE-0124 |  |  | D-DWG-PHW-016.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TT-0075 | 11171.188 | 11191.258 | 20.07 | PHW | Trench Type | TRENCH SECTION |  | 6 | 20.07 | D-DWG-PHW-016.2 | D-DWG-PHW-016.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 80
PHW-PIPE-0125 | 11171.188 | 11252.039 | 80.851 | PHW | Pipe | PIPE | PHW-PIPE-0125 |  |  | D-DWG-PHW-016.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Open Trenched Creek Crossings | Pipelay Crew
PHW-RD-0009 | 11174 | 11181 | 7 | PHW | Road & Rail Crossing | MINOR ROAD CROSSING | PHW-RD-0009 |  | 7 | [5 empty] | PHW | Wirth Road |  | Sealed | 600 |  |  | DN600 PN35 DICL RRJ | 7 |  |  |  | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 16 | [28 empty] | TRENCH | 0 | NO
PHW-VG-0061 | 11180 | 11190 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW061 | [49 empty] | 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 78 | 23.8 | LIGHT | [26 empty] | TRENCH | 0 | NO
PHW-CM-0034 | 11188 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0034 |  |  | D-DWG-PHW-016.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMS | [9 empty] | Telstra | [30 empty] | Forreign service raw data.xlsx | 103
PHW-TT-0076 | 11191.258 | 11382.203 | 190.945 | PHW | Trench Type | TRENCH SECTION |  | 1A | 190.945 | D-DWG-PHW-016.2 | D-DWG-PHW-017.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 81
PHW-PIPE-0126 | 11252.039 | 11354.666 | 102.627 | PHW | Pipe | PIPE | PHW-PIPE-0126 |  |  | D-DWG-PHW-016.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TS-0383 | 11279.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0383 |  |  | D-DWG-PHW-017 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 428 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0384 | 11328.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0384 |  |  | D-DWG-PHW-017 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 429 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0385 | 11345.9 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0385 |  |  | D-DWG-PHW-017 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 430 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0127 | 11354.666 | 11382.203 | 27.537 | PHW | Pipe | PIPE | PHW-PIPE-0127 |  |  | D-DWG-PHW-016.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TB-064 | 11370.095 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-064 | [7 empty] | PHW |  | Type 3 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 76 |  |  | Bend | [9 empty] | 16755 | 1 | each | 16755 | Bend | 45 | DICL | 600 | 3044 | 150 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-EL-0019 | 11379 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0019 |  |  | D-DWG-PHW-017.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 104
PHW-TB-065 | 11382.203 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-065 | [7 empty] | PHW |  | Type 6 | [11 empty] | MSCL | 650 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 77 |  |  | Bend | [9 empty] | 19811 | 1 | each | 19811 | Bend | 10 | MSCL | 650 | 3044 | 150 | Bend; MS - 10° | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TT-0077 | 11382.203 | 11427.143 | 44.94 | PHW | Trench Type | TRENCH SECTION |  | 4 | 44.94 | D-DWG-PHW-017.2 | D-DWG-PHW-017.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 82
PHW-PIPE-0128 | 11382.203 | 11427.143 | 44.94 | PHW | Pipe | PIPE | PHW-PIPE-0128 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TB-087 | 11396.642 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-087 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 246 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN600xDN150 DIFBE SCOUR TEE |  | 150 | 3045 | 150 | Tee; DN600XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-SCV-012 | 11397 |  |  | PHW | Valve | SCV | PHW-SCV-012 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PHW-RD-0010 | 11427.142 | 11509.11 | 81.968 | PHW | Road & Rail Crossing | MAJOR ROAD CROSSING | PHW-RD-0010 |  | 81.968 | [5 empty] | PHW | Second Range Crossing |  | Sealed | 600 |  |  | OD660x6WT MSCL Sintalock Type 2 PN35 Carrier & OD813x12WT MS Enveloper |  |  |  |  | TMR | [15 empty] | Thrust Boring | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 17 | [28 empty] | TRENCH | 0 | NO
PHW-TT-0078 | 11427.143 | 11509.11 | 81.967 | PHW | Trench Type | TRENCH SECTION |  | 8A | 81.967 | D-DWG-PHW-017.2 | D-DWG-PHW-017.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 83
PHW-PIPE-0129 | 11427.143 | 11509.11 | 81.967 | PHW | Pipe | PIPE | PHW-PIPE-0129 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 + OD813 12WT MS Enveloper | [6 empty] | MSCL | 660 | [54 empty] | A39 - Major Highway | Trenchless
PHW-TT-0079 | 11509.11 | 11589.46 | 80.35 | PHW | Trench Type | TRENCH SECTION |  | 5 | 80.35 | D-DWG-PHW-017.2 | D-DWG-PHW-017.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 84
PHW-PIPE-0130 | 11509.11 | 11561.518 | 52.408 | PHW | Pipe | PIPE | PHW-PIPE-0130 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Open trenched Major creek crossing | Special Crossings
PHW-BND-065 | 11509.61 |  |  | PHW | Bend | HOR | PHW-BND-065 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 45° | DICL | 600 | [7 empty] | 45 | PIPE | 0 | NO
PHW-BND-066 | 11512.834 |  |  | PHW | Bend | HOR | PHW-BND-066 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 44° | MSCL | 650 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PHW-CC-0010 | 11532 | 11589 | 57 | PHW | Creek Crossing | TRENCHED CREEK CROSSING | PHW-CC-0010 | [7 empty] | PHW | DRY CREEK |  |  |  | LOOSE ROCK | C | [36 empty] | PHw_PWG_Creek_Crossings.xlsx | 12 | [28 empty] | TRENCH | 0 | NO
PHW-AV-023 | 11532 |  |  | PHW | Valve | AV | PHW-AV-023 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-PIPE-0131 | 11561.518 | 11589.46 | 27.942 | PHW | Pipe | PIPE | PHW-PIPE-0131 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-BND-067 | 11574.038 |  |  | PHW | Bend | VERT | PHW-BND-067 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 8.5° | MSCL | 650 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PHW-BND-068 | 11579.296 |  |  | PHW | Bend | VERT | PHW-BND-068 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 17.2° | MSCL | 650 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PHW-TS-0386 | 11581 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0386 |  |  | D-DWG-PHW-017 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 431 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0387 | 11584.3 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0387 |  |  | D-DWG-PHW-017 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 432 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0388 | 11587.6 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0388 |  |  | D-DWG-PHW-017 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 433 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TB-066 | 11589.46 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-066 | [7 empty] | PHW |  | Type 4 | [11 empty] | MSCL | 650 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 78 |  |  | Bend | [9 empty] | 20678 | 1 | each | 20678 | Bend | 13.9 | MSCL | 650 | 3049 | 100 | Bend; MS - 13.9° | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TT-0080 | 11589.46 | 11596.46 | 7 | PHW | Trench Type | TRENCH SECTION |  | 1A | 7 | D-DWG-PHW-017.2 | D-DWG-PHW-017.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 85
PHW-BND-069 | 11589.46 |  |  | PHW | Bend | VERT | PHW-BND-069 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 13.9° | MSCL | 650 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PHW-PIPE-0132 | 11589.46 | 11596.46 | 7 | PHW | Pipe | PIPE | PHW-PIPE-0132 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-AV-024 | 11592 |  |  | PHW | Valve | AV | PHW-AV-024 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-SCV-013 | 11596 |  |  | PHW | Valve | SCV | PHW-SCV-013 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PHW-TT-0081 | 11596.46 | 11750.532 | 154.072 | PHW | Trench Type | TRENCH SECTION |  | 5 | 154.072 | D-DWG-PHW-017.2 | D-DWG-PHW-017.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 86
PHW-TB-088 | 11596.46 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-088 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 247 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN600xDN150 DIFBE SCOUR TEE |  | 150 | 3047 | 100 | Tee; DN600XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-PIPE-0133 | 11596.46 | 11750.532 | 154.072 | PHW | Pipe | PIPE | PHW-PIPE-0133 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-BND-070 | 11715.917 |  |  | PHW | Bend | HOR | PHW-BND-070 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 34° | MSCL | 650 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PHW-CC-0011 | 11735 | 11765 | 30 | PHW | Creek Crossing | TRENCHED CREEK CROSSING | PHW-CC-0011 | [7 empty] | PHW | DRY CREEK ARM |  |  |  | LOOSE ROCK | [37 empty] | PHw_PWG_Creek_Crossings.xlsx | 13 | [28 empty] | TRENCH | 0 | NO
PHW-FN-0019 | 11735 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0019 |  |  | D-DWG-PHW-017.2 |  |  |  | Yes | PHW |  | FENCE LINE NO POST - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 105
PHW-TT-0082 | 11750.532 | 12441.199 | 690.667 | PHW | Trench Type | TRENCH SECTION |  | 1A | 690.667 | D-DWG-PHW-017.2 | D-DWG-PHW-018.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 87
PHW-PIPE-0134 | 11750.532 | 12441.199 | 690.667 | PHW | Pipe | PIPE | PHW-PIPE-0134 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-AV-025 | 12358 |  |  | PHW | Valve | AV | PHW-AV-025 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-TT-0083 | 12441.199 | 12457.644 | 16.445 | PHW | Trench Type | TRENCH SECTION |  | 4 | 16.445 | D-DWG-PHW-018.2 | D-DWG-PHW-018.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 88
PHW-PIPE-0135 | 12441.199 | 12457.644 | 16.445 | PHW | Pipe | PIPE | PHW-PIPE-0135 |  |  | D-DWG-PHW-018.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Open trench minor road Crossing | Special Crossings
PHW-CM-0035 | 12452 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0035 |  |  | D-DWG-PHW-018.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMS DN100 | [9 empty] | Telstra |  |  | 100 | [27 empty] | Forreign service raw data.xlsx | 106
PHW-TT-0084 | 12457.644 | 12471.05 | 13.406 | PHW | Trench Type | TRENCH SECTION |  | 7 | 13.406 | D-DWG-PHW-018.2 | D-DWG-PHW-018.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 89
PHW-PIPE-0136 | 12457.644 | 12471.05 | 13.406 | PHW | Pipe | PIPE | PHW-PIPE-0136 |  |  | D-DWG-PHW-018.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-RD-0011 | 12461 | 12469 | 8 | PHW | Road & Rail Crossing | MINOR ROAD CROSSING | PHW-RD-0011 |  | 8 | [5 empty] | PHW | Carrington Road |  | Unsealed | 600 |  |  | DN600 PN35 DICL RRJ |  | 8 |  |  | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 18 | [28 empty] | TRENCH | 0 | NO
PHW-TS-0389 | 12461 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0389 |  |  | D-DWG-PHW-018 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 434 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0390 | 12468 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0390 |  |  | D-DWG-PHW-018 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 435 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-CM-0036 | 12470 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0036 |  |  | D-DWG-PHW-018.2 |  |  | BYDA | Yes | PHW |  | BYDA COMMS DN100 | [12 empty] | 100 | [27 empty] | Forreign service raw data.xlsx | 109
PHW-EL-0020 | 12470 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0020 |  |  | D-DWG-PHW-018.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 107
PHW-EL-0021 | 12470 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0021 |  |  | D-DWG-PHW-018.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 108
PHW-TT-0085 | 12471.05 | 13274.77 | 803.72 | PHW | Trench Type | TRENCH SECTION |  | 1A | 803.72 | D-DWG-PHW-018.2 | D-DWG-PHW-019.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 90
PHW-PIPE-0137 | 12471.05 | 12561.518 | 90.468 | PHW | Pipe | PIPE | PHW-PIPE-0137 |  |  | D-DWG-PHW-018.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-EL-0022 | 12507 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0022 |  |  | D-DWG-PHW-018.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 110
PHW-CM-0037 | 12528 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0037 |  |  | D-DWG-PHW-018.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMS DN100 | [9 empty] | Telstra |  |  | 100 | [27 empty] | Forreign service raw data.xlsx | 111
PHW-PIPE-0138 | 12561.518 | 12641.845 | 80.327 | PHW | Pipe | PIPE | PHW-PIPE-0138 |  |  | D-DWG-PHW-018.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-PIPE-0139 | 12641.845 | 12651.518 | 9.673 | PHW | Pipe | PIPE | PHW-PIPE-0139 |  |  | D-DWG-PHW-018.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TS-0391 | 12646.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0391 |  |  | D-DWG-PHW-019 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 436 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0140 | 12651.518 | 13230.192 | 578.674 | PHW | Pipe | PIPE | PHW-PIPE-0140 |  |  | D-DWG-PHW-018.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-AV-026 | 12851 |  |  | PHW | Valve | AV | PHW-AV-026 |  |  | D-DWG-PHW-018.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-EL-0023 | 12915 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0023 |  |  | D-DWG-PHW-019.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 112
PHW-CM-0038 | 12969 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0038 |  |  | D-DWG-PHW-019.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMS | [9 empty] | Telstra | [30 empty] | Forreign service raw data.xlsx | 113
PHW-EL-0024 | 13024 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0024 |  |  | D-DWG-PHW-019.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 114
PHW-TB-089 | 13125.991 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-089 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 248 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN600xDN150 DIFBE SCOUR TEE |  | 150 | 2681 | 200 | Tee; DN600XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-SCV-014 | 13126 |  |  | PHW | Valve | SCV | PHW-SCV-014 |  |  | D-DWG-PHW-018.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PHW-TB-067 | 13230.192 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-067 | [7 empty] | PHW |  | Type 4 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 79 |  |  | Bend | [9 empty] | 16211 | 1 | each | 16211 | Bend | 45 | DICL | 600 | 2643 | 200 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-071 | 13230.192 |  |  | PHW | Bend | HOR | PHW-BND-071 |  |  | D-DWG-PHW-018.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 45° | DICL | 600 | [7 empty] | 45 | PIPE | 0 | NO
PHW-PIPE-0141 | 13230.192 | 13253 | 22.808 | PHW | Pipe | PIPE | PHW-PIPE-0141 |  |  | D-DWG-PHW-018.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-WA-0017 | 13236 |  |  | PHW | Foreign Service | WATER | PHW-WA-0017 |  |  | D-DWG-PHW-019.2 |  |  | BYDA | Yes | PHW |  | BYDA TRC WATER DN300 | [9 empty] | Toowoomba Regional Council |  |  | 300 | [26 empty] | LOCATION/DEPTH OF WATER SERVICE NOT KNOWN.CONTRACTOR TO CONFIRM PRIOR TO CONSTRUCTION | Forreign service raw data.xlsx | 115
PHW-TB-068 | 13238.609 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-068 | [7 empty] | PHW |  | Type 4 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 80 |  |  | Bend | [9 empty] | 16211 | 1 | each | 16211 | Bend | 45 | DICL | 600 | 2642 | 200 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-072 | 13238.609 |  |  | PHW | Bend | HOR | PHW-BND-072 |  |  | D-DWG-PHW-018.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 45° | DICL | 600 | [7 empty] | 45 | PIPE | 0 | NO
PHW-TS-0392 | 13242.2 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0392 |  |  | D-DWG-PHW-019 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 437 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-EL-0025 | 13243 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0025 |  |  | D-DWG-PHW-019.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 116
PHW-TS-0393 | 13249.7 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0393 |  |  | D-DWG-PHW-019 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 438 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0142 | 13253 | 13265 | 12 | PHW | Pipe | PIPE | PHW-PIPE-0142 |  |  | D-DWG-PHW-018.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-PIPE-0143 | 13265 | 13274.77 | 9.77 | PHW | Pipe | PIPE | PHW-PIPE-0143 |  |  | D-DWG-PHW-018.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-RD-0012 | 13274.77 | 13346.373 | 71.603 | PHW | Road & Rail Crossing | MAJOR ROAD CROSSING | PHW-RD-0012 |  | 71.603 | [5 empty] | PHW | Toowoomba Cecil Plains Road |  | Sealed | 600 |  |  | OD660x6WT MSCL Sintalock Type 2 PN35 Carrier & OD813x12WT MS Enveloper |  |  |  |  | TMR | [15 empty] | Thrust Boring | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 19 | [28 empty] | TRENCH | 0 | NO
PHW-TT-0086 | 13274.77 | 13346.374 | 71.604 | PHW | Trench Type | TRENCH SECTION |  | 8A | 71.604 | D-DWG-PHW-019.2 | D-DWG-PHW-020.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 91
PHW-PIPE-0144 | 13274.77 | 13346.374 | 71.604 | PHW | Pipe | PIPE | PHW-PIPE-0144 |  |  | D-DWG-PHW-019.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 + OD813 12WT MS Enveloper | [6 empty] | MSCL | 660 | [54 empty] | Toowoomba Cecil Plains road | Trenchless
PHW-CM-0039 | 13275 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0039 |  |  | D-DWG-PHW-019.2 |  |  | PUP | Yes | PHW |  | PUP COMMS DN100 | [12 empty] | 100 | [27 empty] | Forreign service raw data.xlsx | 117
PHW-CM-0040 | 13278 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0040 |  |  | D-DWG-PHW-019.2 |  |  | PUP | Yes | PHW |  | PUP COMMS DN100 | [12 empty] | 100 | [27 empty] | Forreign service raw data.xlsx | 118
PHW-CM-0041 | 13278 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0041 |  |  | D-DWG-PHW-019.2 |  |  | PUP | Yes | PHW |  | PUP COMMS DN100 | [12 empty] | 100 | [27 empty] | Forreign service raw data.xlsx | 119
PHW-CM-0042 | 13278 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0042 |  |  | D-DWG-PHW-019.2 |  |  | BYDA | Yes | PHW |  | BYDA NBN COMMS DN100 | [9 empty] | NBN Co |  |  | 100 | [27 empty] | Forreign service raw data.xlsx | 120
PHW-EL-0026 | 13287 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0026 |  |  | D-DWG-PHW-019.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 121
PHW-CM-0043 | 13323 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0043 |  |  | D-DWG-PHW-020.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMS DN100 | [9 empty] | Telstra |  |  | 100 | [27 empty] | Forreign service raw data.xlsx | 122
PHW-TT-0087 | 13346.374 | 14778.123 | 1431.749 | PHW | Trench Type | TRENCH SECTION |  | 1A | 1431.749 | D-DWG-PHW-020.2 | D-DWG-PHW-022.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 92
PHW-PIPE-0145 | 13346.374 | 13376 | 29.626 | PHW | Pipe | PIPE | PHW-PIPE-0145 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-PIPE-0146 | 13376 | 13381 | 5 | PHW | Pipe | PIPE | PHW-PIPE-0146 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Pipelay Crew
PHW-PIPE-0147 | 13381 | 13515 | 134 | PHW | Pipe | PIPE | PHW-PIPE-0147 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-EL-0027 | 13395 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0027 |  |  | D-DWG-PHW-020.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 123
PHW-PIPE-0148 | 13515 | 13535.334 | 20.334 | PHW | Pipe | PIPE | PHW-PIPE-0148 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Pipelay Crew
PHW-AV-027 | 13535 |  |  | PHW | Valve | AV | PHW-AV-027 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-PIPE-0149 | 13535.334 | 13576 | 40.666 | PHW | Pipe | PIPE | PHW-PIPE-0149 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-EL-0028 | 13556 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0028 |  |  | D-DWG-PHW-020.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 124
PHW-PIPE-0150 | 13576 | 13586 | 10 | PHW | Pipe | PIPE | PHW-PIPE-0150 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Pipelay Crew
PHW-PIPE-0151 | 13586 | 13620 | 34 | PHW | Pipe | PIPE | PHW-PIPE-0151 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-VG-0062 | 13590 | 13610 | 20 | PHW | Vegetation | TREE REMOVAL | VEG_PHW062 | [49 empty] | 4 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 79 | 90 | LIGHT | [26 empty] | TRENCH | 0 | NO
PHW-EL-0029 | 13606 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0029 |  |  | D-DWG-PHW-020.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 125
PHW-EL-0030 | 13613 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0030 |  |  | D-DWG-PHW-020.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 126
PHW-PIPE-0152 | 13620 | 13630 | 10 | PHW | Pipe | PIPE | PHW-PIPE-0152 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-EL-0031 | 13628 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0031 |  |  | D-DWG-PHW-020.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 127
PHW-PIPE-0153 | 13630 | 13698.342 | 68.342 | PHW | Pipe | PIPE | PHW-PIPE-0153 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-WA-0018 | 13644 |  |  | PHW | Foreign Service | WATER | PHW-WA-0018 |  |  | D-DWG-PHW-020.2 |  |  | BYDA | Yes | PHW |  | BYDA TRC WATER DN375 | [9 empty] | Toowoomba Regional Council |  |  | 375 | [26 empty] | LOCATION/DEPTH OF WATER SERVICE NOT KNOWN.CONTRACTOR TO CONFIRM PRIOR TO CONSTRUCTION | Forreign service raw data.xlsx | 128
PHW-CM-0044 | 13650 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0044 |  |  | D-DWG-PHW-020.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTA COMMS DN100 | [9 empty] | Telstra |  |  | 100 | [27 empty] | Forreign service raw data.xlsx | 129
PHW-TB-069 | 13674.348 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-069 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 81 |  |  | Bend | [9 empty] | 14150 | 1 | each | 14150 | Bend | 11.25 | DICL | 600 | 2577 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-073 | 13674.348 |  |  | PHW | Bend | HOR | PHW-BND-073 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-PIPE-0154 | 13698.342 | 13932.104 | 233.762 | PHW | Pipe | PIPE | PHW-PIPE-0154 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-PIPE-0155 | 13932.104 | 13965 | 32.896 | PHW | Pipe | PIPE | PHW-PIPE-0155 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Pipelay Crew
PHW-EL-0032 | 13950 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0032 |  |  | D-DWG-PHW-020.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 130
PHW-VG-0063 | 13960 | 13980 | 20 | PHW | Vegetation | TREE REMOVAL | VEG_PHW063 | [49 empty] | 3 LARGE TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 80 | 73 | TRIM | [26 empty] | TRENCH | 0 | NO
PHW-PIPE-0156 | 13965 | 14233.48 | 268.48 | PHW | Pipe | PIPE | PHW-PIPE-0156 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TB-070 | 14107.829 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-070 | [7 empty] | PHW |  | Type 1 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 82 |  |  | Bend | [9 empty] | 114663 | 1 | each | 114663 | Bend | 45 | DICL | 600 | 2641 | 100 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-074 | 14107.829 |  |  | PHW | Bend | HOR | PHW-BND-074 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 45° | DICL | 600 | [7 empty] | 45 | PIPE | 0 | NO
PHW-CM-0045 | 14114 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0045 |  |  | D-DWG-PHW-021.2 |  |  | BYDA | Yes | PHW |  | BYDA NBN COMMS DN100 | [9 empty] | NBN Co |  |  | 100 | [27 empty] | Forreign service raw data.xlsx | 131
PHW-CM-0046 | 14116 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0046 |  |  | D-DWG-PHW-021.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMS DN35 | [9 empty] | Telstra |  |  | 35 | [27 empty] | Forreign service raw data.xlsx | 132
PHW-TB-071 | 14119.348 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-071 | [7 empty] | PHW |  | Type 1 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 83 |  |  | Bend | [9 empty] | 114663 | 1 | each | 114663 | Bend | 45 | DICL | 600 | 2643 | 100 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-075 | 14119.348 |  |  | PHW | Bend | HOR | PHW-BND-075 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 45° | DICL | 600 | [7 empty] | 45 | PIPE | 0 | NO
PHW-EL-0033 | 14192 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0033 |  |  | D-DWG-PHW-021.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 133
PHW-PIPE-0157 | 14233.48 | 14242 | 8.52 | PHW | Pipe | PIPE | PHW-PIPE-0157 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Pipelay Crew
PHW-PIPE-0158 | 14242 | 14326.695 | 84.695 | PHW | Pipe | PIPE | PHW-PIPE-0158 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-VG-0064 | 14250 | 14260 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW064 | [49 empty] | 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 81 | 21.5 | LIGHT | [26 empty] | TRENCH | 0 | NO
PHW-TB-097 | 14323.567 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-097 | [7 empty] | PHW |  | Type 12 | [12 empty] | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 256 |  |  | Isolation Valve | [10 empty] | 1 | each |  | Isolation Valve |  |  | 600 | 2707 | 100 | Isolation valve | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-IV-005 | 14324 |  |  | PHW | Valve | IV | PHW-IV-005 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW | [55 empty] | Supplied |  | 1 | each | [9 empty] | 3 |  |  |  | PIPE | 0 | NO
PHW-AV-028 | 14324 |  |  | PHW | Valve | AV | PHW-AV-028 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PHW-PIPE-0159 | 14326.695 | 14335.85 | 9.155 | PHW | Pipe | PIPE | PHW-PIPE-0159 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Pipelay Crew
PHW-EL-0034 | 14335 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0034 |  |  | D-DWG-PHW-021.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 134
PHW-PIPE-0160 | 14335.85 | 14360 | 24.15 | PHW | Pipe | PIPE | PHW-PIPE-0160 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-VG-0065 | 14350 | 14360 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW065 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 82 | 29 | TRIM | [26 empty] | TRENCH | 0 | NO
PHW-PIPE-0161 | 14360 | 14366.236 | 6.236 | PHW | Pipe | PIPE | PHW-PIPE-0161 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Pipelay Crew
PHW-PIPE-0162 | 14366.236 | 14577.68 | 211.444 | PHW | Pipe | PIPE | PHW-PIPE-0162 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-PIPE-0163 | 14577.68 | 14589 | 11.32 | PHW | Pipe | PIPE | PHW-PIPE-0163 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Pipelay Crew
PHW-PIPE-0164 | 14589 | 14778.123 | 189.123 | PHW | Pipe | PIPE | PHW-PIPE-0164 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-CM-0047 | 14630 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0047 |  |  | D-DWG-PHW-021.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMS DN35 | [9 empty] | Telstra |  |  | 35 | [27 empty] | Forreign service raw data.xlsx | 135
PHW-TT-0088 | 14778.123 | 14806.133 | 28.01 | PHW | Trench Type | TRENCH SECTION |  | 4 | 28.01 | D-DWG-PHW-022.2 | D-DWG-PHW-022.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 93
PHW-PIPE-0165 | 14778.123 | 14806.133 | 28.01 | PHW | Pipe | PIPE | PHW-PIPE-0165 |  |  | D-DWG-PHW-022.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-BND-076 | 14798.123 |  |  | PHW | Bend | HOR | PHW-BND-076 |  |  | D-DWG-PHW-022.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 45.5° | MSCL | 650 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PHW-SW-0004 | 14803 |  |  | PHW | Foreign Service | SEWER | PHW-SW-0004 |  |  | D-DWG-PHW-022.2 |  | D-DWG-PHW-022_C | BYDA | Yes | PHW |  | BYDA TRC SEWER | [9 empty] | Toowoomba Regional Council | [30 empty] | Forreign service raw data.xlsx | 136
PHW-RD-0013 | 14806.133 | 14839.513 | 33.38 | PHW | Road & Rail Crossing | MAJOR ROAD CROSSING | PHW-RD-0013 |  | 33.38 | [5 empty] | PHW | Drayton Wellcamp Road |  | Sealed | 600 |  |  | OD660x6WT MSCL Sintalock Type 2 PN35 Carrier & OD813x12WT MS Enveloper |  |  |  |  | TRC | [15 empty] | Thrust Boring | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 20 | [28 empty] | TRENCH | 0 | NO
PHW-TT-0089 | 14806.133 | 14839.513 | 33.38 | PHW | Trench Type | TRENCH SECTION |  | 8A | 33.38 | D-DWG-PHW-022.2 | D-DWG-PHW-022.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 94
PHW-BND-077 | 14806.133 |  |  | PHW | Bend | HOR | PHW-BND-077 |  |  | D-DWG-PHW-022.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 44.5° | MSCL | 650 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PHW-PIPE-0166 | 14806.133 | 14839.513 | 33.38 | PHW | Pipe | PIPE | PHW-PIPE-0166 |  |  | D-DWG-PHW-022.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 + OD813 12WT MS Enveloper | [6 empty] | MSCL | 660 | [54 empty] | Drayton Wellcamp Road | Trenchless
PHW-EL-0035 | 14830 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0035 |  |  | D-DWG-PHW-022.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 137
PHW-CM-0048 | 14832 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0048 |  |  | D-DWG-PHW-022.2 |  |  | PUP | Yes | PHW |  | PUP COMMS DN100 | [12 empty] | 100 | [27 empty] | Forreign service raw data.xlsx | 138
PHW-TT-0090 | 14839.513 | 15743.419 | 903.906 | PHW | Trench Type | TRENCH SECTION |  | 1A | 903.906 | D-DWG-PHW-022.2 | D-DWG-PHW-023.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 95
PHW-PIPE-0167 | 14839.513 | 14932.21 | 92.697 | PHW | Pipe | PIPE | PHW-PIPE-0167 |  |  | D-DWG-PHW-022.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-EL-0036 | 14925 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0036 |  |  | D-DWG-PHW-022.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 139
PHW-PIPE-0168 | 14932.21 | 14940 | 7.79 | PHW | Pipe | PIPE | PHW-PIPE-0168 |  |  | D-DWG-PHW-022.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Pipelay Crew
PHW-PIPE-0169 | 14940 | 15004.47 | 64.47 | PHW | Pipe | PIPE | PHW-PIPE-0169 |  |  | D-DWG-PHW-022.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-AV-029 | 14993 |  |  | PHW | Valve | AV | PHW-AV-029 |  |  | D-DWG-PHW-022.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-PIPE-0170 | 15004.47 | 15011 | 6.53 | PHW | Pipe | PIPE | PHW-PIPE-0170 |  |  | D-DWG-PHW-022.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Pipelay Crew
PHW-PIPE-0171 | 15011 | 15046.72 | 35.72 | PHW | Pipe | PIPE | PHW-PIPE-0171 |  |  | D-DWG-PHW-022.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-PIPE-0172 | 15046.72 | 15072 | 25.28 | PHW | Pipe | PIPE | PHW-PIPE-0172 |  |  | D-DWG-PHW-022.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Pipelay Crew
PHW-EL-0037 | 15049 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0037 |  |  | D-DWG-PHW-022.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 140
PHW-EL-0038 | 15052 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0038 |  |  | D-DWG-PHW-022.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 141
PHW-CM-0049 | 15054 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0049 |  |  | D-DWG-PHW-022.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMS DN50 | [9 empty] | Telstra |  |  | 50 | [27 empty] | Forreign service raw data.xlsx | 142
PHW-PIPE-0173 | 15072 | 15298.457 | 226.457 | PHW | Pipe | PIPE | PHW-PIPE-0173 |  |  | D-DWG-PHW-022.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-SCV-015 | 15248 |  |  | PHW | Valve | SCV | PHW-SCV-015 |  |  | D-DWG-PHW-022.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PHW-TB-090 | 15248.457 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-090 | [7 empty] | PHW |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 249 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN600xDN150 DIFBE SCOUR TEE |  | 150 | 2900 | 100 | Tee; DN600XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-PIPE-0174 | 15298.457 | 15743.419 | 444.962 | PHW | Pipe | PIPE | PHW-PIPE-0174 |  |  | D-DWG-PHW-022.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Pipelay Crew
PHW-AV-030 | 15685 |  |  | PHW | Valve | AV | PHW-AV-030 |  |  | D-DWG-PHW-022.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-TT-0091 | 15743.419 | 15762.576 | 19.157 | PHW | Trench Type | TRENCH SECTION |  | 6 | 19.157 | D-DWG-PHW-023.2 | D-DWG-PHW-023.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 96
PHW-PIPE-0175 | 15743.419 | 15762.576 | 19.157 | PHW | Pipe | PIPE | PHW-PIPE-0175 |  |  | D-DWG-PHW-023.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Open trench minor road Crossing | Pipelay Crew
PHW-CM-0050 | 15758 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0050 |  |  | D-DWG-PHW-023.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMS DN50 | [9 empty] | Telstra |  |  | 50 | [27 empty] | Forreign service raw data.xlsx | 143
PHW-VG-0066 | 15760 | 15770 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW066 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 83 | 43 | TRIM | [26 empty] | TRENCH | 0 | NO
PHW-RD-0014 | 15762 | 15777 | 15 | PHW | Road & Rail Crossing | MINOR ROAD CROSSING | PHW-RD-0014 |  | 15 | [5 empty] | PHW | Max Smith Road |  | Sealed | 600 |  |  | DN600 PN35 DICL RRJ | 15 |  |  |  | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 21 | [28 empty] | TRENCH | 0 | NO
PHW-TT-0092 | 15762.576 | 16145.329 | 382.753 | PHW | Trench Type | TRENCH SECTION |  | 1A | 382.753 | D-DWG-PHW-023.2 | D-DWG-PHW-024.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 97
PHW-PIPE-0176 | 15762.576 | 16145.329 | 382.753 | PHW | Pipe | PIPE | PHW-PIPE-0176 |  |  | D-DWG-PHW-023.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-CM-0051 | 15763 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0051 |  |  | D-DWG-PHW-023.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMS DN50 | [9 empty] | Telstra |  |  | 50 | [27 empty] | Forreign service raw data.xlsx | 144
PHW-EL-0039 | 15769 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0039 |  |  | D-DWG-PHW-023.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 145
PHW-TT-0093 | 16145.329 | 16226.018 | 80.689 | PHW | Trench Type | TRENCH SECTION |  | 1A/1B/1C | 80.689 | D-DWG-PHW-024.2 | D-DWG-PHW-024.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 98
PHW-PIPE-0177 | 16145.329 | 16226.018 | 80.689 | PHW | Pipe | PIPE | PHW-PIPE-0177 |  |  | D-DWG-PHW-024.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Open cut trench Minor Creek Crossing | Pipelay Crew
PHW-CC-0012 | 16180 | 16191 | 11 | PHW | Creek Crossing | TRENCHED CREEK CROSSING | PHW-CC-0012 | [7 empty] | PHW |  |  |  |  | FABRIC/VEGETATION | [37 empty] | PHw_PWG_Creek_Crossings.xlsx | 14 | [28 empty] | TRENCH | 0 | NO
PHW-TT-0094 | 16226.018 | 16956.128 | 730.11 | PHW | Trench Type | TRENCH SECTION |  | 1A | 730.11 | D-DWG-PHW-024.2 | D-DWG-PHW-025.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 99
PHW-PIPE-0178 | 16226.018 | 16956.128 | 730.11 | PHW | Pipe | PIPE | PHW-PIPE-0178 |  |  | D-DWG-PHW-024.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-AV-031 | 16385 |  |  | PHW | Valve | AV | PHW-AV-031 |  |  | D-DWG-PHW-024.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-EL-0040 | 16590 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0040 |  |  | D-DWG-PHW-024.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 146
PHW-TT-0095 | 16956.128 | 17043.684 | 87.556 | PHW | Trench Type | TRENCH SECTION |  | 5 | 87.556 | D-DWG-PHW-025.2 | D-DWG-PHW-025.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 100
PHW-PIPE-0179 | 16956.128 | 16988.429 | 32.301 | PHW | Pipe | PIPE | PHW-PIPE-0179 |  |  | D-DWG-PHW-025.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Open Cut Trench Major Creek Crossing | Special Crossings
PHW-BND-078 | 16966.302 |  |  | PHW | Bend | VERT | PHW-BND-078 |  |  | D-DWG-PHW-025.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 6.8° | MSCL | 650 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PHW-CC-0013 | 16978 | 17002 | 24 | PHW | Creek Crossing | TRENCHED CREEK CROSSING | PHW-CC-0013 | [7 empty] | PHW | SPRING CREEK |  |  |  | LOOSE ROCK | A | [36 empty] | PHw_PWG_Creek_Crossings.xlsx | 15 | [28 empty] | TRENCH | 0 | NO
PHW-BND-079 | 16978.492 |  |  | PHW | Bend | COMPOUND | PHW-BND-079 |  |  | D-DWG-PHW-025.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 7.1° | MSCL | 650 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PHW-BND-080 | 16985.882 |  |  | PHW | Bend | HOR | PHW-BND-080 |  |  | D-DWG-PHW-025.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 7.1° | MSCL | 650 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PHW-BND-081 | 16988.429 |  |  | PHW | Bend | VERT | PHW-BND-081 |  |  | D-DWG-PHW-025.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 6.8° | MSCL | 650 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PHW-PIPE-0180 | 16988.429 | 17043.684 | 55.255 | PHW | Pipe | PIPE | PHW-PIPE-0180 |  |  | D-DWG-PHW-025.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Open Cut Trench Major Creek Crossing | Special Crossings
PHW-SW-0005 | 17031 |  |  | PHW | Foreign Service | SEWER | PHW-SW-0005 |  |  | D-DWG-PHW-025.2 |  |  | PUP | Yes | PHW |  | PUP SEWER DN375 | [12 empty] | 375 | [27 empty] | Forreign service raw data.xlsx | 147
PHW-SCV-016 | 17038 |  |  | PHW | Valve | SCV | PHW-SCV-016 |  |  | D-DWG-PHW-025.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PHW-TB-091 | 17038.094 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-091 | [7 empty] | PHW |  | Type 6 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 250 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN600xDN150 DIFBE SCOUR TEE |  | 150 | 3114 | 25 | Tee; DN600XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-082 | 17038.095 |  |  | PHW | Bend | VERT | PHW-BND-082 |  |  | D-DWG-PHW-025.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.1° | MSCL | 650 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PHW-TB-072 | 17043.684 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-072 | [7 empty] | PHW |  | Type 10 | [11 empty] | MSCL | 650 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 84 |  |  | Bend | [9 empty] | 49509 | 1 | each | 49509 | Bend | 8.6 | MSCL | 650 | 3103 | 25 | Bend; MS - 8.6° | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TT-0096 | 17043.684 | 17910.948 | 867.264 | PHW | Trench Type | TRENCH SECTION |  | 1A | 867.264 | D-DWG-PHW-025.2 | D-DWG-PHW-026.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 101
PHW-BND-083 | 17043.684 |  |  | PHW | Bend | VERT | PHW-BND-083 |  |  | D-DWG-PHW-025.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 8.6° | MSCL | 650 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PHW-PIPE-0181 | 17043.684 | 17910.948 | 867.264 | PHW | Pipe | PIPE | PHW-PIPE-0181 |  |  | D-DWG-PHW-025.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-AV-032 | 17245 |  |  | PHW | Valve | AV | PHW-AV-032 |  |  | D-DWG-PHW-025.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-CC-0014 | 17900 | 18040 | 140 | PHW | Creek Crossing | TRENCHED CREEK CROSSING | PHW-CC-0014 | [7 empty] | PHW |  |  |  |  | FABRIC/VEGETATION | [37 empty] | PHw_PWG_Creek_Crossings.xlsx | 16 | [28 empty] | TRENCH | 0 | NO
PHW-TT-0097 | 17910.948 | 17996.139 | 85.191 | PHW | Trench Type | TRENCH SECTION |  | 4 | 85.191 | D-DWG-PHW-026.2 | D-DWG-PHW-026.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 102
PHW-PIPE-0182 | 17910.948 | 17996.139 | 85.191 | PHW | Pipe | PIPE | PHW-PIPE-0182 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Open cut trench Minor Creek Crossing | Special Crossings
PHW-TB-092 | 17984.612 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-092 | [7 empty] | PHW |  | Type 6 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 251 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN600xDN150 DIFBE SCOUR TEE |  | 150 | 3134 | 50 | Tee; DN600XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-SCV-017 | 17985 |  |  | PHW | Valve | SCV | PHW-SCV-017 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PHW-TT-0098 | 17996.139 | 18075.205 | 79.066 | PHW | Trench Type | TRENCH SECTION |  | 1A | 79.066 | D-DWG-PHW-026.2 | D-DWG-PHW-026.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 103
PHW-PIPE-0183 | 17996.139 | 18075.205 | 79.066 | PHW | Pipe | PIPE | PHW-PIPE-0183 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PHW-TB-073 | 18060.322 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-073 | [7 empty] | PHW |  | Type 1 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 85 |  |  | Bend | [9 empty] | 114663 | 1 | each | 114663 | Bend | 45 | DICL | 600 | 3127 | 50 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-084 | 18060.652 |  |  | PHW | Bend | HOR | PHW-BND-084 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 45° | DICL | 600 | [7 empty] | 45 | PIPE | 0 | NO
PHW-TB-074 | 18066.852 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-074 | [7 empty] | PHW |  | Type 1 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 86 |  |  | Bend | [9 empty] | 114663 | 1 | each | 114663 | Bend | 45 | DICL | 600 | 3127 | 50 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-085 | 18067.59 |  |  | PHW | Bend | HOR | PHW-BND-085 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 45° | DICL | 600 | [7 empty] | 45 | PIPE | 0 | NO
PHW-TT-0099 | 18075.205 | 18080.497 | 5.292 | PHW | Trench Type | TRENCH SECTION |  | 4 | 5.292 | D-DWG-PHW-026.2 | D-DWG-PHW-026.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 104
PHW-PIPE-0184 | 18075.205 | 18080.497 | 5.292 | PHW | Pipe | PIPE | PHW-PIPE-0184 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Crossing DN375 Sewer | Special Crossings
PHW-SW-0006 | 18078 |  |  | PHW | Foreign Service | SEWER | PHW-SW-0006 |  |  | D-DWG-PHW-026.2 |  |  | BYDA | Yes | PHW |  | BYDA SEWER DN375 | [12 empty] | 375 | [27 empty] | Forreign service raw data.xlsx | 148
PHW-CM-0052 | 18079 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0052 |  |  | D-DWG-PHW-026.2 |  |  | BYDA | Yes | PHW |  | BYD TELSTRA COMMS | [9 empty] | Telstra | [30 empty] | Forreign service raw data.xlsx | 149
PHW-TT-0100 | 18080.497 | 19120.154 | 1039.657 | PHW | Trench Type | TRENCH SECTION |  | 1A | 1039.657 | D-DWG-PHW-026.2 | D-DWG-PHW-028.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 105
PHW-PIPE-0185 | 18080.497 | 18499.436 | 418.939 | PHW | Pipe | PIPE | PHW-PIPE-0185 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-FN-0020 | 18452 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0020 |  |  | D-DWG-PHW-027.2 |  |  |  | Yes | PHW |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 150
PHW-CC-0015 | 18469 | 18539 | 70 | PHW | Creek Crossing | TRENCHED CREEK CROSSING | PHW-CC-0015 | [7 empty] | PHW |  |  |  |  | FABRIC/VEGETATION | [37 empty] | PHw_PWG_Creek_Crossings.xlsx | 17 | [28 empty] | TRENCH | 0 | NO
PHW-PIPE-0186 | 18499.436 | 18545.51 | 46.074 | PHW | Pipe | PIPE | PHW-PIPE-0186 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Open cut trench Minor Creek Crossing | Pipelay Crew
PHW-FN-0021 | 18507 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0021 |  |  | D-DWG-PHW-027.2 |  |  |  | Yes | PHW |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 151
PHW-PIPE-0187 | 18545.51 | 18554 | 8.49 | PHW | Pipe | PIPE | PHW-PIPE-0187 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Pipelay Crew
PHW-PIPE-0188 | 18554 | 18614 | 60 | PHW | Pipe | PIPE | PHW-PIPE-0188 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TB-075 | 18577.023 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-075 | [7 empty] | PHW |  | Type 4 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 87 |  |  | Bend | [9 empty] | 15563 | 1 | each | 15563 | Bend | 11.25 | DICL | 600 | 3057 | 50 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-086 | 18577.024 |  |  | PHW | Bend | HOR | PHW-BND-086 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-TB-076 | 18590.921 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-076 | [7 empty] | PHW |  | Type 4 | [11 empty] | DICL | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 88 |  |  | Bend | [9 empty] | 15563 | 1 | each | 15563 | Bend | 11.25 | DICL | 600 | 3053 | 50 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-BND-087 | 18590.921 |  |  | PHW | Bend | HOR | PHW-BND-087 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 600 | [7 empty] | 11.25 | PIPE | 0 | NO
PHW-EL-0041 | 18601 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0041 |  |  | D-DWG-PHW-027.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 152
PHW-PIPE-0189 | 18614 | 18624 | 10 | PHW | Pipe | PIPE | PHW-PIPE-0189 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Pipelay Crew
PHW-PIPE-0190 | 18624 | 18752.41 | 128.41 | PHW | Pipe | PIPE | PHW-PIPE-0190 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-AV-033 | 18677 |  |  | PHW | Valve | AV | PHW-AV-033 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-CM-0053 | 18717 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0053 |  |  | D-DWG-PHW-027.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMSTUD | [9 empty] | Telstra | [29 empty] | LOCATION OF TELECOMS SERVICE NOT KNOWN.CONTRACTOR TO CONFIRM PRIOR TO CONSTRUCTION | Forreign service raw data.xlsx | 153
PHW-PIPE-0191 | 18752.41 | 18881.16 | 128.75 | PHW | Pipe | PIPE | PHW-PIPE-0191 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-CM-0054 | 18828 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0054 |  |  | D-DWG-PHW-027.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMS DN35 | [9 empty] | Telstra |  |  | 35 | [27 empty] | Forreign service raw data.xlsx | 154
PHW-PIPE-0192 | 18881.16 | 18890 | 8.84 | PHW | Pipe | PIPE | PHW-PIPE-0192 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Pipelay Crew
PHW-EL-0042 | 18889 |  |  | PHW | Foreign Service | ELECTRICITY | PHW-EL-0042 |  |  | D-DWG-PHW-027.2 |  |  | PUP | Yes | PHW |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 155
PHW-PIPE-0193 | 18890 | 19002.445 | 112.445 | PHW | Pipe | PIPE | PHW-PIPE-0193 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-VG-0067 | 18990 | 19000 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW067 | [49 empty] | 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 84 | 63.7 | LIGHT | [26 empty] | TRENCH | 0 | NO
PHW-PIPE-0194 | 19002.445 | 19047.78 | 45.335 | PHW | Pipe | PIPE | PHW-PIPE-0194 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Pipelay Crew
PHW-TS-0394 | 19009.5 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0394 |  |  | D-DWG-PHW-028 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 439 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0068 | 19010 | 19060 | 50 | PHW | Vegetation | TREE REMOVAL | VEG_PHW068 | [49 empty] | 6 LARGE TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 85 | 593 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-TS-0395 | 19022.1 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0395 |  |  | D-DWG-PHW-028 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 440 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0396 | 19039.67 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0396 |  |  | D-DWG-PHW-028 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 441 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0397 | 19047.47 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0397 |  |  | D-DWG-PHW-028 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 442 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0195 | 19047.78 | 19058 | 10.22 | PHW | Pipe | PIPE | PHW-PIPE-0195 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-TS-0398 | 19055.27 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0398 |  |  | D-DWG-PHW-028 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 443 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-PIPE-0196 | 19058 | 19097.802 | 39.802 | PHW | Pipe | PIPE | PHW-PIPE-0196 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Driveway crossings | Pipelay Crew
PHW-TS-0399 | 19063.07 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0399 |  |  | D-DWG-PHW-028 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 444 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0400 | 19070.87 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0400 |  |  | D-DWG-PHW-028 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 445 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0401 | 19078.67 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0401 |  |  | D-DWG-PHW-028 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 446 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0402 | 19086.47 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0402 |  |  | D-DWG-PHW-028 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 447 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0403 | 19094.27 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0403 |  |  | D-DWG-PHW-028 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 448 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TB-101 | 19097.802 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-101 | [7 empty] | PHW |  | 2 x Type 12 | [12 empty] | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 260 |  |  | Pigging Station | [10 empty] | 2 | each |  | Pigging Station |  |  | 600 | 2877 | 150 | Pigging station | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-PIPE-0197 | 19097.802 | 19120.154 | 22.352 | PHW | Pipe | PIPE | PHW-PIPE-0197 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW |  |  |  | 600 |  |  | DN600 DICL PN35 | [6 empty] | DICL | 600 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-PIG-002 | 19098 |  |  | PHW | Valve | PIG | PHW-PIG-002 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [13 empty] | PIPE | 0 | NO
PHW-TS-0404 | 19102.07 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0404 |  |  | D-DWG-PHW-028 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 449 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-TS-0405 | 19109.87 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0405 |  |  | D-DWG-PHW-028 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 450 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-VG-0069 | 19110 | 19120 | 10 | PHW | Vegetation | TREE REMOVAL | VEG_PHW069 | [49 empty] | 2 LARGE TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 86 | 105 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-TS-0406 | 19111 |  |  | PHW | Trench Stop & Bulkhead | TRENCH STOP | PHW-TS-0406 |  |  | D-DWG-PHW-028 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 451 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PHW-AV-034 | 19118 |  |  | PHW | Valve | AV | PHW-AV-034 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PHW | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PHW-TB-098 | 19120.153 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-098 | [7 empty] | PHW |  | Type 14 | [12 empty] | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 257 |  |  | In-Line | [10 empty] | 1 | each |  | In-Line |  |  | 600 | 2863 | 150 | In-line | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-TT-0101 | 19120.154 | 19155.385 | 35.231 | PHW | Trench Type | TRENCH SECTION |  | 5 | 35.231 | D-DWG-PHW-028.2 | D-DWG-PHW-028.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 106
PHW-BND-088 | 19120.154 |  |  | PHW | Bend | HOR | PHW-BND-088 |  |  | D-DWG-PHW-028.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 45° | DICL | 600 | [7 empty] | 45 | PIPE | 0 | NO
PHW-PIPE-0198 | 19120.154 | 19138.361 | 18.207 | PHW | Pipe | PIPE | PHW-PIPE-0198 |  |  | D-DWG-PHW-028.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-CM-0055 | 19123 |  |  | PHW | Foreign Service | COMMUNICATIONS | PHW-CM-0055 |  |  | D-DWG-PHW-028.2 |  |  | BYDA | Yes | PHW |  | BYDA TELSTRA COMMS DN20 | [9 empty] | Telstra |  |  | 20 | [26 empty] | CONTRACTOR TO LOCATE EXISTING TELECOMS AND ENSURE PIGGING STATION DOES NOT CLASH | Forreign service raw data.xlsx | 156
PHW-FN-0022 | 19124 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0022 |  |  | D-DWG-PHW-028.2 |  |  |  | Yes | PHW |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 157
PHW-BND-089 | 19130.885 |  |  | PHW | Bend | VERT | PHW-BND-089 |  |  | D-DWG-PHW-028.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 11.3° | MSCL | 650 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PHW-VG-0070 | 19132 | 19132 | 0 | PHW | Vegetation | TREE REMOVAL | VEG_PHW070 | [49 empty] | 1 LARGE TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 87 | 73 | HEAVY | [26 empty] | TRENCH | 0 | NO
PHW-BND-090 | 19138.361 |  |  | PHW | Bend | VERT | PHW-BND-090 |  |  | D-DWG-PHW-028.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 37.2° | MSCL | 650 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PHW-PIPE-0199 | 19138.361 | 19155.385 | 17.024 | PHW | Pipe | PIPE | PHW-PIPE-0199 |  |  | D-DWG-PHW-028.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | [6 empty] | MSCL | 660 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PHW-BS-0041 | 19139.744 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0041 |  |  | D-DWG-PHW-028 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 452 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-BND-091 | 19139.744 |  |  | PHW | Bend | HOR | PHW-BND-091 |  |  | D-DWG-PHW-028.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 9.3° | MSCL | 650 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PHW-BS-0042 | 19141.144 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0042 |  |  | D-DWG-PHW-028 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 453 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0043 | 19142.544 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0043 |  |  | D-DWG-PHW-028 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 454 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-BND-092 | 19142.608 |  |  | PHW | Bend | VERT | PHW-BND-092 |  |  | D-DWG-PHW-028.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 8.9° | MSCL | 650 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PHW-BND-093 | 19143.359 |  |  | PHW | Bend | COMPOUND | PHW-BND-093 |  |  | D-DWG-PHW-028.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 17.4° | MSCL | 650 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PHW-BS-0044 | 19143.944 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0044 |  |  | D-DWG-PHW-028 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 455 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0045 | 19145.344 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0045 |  |  | D-DWG-PHW-028 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 456 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-BS-0046 | 19146.744 |  |  | PHW | Trench Stop & Bulkhead | BULK HEAD | PHW-BS-0046 |  |  | D-DWG-PHW-028 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 457 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PHW-BND-094 | 19146.854 |  |  | PHW | Bend | VERT | PHW-BND-094 |  |  | D-DWG-PHW-028.2 |  |  |  |  | PHW | [57 empty] | 1 | each |  | Bend | 36.2° | MSCL | 650 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PHW-FN-0023 | 19155 |  |  | PHW | Foreign Service | FENCE | PHW-FN-0023 |  |  | D-DWG-PHW-028.2 |  |  |  | Yes | PHW |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 158
PHW-TT-0102 | 19155.385 | 19156.739 | 1.354 | PHW | Trench Type | TRENCH SECTION |  | 1A | 1.354 | D-DWG-PHW-028.2 | D-DWG-PHW-028.2 |  |  |  | PHW | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 107
PHW-TB-099 | 19155.385 |  |  | PHW | Thrust Block | THRUST BLOCK | PHW-TB-099 | [7 empty] | PHW |  | Type 14 | [12 empty] | 600 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 258 |  |  | In-Line | [10 empty] | 1 | each |  | In-Line |  |  | 600 | 2834 | 150 | In-line | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PHW-PIPE-0200 | 19155.385 | 19156.739 | 1.354 | PHW | Pipe | PIPE | PHW-PIPE-0200 |  |  | D-DWG-PHW-028.2 |  |  |  |  | PHW |  |  |  | 660 |  |  | OD660 MSCL 6WT RRJ PN35 | [6 empty] | MSCL | 660 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PPH-TB-001 | 63.236 |  |  | PPH | Thrust Block | THRUST BLOCK | PPH-TB-001 | [7 empty] | PPH |  | Type 5 | [11 empty] | DICL | 500 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 6 |  |  | Bend | [10 empty] | 1 | each |  | Bend | 45+11.25 | DICL | 500 | 1558 | 150 | Bend; 45+11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH
PPH-TB-002 | 81.352 |  |  | PPH | Thrust Block | THRUST BLOCK | PPH-TB-002 | [7 empty] | PPH |  | Type 5 | [11 empty] | DICL | 500 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 7 |  |  | Bend | [10 empty] | 1 | each |  | Bend | 45 | DICL | 500 | 1555 | 150 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH
PPH-TB-003 | 94.039 |  |  | PPH | Thrust Block | THRUST BLOCK | PPH-TB-003 | [7 empty] | PPH |  | Type 5 | [11 empty] | DICL | 500 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 8 |  |  | Bend | [10 empty] | 1 | each |  | Bend | 45 | DICL | 500 | 1555 | 150 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH
PPH-TB-004 | 833.013 |  |  | PPH | Thrust Block | THRUST BLOCK | PPH-TB-004 | [7 empty] | PPH |  | Type 5 | [11 empty] | DICL | 500 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 9 |  |  | Bend | [10 empty] | 1 | each |  | Bend | 45 | DICL | 500 | 1441 | 150 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH
PPH-TB-005 | 871.821 |  |  | PPH | Thrust Block | THRUST BLOCK | PPH-TB-005 | [7 empty] | PPH |  | Type 5 | [11 empty] | DICL | 500 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 10 |  |  | Bend | [10 empty] | 1 | each |  | Bend | 45 | DICL | 500 | 1432 | 150 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH
PPH-TB-006 | 988.07 |  |  | PPH | Thrust Block | THRUST BLOCK | PPH-TB-006 | [7 empty] | PPH |  | Type 5 | [11 empty] | DICL | 500 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 11 |  |  | Bend | [10 empty] | 1 | each |  | Bend | 45 | DICL | 500 | 1426 | 150 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH
PPH-TB-007 | 992.261 |  |  | PPH | Thrust Block | THRUST BLOCK | PPH-TB-007 | [7 empty] | PPH |  | Type 5 | [11 empty] | DICL | 500 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 12 |  |  | Bend | [10 empty] | 1 | each |  | Bend | 45 | DICL | 500 | 1424 | 150 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH
PWG-TT-0001 | 0 | 3.804 | 3.804 | PWG | Trench Type | TRENCH SECTION |  | 1A | 3.804 | D-DWG-PWG-001.2 | D-DWG-PWG-001.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 109
PWG-PIPE-0001 | 0 | 1.332 | 1.332 | PWG | Pipe | PIPE | PWG-PIPE-0001 |  |  | D-DWG-PWG-001.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-TB-001 | 0.548 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-001 | [7 empty] | PWG |  | Type 11 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 89 |  |  | Bend | [9 empty] | 28674 | 1 | each | 28674 | Bend | 11.25 | DICL | 375 | 2833 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-PIPE-0002 | 1.332 | 6.229 | 4.897 | PWG | Pipe | PIPE | PWG-PIPE-0002 |  |  | D-DWG-PWG-001.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-TS-0001 | 2 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0001 |  |  | D-DWG-PWG-001 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 458 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TT-0002 | 3.804 | 6.229 | 2.425 | PWG | Trench Type | TRENCH SECTION |  | 4 | 2.425 | D-DWG-PWG-001.2 | D-DWG-PWG-001.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 110
PWG-TT-0003 | 6.229 | 14.172 | 7.943 | PWG | Trench Type | TRENCH SECTION |  | 1A | 7.943 | D-DWG-PWG-001.2 | D-DWG-PWG-001.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 111
PWG-PIPE-0003 | 6.229 | 14.172 | 7.943 | PWG | Pipe | PIPE | PWG-PIPE-0003 |  |  | D-DWG-PWG-001.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-BS-0001 | 7 |  |  | PWG | Trench Stop & Bulkhead | BULK HEAD | PWG-BS-0001 |  |  | D-DWG-PWG-001 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 459 | [12 empty] | 20507 | 1 | each | 20507 | [12 empty] | TRENCH | 0 | NO
PWG-CM-0001 | 12 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0001 |  |  | D-DWG-PWG-001.2 |  |  | BYDA | Yes | PWG |  | BYDA TELSTRA COMMS DN20 | [9 empty] | Telstra |  |  | 20 | [27 empty] | Forreign service raw data.xlsx | 159
PWG-TS-0002 | 12 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0002 |  |  | D-DWG-PWG-001 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 460 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TB-002 | 14.172 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-002 | [7 empty] | PWG |  | Type 9 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 90 |  |  | Bend | [9 empty] | 12764 | 1 | each | 12764 | Bend | 11.25 | DICL | 375 | 2861 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-TT-0004 | 14.172 | 42.513 | 28.341 | PWG | Trench Type | TRENCH SECTION |  | 7 | 28.341 | D-DWG-PWG-001.2 | D-DWG-PWG-001.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 112
PWG-BND-001 | 14.172 |  |  | PWG | Bend | VERT | PWG-BND-001 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-PIPE-0004 | 14.172 | 42.513 | 28.341 | PWG | Pipe | PIPE | PWG-PIPE-0004 |  |  | D-DWG-PWG-001.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Special Crossings
PWG-RD-0001 | 16 | 27 | 11 | PWG | Road & Rail Crossing | MINOR ROAD CROSSING | PWG-RD-0001 |  | 11 | [5 empty] | PWG | E. Drews Road |  | Unsealed | 375 |  |  | DN375 PN35 DICL RRJ |  | 11 |  |  | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 6 | [28 empty] | TRENCH | 0 | NO
PWG-TB-003 | 42.513 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-003 | [7 empty] | PWG |  | Type 5 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 91 |  |  | Bend | [9 empty] | 13282 | 1 | each | 13282 | Bend | 45 | DICL | 375 | 2865 | 150 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-TT-0005 | 42.513 | 823.6 | 781.087 | PWG | Trench Type | TRENCH SECTION |  | 1A | 781.087 | D-DWG-PWG-001.2 | D-DWG-PWG-002.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 113
PWG-BND-002 | 42.513 |  |  | PWG | Bend | HOR | PWG-BND-002 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 45° | DICL | 375 | [7 empty] | 45 | PIPE | 0 | NO
PWG-PIPE-0005 | 42.513 | 114.113 | 71.6 | PWG | Pipe | PIPE | PWG-PIPE-0005 |  |  | D-DWG-PWG-001.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-132 | 99.181 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-132 | [7 empty] | PWG |  | 2 x Type 13 | [12 empty] | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 233 |  |  | Pigging Station | [10 empty] | 2 | each |  | Pigging Station |  |  | 375 | 2873 | 150 | Pigging station | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-PIG-001 | 99.181 |  |  | PWG | Valve | PIG | PWG-PIG-001 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [13 empty] | PIPE | 0 | NO
PWG-PIPE-0006 | 114.113 | 238.728 | 124.615 | PWG | Pipe | PIPE | PWG-PIPE-0006 |  |  | D-DWG-PWG-001.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-004 | 228.027 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-004 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 92 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 2892 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-003 | 228.027 |  |  | PWG | Bend | HOR | PWG-BND-003 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-TB-103 | 230.031 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-103 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 204 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 2892 | 150 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-SCV-001 | 230.031 |  |  | PWG | Valve | SCV | PWG-SCV-001 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-PIPE-0007 | 238.728 | 659.59 | 420.862 | PWG | Pipe | PIPE | PWG-PIPE-0007 |  |  | D-DWG-PWG-001.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-005 | 323.528 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-005 | [7 empty] | PWG |  | Type 6 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 93 |  |  | Bend | [9 empty] | 13283 | 1 | each | 13283 | Bend | 22.5 | DICL | 375 | 2880 | 150 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-004 | 323.528 |  |  | PWG | Bend | HOR | PWG-BND-004 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 375 | [7 empty] | 22.5 | PIPE | 0 | NO
PWG-VG-0001 | 400 | 430 | 30 | PWG | Vegetation | TREE REMOVAL | VEG_PWG001 | [49 empty] | 4 SMALL TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 88 | 234 | HEAVY | [26 empty] | TRENCH | 0 | NO
PWG-TB-006 | 424.209 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-006 | [7 empty] | PWG |  | Type 6 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 94 |  |  | Bend | [9 empty] | 13283 | 1 | each | 13283 | Bend | 22.5 | DICL | 375 | 2857 | 150 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-005 | 424.209 |  |  | PWG | Bend | HOR | PWG-BND-005 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 375 | [7 empty] | 22.5 | PIPE | 0 | NO
PWG-VG-0002 | 440 | 450 | 10 | PWG | Vegetation | TREE REMOVAL | VEG_PWG002 | [49 empty] | 2 SMALL TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 89 | 113 | LIGHT | [26 empty] | TRENCH | 0 | NO
PWG-VG-0003 | 490 | 530 | 40 | PWG | Vegetation | TREE REMOVAL | VEG_PWG003 | [49 empty] | MULTIPLE SMALL TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 90 | 273 | HEAVY | [26 empty] | TRENCH | 0 | NO
PWG-VG-0004 | 590 | 740 | 150 | PWG | Vegetation | TREE REMOVAL | VEG_PWG004 | [49 empty] | MULTIPLE LARGE & SMALL TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 91 | 1550 | HEAVY | [26 empty] | TRENCH | 0 | NO
PWG-TB-007 | 611.583 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-007 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 95 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 2853 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-006 | 611.583 |  |  | PWG | Bend | HOR | PWG-BND-006 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-FN-0001 | 635 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0001 |  |  | D-DWG-PWG-001.2 |  |  |  | Yes | PWG |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 160
PWG-AV-001 | 643.786 |  |  | PWG | Valve | AV | PWG-AV-001 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PWG-FN-0002 | 653 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0002 |  |  | D-DWG-PWG-001.2 |  |  |  | Yes | PWG |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 161
PWG-PIPE-0008 | 659.59 | 836.889 | 177.299 | PWG | Pipe | PIPE | PWG-PIPE-0008 |  |  | D-DWG-PWG-001.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-008 | 700.553 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-008 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 96 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 2853 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-007 | 700.553 |  |  | PWG | Bend | HOR | PWG-BND-007 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-TB-104 | 702.553 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-104 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 205 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 2853 | 150 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-SCV-002 | 702.553 |  |  | PWG | Valve | SCV | PWG-SCV-002 |  |  | D-DWG-PHW-001.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-FN-0003 | 755 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0003 |  |  | D-DWG-PWG-002.2 |  |  |  | Yes | PWG |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 162
PWG-VG-0005 | 760 | 880 | 120 | PWG | Vegetation | TREE REMOVAL | VEG_PWG005 | [49 empty] | MULTIPLE LARGE & SMALL TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 92 | 1520 | HEAVY | [26 empty] | TRENCH | 0 | NO
PWG-TT-0006 | 823.6 | 889.23 | 65.63 | PWG | Trench Type | TRENCH SECTION |  | 5 | 65.63 | D-DWG-PWG-002.2 | D-DWG-PWG-002.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 114
PWG-PIPE-0009 | 836.889 | 889.23 | 52.341 | PWG | Pipe | PIPE | PWG-PIPE-0009 |  |  | D-DWG-PWG-002.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TT-0007 | 889.23 | 929.856 | 40.626 | PWG | Trench Type | TRENCH SECTION |  | 1A/1B/1C | 40.626 | D-DWG-PWG-002.2 | D-DWG-PWG-002.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 115
PWG-PIPE-0010 | 889.23 | 904.59 | 15.36 | PWG | Pipe | PIPE | PWG-PIPE-0010 |  |  | D-DWG-PWG-002.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Creek Crossings | Pipelay Crew
PWG-CC-0001 | 903 | 912 | 9 | PWG | Creek Crossing | TRENCHED CREEK CROSSING | PWG-CC-0001 | [7 empty] | PWG |  |  |  |  | FABRIC/VEGETATION | [37 empty] | PHw_PWG_Creek_Crossings.xlsx | 3 | [28 empty] | TRENCH | 0 | NO
PWG-PIPE-0011 | 904.59 | 929.856 | 25.266 | PWG | Pipe | PIPE | PWG-PIPE-0011 |  |  | D-DWG-PWG-002.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Creek Crossings | Pipelay Crew
PWG-FN-0004 | 905 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0004 |  |  | D-DWG-PWG-002.2 |  | D-DWG-PWG-002_C |  | Yes | PWG |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 163
PWG-TT-0008 | 929.856 | 1181.379 | 251.523 | PWG | Trench Type | TRENCH SECTION |  | 1A | 251.523 | D-DWG-PWG-002.2 | D-DWG-PWG-002.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 116
PWG-PIPE-0012 | 929.856 | 1181.379 | 251.523 | PWG | Pipe | PIPE | PWG-PIPE-0012 |  |  | D-DWG-PWG-002.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-VG-0006 | 990 | 1000 | 10 | PWG | Vegetation | TREE REMOVAL | VEG_PWG006 | [49 empty] | 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 93 | 56.6 | LIGHT | [26 empty] | TRENCH | 0 | NO
PWG-TB-009 | 995.153 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-009 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 97 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 2800 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-008 | 995.153 |  |  | PWG | Bend | HOR | PWG-BND-008 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-VG-0007 | 1040 | 1050 | 10 | PWG | Vegetation | TREE REMOVAL | VEG_PWG007 | [49 empty] | 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 94 | 27 | LIGHT | [26 empty] | TRENCH | 0 | NO
PWG-TT-0009 | 1181.379 | 1186.379 | 5 | PWG | Trench Type | TRENCH SECTION |  | 4 | 5 | D-DWG-PWG-002.2 | D-DWG-PWG-002.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 117
PWG-PIPE-0013 | 1181.379 | 1186.379 | 5 | PWG | Pipe | PIPE | PWG-PIPE-0013 |  |  | D-DWG-PWG-002.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-SW-0001 | 1183 |  |  | PWG | Foreign Service | SEWER | PWG-SW-0001 |  |  | D-DWG-PWG-002.2 |  |  | BYDA | Yes | PWG |  | BYDA SEWER DN375 | [12 empty] | 375 | [27 empty] | Forreign service raw data.xlsx | 164
PWG-TT-0010 | 1186.379 | 1488.93 | 302.551 | PWG | Trench Type | TRENCH SECTION |  | 1A | 302.551 | D-DWG-PWG-002.2 | D-DWG-PWG-003.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 118
PWG-PIPE-0014 | 1186.379 | 1194.438 | 8.059 | PWG | Pipe | PIPE | PWG-PIPE-0014 |  |  | D-DWG-PWG-002.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TS-0003 | 1190.9 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0003 |  |  | D-DWG-PWG-002 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 461 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-PIPE-0015 | 1194.438 | 1206.954 | 12.516 | PWG | Pipe | PIPE | PWG-PIPE-0015 |  |  | D-DWG-PWG-002.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Driveway crossings | Pipelay Crew
PWG-PIPE-0016 | 1206.954 | 1459 | 252.046 | PWG | Pipe | PIPE | PWG-PIPE-0016 |  |  | D-DWG-PWG-002.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-EL-0001 | 1403 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0001 |  |  | D-DWG-PWG-003.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 165
PWG-CM-0002 | 1425 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0002 |  |  | D-DWG-PWG-003.2 |  |  | BYDA | Yes | PWG |  | BYDA TELSTRA COMMS | [9 empty] | Telstra | [30 empty] | Forreign service raw data.xlsx | 166
PWG-VG-0008 | 1430 | 1460 | 30 | PWG | Vegetation | TREE REMOVAL | VEG_PWG008 | [49 empty] | MULTIPLE SMALL TREES & 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 95 | 215 | HEAVY | [26 empty] | TRENCH | 0 | NO
PWG-PIPE-0017 | 1459 | 1466.83 | 7.83 | PWG | Pipe | PIPE | PWG-PIPE-0017 |  |  | D-DWG-PWG-002.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Driveway crossings | Pipelay Crew
PWG-PIPE-0018 | 1466.83 | 1488.93 | 22.1 | PWG | Pipe | PIPE | PWG-PIPE-0018 |  |  | D-DWG-PWG-002.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-CM-0003 | 1469 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0003 |  |  | D-DWG-PWG-003.2 |  | D-DWG-PWG-003_C | PUP | Yes | PWG |  | PUP COMMS DN50 | [12 empty] | 50 | [27 empty] | Forreign service raw data.xlsx | 167
PWG-TB-010 | 1488.93 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-010 | [7 empty] | PWG |  | Type 5 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 98 |  |  | Bend | [9 empty] | 13282 | 1 | each | 13282 | Bend | 45 | DICL | 375 | 2701 | 150 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-TT-0011 | 1488.93 | 1507.505 | 18.575 | PWG | Trench Type | TRENCH SECTION |  | 7 | 18.575 | D-DWG-PWG-003.2 | D-DWG-PWG-003.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 119
PWG-BND-009 | 1488.93 |  |  | PWG | Bend | HOR | PWG-BND-009 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 45° | DICL | 375 | [7 empty] | 45 | PIPE | 0 | NO
PWG-PIPE-0019 | 1488.93 | 1507.505 | 18.575 | PWG | Pipe | PIPE | PWG-PIPE-0019 |  |  | D-DWG-PWG-003.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Pipelay Crew
PWG-RD-0002 | 1490 | 1501 | 11 | PWG | Road & Rail Crossing | MINOR ROAD CROSSING | PWG-RD-0002 |  | 11 | [5 empty] | PWG | Keding Road |  | Unsealed | 375 |  |  | DN375 PN35 DICL RRJ |  | 11 |  |  | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 7 | [28 empty] | TRENCH | 0 | NO
PWG-EL-0002 | 1494 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0002 |  |  | D-DWG-PWG-003.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 168
PWG-TB-011 | 1507.505 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-011 | [7 empty] | PWG |  | Type 5 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 99 |  |  | Bend | [9 empty] | 13282 | 1 | each | 13282 | Bend | 45 | DICL | 375 | 2700 | 150 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-TT-0012 | 1507.505 | 1856.862 | 349.357 | PWG | Trench Type | TRENCH SECTION |  | 1A | 349.357 | D-DWG-PWG-003.2 | D-DWG-PWG-003.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 120
PWG-BND-010 | 1507.505 |  |  | PWG | Bend | HOR | PWG-BND-010 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 45° | DICL | 375 | [7 empty] | 45 | PIPE | 0 | NO
PWG-PIPE-0020 | 1507.505 | 1608.82 | 101.315 | PWG | Pipe | PIPE | PWG-PIPE-0020 |  |  | D-DWG-PWG-003.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-AV-002 | 1511.079 |  |  | PWG | Valve | AV | PWG-AV-002 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PWG-TB-012 | 1570.993 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-012 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 100 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 2695 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-011 | 1570.993 |  |  | PWG | Bend | HOR | PWG-BND-011 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-PIPE-0021 | 1608.82 | 1614.19 | 5.37 | PWG | Pipe | PIPE | PWG-PIPE-0021 |  |  | D-DWG-PWG-003.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Driveway crossings | Pipelay Crew
PWG-PIPE-0022 | 1614.19 | 1856.862 | 242.672 | PWG | Pipe | PIPE | PWG-PIPE-0022 |  |  | D-DWG-PWG-003.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-013 | 1630.183 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-013 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 101 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 2686 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-012 | 1630.183 |  |  | PWG | Bend | HOR | PWG-BND-012 |  |  | D-DWG-PHW-002.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-EL-0003 | 1788 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0003 |  |  | D-DWG-PWG-003.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 169
PWG-AV-003 | 1833.632 |  |  | PWG | Valve | AV | PWG-AV-003 |  |  | D-DWG-PHW-003.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PWG-EL-0004 | 1839 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0004 |  |  | D-DWG-PWG-003.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 170
PWG-TT-0013 | 1856.862 | 1876.481 | 19.619 | PWG | Trench Type | TRENCH SECTION |  | 7 | 19.619 | D-DWG-PWG-003.2 | D-DWG-PWG-003.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 121
PWG-PIPE-0023 | 1856.862 | 1876.481 | 19.619 | PWG | Pipe | PIPE | PWG-PIPE-0023 |  |  | D-DWG-PWG-003.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Special Crossings
PWG-RD-0003 | 1857 | 1880 | 23 | PWG | Road & Rail Crossing | MINOR ROAD CROSSING | PWG-RD-0003 |  | 23 | [5 empty] | PWG | Crockers Road |  | Unsealed | 375 |  |  | DN375 PN35 DICL RRJ |  | 23 |  |  | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 8 | [28 empty] | TRENCH | 0 | NO
PWG-CM-0004 | 1867 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0004 |  |  | D-DWG-PWG-003.2 |  |  | PUP | Yes | PWG |  | PUP COMMS DN100 | [12 empty] | 100 | [27 empty] | Forreign service raw data.xlsx | 171
PWG-CM-0005 | 1871 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0005 |  |  | D-DWG-PWG-003.2 |  |  | BYDA | Yes | PWG |  | BYDA NBN COMMS DN30 | [9 empty] | NBN Co |  |  | 30 | [27 empty] | Forreign service raw data.xlsx | 172
PWG-CM-0006 | 1872 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0006 |  |  | D-DWG-PWG-003.2 |  |  | PUP | Yes | PWG |  | PUP COMMS DN35 | [12 empty] | 35 | [27 empty] | Forreign service raw data.xlsx | 173
PWG-TT-0014 | 1876.481 | 1888.54 | 12.059 | PWG | Trench Type | TRENCH SECTION |  | 1A | 12.059 | D-DWG-PWG-003.2 | D-DWG-PWG-003.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 122
PWG-PIPE-0024 | 1876.481 | 1888.54 | 12.059 | PWG | Pipe | PIPE | PWG-PIPE-0024 |  |  | D-DWG-PWG-003.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-BND-013 | 1883.634 |  |  | PWG | Bend | HOR | PWG-BND-013 |  |  | D-DWG-PHW-003.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 45° | DICL | 375 | [7 empty] | 45 | PIPE | 0 | NO
PWG-RD-0004 | 1888.54 | 1900 | 11.46 | PWG | Road & Rail Crossing | MINOR ROAD CROSSING | PWG-RD-0004 |  | 11.46 | [5 empty] | PWG | Keding Road |  | Unsealed | 375 |  |  | OD457x5WT Sintalock Type 1 MSCL |  |  | 11.46 |  | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 9 | [28 empty] | TRENCH | 0 | NO
PWG-TT-0015 | 1888.54 | 1902.016 | 13.476 | PWG | Trench Type | TRENCH SECTION |  | 4&7 | 13.476 | D-DWG-PWG-003.2 | D-DWG-PWG-003.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 123
PWG-PIPE-0025 | 1888.54 | 1902.016 | 13.476 | PWG | Pipe | PIPE | PWG-PIPE-0025 |  |  | D-DWG-PWG-003.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Special Crossings
PWG-DR-0001 | 1894 |  |  | PWG | Foreign Service | DRAINAGE | PWG-DR-0001 |  |  | D-DWG-PWG-003.2 |  |  | PUP | Yes | PWG |  | PUP DRAINAGE DN1200x450 | [12 empty] | 1200 x 450 | [27 empty] | Forreign service raw data.xlsx | 174
PWG-SW-0002 | 1900 |  |  | PWG | Foreign Service | SEWER | PWG-SW-0002 |  |  | D-DWG-PWG-003.2 |  |  | BYDA | Yes | PWG |  | BYDA SEWER DN250 | [12 empty] | 250 | [27 empty] | Forreign service raw data.xlsx | 175
PWG-TT-0016 | 1902.016 | 2043.24 | 141.224 | PWG | Trench Type | TRENCH SECTION |  | 1A | 141.224 | D-DWG-PWG-003.2 | D-DWG-PWG-003.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 124
PWG-PIPE-0026 | 1902.016 | 2043.24 | 141.224 | PWG | Pipe | PIPE | PWG-PIPE-0026 |  |  | D-DWG-PWG-003.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-TB-014 | 1906.136 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-014 | [7 empty] | PWG |  | Type 5 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 102 |  |  | Bend | [9 empty] | 13282 | 1 | each | 13282 | Bend | 45 | DICL | 375 | 2654 | 150 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-014 | 1906.136 |  |  | PWG | Bend | HOR | PWG-BND-014 |  |  | D-DWG-PHW-003.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 45° | DICL | 375 | [7 empty] | 45 | PIPE | 0 | NO
PWG-TT-0017 | 2043.24 | 2048.591 | 5.351 | PWG | Trench Type | TRENCH SECTION |  | 4 | 5.351 | D-DWG-PWG-003.2 | D-DWG-PWG-003.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 125
PWG-PIPE-0027 | 2043.24 | 2048.591 | 5.351 | PWG | Pipe | PIPE | PWG-PIPE-0027 |  |  | D-DWG-PWG-003.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-SW-0003 | 2046 |  |  | PWG | Foreign Service | SEWER | PWG-SW-0003 |  |  | D-DWG-PWG-003.2 |  |  | BYDA | Yes | PWG |  | BDYA TRC SEWER DN 150 | [9 empty] | Toowoomba Regional Council |  |  | 150 | [27 empty] | Forreign service raw data.xlsx | 176
PWG-TT-0018 | 2048.591 | 2413.402 | 364.811 | PWG | Trench Type | TRENCH SECTION |  | 1A | 364.811 | D-DWG-PWG-003.2 | D-DWG-PWG-004.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 126
PWG-PIPE-0028 | 2048.591 | 2065.863 | 17.272 | PWG | Pipe | PIPE | PWG-PIPE-0028 |  |  | D-DWG-PWG-003.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-TS-0004 | 2052.9 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0004 |  |  | D-DWG-PWG-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 462 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TS-0005 | 2061.5 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0005 |  |  | D-DWG-PWG-003 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 463 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-PIPE-0029 | 2065.863 | 2413.402 | 347.539 | PWG | Pipe | PIPE | PWG-PIPE-0029 |  |  | D-DWG-PWG-003.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-EL-0005 | 2186 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0005 |  |  | D-DWG-PWG-004.2 |  |  | BYDA | Yes | PWG |  | BYDA ELECTRICITY UGD DN100 | [12 empty] | 100 | [27 empty] | Forreign service raw data.xlsx | 177
PWG-VG-0009 | 2210 | 2220 | 10 | PWG | Vegetation | TREE REMOVAL | VEG_PWG009 | [49 empty] | MULTIPLE SMALL TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 96 | 80 | HEAVY | [26 empty] | TRENCH | 0 | NO
PWG-DR-0002 | 2217 |  |  | PWG | Foreign Service | DRAINAGE | PWG-DR-0002 |  |  | D-DWG-PWG-004.2 |  |  | PUP | Yes | PWG |  | PUP DRAINAGE DN900x450 | [12 empty] | 900 x 450 | [27 empty] | Forreign service raw data.xlsx | 178
PWG-VG-0010 | 2370 | 2380 | 10 | PWG | Vegetation | TREE REMOVAL | VEG_PWG010 | [49 empty] | 2 SMALL TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 97 | 50 | LIGHT | [26 empty] | TRENCH | 0 | NO
PWG-TT-0019 | 2413.402 | 2564.395 | 150.993 | PWG | Trench Type | TRENCH SECTION |  | 4 | 150.993 | D-DWG-PWG-004.2 | D-DWG-PWG-004.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 127
PWG-PIPE-0030 | 2413.402 | 2564.645 | 151.243 | PWG | Pipe | PIPE | PWG-PIPE-0030 |  |  | D-DWG-PWG-004.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-DR-0003 | 2494 |  |  | PWG | Foreign Service | DRAINAGE | PWG-DR-0003 |  |  | D-DWG-PWG-004.2 |  |  | PUP | Yes | PWG |  | PUP DRAINAGE DN450 | [12 empty] | 450 | [27 empty] | Forreign service raw data.xlsx | 179
PWG-BND-015 | 2545.832 |  |  | PWG | Bend | HOR | PWG-BND-015 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 7.8° | MSCL | 450 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PWG-SW-0004 | 2556 |  |  | PWG | Foreign Service | SEWER | PWG-SW-0004 |  |  | D-DWG-PWG-004.2 |  |  | BYDA | Yes | PWG |  | BYDA SEWER DN250 | [12 empty] | 250 | [27 empty] | Forreign service raw data.xlsx | 180
PWG-DR-0004 | 2560 |  |  | PWG | Foreign Service | DRAINAGE | PWG-DR-0004 |  |  | D-DWG-PWG-004.2 |  |  | PUP | Yes | PWG |  | PUP DRAINAGE DN600 | [12 empty] | 600 | [27 empty] | Forreign service raw data.xlsx | 181
PWG-TT-0020 | 2564.395 | 2592.076 | 27.681 | PWG | Trench Type | TRENCH SECTION |  | 4&6 | 27.681 | D-DWG-PWG-004.2 | D-DWG-PWG-004.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 128
PWG-BND-016 | 2564.395 |  |  | PWG | Bend | HOR | PWG-BND-016 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 6.1° | MSCL | 450 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PWG-PIPE-0031 | 2564.645 | 2592.076 | 27.431 | PWG | Pipe | PIPE | PWG-PIPE-0031 |  |  | D-DWG-PWG-004.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Special Crossings
PWG-RD-0005 | 2572 | 2596 | 24 | PWG | Road & Rail Crossing | MINOR ROAD CROSSING | PWG-RD-0005 |  | 24 | [5 empty] | PWG | Gore Street |  | Sealed | 375 |  |  | OD457x5WT Sintalock Type 1 MSCL | 3.9 |  |  | 20.1 | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 10 | [28 empty] | TRENCH | 0 | NO
PWG-WA-0001 | 2578 |  |  | PWG | Foreign Service | WATER | PWG-WA-0001 |  |  | D-DWG-PWG-004.2 |  |  | BYDA | Yes | PWG |  | BYDA WATER DN150 | [12 empty] | 150 | [27 empty] | Forreign service raw data.xlsx | 182
PWG-TT-0021 | 2592.076 | 2631.951 | 39.875 | PWG | Trench Type | TRENCH SECTION |  | 1A | 39.875 | D-DWG-PWG-004.2 | D-DWG-PWG-004.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 129
PWG-PIPE-0032 | 2592.076 | 2631.951 | 39.875 | PWG | Pipe | PIPE | PWG-PIPE-0032 |  |  | D-DWG-PWG-004.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-TB-015 | 2596.042 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-015 | [7 empty] | PWG |  | Type 6 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 103 |  |  | Bend | [9 empty] | 13159 | 1 | each | 13159 | Bend | 11.25 | DICL | 375 | 2547 | 50 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-017 | 2596.042 |  |  | PWG | Bend | HOR | PWG-BND-017 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-AV-004 | 2599.042 |  |  | PWG | Valve | AV | PWG-AV-004 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PWG-CP-0001 | 2626 | 2694 | 68 | PWG | Road & Rail Crossing | CARPARK/SIDE LANE | PWG-CP-0001 |  | 68 | [5 empty] | PWG | Progress Avenue |  | Unsealed | 375 |  |  | DN375 PN35 DICL RRJ |  | 68 |  |  | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 11 | [28 empty] | TRENCH | 0 | NO
PWG-TT-0022 | 2631.951 | 2691.626 | 59.675 | PWG | Trench Type | TRENCH SECTION |  | 7 | 59.675 | D-DWG-PWG-004.2 | D-DWG-PWG-004.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 130
PWG-PIPE-0033 | 2631.951 | 2691.626 | 59.675 | PWG | Pipe | PIPE | PWG-PIPE-0033 |  |  | D-DWG-PWG-004.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Special Crossings
PWG-TB-016 | 2691.626 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-016 | [7 empty] | PWG |  | Type 6 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 104 |  |  | Bend | [9 empty] | 13159 | 1 | each | 13159 | Bend | 11.25 | DICL | 375 | 2577 | 50 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-TT-0023 | 2691.626 | 2739.593 | 47.967 | PWG | Trench Type | TRENCH SECTION |  | 6 | 47.967 | D-DWG-PWG-004.2 | D-DWG-PWG-004.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 131
PWG-PIPE-0034 | 2691.626 | 2739.593 | 47.967 | PWG | Pipe | PIPE | PWG-PIPE-0034 |  |  | D-DWG-PWG-004.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Special Crossings
PWG-BND-018 | 2691.628 |  |  | PWG | Bend | HOR | PWG-BND-018 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-RD-0006 | 2694 | 2739 | 45 | PWG | Road & Rail Crossing | MINOR ROAD CROSSING | PWG-RD-0006 |  | 45 | [5 empty] | PWG | Progress Avenue |  | Sealed | 375 |  |  | DN375 PN35 DICL RRJ | 45 |  |  |  | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 12 | [28 empty] | TRENCH | 0 | NO
PWG-TT-0024 | 2739.593 | 2750.013 | 10.42 | PWG | Trench Type | TRENCH SECTION |  | 4 | 10.42 | D-DWG-PWG-004.2 | D-DWG-PWG-004.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 132
PWG-PIPE-0035 | 2739.593 | 2750.013 | 10.42 | PWG | Pipe | PIPE | PWG-PIPE-0035 |  |  | D-DWG-PWG-004.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-EL-0006 | 2744 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0006 |  |  | D-DWG-PWG-004.2 |  | D-DWG-PWG-004_C | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 183
PWG-TT-0025 | 2750.013 | 2783.074 | 33.061 | PWG | Trench Type | TRENCH SECTION |  | 4&6 | 33.061 | D-DWG-PWG-004.2 | D-DWG-PWG-004.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 133
PWG-PIPE-0036 | 2750.013 | 2783.074 | 33.061 | PWG | Pipe | PIPE | PWG-PIPE-0036 |  |  | D-DWG-PWG-004.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 + OD610 9WT MS Enveloper | [6 empty] | MSCL | 457 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Special Crossings
PWG-CM-0007 | 2754 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0007 |  |  | D-DWG-PWG-004.2 |  |  | BYDA | Yes | PWG |  | BYDA TELSTRA COMMS DN100 | [9 empty] | Telstra |  |  | 100 | [27 empty] | Forreign service raw data.xlsx | 185
PWG-CM-0008 | 2754 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0008 |  |  | D-DWG-PWG-004.2 |  |  | BYDA | Yes | PWG |  | BYDA TELSTRA COMMS DN100 | [9 empty] | Telstra |  |  | 100 | [27 empty] | Forreign service raw data.xlsx | 186
PWG-CM-0009 | 2754 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0009 |  |  | D-DWG-PWG-004.2 |  |  | BYDA | Yes | PWG |  | BYDA NBN COMMS DN30 | [9 empty] | NBN Co |  |  | 30 | [27 empty] | Forreign service raw data.xlsx | 187
PWG-CM-0010 | 2754 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0010 |  |  | D-DWG-PWG-004.2 |  |  | BYDA | Yes | PWG |  | BYDA NBN COMMS DN30 | [9 empty] | NBN Co |  |  | 30 | [27 empty] | Forreign service raw data.xlsx | 188
PWG-CM-0011 | 2754 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0011 |  |  | D-DWG-PWG-004.2 |  |  | BYDA | Yes | PWG |  | BYDA NBN COMMS DN30 | [9 empty] | NBN Co |  |  | 30 | [27 empty] | Forreign service raw data.xlsx | 189
PWG-CM-0012 | 2754 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0012 |  |  | D-DWG-PWG-004.2 |  |  | BYDA | Yes | PWG |  | BYDA NBN COMMS DN30 | [9 empty] | NBN Co |  |  | 30 | [27 empty] | Forreign service raw data.xlsx | 190
PWG-CM-0013 | 2754 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0013 |  |  | D-DWG-PWG-004.2 |  |  | BYDA | Yes | PWG |  | BYDA NBN COMMS DN30 | [9 empty] | NBN Co |  |  | 30 | [27 empty] | Forreign service raw data.xlsx | 191
PWG-CM-0014 | 2754 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0014 |  |  | D-DWG-PWG-004.2 |  |  | BYDA | Yes | PWG |  | BYDA NBN COMMS DN30 | [9 empty] | NBN Co |  |  | 30 | [27 empty] | Forreign service raw data.xlsx | 192
PWG-WA-0002 | 2754 |  |  | PWG | Foreign Service | WATER | PWG-WA-0002 |  |  | D-DWG-PWG-004.2 |  |  | BYDA | Yes | PWG |  | BYDA TRC WATER DN100 | [9 empty] | Toowoomba Regional Council |  |  | 100 | [27 empty] | Forreign service raw data.xlsx | 184
PWG-EL-0007 | 2763 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0007 |  |  | D-DWG-PWG-004.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 193
PWG-EL-0008 | 2763 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0008 |  |  | D-DWG-PWG-004.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 196
PWG-WA-0003 | 2763 |  |  | PWG | Foreign Service | WATER | PWG-WA-0003 |  |  | D-DWG-PWG-004.2 |  |  | BYDA | Yes | PWG |  | BYDA WATER DN200 | [12 empty] | 200 | [27 empty] | Forreign service raw data.xlsx | 194
PWG-WA-0004 | 2763 |  |  | PWG | Foreign Service | WATER | PWG-WA-0004 |  |  | D-DWG-PWG-004.2 |  |  | BYDA | Yes | PWG |  | BYDA TRC WATER | [9 empty] | Toowoomba Regional Council | [30 empty] | Forreign service raw data.xlsx | 195
PWG-RD-0007 | 2763 | 2777 | 14 | PWG | Road & Rail Crossing | MINOR ROAD CROSSING | PWG-RD-0007 |  | 14 | [5 empty] | PWG | Main Street |  | Sealed | 375 |  |  | OD457x5WT Sintalock Type 1 MSCL |  |  |  | 14 | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 13 | [28 empty] | TRENCH | 0 | NO
PWG-BND-019 | 2767.354 |  |  | PWG | Bend | HOR | PWG-BND-019 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 33.3° | MSCL | 450 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PWG-EL-0009 | 2768 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0009 |  |  | D-DWG-PWG-004.2 |  | D-DWG-PWG-004_C | BYDA | Yes | PWG |  | BYDA ELECTRICITYELD LV | [40 empty] | Forreign service raw data.xlsx | 197
PWG-EL-0010 | 2771 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0010 |  |  | D-DWG-PWG-004.2 |  |  | BYDA | Yes | PWG |  | BYDA ELECTRICITY UGD DN50 | [12 empty] | 50 | [27 empty] | Forreign service raw data.xlsx | 199
PWG-SW-0005 | 2771 |  |  | PWG | Foreign Service | SEWER | PWG-SW-0005 |  |  | D-DWG-PWG-004.2 |  |  | BYDA | Yes | PWG |  | BYDA TRC SEWER DN110 | [9 empty] | Toowoomba Regional Council |  |  | 110 | [27 empty] | Forreign service raw data.xlsx | 198
PWG-SW-0006 | 2773 |  |  | PWG | Foreign Service | SEWER | PWG-SW-0006 |  |  | D-DWG-PWG-004.2 |  |  | BYDA | Yes | PWG |  | BYDA TRC SEWER DN63 | [9 empty] | Toowoomba Regional Council |  |  | 63 | [27 empty] | Forreign service raw data.xlsx | 200
PWG-SW-0007 | 2775 |  |  | PWG | Foreign Service | SEWER | PWG-SW-0007 |  |  | D-DWG-PWG-004.2 |  |  | BYDA | Yes | PWG |  | BYDA SEWER DN315 | [12 empty] | 315 | [27 empty] | Forreign service raw data.xlsx | 201
PWG-SW-0008 | 2777 |  |  | PWG | Foreign Service | SEWER | PWG-SW-0008 |  |  | D-DWG-PWG-004.2 |  |  | PUP | Yes | PWG |  | PUP SEWER DN150 | [12 empty] | 150 | [27 empty] | Forreign service raw data.xlsx | 202
PWG-CM-0015 | 2781 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0015 |  |  | D-DWG-PWG-004.2 |  |  | PUP | Yes | PWG |  | PUP COMMS DN100 | [12 empty] | 100 | [27 empty] | Forreign service raw data.xlsx | 203
PWG-TT-0026 | 2783.074 | 2797.815 | 14.741 | PWG | Trench Type | TRENCH SECTION |  | 4 | 14.741 | D-DWG-PWG-004.2 | D-DWG-PWG-004.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 134
PWG-BND-020 | 2783.074 |  |  | PWG | Bend | HOR | PWG-BND-020 |  |  | D-DWG-PHW-004.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 39.1° | MSCL | 450 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PWG-PIPE-0037 | 2783.074 | 2797.815 | 14.741 | PWG | Pipe | PIPE | PWG-PIPE-0037 |  |  | D-DWG-PWG-004.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-TT-0027 | 2797.815 | 2865.366 | 67.551 | PWG | Trench Type | TRENCH SECTION |  | 1A | 67.551 | D-DWG-PWG-004.2 | D-DWG-PWG-005.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 135
PWG-PIPE-0038 | 2797.815 | 2861.368 | 63.553 | PWG | Pipe | PIPE | PWG-PIPE-0038 |  |  | D-DWG-PWG-004.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-CM-0016 | 2805 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0016 |  |  | D-DWG-PWG-005.2 |  |  | PUP | Yes | PWG |  | PUP COMMS DN50 | [12 empty] | 50 | [27 empty] | Forreign service raw data.xlsx | 204
PWG-PIPE-0039 | 2861.368 | 2865.366 | 3.998 | PWG | Pipe | PIPE | PWG-PIPE-0039 |  |  | D-DWG-PWG-004.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-BND-021 | 2864.868 |  |  | PWG | Bend | HOR | PWG-BND-021 |  |  | D-DWG-PHW-005.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 20° | MSCL | 450 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PWG-RD-0008 | 2865.366 | 2908.821 | 43.455 | PWG | Road & Rail Crossing | MAJOR ROAD CROSSING | PWG-RD-0008 |  | 43.455 | [5 empty] | PWG | Toowoomba-Athol Road |  | Sealed | 375 |  |  | OD457x5WT Sintalock Type 1 MSCL Carrier & OD610x9WT MS Enveloper |  |  |  |  | TMR | [15 empty] | Thrust Boring | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 14 | [28 empty] | TRENCH | 0 | NO
PWG-TT-0028 | 2865.366 | 2908.821 | 43.455 | PWG | Trench Type | TRENCH SECTION |  | 8A | 43.455 | D-DWG-PWG-005.2 | D-DWG-PWG-005.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 136
PWG-PIPE-0040 | 2865.366 | 2908.821 | 43.455 | PWG | Pipe | PIPE | PWG-PIPE-0040 |  |  | D-DWG-PWG-005.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 + OD610 9WT MS Enveloper | [6 empty] | MSCL | 457 | [54 empty] | Major Road - Trenchless | Trenchless
PWG-SW-0009 | 2868 |  |  | PWG | Foreign Service | SEWER | PWG-SW-0009 |  |  | D-DWG-PWG-005.2 |  |  | PUP | Yes | PWG |  | PUP SEWER DN150 | [12 empty] | 150 | [27 empty] | Forreign service raw data.xlsx | 205
PWG-FN-0005 | 2908 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0005 |  |  | D-DWG-PWG-005.2 |  |  |  | Yes | PWG |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 206
PWG-TT-0029 | 2908.821 | 3071.909 | 163.088 | PWG | Trench Type | TRENCH SECTION |  | 1A | 163.088 | D-DWG-PWG-005.2 | D-DWG-PWG-005.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 137
PWG-PIPE-0041 | 2908.821 | 3071.909 | 163.088 | PWG | Pipe | PIPE | PWG-PIPE-0041 |  |  | D-DWG-PWG-005.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-TB-017 | 2916.826 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-017 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 105 |  |  | Bend | [9 empty] | 12690 | 1 | each | 12690 | Bend | 22.5 | DICL | 375 | 2623 | 150 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-022 | 2916.826 |  |  | PWG | Bend | HOR | PWG-BND-022 |  |  | D-DWG-PHW-005.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 375 | [7 empty] | 22.5 | PIPE | 0 | NO
PWG-TT-0030 | 3071.909 | 3151.909 | 80 | PWG | Trench Type | TRENCH SECTION |  | 5 | 80 | D-DWG-PWG-005.2 | D-DWG-PWG-005.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 138
PWG-PIPE-0042 | 3071.909 | 3151.909 | 80 | PWG | Pipe | PIPE | PWG-PIPE-0042 |  |  | D-DWG-PWG-005.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Open Trenched Creek Crossings | Special Crossings
PWG-CC-0002 | 3072 | 3152 | 80 | PWG | Creek Crossing | TRENCHED CREEK CROSSING | PWG-CC-0002 | [7 empty] | PWG | WESTBROOK CREEK |  |  |  | LOOSE ROCK | B | [36 empty] | PHw_PWG_Creek_Crossings.xlsx | 4 | [28 empty] | TRENCH | 0 | NO
PWG-TT-0031 | 3151.909 | 3991.367 | 839.458 | PWG | Trench Type | TRENCH SECTION |  | 1A | 839.458 | D-DWG-PWG-005.2 | D-DWG-PWG-006.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 139
PWG-SCV-003 | 3151.909 |  |  | PWG | Valve | SCV | PWG-SCV-003 |  |  | D-DWG-PHW-005.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 2 |  |  |  | PIPE | 0 | NO
PWG-PIPE-0043 | 3151.909 | 3991.367 | 839.458 | PWG | Pipe | PIPE | PWG-PIPE-0043 |  |  | D-DWG-PWG-005.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-VG-0011 | 3250 | 3260 | 10 | PWG | Vegetation | TREE REMOVAL | VEG_PWG011 | [49 empty] | 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 98 | 31.4 | LIGHT | [26 empty] | TRENCH | 0 | NO
PWG-AV-005 | 3324.224 |  |  | PWG | Valve | AV | PWG-AV-005 |  |  | D-DWG-PHW-005.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 2 |  |  |  | PIPE | 0 | NO
PWG-FN-0006 | 3368 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0006 |  |  | D-DWG-PWG-005.2 |  |  |  | Yes | PWG |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 207
PWG-VG-0012 | 3540 | 3560 | 20 | PWG | Vegetation | TREE REMOVAL | VEG_PWG012 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 99 | 145 | HEAVY | [26 empty] | TRENCH | 0 | NO
PWG-VG-0013 | 3590 | 3600 | 10 | PWG | Vegetation | TREE REMOVAL | VEG_PWG013 | [49 empty] | 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 100 | 13.6 | LIGHT | [26 empty] | TRENCH | 0 | NO
PWG-TT-0032 | 3991.367 | 4014.479 | 23.112 | PWG | Trench Type | TRENCH SECTION |  | 1A/1B/1C | 23.112 | D-DWG-PWG-006.2 | D-DWG-PWG-006.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 140
PWG-SCV-004 | 3991.367 |  |  | PWG | Valve | SCV | PWG-SCV-004 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 2 |  |  |  | PIPE | 0 | NO
PWG-PIPE-0044 | 3991.367 | 4014.479 | 23.112 | PWG | Pipe | PIPE | PWG-PIPE-0044 |  |  | D-DWG-PWG-006.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-CC-0003 | 3992 | 4014 | 22 | PWG | Creek Crossing | TRENCHED CREEK CROSSING | PWG-CC-0003 | [7 empty] | PWG |  |  |  |  | FABRIC/VEGETATION | [37 empty] | PHw_PWG_Creek_Crossings.xlsx | 5 | [28 empty] | TRENCH | 0 | NO
PWG-TB-018 | 4005.999 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-018 | [7 empty] | PWG |  | Type 9 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 106 |  |  | Bend | [9 empty] | 12764 | 1 | each | 12764 | Bend | 11.25 | DICL | 375 | 2668 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-023 | 4005.999 |  |  | PWG | Bend | VERT | PWG-BND-023 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-TS-0006 | 4010.3 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0006 |  |  | D-DWG-PWG-006 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 464 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TT-0033 | 4014.479 | 5447.953 | 1433.474 | PWG | Trench Type | TRENCH SECTION |  | 1A | 1433.474 | D-DWG-PWG-006.2 | D-DWG-PWG-008.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 141
PWG-PIPE-0045 | 4014.479 | 4043.508 | 29.029 | PWG | Pipe | PIPE | PWG-PIPE-0045 |  |  | D-DWG-PWG-006.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-TB-126 | 4040.672 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-126 | [7 empty] | PWG |  | Type 12 | [12 empty] | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 227 |  |  | Isolation Valve | [10 empty] | 1 | each |  | Isolation Valve |  |  | 375 | 2788 | 200 | Isolation valve | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-IV-001 | 4040.672 |  |  | PWG | Valve | IV | PWG-IV-001 |  |  | D-DWG-PHW-006.2 |  |  |  |  | PWG | [55 empty] | Supplied |  | 1 | each | [9 empty] | 3 |  |  |  | PIPE | 0 | NO
PWG-PIPE-0046 | 4043.508 | 5447.953 | 1404.445 | PWG | Pipe | PIPE | PWG-PIPE-0046 |  |  | D-DWG-PWG-006.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-VG-0014 | 4080 | 4090 | 10 | PWG | Vegetation | TREE REMOVAL | VEG_PWG014 | [49 empty] | 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 101 | 46.6 | LIGHT | [26 empty] | TRENCH | 0 | NO
PWG-SCV-005 | 4501.909 |  |  | PWG | Valve | SCV | PWG-SCV-005 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 2 |  |  |  | PIPE | 0 | NO
PWG-FN-0007 | 4640 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0007 |  |  | D-DWG-PWG-007.2 |  | D-DWG-PWG-007_C |  | Yes | PWG |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 208
PWG-AV-006 | 4846.524 |  |  | PWG | Valve | AV | PWG-AV-006 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 2 |  |  |  | PIPE | 0 | NO
PWG-SCV-006 | 5424.14 |  |  | PWG | Valve | SCV | PWG-SCV-006 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 2 |  |  |  | PIPE | 0 | NO
PWG-AV-007 | 5438.513 |  |  | PWG | Valve | AV | PWG-AV-007 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 2 |  |  |  | PIPE | 0 | NO
PWG-TB-019 | 5442.668 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-019 | [7 empty] | PWG |  | Type 11 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 107 |  |  | Bend | [9 empty] | 28674 | 1 | each | 28674 | Bend | 11.25 | DICL | 375 | 2690 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-024 | 5442.668 |  |  | PWG | Bend | VERT | PWG-BND-024 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-TS-0007 | 5445.3 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0007 |  |  | D-DWG-PWG-008 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 465 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TT-0034 | 5447.953 | 5475.997 | 28.044 | PWG | Trench Type | TRENCH SECTION |  | 5 | 28.044 | D-DWG-PWG-008.2 | D-DWG-PWG-008.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 142
PWG-PIPE-0047 | 5447.953 | 5475.997 | 28.044 | PWG | Pipe | PIPE | PWG-PIPE-0047 |  |  | D-DWG-PWG-008.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Open Trenched Creek Crossings | Special Crossings
PWG-CC-0004 | 5448 | 5476 | 28 | PWG | Creek Crossing | TRENCHED CREEK CROSSING | PWG-CC-0004 | [7 empty] | PWG | DRY CHANNEL |  |  |  | GABION/MATRESS | NOTE 1 | [36 empty] | PHw_PWG_Creek_Crossings.xlsx | 6 | [28 empty] | TRENCH | 0 | NO
PWG-FN-0008 | 5448 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0008 |  |  | D-DWG-PWG-008.2 |  |  |  | Yes | PWG |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 209
PWG-BND-025 | 5453.681 |  |  | PWG | Bend | VERT | PWG-BND-025 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 14.1° | MSCL | 450 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PWG-BND-026 | 5465.147 |  |  | PWG | Bend | VERT | PWG-BND-026 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.4° | MSCL | 450 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PWG-TB-020 | 5475.997 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-020 | [7 empty] | PWG |  | Type 11 | [11 empty] | MSCL | 450 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 108 |  |  | Bend | [9 empty] | 35673 | 1 | each | 35673 | Bend | 8.9 | MSCL | 450 | 2700 | 200 | Bend; MS - 8.9° | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-TT-0035 | 5475.997 | 7092.671 | 1616.674 | PWG | Trench Type | TRENCH SECTION |  | 1A | 1616.674 | D-DWG-PWG-008.2 | D-DWG-PWG-011.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 143
PWG-BND-027 | 5475.997 |  |  | PWG | Bend | VERT | PWG-BND-027 |  |  | D-DWG-PHW-007.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 8.9° | MSCL | 450 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PWG-PIPE-0048 | 5475.997 | 6507.647 | 1031.65 | PWG | Pipe | PIPE | PWG-PIPE-0048 |  |  | D-DWG-PWG-008.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-AV-008 | 6064.74 |  |  | PWG | Valve | AV | PWG-AV-008 |  |  | D-DWG-PHW-009.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 2 |  |  |  | PIPE | 0 | NO
PWG-SCV-007 | 6307.647 |  |  | PWG | Valve | SCV | PWG-SCV-007 |  |  | D-DWG-PHW-009.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 2 |  |  |  | PIPE | 0 | NO
PWG-FN-0009 | 6505 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0009 |  |  | D-DWG-PWG-010.2 |  | D-DWG-PWG-010_C |  | Yes | PWG |  | FENCE LINE NO POSTS | [40 empty] | Forreign service raw data.xlsx | 210
PWG-AV-009 | 6507.647 |  |  | PWG | Valve | AV | PWG-AV-009 |  |  | D-DWG-PHW-010.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 2 |  |  |  | PIPE | 0 | NO
PWG-PIPE-0049 | 6507.647 | 6666.39 | 158.743 | PWG | Pipe | PIPE | PWG-PIPE-0049 |  |  | D-DWG-PWG-008.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-PIPE-0050 | 6666.39 | 7092.108 | 425.718 | PWG | Pipe | PIPE | PWG-PIPE-0050 |  |  | D-DWG-PWG-008.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-CM-0017 | 7079 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0017 |  |  | D-DWG-PWG-011.2 |  |  | BYDA | Yes | PWG |  | BYDA NEXTGEN COMMS DN50 | [9 empty] | Nextgen |  |  | 50 | [27 empty] | Forreign service raw data.xlsx | 211
PWG-PIPE-0051 | 7092.108 | 7122.979 | 30.871 | PWG | Pipe | PIPE | PWG-PIPE-0051 |  |  | D-DWG-PWG-008.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Trenchless
PWG-TT-0036 | 7092.671 | 7122.979 | 30.308 | PWG | Trench Type | TRENCH SECTION |  | 1A/1B/1C | 30.308 | D-DWG-PWG-011.2 | D-DWG-PWG-011.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 144
PWG-TB-105 | 7092.671 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-105 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 206 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 2745 | 240 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-SCV-008 | 7092.671 |  |  | PWG | Valve | SCV | PWG-SCV-008 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-CC-0005 | 7097 | 7115 | 18 | PWG | Creek Crossing | TRENCHED CREEK CROSSING | PWG-CC-0005 | [7 empty] | PWG |  |  |  |  | FABRIC/VEGETATION | [37 empty] | PHw_PWG_Creek_Crossings.xlsx | 7 | [28 empty] | TRENCH | 0 | NO
PWG-FN-0010 | 7098 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0010 |  |  | D-DWG-PWG-011.2 |  |  |  | Yes | PWG |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 212
PWG-FN-0011 | 7116 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0011 |  |  | D-DWG-PWG-011.2 |  |  |  | Yes | PWG |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 213
PWG-TB-021 | 7122.979 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-021 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 109 |  |  | Bend | [9 empty] | 12690 | 1 | each | 12690 | Bend | 22.5 | DICL | 375 | 2740 | 240 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-TT-0037 | 7122.979 | 7146.681 | 23.702 | PWG | Trench Type | TRENCH SECTION |  | 1A | 23.702 | D-DWG-PWG-011.2 | D-DWG-PWG-011.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 145
PWG-BND-028 | 7122.979 |  |  | PWG | Bend | HOR | PWG-BND-028 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 375 | [7 empty] | 22.5 | PIPE | 0 | NO
PWG-PIPE-0052 | 7122.979 | 7146.681 | 23.702 | PWG | Pipe | PIPE | PWG-PIPE-0052 |  |  | D-DWG-PWG-011.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TT-0038 | 7146.681 | 7174.681 | 28 | PWG | Trench Type | TRENCH SECTION |  | 4 | 28 | D-DWG-PWG-011.2 | D-DWG-PWG-011.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 146
PWG-PIPE-0053 | 7146.681 | 7174.681 | 28 | PWG | Pipe | PIPE | PWG-PIPE-0053 |  |  | D-DWG-PWG-011.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TT-0039 | 7174.681 | 7539.66 | 364.979 | PWG | Trench Type | TRENCH SECTION |  | 1A | 364.979 | D-DWG-PWG-011.2 | D-DWG-PWG-011.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 147
PWG-PIPE-0054 | 7174.681 | 7539.66 | 364.979 | PWG | Pipe | PIPE | PWG-PIPE-0054 |  |  | D-DWG-PWG-011.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-022 | 7177.914 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-022 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 110 |  |  | Bend | [9 empty] | 12690 | 1 | each | 12690 | Bend | 22.5 | DICL | 375 | 2740 | 240 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-029 | 7177.914 |  |  | PWG | Bend | HOR | PWG-BND-029 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 375 | [7 empty] | 22.5 | PIPE | 0 | NO
PWG-FN-0012 | 7260 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0012 |  |  | D-DWG-PWG-011.2 |  | D-DWG-PWG-011_C |  | Yes | PWG |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 214
PWG-TB-127 | 7536.828 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-127 | [7 empty] | PWG |  | Type 13 | [12 empty] | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 228 |  |  | Isolation Valve | [10 empty] | 1 | each |  | Isolation Valve |  |  | 375 | 2690 | 240 | Isolation valve | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-IV-002 | 7536.828 |  |  | PWG | Valve | IV | PWG-IV-002 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PWG | [55 empty] | Supplied |  | 1 | each | [9 empty] | 3 |  |  |  | PIPE | 0 | NO
PWG-TT-0040 | 7539.66 | 7547.413 | 7.753 | PWG | Trench Type | TRENCH SECTION |  | 4 | 7.753 | D-DWG-PWG-011.2 | D-DWG-PWG-011.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 148
PWG-PIPE-0055 | 7539.66 | 7547.413 | 7.753 | PWG | Pipe | PIPE | PWG-PIPE-0055 |  |  | D-DWG-PWG-011.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-023 | 7542.564 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-023 | [7 empty] | PWG |  | Type 6 | [11 empty] | MSCL | 450 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 111 |  |  | Bend | [9 empty] | 22689 | 1 | each | 22689 | Bend | 31.9 | MSCL | 450 | 2693 | 240 | Bend; MS - 31.9° | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-030 | 7542.564 |  |  | PWG | Bend | HOR | PWG-BND-030 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 31.9° | MSCL | 450 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PWG-TB-024 | 7546.037 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-024 | [7 empty] | PWG |  | Type 6 | [11 empty] | MSCL | 450 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 112 |  |  | Bend | [9 empty] | 22689 | 1 | each | 22689 | Bend | 37.4 | MSCL | 450 | 2695 | 240 | Bend; MS - 37.4° | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-031 | 7546.037 |  |  | PWG | Bend | HOR | PWG-BND-031 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 37.5° | MSCL | 450 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PWG-RL-0001 | 7547.413 | 7579.15 | 31.737 | PWG | Road & Rail Crossing | MAJOR RAIL CROSSING | PWG-RL-0001 |  | 31.737 | [5 empty] | PWG | South Western System |  | Rail | 375 |  |  | OD457x5WT Sintalock Type 1 MSCL Carrier & OD610x12WT MS Enveloper |  |  |  |  | QLD Rail | [15 empty] | Thrust Boring | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 15 | [28 empty] | TRENCH | 0 | NO
PWG-TT-0041 | 7547.413 | 7579 | 31.587 | PWG | Trench Type | TRENCH SECTION |  | 8A | 31.587 | D-DWG-PWG-011.2 | D-DWG-PWG-011.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 149
PWG-BND-032 | 7547.413 |  |  | PWG | Bend | VERT | PWG-BND-032 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 7.8° | MSCL | 450 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PWG-PIPE-0056 | 7547.413 | 7579.15 | 31.737 | PWG | Pipe | PIPE | PWG-PIPE-0056 |  |  | D-DWG-PWG-011.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 + OD610 12WT MS Enveloper | [6 empty] | MSCL | 457 | [54 empty] | Supply and Installation of Pipe | Trenchless
PWG-FN-0013 | 7577 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0013 |  |  | D-DWG-PWG-011.2 |  |  |  | Yes | PWG |  | FENCE LINE NO POSTS - WIRES ON | [40 empty] | Forreign service raw data.xlsx | 215
PWG-TT-0042 | 7579 | 7624.121 | 45.121 | PWG | Trench Type | TRENCH SECTION |  | 4 | 45.121 | D-DWG-PWG-011.2 | D-DWG-PWG-011.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 150
PWG-PIPE-0057 | 7579.15 | 7624.121 | 44.971 | PWG | Pipe | PIPE | PWG-PIPE-0057 |  |  | D-DWG-PWG-011.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-TB-025 | 7583.581 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-025 | [7 empty] | PWG |  | Type 6 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 113 |  |  | Bend | [9 empty] | 13458 | 1 | each | 13458 | Bend | 45 | DICL | 375 | 2684 | 240 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-033 | 7583.581 |  |  | PWG | Bend | HOR | PWG-BND-033 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 45° | DICL | 375 | [7 empty] | 45 | PIPE | 0 | NO
PWG-TB-026 | 7587.138 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-026 | [7 empty] | PWG |  | Type 6 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 127 |  |  | Bend | [9 empty] | 13458 | 1 | each | 13458 | Bend | 45 | DICL | 375 | 2682 | 240 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-034 | 7587.138 |  |  | PWG | Bend | HOR | PWG-BND-034 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 45° | DICL | 375 | [7 empty] | 45 | PIPE | 0 | NO
PWG-TB-133 | 7595.718 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-133 | [7 empty] | PWG |  | 2 x Type 13 | [12 empty] | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 234 |  |  | Pigging Station | [10 empty] | 2 | each |  | Pigging Station |  |  | 375 | 2680 | 240 | Pigging station | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-PIG-002 | 7595.718 |  |  | PWG | Valve | PIG | PWG-PIG-002 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [13 empty] | PIPE | 0 | NO
PWG-EL-0011 | 7609 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0011 |  |  | D-DWG-PWG-011.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 217
PWG-WA-0005 | 7609 |  |  | PWG | Foreign Service | WATER | PWG-WA-0005 |  |  | D-DWG-PWG-011.2 |  |  | BYDA | Yes | PWG |  | BYDA WATER | [40 empty] | Forreign service raw data.xlsx | 216
PWG-AV-010 | 7615.732 |  |  | PWG | Valve | AV | PWG-AV-010 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PWG-TB-027 | 7618.704 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-027 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 128 |  |  | Bend | [9 empty] | 12690 | 1 | each | 12690 | Bend | 22.5 | DICL | 375 | 2677 | 240 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-035 | 7618.704 |  |  | PWG | Bend | HOR | PWG-BND-035 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 375 | [7 empty] | 22.5 | PIPE | 0 | NO
PWG-TB-028 | 7619.979 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-028 | [7 empty] | PWG |  | Type 11 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 129 |  |  | Bend | [9 empty] | 28674 | 1 | each | 28674 | Bend | 11.25 | DICL | 375 | 2676 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-036 | 7619.979 |  |  | PWG | Bend | VERT | PWG-BND-036 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-TT-0043 | 7624.121 | 7725.73 | 101.609 | PWG | Trench Type | TRENCH SECTION |  | 1A | 101.609 | D-DWG-PWG-011.2 | D-DWG-PWG-012.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 151
PWG-PIPE-0058 | 7624.121 | 7642.224 | 18.103 | PWG | Pipe | PIPE | PWG-PIPE-0058 |  |  | D-DWG-PWG-011.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Open Trench Oil Pipe Crossing | Special Crossings
PWG-BND-037 | 7628.193 |  |  | PWG | Bend | VERT | PWG-BND-037 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 8.5° | MSCL | 450 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PWG-OI-0001 | 7633 |  |  | PWG | Foreign Service | OIL | PWG-OI-0001 |  |  | D-DWG-PWG-011.2 |  |  | BYDA | Yes | PWG |  | BYDA OIL | [40 empty] | Forreign service raw data.xlsx | 218
PWG-BND-038 | 7638.763 |  |  | PWG | Bend | VERT | PWG-BND-038 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 10.9° | MSCL | 450 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PWG-PIPE-0059 | 7642.224 | 7724 | 81.776 | PWG | Pipe | PIPE | PWG-PIPE-0059 |  |  | D-DWG-PWG-011.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-029 | 7646.073 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-029 | [7 empty] | PWG |  | Type 11 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 130 |  |  | Bend | [9 empty] | 28674 | 1 | each | 28674 | Bend | 11.25 | DICL | 375 | 2675 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-039 | 7646.073 |  |  | PWG | Bend | VERT | PWG-BND-039 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-AV-011 | 7648.073 |  |  | PWG | Valve | AV | PWG-AV-011 |  |  | D-DWG-PHW-011.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PWG-PIPE-0060 | 7724 | 7751 | 27 | PWG | Pipe | PIPE | PWG-PIPE-0060 |  |  | D-DWG-PWG-011.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-RD-0009 | 7725 | 7743 | 18 | PWG | Road & Rail Crossing | MINOR ROAD CROSSING | PWG-RD-0009 |  | 18 | [5 empty] | PWG | Hartvigsen Street |  | Unsealed | 375 |  |  | DN375 PN35 DICL RRJ |  | 18 |  |  | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 16 | [28 empty] | TRENCH | 0 | NO
PWG-TT-0044 | 7725.73 | 7742.01 | 16.28 | PWG | Trench Type | TRENCH SECTION |  | 7 | 16.28 | D-DWG-PWG-012.2 | D-DWG-PWG-012.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 152
PWG-TT-0045 | 7742.01 | 7939.101 | 197.091 | PWG | Trench Type | TRENCH SECTION |  | 1A | 197.091 | D-DWG-PWG-012.2 | D-DWG-PWG-012.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 153
PWG-PIPE-0061 | 7751 | 7939.101 | 188.101 | PWG | Pipe | PIPE | PWG-PIPE-0061 |  |  | D-DWG-PWG-012.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Driveway crossings | Pipelay Crew
PWG-WA-0006 | 7820 |  |  | PWG | Foreign Service | WATER | PWG-WA-0006 |  |  | D-DWG-PWG-012.2 |  |  |  | Yes | PWG |  | UNKNOW WATER | [40 empty] | Forreign service raw data.xlsx | 219
PWG-EL-0012 | 7826 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0012 |  |  | D-DWG-PWG-012.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 220
PWG-EL-0013 | 7826 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0013 |  |  | D-DWG-PWG-012.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 221
PWG-WA-0007 | 7854 |  |  | PWG | Foreign Service | WATER | PWG-WA-0007 |  |  | D-DWG-PWG-012.2 |  |  | BYDA | Yes | PWG |  | BYDA WATER DN375 | [12 empty] | 375 | [27 empty] | Forreign service raw data.xlsx | 222
PWG-TB-030 | 7862.684 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-030 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 131 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 2666 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-TB-031 | 7910.66 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-031 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 132 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 2664 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-040 | 7910.66 |  |  | PWG | Bend | HOR | PWG-BND-040 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-WA-0008 | 7915 |  |  | PWG | Foreign Service | WATER | PWG-WA-0008 |  |  | D-DWG-PWG-012.2 |  |  | BYDA | Yes | PWG |  | BYDA WATER DN375 | [12 empty] | 375 | [27 empty] | Forreign service raw data.xlsx | 223
PWG-TT-0046 | 7939.101 | 7941.464 | 2.363 | PWG | Trench Type | TRENCH SECTION |  | 4 | 2.363 | D-DWG-PWG-012.2 | D-DWG-PWG-012.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 154
PWG-PIPE-0062 | 7939.101 | 7941.464 | 2.363 | PWG | Pipe | PIPE | PWG-PIPE-0062 |  |  | D-DWG-PWG-012.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TT-0047 | 7941.464 | 8288.124 | 346.66 | PWG | Trench Type | TRENCH SECTION |  | 1A | 346.66 | D-DWG-PWG-012.2 | D-DWG-PWG-012.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 155
PWG-PIPE-0063 | 7941.464 | 8045.962 | 104.498 | PWG | Pipe | PIPE | PWG-PIPE-0063 |  |  | D-DWG-PWG-012.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-DR-0005 | 7953 |  |  | PWG | Foreign Service | DRAINAGE | PWG-DR-0005 |  |  | D-DWG-PWG-012.2 |  |  | PUP | Yes | PWG |  | PUP DRAINAGE DN200x500 | [12 empty] | 200 x 500 | [27 empty] | Forreign service raw data.xlsx | 225
PWG-WA-0009 | 7953 |  |  | PWG | Foreign Service | WATER | PWG-WA-0009 |  |  | D-DWG-PWG-012.2 |  |  | BYDA | Yes | PWG |  | BYDA WATER DN150 | [12 empty] | 150 | [27 empty] | Forreign service raw data.xlsx | 224
PWG-TB-032 | 7957.939 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-032 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 133 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 2663 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-041 | 7957.939 |  |  | PWG | Bend | HOR | PWG-BND-041 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-EL-0014 | 7958 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0014 |  |  | D-DWG-PWG-012.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 226
PWG-TB-033 | 7973.15 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-033 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 134 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 2663 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-042 | 7973.15 |  |  | PWG | Bend | HOR | PWG-BND-042 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-EL-0015 | 8041 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0015 |  |  | D-DWG-PWG-012.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 227
PWG-EL-0016 | 8042 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0016 |  |  | D-DWG-PWG-012.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 228
PWG-PIPE-0064 | 8045.962 | 8080.278 | 34.316 | PWG | Pipe | PIPE | PWG-PIPE-0064 |  |  | D-DWG-PWG-012.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Open Trenched Creek Crossings | Pipelay Crew
PWG-WA-0010 | 8067 |  |  | PWG | Foreign Service | WATER | PWG-WA-0010 |  |  | D-DWG-PWG-012.2 |  |  | BYDA | Yes | PWG |  | BYDA WATER DN150 | [12 empty] | 150 | [27 empty] | Forreign service raw data.xlsx | 229
PWG-PIPE-0065 | 8080.278 | 8293.259 | 212.981 | PWG | Pipe | PIPE | PWG-PIPE-0065 |  |  | D-DWG-PWG-012.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-034 | 8109.465 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-034 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 135 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 2652 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-043 | 8109.465 |  |  | PWG | Bend | HOR | PWG-BND-043 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-WA-0011 | 8117 |  |  | PWG | Foreign Service | WATER | PWG-WA-0011 |  |  | D-DWG-PWG-012.2 |  |  | BYDA | Yes | PWG |  | BYDA WATER | [40 empty] | Forreign service raw data.xlsx | 230
PWG-AV-012 | 8159.045 |  |  | PWG | Valve | AV | PWG-AV-012 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PWG-TB-035 | 8202.694 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-035 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 136 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 2653 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-044 | 8202.816 |  |  | PWG | Bend | HOR | PWG-BND-044 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-WA-0012 | 8220 |  |  | PWG | Foreign Service | WATER | PWG-WA-0012 |  |  | D-DWG-PWG-012.2 |  | D-DWG-PWG-012_C | BYDA | Yes | PWG |  | BYDA WATER | [40 empty] | Forreign service raw data.xlsx | 231
PWG-EL-0017 | 8234 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0017 |  |  | D-DWG-PWG-012.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 232
PWG-TB-036 | 8245.381 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-036 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 137 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 2658 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-045 | 8245.381 |  |  | PWG | Bend | HOR | PWG-BND-045 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-WA-0013 | 8257 |  |  | PWG | Foreign Service | WATER | PWG-WA-0013 |  |  | D-DWG-PWG-012.2 |  |  | BYDA | Yes | PWG |  | BYDA WATER | [40 empty] | Forreign service raw data.xlsx | 233
PWG-EL-0018 | 8266 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0018 |  |  | D-DWG-PWG-012.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 234
PWG-WA-0014 | 8278 |  |  | PWG | Foreign Service | WATER | PWG-WA-0014 |  |  | D-DWG-PWG-012.2 |  |  | BYDA | Yes | PWG |  | BYDA WATER DN150 | [12 empty] | 150 | [27 empty] | Forreign service raw data.xlsx | 235
PWG-TT-0048 | 8288.124 | 8315.201 | 27.077 | PWG | Trench Type | TRENCH SECTION |  | 8A | 27.077 | D-DWG-PWG-012.2 | D-DWG-PWG-012.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 156
PWG-TB-037 | 8288.124 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-037 | [7 empty] | PWG |  | Type 6 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 138 |  |  | Bend | [9 empty] | 13458 | 1 | each | 13458 | Bend | 45 | DICL | 375 | 2663 | 200 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-046 | 8288.124 |  |  | PWG | Bend | HOR | PWG-BND-046 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 45° | DICL | 375 | [7 empty] | 45 | PIPE | 0 | NO
PWG-CM-0018 | 8289 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0018 |  |  | D-DWG-PWG-012.2 |  |  | PUP | Yes | PWG |  | PUP COMMS DN300 | [12 empty] | 300 | [27 empty] | Forreign service raw data.xlsx | 236
PWG-PIPE-0066 | 8293.259 | 8315.201 | 21.942 | PWG | Pipe | PIPE | PWG-PIPE-0066 |  |  | D-DWG-PWG-012.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 + OD610 9WT MS Enveloper | [6 empty] | MSCL | 457 | [54 empty] | Major Road - Trenchless | Trenchless
PWG-RD-0010 | 8293.647 | 8315.201 | 21.554 | PWG | Road & Rail Crossing | MAJOR ROAD CROSSING | PWG-RD-0010 |  | 21.554 | [5 empty] | PWG | Umbiram Road |  | Sealed | 375 |  |  | OD457x5WT Sintalock Type 1 MSCL Carrier & OD610x9WT MS Enveloper |  |  |  |  | TRC | [15 empty] | Thrust Boring | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 17 | [28 empty] | TRENCH | 0 | NO
PWG-EL-0019 | 8306 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0019 |  |  | D-DWG-PWG-012.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 237
PWG-WA-0015 | 8306 |  |  | PWG | Foreign Service | WATER | PWG-WA-0015 |  |  | D-DWG-PWG-012.2 |  |  | BYDA | Yes | PWG |  | BYDA WATER | [40 empty] | Forreign service raw data.xlsx | 238
PWG-EL-0020 | 8310 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0020 |  |  | D-DWG-PWG-012.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 239
PWG-TT-0049 | 8315.201 | 8323.259 | 8.058 | PWG | Trench Type | TRENCH SECTION |  | 1A | 8.058 | D-DWG-PWG-012.2 | D-DWG-PWG-012.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 157
PWG-PIPE-0067 | 8315.201 | 8323.259 | 8.058 | PWG | Pipe | PIPE | PWG-PIPE-0067 |  |  | D-DWG-PWG-012.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TT-0050 | 8323.259 | 8335.614 | 12.355 | PWG | Trench Type | TRENCH SECTION |  | 4 | 12.355 | D-DWG-PWG-012.2 | D-DWG-PWG-012.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 158
PWG-PIPE-0068 | 8323.259 | 8335.614 | 12.355 | PWG | Pipe | PIPE | PWG-PIPE-0068 |  |  | D-DWG-PWG-012.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-BND-047 | 8328.858 |  |  | PWG | Bend | HOR | PWG-BND-047 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 27° | MSCL | 450 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PWG-PT-0001 | 8335.614 | 8400.622 | 65.008 | PWG | Road & Rail Crossing | SIGNIFICANT PROTECTED TREES | PWG-PT-0001 |  | 65.008 | [5 empty] | PWG | Wyreema Memorial Park |  | N/A | 375 |  |  | OD457x5WT Sintalock Type 1 MSCL Carrier & OD610x9WT MS Enveloper |  |  |  |  | TRC | [15 empty] | Thrust Boring | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 18 | [28 empty] | TRENCH | 0 | NO
PWG-TT-0051 | 8335.614 | 8400.622 | 65.008 | PWG | Trench Type | TRENCH SECTION |  | 8A | 65.008 | D-DWG-PWG-012.2 | D-DWG-PWG-013.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 159
PWG-PIPE-0069 | 8335.614 | 8400.622 | 65.008 | PWG | Pipe | PIPE | PWG-PIPE-0069 |  |  | D-DWG-PWG-012.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 + OD610 9WT MS Enveloper | [6 empty] | MSCL | 457 | [54 empty] | Major Crossing - Trenchless | Trenchless
PWG-CM-0019 | 8358 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0019 |  |  | D-DWG-PWG-012.2 |  |  | BYDA | Yes | PWG |  | BYDA COMMS DN100 | [12 empty] | 100 | [27 empty] | Forreign service raw data.xlsx | 240
PWG-CM-0020 | 8370 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0020 |  |  | D-DWG-PWG-012.2 |  |  | BYDA | Yes | PWG |  | BYDA TELSTRA COMMS DN100 | [9 empty] | Telstra |  |  | 100 | [27 empty] | Forreign service raw data.xlsx | 241
PWG-CM-0021 | 8372 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0021 |  |  | D-DWG-PWG-012.2 |  |  | BYDA | Yes | PWG |  | BYDA TELSTRA COMMS DN30 | [9 empty] | Telstra |  |  | 30 | [27 empty] | Forreign service raw data.xlsx | 242
PWG-TT-0052 | 8400.622 | 8427.328 | 26.706 | PWG | Trench Type | TRENCH SECTION |  | 1A | 26.706 | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 160
PWG-PIPE-0070 | 8400.622 | 8427.328 | 26.706 | PWG | Pipe | PIPE | PWG-PIPE-0070 |  |  | D-DWG-PWG-013.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-TT-0053 | 8427.328 | 8465.757 | 38.429 | PWG | Trench Type | TRENCH SECTION |  | 4 | 38.429 | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 161
PWG-PIPE-0071 | 8427.328 | 8465.757 | 38.429 | PWG | Pipe | PIPE | PWG-PIPE-0071 |  |  | D-DWG-PWG-013.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-BND-048 | 8439.328 |  |  | PWG | Bend | HOR | PWG-BND-048 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 37° | MSCL | 450 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PWG-WA-0016 | 8442 |  |  | PWG | Foreign Service | WATER | PWG-WA-0016 |  |  | D-DWG-PWG-013.2 |  |  | BYDA | Yes | PWG |  | BYDA WATER "SIZE TBC" | [12 empty] | TBC | [27 empty] | Forreign service raw data.xlsx | 243
PWG-BND-049 | 8450.4 |  |  | PWG | Bend | COMPOUND | PWG-BND-049 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 37.6° | MSCL | 450 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PWG-TT-0054 | 8465.757 | 8488.53 | 22.773 | PWG | Trench Type | TRENCH SECTION |  | 1A | 22.773 | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 162
PWG-TB-038 | 8465.757 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-038 | [7 empty] | PWG |  | Type 9 | [11 empty] | MSCL | 450 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 139 |  |  | Bend | [9 empty] | 12887 | 1 | each | 12887 | Bend | 8.9 | MSCL | 450 | 2728 | 150 | Bend; MS - 8.9° | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-050 | 8465.757 |  |  | PWG | Bend | VERT | PWG-BND-050 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 8.6° | MSCL | 450 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PWG-PIPE-0072 | 8465.757 | 8487.151 | 21.394 | PWG | Pipe | PIPE | PWG-PIPE-0072 |  |  | D-DWG-PWG-013.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-TB-128 | 8475.323 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-128 | [7 empty] | PWG |  | Type 13 | [12 empty] | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 229 |  |  | Isolation Valve | [10 empty] | 1 | each |  | Isolation Valve |  |  | 375 | 2728 | 100 | Isolation valve | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-IV-003 | 8475.323 |  |  | PWG | Valve | IV | PWG-IV-003 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PWG | [55 empty] | Supplied |  | 1 | each | [9 empty] | 2 |  |  |  | PIPE | 0 | NO
PWG-TB-039 | 8481.865 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-039 | [7 empty] | PWG |  | Type 4 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 140 |  |  | Bend | [9 empty] | 14280 | 1 | each | 14280 | Bend | 45 | DICL | 375 | 2731 | 100 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-051 | 8481.865 |  |  | PWG | Bend | HOR | PWG-BND-051 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 45° | DICL | 375 | [7 empty] | 45 | PIPE | 0 | NO
PWG-TB-040 | 8485.834 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-040 | [7 empty] | PWG |  | Type 6 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 141 |  |  | Bend | [9 empty] | 13458 | 1 | each | 13458 | Bend | 45 | DICL | 375 | 2733 | 200 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-052 | 8485.834 |  |  | PWG | Bend | HOR | PWG-BND-052 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 45° | DICL | 375 | [7 empty] | 45 | PIPE | 0 | NO
PWG-WA-0017 | 8487 |  |  | PWG | Foreign Service | WATER | PWG-WA-0017 |  |  | D-DWG-PWG-013.2 |  |  | BYDA | Yes | PWG |  | BYDA WATER | [40 empty] | Forreign service raw data.xlsx | 244
PWG-RL-0002 | 8487.151 | 8542.069 | 54.918 | PWG | Road & Rail Crossing | MAJOR RAIL CROSSING | PWG-RL-0002 |  | 54.918 | [5 empty] | PWG | South Western System |  | Rail | 375 |  |  | OD457x5WT Sintalock Type 1 MSCL Carrier & OD610x12WT MS Enveloper |  |  |  |  | QLD Rail | [15 empty] | Thrust Boring | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 19 | [28 empty] | TRENCH | 0 | NO
PWG-PIPE-0073 | 8487.151 | 8542.069 | 54.918 | PWG | Pipe | PIPE | PWG-PIPE-0073 |  |  | D-DWG-PWG-013.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 + OD610 12WT MS Enveloper | [6 empty] | MSCL | 457 | [54 empty] | Major Crossing - Trenchless | Trenchless
PWG-TT-0055 | 8488.53 | 8542.069 | 53.539 | PWG | Trench Type | TRENCH SECTION |  | 8A | 53.539 | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 163
PWG-CM-0022 | 8489 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0022 |  |  | D-DWG-PWG-013.2 |  |  | BYDA | Yes | PWG |  | BYDA TELSTRA COMMS DN100 | [9 empty] | Telstra |  |  | 100 | [27 empty] | Forreign service raw data.xlsx | 245
PWG-FN-0014 | 8491 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0014 |  |  | D-DWG-PWG-013.2 |  |  |  | Yes | PWG |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 246
PWG-CM-0023 | 8532 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0023 |  |  | D-DWG-PWG-013.2 |  |  | PUP | Yes | PWG |  | PUP COMMS DN200 PVC | [12 empty] | 200 | [27 empty] | Forreign service raw data.xlsx | 247
PWG-TT-0056 | 8542.069 | 8545.354 | 3.285 | PWG | Trench Type | TRENCH SECTION |  | 4 | 3.285 | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 164
PWG-PIPE-0074 | 8542.069 | 8545.354 | 3.285 | PWG | Pipe | PIPE | PWG-PIPE-0074 |  |  | D-DWG-PWG-013.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-TT-0057 | 8545.354 | 8584.129 | 38.775 | PWG | Trench Type | TRENCH SECTION |  | 1A | 38.775 | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 165
PWG-TB-041 | 8545.354 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-041 | [7 empty] | PWG |  | Type 6 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 142 |  |  | Bend | [9 empty] | 13458 | 1 | each | 13458 | Bend | 45 | DICL | 375 | 2718 | 200 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-053 | 8545.354 |  |  | PWG | Bend | HOR | PWG-BND-053 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 45° | DICL | 375 | [7 empty] | 45 | PIPE | 0 | NO
PWG-PIPE-0075 | 8545.354 | 8580 | 34.646 | PWG | Pipe | PIPE | PWG-PIPE-0075 |  |  | D-DWG-PWG-013.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-TB-042 | 8547.89 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-042 | [7 empty] | PWG |  | Type 6 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 143 |  |  | Bend | [9 empty] | 13458 | 1 | each | 13458 | Bend | 45 | DICL | 375 | 2717 | 200 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-054 | 8547.89 |  |  | PWG | Bend | HOR | PWG-BND-054 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 45° | DICL | 375 | [7 empty] | 45 | PIPE | 0 | NO
PWG-TB-129 | 8562.951 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-129 | [7 empty] | PWG |  | Type 13 | [12 empty] | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 230 |  |  | Isolation Valve | [10 empty] | 1 | each |  | Isolation Valve |  |  | 375 | 2716 | 200 | Isolation valve | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-IV-004 | 8562.951 |  |  | PWG | Valve | IV | PWG-IV-004 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PWG | [55 empty] | Supplied |  | 1 | each | [9 empty] | 3 |  |  |  | PIPE | 0 | NO
PWG-CM-0024 | 8577 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0024 |  |  | D-DWG-PWG-013.2 |  |  | BYDA | Yes | PWG |  | BYDA NBN COMMS DN30 | [9 empty] | NBN Co |  |  | 30 | [27 empty] | Forreign service raw data.xlsx | 248
PWG-CP-0002 | 8578 | 8622 | 44 | PWG | Road & Rail Crossing | CARPARK/SIDE LANE | PWG-CP-0002 |  | 44 | [5 empty] | PWG | Wyreema Cambooya Road Side Bay |  | Unsealed | 375 |  |  | DN375 PN35 DICL RRJ |  | 39.01 | 4.99 |  | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 20 | [28 empty] | TRENCH | 0 | NO
PWG-PIPE-0076 | 8580 | 8605.285 | 25.285 | PWG | Pipe | PIPE | PWG-PIPE-0076 |  |  | D-DWG-PWG-013.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-TT-0058 | 8584.129 | 8605.285 | 21.156 | PWG | Trench Type | TRENCH SECTION |  | 7 | 21.156 | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 166
PWG-CM-0025 | 8596 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0025 |  |  | D-DWG-PWG-013.2 |  |  | BYDA | Yes | PWG |  | BYDA NBN COMMS | [9 empty] | NBN Co | [30 empty] | Forreign service raw data.xlsx | 249
PWG-CM-0026 | 8597 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0026 |  |  | D-DWG-PWG-013.2 |  |  | PUP | Yes | PWG |  | PUP COMMS PVC | [40 empty] | Forreign service raw data.xlsx | 250
PWG-WA-0018 | 8603 |  |  | PWG | Foreign Service | WATER | PWG-WA-0018 |  |  | D-DWG-PWG-013.2 |  |  | BYDA | Yes | PWG |  | BYDA WATER DN150 | [12 empty] | 150 | [27 empty] | Forreign service raw data.xlsx | 251
PWG-TT-0059 | 8605.285 | 8610.275 | 4.99 | PWG | Trench Type | TRENCH SECTION |  | 4&7 | 4.99 | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 167
PWG-PIPE-0077 | 8605.285 | 8610.275 | 4.99 | PWG | Pipe | PIPE | PWG-PIPE-0077 |  |  | D-DWG-PWG-013.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-SW-0010 | 8607 |  |  | PWG | Foreign Service | SEWER | PWG-SW-0010 |  |  | D-DWG-PWG-013.2 |  |  | PUP | Yes | PWG |  | PUP SEWER DN150 | [12 empty] | 150 | [27 empty] | Forreign service raw data.xlsx | 252
PWG-TT-0060 | 8610.275 | 8613.442 | 3.167 | PWG | Trench Type | TRENCH SECTION |  | 7 | 3.167 | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 168
PWG-PIPE-0078 | 8610.275 | 8619.56 | 9.285 | PWG | Pipe | PIPE | PWG-PIPE-0078 |  |  | D-DWG-PWG-013.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-TT-0061 | 8613.442 | 8692.124 | 78.682 | PWG | Trench Type | TRENCH SECTION |  | 1A | 78.682 | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 169
PWG-PIPE-0079 | 8619.56 | 8692.124 | 72.564 | PWG | Pipe | PIPE | PWG-PIPE-0079 |  |  | D-DWG-PWG-013.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-TS-0008 | 8669.8 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0008 |  |  | D-DWG-PWG-013 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 466 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TS-0009 | 8677 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0009 |  |  | D-DWG-PWG-013 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 467 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TT-0062 | 8692.124 | 8706.792 | 14.668 | PWG | Trench Type | TRENCH SECTION |  | 4 | 14.668 | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 170
PWG-PIPE-0080 | 8692.124 | 8706.792 | 14.668 | PWG | Pipe | PIPE | PWG-PIPE-0080 |  |  | D-DWG-PWG-013.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-SW-0011 | 8697 |  |  | PWG | Foreign Service | SEWER | PWG-SW-0011 |  |  | D-DWG-PWG-013.2 |  |  | PUP | Yes | PWG |  | PUP SEWER DN315 | [12 empty] | 315 | [27 empty] | Forreign service raw data.xlsx | 253
PWG-TT-0063 | 8706.792 | 8808.151 | 101.359 | PWG | Trench Type | TRENCH SECTION |  | 1A | 101.359 | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 171
PWG-PIPE-0081 | 8706.792 | 8808.151 | 101.359 | PWG | Pipe | PIPE | PWG-PIPE-0081 |  |  | D-DWG-PWG-013.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-CP-0003 | 8780 | 8840 | 60 | PWG | Road & Rail Crossing | CARPARK/SIDE LANE | PWG-CP-0003 |  | 60 | [5 empty] | PWG | Wyreema Cambooya Road Side Bay |  | Unsealed | 375 |  |  | DN375 PN35 DICL RRJ |  | 60 |  |  | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 21 | [28 empty] | TRENCH | 0 | NO
PWG-TT-0064 | 8808.151 | 8858.11 | 49.959 | PWG | Trench Type | TRENCH SECTION |  | 7 | 49.959 | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 172
PWG-PIPE-0082 | 8808.151 | 8858.11 | 49.959 | PWG | Pipe | PIPE | PWG-PIPE-0082 |  |  | D-DWG-PWG-013.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TT-0065 | 8858.11 | 9100 | 241.89 | PWG | Trench Type | TRENCH SECTION |  | 1A | 241.89 | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 173
PWG-PIPE-0083 | 8858.11 | 9100 | 241.89 | PWG | Pipe | PIPE | PWG-PIPE-0083 |  |  | D-DWG-PWG-013.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-106 | 8908.151 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-106 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 207 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 2779 | 200 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-SCV-009 | 8908.151 |  |  | PWG | Valve | SCV | PWG-SCV-009 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-AV-013 | 9036.11 |  |  | PWG | Valve | AV | PWG-AV-013 |  |  | D-DWG-PHW-012.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PWG-TT-0066 | 9100 | 9154.955 | 54.955 | PWG | Trench Type | TRENCH SECTION |  | 7 | 54.955 | D-DWG-PWG-014.2 | D-DWG-PWG-014.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 174
PWG-PIPE-0084 | 9100 | 9153.955 | 53.955 | PWG | Pipe | PIPE | PWG-PIPE-0084 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-CP-0004 | 9115 | 9157 | 42 | PWG | Road & Rail Crossing | CARPARK/SIDE LANE | PWG-CP-0004 |  | 42 | [5 empty] | PWG | Wyreema Cambooya Road Side Bay |  | Unsealed | 375 |  |  | DN375 PN35 DICL RRJ |  | 42 |  |  | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 22 | [28 empty] | TRENCH | 0 | NO
PWG-PIPE-0085 | 9153.955 | 9473.063 | 319.108 | PWG | Pipe | PIPE | PWG-PIPE-0085 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TT-0067 | 9154.955 | 12307.423 | 3152.468 | PWG | Trench Type | TRENCH SECTION |  | 1A | 3152.468 | D-DWG-PWG-014.2 | D-DWG-PWG-018.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 175
PWG-CM-0027 | 9243 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0027 |  |  | D-DWG-PWG-014.2 |  |  | BYDA | Yes | PWG |  | BYDA TELSTRA COMMS DN50 CONC COVER | [9 empty] | Telstra |  |  | 50 | [27 empty] | Forreign service raw data.xlsx | 254
PWG-TS-0010 | 9344.9 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0010 |  |  | D-DWG-PWG-014 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 468 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TS-0011 | 9358.4 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0011 |  |  | D-DWG-PWG-014 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 469 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TS-0012 | 9371.9 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0012 |  |  | D-DWG-PWG-014 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 470 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TB-043 | 9455.661 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-043 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 144 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 2844 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-055 | 9455.661 |  |  | PWG | Bend | HOR | PWG-BND-055 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-CC-0006 | 9456 | 9480 | 24 | PWG | Creek Crossing | TRENCHED CREEK CROSSING | PWG-CC-0006 | [7 empty] | PWG |  |  |  |  | FABRIC/VEGETATION | [37 empty] | PHw_PWG_Creek_Crossings.xlsx | 8 | [28 empty] | TRENCH | 0 | NO
PWG-TB-107 | 9473.063 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-107 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 208 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 2845 | 200 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-SCV-010 | 9473.063 |  |  | PWG | Valve | SCV | PWG-SCV-010 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-PIPE-0086 | 9473.063 | 9680 | 206.937 | PWG | Pipe | PIPE | PWG-PIPE-0086 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-EL-0021 | 9561 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0021 |  |  | D-DWG-PWG-014.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 255
PWG-EL-0022 | 9585 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0022 |  |  | D-DWG-PWG-014.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 256
PWG-EL-0023 | 9585 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0023 |  |  | D-DWG-PWG-014.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 257
PWG-AV-014 | 9672.334 |  |  | PWG | Valve | AV | PWG-AV-014 |  |  | D-DWG-PHW-014.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PWG-PIPE-0087 | 9680 | 9690 | 10 | PWG | Pipe | PIPE | PWG-PIPE-0087 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Driveway crossings | Pipelay Crew
PWG-PIPE-0088 | 9690 | 10226.176 | 536.176 | PWG | Pipe | PIPE | PWG-PIPE-0088 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-EL-0024 | 9788 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0024 |  |  | D-DWG-PWG-014.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 258
PWG-TS-0013 | 9810.2 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0013 |  |  | D-DWG-PWG-015 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 471 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TS-0014 | 9825.8 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0014 |  |  | D-DWG-PWG-015 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 472 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TS-0015 | 9841.4 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0015 |  |  | D-DWG-PWG-015 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 473 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-PIPE-0089 | 10226.176 | 10270.319 | 44.143 | PWG | Pipe | PIPE | PWG-PIPE-0089 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-CC-0007 | 10243 | 10260 | 17 | PWG | Creek Crossing | TRENCHED CREEK CROSSING | PWG-CC-0007 | [7 empty] | PWG |  |  |  |  | FABRIC/VEGETATION | [37 empty] | PHw_PWG_Creek_Crossings.xlsx | 9 | [28 empty] | TRENCH | 0 | NO
PWG-PIPE-0090 | 10270.319 | 10347.552 | 77.233 | PWG | Pipe | PIPE | PWG-PIPE-0090 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-AV-015 | 10290.319 |  |  | PWG | Valve | AV | PWG-AV-015 |  |  | D-DWG-PHW-015.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PWG-EL-0025 | 10298 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0025 |  |  | D-DWG-PWG-015.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 259
PWG-PIPE-0091 | 10347.552 | 10664.861 | 317.309 | PWG | Pipe | PIPE | PWG-PIPE-0091 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Miscellaneous Surface Treatment | Pipelay Crew
PWG-CM-0028 | 10433 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0028 |  |  | D-DWG-PWG-015.2 |  |  | BYDA | Yes | PWG |  | BYDA TELSTRA COMMS DN50 CONC COVER | [9 empty] | Telstra |  |  | 50 | [27 empty] | Forreign service raw data.xlsx | 260
PWG-CM-0029 | 10433 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0029 |  |  | D-DWG-PWG-015.2 |  |  | BYDA | Yes | PWG |  | BYDA NBN COMMS DN30 | [9 empty] | NBN Co |  |  | 30 | [27 empty] | Forreign service raw data.xlsx | 261
PWG-CM-0030 | 10433 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0030 |  |  | D-DWG-PWG-015.2 |  |  | BYDA | Yes | PWG |  | BYDA TELSTRACOMMS DN30 | [9 empty] | Telstra |  |  | 30 | [27 empty] | Forreign service raw data.xlsx | 262
PWG-TB-108 | 10553.492 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-108 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 209 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 3012 | 240 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-SCV-011 | 10553.492 |  |  | PWG | Valve | SCV | PWG-SCV-011 |  |  | D-DWG-PHW-016.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-PIPE-0092 | 10664.861 | 10856.72 | 191.859 | PWG | Pipe | PIPE | PWG-PIPE-0092 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-VG-0015 | 10680 | 10690 | 10 | PWG | Vegetation | TREE REMOVAL | VEG_PWG015 | [49 empty] | MULTIPLE SMALL TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 102 | 116 | HEAVY | [26 empty] | TRENCH | 0 | NO
PWG-TB-044 | 10741.055 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-044 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 145 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 2979 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-056 | 10741.055 |  |  | PWG | Bend | HOR | PWG-BND-056 |  |  | D-DWG-PHW-016.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-BND-057 | 10780.173 |  |  | PWG | Bend | HOR | PWG-BND-057 |  |  | D-DWG-PHW-016.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-TB-045 | 10780.713 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-045 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 146 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 2973 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-AV-016 | 10830.046 |  |  | PWG | Valve | AV | PWG-AV-016 |  |  | D-DWG-PHW-016.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PWG-PIPE-0093 | 10856.72 | 10863 | 6.28 | PWG | Pipe | PIPE | PWG-PIPE-0093 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Driveway crossings | Pipelay Crew
PWG-PIPE-0094 | 10863 | 11107.59 | 244.59 | PWG | Pipe | PIPE | PWG-PIPE-0094 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-EL-0026 | 10905 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0026 |  |  | D-DWG-PWG-016.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 263
PWG-PIPE-0095 | 11107.59 | 11129.673 | 22.083 | PWG | Pipe | PIPE | PWG-PIPE-0095 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TS-0016 | 11111.31 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0016 |  |  | D-DWG-PWG-016 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 474 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TS-0017 | 11118.61 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0017 |  |  | D-DWG-PWG-016 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 475 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TS-0018 | 11125.91 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0018 |  |  | D-DWG-PWG-016 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 476 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-PIPE-0096 | 11129.673 | 11518 | 388.327 | PWG | Pipe | PIPE | PWG-PIPE-0096 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-EL-0027 | 11179 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0027 |  |  | D-DWG-PWG-016.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 264
PWG-TS-0019 | 11305.8 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0019 |  |  | D-DWG-PWG-017 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 477 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TS-0020 | 11318.5 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0020 |  |  | D-DWG-PWG-017 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 478 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TS-0021 | 11331.2 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0021 |  |  | D-DWG-PWG-017 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 479 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TB-046 | 11468.159 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-046 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 147 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3179 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-058 | 11468.159 |  |  | PWG | Bend | HOR | PWG-BND-058 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-EL-0028 | 11482 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0028 |  |  | D-DWG-PWG-017.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 265
PWG-PIPE-0097 | 11518 | 11524 | 6 | PWG | Pipe | PIPE | PWG-PIPE-0097 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Driveway crossings | Pipelay Crew
PWG-PIPE-0098 | 11524 | 11731 | 207 | PWG | Pipe | PIPE | PWG-PIPE-0098 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-CC-0008 | 11558 | 11574 | 16 | PWG | Creek Crossing | TRENCHED CREEK CROSSING | PWG-CC-0008 | [7 empty] | PWG |  |  |  |  | FABRIC/VEGETATION | [37 empty] | PHw_PWG_Creek_Crossings.xlsx | 10 | [28 empty] | TRENCH | 0 | NO
PWG-PIPE-0099 | 11731 | 11737 | 6 | PWG | Pipe | PIPE | PWG-PIPE-0099 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Driveway crossings | Pipelay Crew
PWG-PIPE-0100 | 11737 | 11759.158 | 22.158 | PWG | Pipe | PIPE | PWG-PIPE-0100 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-047 | 11759.158 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-047 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 148 |  |  | Bend | [9 empty] | 12690 | 1 | each | 12690 | Bend | 22.5 | DICL | 375 | 3187 | 240 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-059 | 11759.158 |  |  | PWG | Bend | HOR | PWG-BND-059 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 375 | [7 empty] | 22.5 | PIPE | 0 | NO
PWG-PIPE-0101 | 11759.158 | 11773.094 | 13.936 | PWG | Pipe | PIPE | PWG-PIPE-0101 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Driveway crossings | Pipelay Crew
PWG-TB-048 | 11768.094 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-048 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 149 |  |  | Bend | [9 empty] | 12690 | 1 | each | 12690 | Bend | 22.5 | DICL | 375 | 3188 | 240 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-060 | 11768.094 |  |  | PWG | Bend | HOR | PWG-BND-060 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 375 | [7 empty] | 22.5 | PIPE | 0 | NO
PWG-CM-0031 | 11771 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0031 |  |  | D-DWG-PWG-017.2 |  |  | BYDA | Yes | PWG |  | BYDA TELSTRA COMMS DN50 CONC COVER | [9 empty] | Telstra |  |  | 50 | [27 empty] | Forreign service raw data.xlsx | 266
PWG-EL-0029 | 11771 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0029 |  |  | D-DWG-PWG-017.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 267
PWG-TB-049 | 11773.094 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-049 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 150 |  |  | Bend | [9 empty] | 12690 | 1 | each | 12690 | Bend | 22.5 | DICL | 375 | 3188 | 240 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-061 | 11773.094 |  |  | PWG | Bend | HOR | PWG-BND-061 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 375 | [7 empty] | 22.5 | PIPE | 0 | NO
PWG-PIPE-0102 | 11773.094 | 11782.037 | 8.943 | PWG | Pipe | PIPE | PWG-PIPE-0102 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-050 | 11782.037 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-050 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 151 |  |  | Bend | [9 empty] | 12690 | 1 | each | 12690 | Bend | 22.5 | DICL | 375 | 3188 | 240 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-PIPE-0103 | 11782.037 | 11788 | 5.963 | PWG | Pipe | PIPE | PWG-PIPE-0103 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Driveway crossings | Pipelay Crew
PWG-PIPE-0104 | 11788 | 11856.18 | 68.18 | PWG | Pipe | PIPE | PWG-PIPE-0104 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-PIPE-0105 | 11856.18 | 11862 | 5.82 | PWG | Pipe | PIPE | PWG-PIPE-0105 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Driveway crossings | Pipelay Crew
PWG-PIPE-0106 | 11862 | 12307.423 | 445.423 | PWG | Pipe | PIPE | PWG-PIPE-0106 |  |  | D-DWG-PWG-014.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-EL-0030 | 11969 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0030 |  |  | D-DWG-PWG-018.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 268
PWG-EL-0031 | 12094 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0031 |  |  | D-DWG-PWG-018.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 269
PWG-TB-051 | 12099.939 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-051 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 152 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3233 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-062 | 12099.939 |  |  | PWG | Bend | HOR | PWG-BND-062 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-AV-017 | 12193.219 |  |  | PWG | Valve | AV | PWG-AV-017 |  |  | D-DWG-PHW-017.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PWG-FN-0015 | 12214 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0015 |  |  | D-DWG-PWG-018.2 |  |  |  | Yes | PWG |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 270
PWG-FN-0016 | 12273 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0016 |  |  | D-DWG-PWG-018.2 |  |  |  | Yes | PWG |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 271
PWG-CM-0032 | 12307 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0032 |  |  | D-DWG-PWG-018.2 |  |  | BYDA | Yes | PWG |  | BYDA NBN COMMS DN30 | [9 empty] | NBN Co |  |  | 30 | [27 empty] | Forreign service raw data.xlsx | 272
PWG-CM-0033 | 12307 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0033 |  |  | D-DWG-PWG-018.2 |  |  | BYDA | Yes | PWG |  | BYDA NBN COMMS DN30 | [9 empty] | NBN Co |  |  | 30 | [27 empty] | Forreign service raw data.xlsx | 273
PWG-TT-0068 | 12307.423 | 12320.895 | 13.472 | PWG | Trench Type | TRENCH SECTION |  | 6 | 13.472 | D-DWG-PWG-018.2 | D-DWG-PWG-018.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 176
PWG-PIPE-0107 | 12307.423 | 12320.895 | 13.472 | PWG | Pipe | PIPE | PWG-PIPE-0107 |  |  | D-DWG-PWG-018.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-RD-0011 | 12310 | 12320 | 10 | PWG | Road & Rail Crossing | MINOR ROAD CROSSING | PWG-RD-0011 |  | 10 | [5 empty] | PWG | Bourne Road |  | Sealed | 375 |  |  | DN375 PN35 DICL RRJ | 10 |  |  |  | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 23 | [28 empty] | TRENCH | 0 | NO
PWG-CM-0034 | 12320 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0034 |  |  | D-DWG-PWG-018.2 |  |  | BYDA | Yes | PWG |  | BYDA TELSTRA COMMS DN35 | [9 empty] | Telstra |  |  | 35 | [27 empty] | Forreign service raw data.xlsx | 274
PWG-TT-0069 | 12320.895 | 12720.22 | 399.325 | PWG | Trench Type | TRENCH SECTION |  | 1A | 399.325 | D-DWG-PWG-018.2 | D-DWG-PWG-019.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 177
PWG-PIPE-0108 | 12320.895 | 12570.926 | 250.031 | PWG | Pipe | PIPE | PWG-PIPE-0108 |  |  | D-DWG-PWG-018.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-CM-0035 | 12322 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0035 |  |  | D-DWG-PWG-018.2 |  |  | BYDA | Yes | PWG |  | BYDA NBN COMMS DN30 | [9 empty] | NBN Co |  |  | 30 | [27 empty] | Forreign service raw data.xlsx | 275
PWG-CM-0036 | 12322 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0036 |  |  | D-DWG-PWG-018.2 |  |  | BYDA | Yes | PWG |  | BYDA NBN COMMS DN30 | [9 empty] | NBN Co |  |  | 30 | [27 empty] | Forreign service raw data.xlsx | 276
PWG-CM-0037 | 12322 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0037 |  |  | D-DWG-PWG-018.2 |  |  | BYDA | Yes | PWG |  | BYDA NBN COMMS DN30 | [9 empty] | NBN Co |  |  | 30 | [27 empty] | Forreign service raw data.xlsx | 277
PWG-PIPE-0109 | 12570.926 | 12582.142 | 11.216 | PWG | Pipe | PIPE | PWG-PIPE-0109 |  |  | D-DWG-PWG-018.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-PIPE-0110 | 12582.142 | 12702.22 | 120.078 | PWG | Pipe | PIPE | PWG-PIPE-0110 |  |  | D-DWG-PWG-018.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-109 | 12687.754 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-109 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 210 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 3310 | 240 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-SCV-012 | 12687.754 |  |  | PWG | Valve | SCV | PWG-SCV-012 |  |  | D-DWG-PHW-018.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-TB-052 | 12694.713 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-052 | [7 empty] | PWG |  | Type 5 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 153 |  |  | Bend | [9 empty] | 13282 | 1 | each | 13282 | Bend | 45 | DICL | 375 | 3310 | 240 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-063 | 12694.713 |  |  | PWG | Bend | HOR | PWG-BND-063 |  |  | D-DWG-PHW-018.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 45° | DICL | 375 | [7 empty] | 45 | PIPE | 0 | NO
PWG-RD-0012 | 12702.22 | 12734.864 | 32.644 | PWG | Road & Rail Crossing | MINOR ROAD CROSSING | PWG-RD-0012 |  | 32.644 | [5 empty] | PWG | Wyreema Cambooya Road |  | Sealed | 375 |  |  | OD457x5WT Sintalock Type 1 MSCL Carrier & OD610x9WT MS Enveloper |  |  |  |  | TRC | [15 empty] | Thrust Boring | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 24 | [28 empty] | TRENCH | 0 | NO
PWG-PIPE-0111 | 12702.22 | 12734.864 | 32.644 | PWG | Pipe | PIPE | PWG-PIPE-0111 |  |  | D-DWG-PWG-018.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 + OD610 9WT MS Enveloper | [6 empty] | MSCL | 457 | [54 empty] | Major Crossing - Trenchless | Trenchless
PWG-TT-0070 | 12720.22 | 12734.864 | 14.644 | PWG | Trench Type | TRENCH SECTION |  | 8A | 14.644 | D-DWG-PWG-019.2 | D-DWG-PWG-019.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 178
PWG-TT-0071 | 12734.864 | 13218.214 | 483.35 | PWG | Trench Type | TRENCH SECTION |  | 1A | 483.35 | D-DWG-PWG-019.2 | D-DWG-PWG-019.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 179
PWG-PIPE-0112 | 12734.864 | 13218.214 | 483.35 | PWG | Pipe | PIPE | PWG-PIPE-0112 |  |  | D-DWG-PWG-019.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-AV-018 | 12742.264 |  |  | PWG | Valve | AV | PWG-AV-018 |  |  | D-DWG-PHW-018.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PWG-TB-053 | 12747.863 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-053 | [7 empty] | PWG |  | Type 5 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 154 |  |  | Bend | [9 empty] | 13282 | 1 | each | 13282 | Bend | 45 | DICL | 375 | 3304 | 150 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-064 | 12747.863 |  |  | PWG | Bend | HOR | PWG-BND-064 |  |  | D-DWG-PHW-018.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 45° | DICL | 375 | [7 empty] | 45 | PIPE | 0 | NO
PWG-TB-054 | 12782.914 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-054 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 155 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3312 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-065 | 12782.914 |  |  | PWG | Bend | HOR | PWG-BND-065 |  |  | D-DWG-PHW-018.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-TB-110 | 13188.911 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-110 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 211 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 3360 | 240 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-SCV-013 | 13188.911 |  |  | PWG | Valve | SCV | PWG-SCV-013 |  |  | D-DWG-PHW-018.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-RD-0013 | 13218.214 | 13247.005 | 28.791 | PWG | Road & Rail Crossing | MINOR ROAD CROSSING | PWG-RD-0013 |  | 28.791 | [5 empty] | PWG | Cambooya Felton Road |  | Sealed | 375 |  |  | OD457x5WT Sintalock Type 1 MSCL Carrier & OD610x9WT MS Enveloper |  |  |  |  | TRC | [15 empty] | Thrust Boring | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 25 | [28 empty] | TRENCH | 0 | NO
PWG-TT-0072 | 13218.214 | 13247.005 | 28.791 | PWG | Trench Type | TRENCH SECTION |  | 8A | 28.791 | D-DWG-PWG-019.2 | D-DWG-PWG-019.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 180
PWG-PIPE-0113 | 13218.214 | 13247.005 | 28.791 | PWG | Pipe | PIPE | PWG-PIPE-0113 |  |  | D-DWG-PWG-019.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 + OD610 9WT MS Enveloper | [6 empty] | MSCL | 457 | [54 empty] | Major Crossing - Trenchless | Trenchless
PWG-CM-0038 | 13228 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0038 |  |  | D-DWG-PWG-019.2 |  |  | BYDA | Yes | PWG |  | BYDA TELSTRA COMMS DN50 | [9 empty] | Telstra |  |  | 50 | [27 empty] | Forreign service raw data.xlsx | 278
PWG-TT-0073 | 13247.005 | 13622.356 | 375.351 | PWG | Trench Type | TRENCH SECTION |  | 1A | 375.351 | D-DWG-PWG-019.2 | D-DWG-PWG-020.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 181
PWG-PIPE-0114 | 13247.005 | 13336.268 | 89.263 | PWG | Pipe | PIPE | PWG-PIPE-0114 |  |  | D-DWG-PWG-019.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Creek Crossings | Pipelay Crew
PWG-PIPE-0115 | 13336.268 | 13344.268 | 8 | PWG | Pipe | PIPE | PWG-PIPE-0115 |  |  | D-DWG-PWG-019.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-PIPE-0116 | 13344.268 | 13436.291 | 92.023 | PWG | Pipe | PIPE | PWG-PIPE-0116 |  |  | D-DWG-PWG-019.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-130 | 13366.211 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-130 | [7 empty] | PWG |  | Type 13 | [12 empty] | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 231 |  |  | Isolation Valve | [10 empty] | 1 | each |  | Isolation Valve |  |  | 375 | 3336 | 240 | Isolation valve | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-IV-005 | 13366.211 |  |  | PWG | Valve | IV | PWG-IV-005 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PWG | [55 empty] | Supplied |  | 1 | each | [9 empty] | 3 |  |  |  | PIPE | 0 | NO
PWG-FN-0017 | 13375 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0017 |  |  | D-DWG-PWG-020.2 |  |  |  | Yes | PWG |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 279
PWG-FN-0018 | 13375 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0018 |  |  | D-DWG-PWG-020.2 |  |  |  | Yes | PWG |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 280
PWG-FN-0019 | 13375 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0019 |  |  | D-DWG-PWG-020.2 |  |  |  | Yes | PWG |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 281
PWG-TS-0022 | 13376.5 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0022 |  |  | D-DWG-PWG-020 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 480 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-EL-0032 | 13380 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0032 |  |  | D-DWG-PWG-020.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 282
PWG-TS-0023 | 13384.4 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0023 |  |  | D-DWG-PWG-020 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 481 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TS-0024 | 13392.3 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0024 |  |  | D-DWG-PWG-020 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 482 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TB-055 | 13394.686 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-055 | [7 empty] | PWG |  | Type 9 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 156 |  |  | Bend | [9 empty] | 12764 | 1 | each | 12764 | Bend | 11.25 | DICL | 375 | 3366 | 240 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-066 | 13394.686 |  |  | PWG | Bend | VERT | PWG-BND-066 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-TB-056 | 13416.368 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-056 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 157 |  |  | Bend | [9 empty] | 12690 | 1 | each | 12690 | Bend | 22.5 | DICL | 375 | 3367 | 240 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-067 | 13416.368 |  |  | PWG | Bend | HOR | PWG-BND-067 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-PIPE-0117 | 13436.291 | 13622.356 | 186.065 | PWG | Pipe | PIPE | PWG-PIPE-0117 |  |  | D-DWG-PWG-019.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TT-0074 | 13622.356 | 13637.356 | 15 | PWG | Trench Type | TRENCH SECTION |  | 2 | 15 | D-DWG-PWG-020.2 | D-DWG-PWG-020.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 182
PWG-PIPE-0118 | 13622.356 | 13637.356 | 15 | PWG | Pipe | PIPE | PWG-PIPE-0118 |  |  | D-DWG-PWG-020.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TT-0075 | 13637.356 | 14060.93 | 423.574 | PWG | Trench Type | TRENCH SECTION |  | 1A | 423.574 | D-DWG-PWG-020.2 | D-DWG-PWG-021.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 183
PWG-PIPE-0119 | 13637.356 | 14074.214 | 436.858 | PWG | Pipe | PIPE | PWG-PIPE-0119 |  |  | D-DWG-PWG-020.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TT-0076 | 14060.93 | 14076.214 | 15.284 | PWG | Trench Type | TRENCH SECTION |  | 1B/1C | 15.284 | D-DWG-PWG-021.2 | D-DWG-PWG-021.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 184
PWG-FN-0020 | 14071 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0020 |  |  | D-DWG-PWG-021.2 |  |  |  | Yes | PWG |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 283
PWG-PIPE-0120 | 14074.214 | 14082.639 | 8.425 | PWG | Pipe | PIPE | PWG-PIPE-0120 |  |  | D-DWG-PWG-021.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-CC-0009 | 14076 | 14139 | 63 | PWG | Creek Crossing | TRENCHED CREEK CROSSING | PWG-CC-0009 | [7 empty] | PWG | HODGSON CREEK |  |  |  | LOOSE ROCK | B | [36 empty] | PHw_PWG_Creek_Crossings.xlsx | 11 | [28 empty] | TRENCH | 0 | NO
PWG-TT-0077 | 14076.214 | 14139.442 | 63.228 | PWG | Trench Type | TRENCH SECTION |  | 5 | 63.228 | D-DWG-PWG-021.2 | D-DWG-PWG-021.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 185
PWG-TB-057 | 14076.214 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-057 | [7 empty] | PWG |  | Type 11 | [11 empty] | MSCL | 450 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 158 |  |  | Bend | [9 empty] | 35673 | 1 | each | 35673 | Bend | 10.1 | MSCL | 450 | 3415 | 50 | Bend; MS - 10.1° | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-068 | 14076.214 |  |  | PWG | Bend | VERT | PWG-BND-068 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 10.1° | MSCL | 450 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PWG-PIPE-0121 | 14082.639 | 14101.292 | 18.653 | PWG | Pipe | PIPE | PWG-PIPE-0121 |  |  | D-DWG-PWG-021.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Open Trenched Creek Crossings | Special Crossings
PWG-PIPE-0122 | 14101.292 | 14139.442 | 38.15 | PWG | Pipe | PIPE | PWG-PIPE-0122 |  |  | D-DWG-PWG-021.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Open Trenched Creek Crossings | Special Crossings
PWG-BND-069 | 14101.293 |  |  | PWG | Bend | VERT | PWG-BND-069 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.0° | MSCL | 450 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PWG-BND-070 | 14120.815 |  |  | PWG | Bend | VERT | PWG-BND-070 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.9° | MSCL | 450 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PWG-FN-0021 | 14136 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0021 |  |  | D-DWG-PWG-021.2 |  |  |  | Yes | PWG |  | FENCE - CHAINWIRE | [40 empty] | Forreign service raw data.xlsx | 284
PWG-BND-071 | 14136.236 |  |  | PWG | Bend | HOR | PWG-BND-071 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 15.6° | MSCL | 450 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PWG-TT-0078 | 14139.442 | 14178.758 | 39.316 | PWG | Trench Type | TRENCH SECTION |  | 1B/1C | 39.316 | D-DWG-PWG-021.2 | D-DWG-PWG-021.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 186
PWG-TB-058 | 14139.442 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-058 | [7 empty] | PWG |  | Type 10 | [11 empty] | MSCL | 450 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 159 |  |  | Bend | [9 empty] | 49855 | 1 | each | 49855 | Bend | 10.3 | MSCL | 450 | 3424 | 50 | Bend; MS - 10.3° | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-072 | 14139.442 |  |  | PWG | Bend | VERT | PWG-BND-072 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 10.3° | MSCL | 450 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PWG-PIPE-0123 | 14139.442 | 14178.758 | 39.316 | PWG | Pipe | PIPE | PWG-PIPE-0123 |  |  | D-DWG-PWG-021.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Creek Crossings | Special Crossings
PWG-TB-111 | 14143.438 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-111 | [7 empty] | PWG |  | Type 6 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 212 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 3424 | 50 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-SCV-014 | 14143.638 |  |  | PWG | Valve | SCV | PWG-SCV-014 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1E |  |  |  | PIPE | 0 | NO
PWG-AV-019 | 14176.758 |  |  | PWG | Valve | AV | PWG-AV-019 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 2 |  |  |  | PIPE | 0 | NO
PWG-TT-0079 | 14178.758 | 14224.068 | 45.31 | PWG | Trench Type | TRENCH SECTION |  | 5 | 45.31 | D-DWG-PWG-021.2 | D-DWG-PWG-021.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 187
PWG-TB-059 | 14178.758 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-059 | [7 empty] | PWG |  | Type 10 | [11 empty] | MSCL | 450 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 160 |  |  | Bend | [9 empty] | 49855 | 1 | each | 49855 | Bend | 10.6 | MSCL | 450 | 3414 | 50 | Bend; MS - 10.6° | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-073 | 14178.758 |  |  | PWG | Bend | VERT | PWG-BND-073 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 10.6° | MSCL | 450 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PWG-PIPE-0124 | 14178.758 | 14194.829 | 16.071 | PWG | Pipe | PIPE | PWG-PIPE-0124 |  |  | D-DWG-PWG-021.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Open Trenched Creek Crossings | Special Crossings
PWG-CC-0010 | 14179 | 14224 | 45 | PWG | Creek Crossing | TRENCHED CREEK CROSSING | PWG-CC-0010 | [7 empty] | PWG | HODGSON CREEK ARM |  |  |  | LOOSE ROCK | A | [36 empty] | PHw_PWG_Creek_Crossings.xlsx | 12 | [28 empty] | TRENCH | 0 | NO
PWG-BND-074 | 14194.829 |  |  | PWG | Bend | VERT | PWG-BND-074 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 12.8° | MSCL | 450 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PWG-PIPE-0125 | 14194.829 | 14224.068 | 29.239 | PWG | Pipe | PIPE | PWG-PIPE-0125 |  |  | D-DWG-PWG-021.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Open Trenched Creek Crossings | Special Crossings
PWG-FN-0022 | 14214 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0022 |  |  | D-DWG-PWG-021.2 |  |  |  | Yes | PWG |  | FENCE - CHAINWIRE | [40 empty] | Forreign service raw data.xlsx | 285
PWG-CC-0011 | 14224 | 14423 | 199 | PWG | Creek Crossing | TRENCHED CREEK CROSSING | PWG-CC-0011 | [7 empty] | PWG |  |  |  |  | FABRIC/VEGETATION | [37 empty] | PHw_PWG_Creek_Crossings.xlsx | 13 | [28 empty] | TRENCH | 0 | NO
PWG-TT-0080 | 14224.068 | 14259.827 | 35.759 | PWG | Trench Type | TRENCH SECTION |  | 1B/1C | 35.759 | D-DWG-PWG-021.2 | D-DWG-PWG-021.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 188
PWG-TB-112 | 14224.068 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-112 | [7 empty] | PWG |  | Type 6 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 213 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 3434 | 50 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-SCV-015 | 14224.068 |  |  | PWG | Valve | SCV | PWG-SCV-015 |  |  | D-DWG-PHW-020.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1E |  |  |  | PIPE | 0 | NO
PWG-PIPE-0126 | 14224.068 | 14259.827 | 35.759 | PWG | Pipe | PIPE | PWG-PIPE-0126 |  |  | D-DWG-PWG-021.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TS-0025 | 14244.2 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0025 |  |  | D-DWG-PWG-021 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 483 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TS-0026 | 14254.6 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0026 |  |  | D-DWG-PWG-021 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 484 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TT-0081 | 14259.827 | 14304.298 | 44.471 | PWG | Trench Type | TRENCH SECTION |  | 1A | 44.471 | D-DWG-PWG-021.2 | D-DWG-PWG-021.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 189
PWG-PIPE-0127 | 14259.827 | 14304.298 | 44.471 | PWG | Pipe | PIPE | PWG-PIPE-0127 |  |  | D-DWG-PWG-021.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TT-0082 | 14304.298 | 14374.64 | 70.342 | PWG | Trench Type | TRENCH SECTION |  | 4 | 70.342 | D-DWG-PWG-021.2 | D-DWG-PWG-021.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 190
PWG-PIPE-0128 | 14304.298 | 14374.64 | 70.342 | PWG | Pipe | PIPE | PWG-PIPE-0128 |  |  | D-DWG-PWG-021.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Open Trenched Creek Crossings | Pipelay Crew
PWG-TT-0083 | 14374.64 | 14402.293 | 27.653 | PWG | Trench Type | TRENCH SECTION |  | 1A | 27.653 | D-DWG-PWG-021.2 | D-DWG-PWG-021.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 191
PWG-PIPE-0129 | 14374.64 | 14402.293 | 27.653 | PWG | Pipe | PIPE | PWG-PIPE-0129 |  |  | D-DWG-PWG-021.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TT-0084 | 14402.293 | 14410.112 | 7.819 | PWG | Trench Type | TRENCH SECTION |  | 4 | 7.819 | D-DWG-PWG-021.2 | D-DWG-PWG-021.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 192
PWG-PIPE-0130 | 14402.293 | 14410.112 | 7.819 | PWG | Pipe | PIPE | PWG-PIPE-0130 |  |  | D-DWG-PWG-021.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Open Trenched Creek Crossings | Pipelay Crew
PWG-TT-0085 | 14410.112 | 14525.498 | 115.386 | PWG | Trench Type | TRENCH SECTION |  | 1A | 115.386 | D-DWG-PWG-021.2 | D-DWG-PWG-021.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 193
PWG-PIPE-0131 | 14410.112 | 14525.498 | 115.386 | PWG | Pipe | PIPE | PWG-PIPE-0131 |  |  | D-DWG-PWG-021.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-RD-0014 | 14525.498 | 14572.298 | 46.8 | PWG | Road & Rail Crossing | MAJOR ROAD CROSSING | PWG-RD-0014 |  | 46.8 | [5 empty] | PWG | William Street / Toowoomba Karara Road |  | Sealed | 375 |  |  | OD457x5WT Sintalock Type 1 MSCL Carrier & OD610x9WT MS Enveloper |  |  |  |  | TMR | [15 empty] | Thrust Boring | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 26 | [28 empty] | TRENCH | 0 | NO
PWG-TT-0086 | 14525.498 | 14572.298 | 46.8 | PWG | Trench Type | TRENCH SECTION |  | 8A | 46.8 | D-DWG-PWG-021.2 | D-DWG-PWG-021.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 194
PWG-PIPE-0132 | 14525.498 | 14572.298 | 46.8 | PWG | Pipe | PIPE | PWG-PIPE-0132 |  |  | D-DWG-PWG-021.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 + OD610 9WT MS Enveloper | [6 empty] | MSCL | 457 | [54 empty] | Major Crossing - Trenchless | Trenchless
PWG-TT-0087 | 14572.298 | 16409.05 | 1836.752 | PWG | Trench Type | TRENCH SECTION |  | 1A | 1836.752 | D-DWG-PWG-021.2 | D-DWG-PWG-024.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 195
PWG-PIPE-0133 | 14572.298 | 14662.048 | 89.75 | PWG | Pipe | PIPE | PWG-PIPE-0133 |  |  | D-DWG-PWG-021.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TS-0027 | 14577.5 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0027 |  |  | D-DWG-PWG-021 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 485 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TS-0028 | 14588.8 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0028 |  |  | D-DWG-PWG-021 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 486 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TS-0029 | 14600.1 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0029 |  |  | D-DWG-PWG-021 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 487 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TS-0030 | 14611.4 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0030 |  |  | D-DWG-PWG-021 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 488 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TS-0031 | 14622.7 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0031 |  |  | D-DWG-PWG-021 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 489 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-PIPE-0134 | 14662.048 | 14833.219 | 171.171 | PWG | Pipe | PIPE | PWG-PIPE-0134 |  |  | D-DWG-PWG-021.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-PIPE-0135 | 14833.219 | 14883.12 | 49.901 | PWG | Pipe | PIPE | PWG-PIPE-0135 |  |  | D-DWG-PWG-021.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Pipelay Crew
PWG-CM-0039 | 14877 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0039 |  |  | D-DWG-PWG-022.2 |  |  | BYDA | Yes | PWG |  | BYDA TELSTRA COMMS DN20 | [9 empty] | Telstra |  |  | 20 | [27 empty] | Forreign service raw data.xlsx | 291
PWG-FN-0023 | 14883 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0023 |  |  | D-DWG-PWG-022.2 |  |  |  | Yes | PWG |  | FENCE - CHAINWIRE | [40 empty] | Forreign service raw data.xlsx | 292
PWG-TB-060 | 14883.12 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-060 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 161 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3292 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-075 | 14883.12 |  |  | PWG | Bend | HOR | PWG-BND-075 |  |  | D-DWG-PHW-022.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-PIPE-0136 | 14883.12 | 15707.336 | 824.216 | PWG | Pipe | PIPE | PWG-PIPE-0136 |  |  | D-DWG-PWG-021.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-FN-0024 | 15016 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0024 |  |  | D-DWG-PWG-022.2 |  |  |  | Yes | PWG |  | FENCE - CHAINWIRE | [40 empty] | Forreign service raw data.xlsx | 293
PWG-SCV-016 | 15240.436 |  |  | PWG | Valve | SCV | PWG-SCV-016 |  |  | D-DWG-PHW-022.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 2 |  |  |  | PIPE | 0 | NO
PWG-FN-0025 | 15340 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0025 |  |  | D-DWG-PWG-022.2 |  |  |  | Yes | PWG |  | FENCE - CHAINWIRE | [40 empty] | Forreign service raw data.xlsx | 294
PWG-FN-0026 | 15475 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0026 |  |  | D-DWG-PWG-023.2 |  |  |  | Yes | PWG |  | FENCE CHAINWIRE | [40 empty] | Forreign service raw data.xlsx | 297
PWG-FN-0027 | 15528 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0027 |  |  | D-DWG-PWG-021.2 |  |  |  | Yes | PWG |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 286
PWG-FN-0028 | 15528 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0028 |  |  | D-DWG-PWG-021.2 |  |  |  | Yes | PWG |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 287
PWG-CM-0040 | 15533 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0040 |  |  | D-DWG-PWG-021.2 |  |  | BYDA | Yes | PWG |  | BYDA TELSTRA COMMS DN20 | [9 empty] | Telstra |  |  | 20 | [27 empty] | Forreign service raw data.xlsx | 288
PWG-FN-0029 | 15542 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0029 |  |  | D-DWG-PWG-023.2 |  |  |  | Yes | PWG |  | FENCE CHAINWIRE | [40 empty] | Forreign service raw data.xlsx | 298
PWG-CM-0041 | 15566 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0041 |  |  | D-DWG-PWG-021.2 |  |  | BYDA | Yes | PWG |  | BYDA TELSTRA COMMS DN20 | [9 empty] | Telstra |  |  | 20 | [27 empty] | Forreign service raw data.xlsx | 289
PWG-FN-0030 | 15571 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0030 |  |  | D-DWG-PWG-021.2 |  |  |  | Yes | PWG |  | FENCE LINE NO POSTS - WIRES ONLY | [40 empty] | Forreign service raw data.xlsx | 290
PWG-FN-0031 | 15593 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0031 |  |  | D-DWG-PWG-023.2 |  |  |  | Yes | PWG |  | FENCE CHAINWIRE | [40 empty] | Forreign service raw data.xlsx | 299
PWG-CM-0042 | 15663 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0042 |  |  | D-DWG-PWG-022.2 |  |  | BYDA | Yes | PWG |  | BYDA NBN COMMS DN30 | [9 empty] | NBN Co |  |  | 30 | [27 empty] | Forreign service raw data.xlsx | 295
PWG-CM-0043 | 15663 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0043 |  |  | D-DWG-PWG-022.2 |  |  | BYDA | Yes | PWG |  | BYDA NBN COMMS DN30 | [9 empty] | NBN Co |  |  | 30 | [27 empty] | Forreign service raw data.xlsx | 296
PWG-AV-020 | 15707.336 |  |  | PWG | Valve | AV | PWG-AV-020 |  |  | D-DWG-PHW-022.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PWG-PIPE-0137 | 15707.336 | 15788.534 | 81.198 | PWG | Pipe | PIPE | PWG-PIPE-0137 |  |  | D-DWG-PWG-021.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-113 | 15788.534 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-113 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 214 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 3275 | 200 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-SCV-017 | 15788.534 |  |  | PWG | Valve | SCV | PWG-SCV-017 |  |  | D-DWG-PHW-023.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-PIPE-0138 | 15788.534 | 16409.05 | 620.516 | PWG | Pipe | PIPE | PWG-PIPE-0138 |  |  | D-DWG-PWG-021.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-CC-0012 | 15810 | 15826 | 16 | PWG | Creek Crossing | TRENCHED CREEK CROSSING | PWG-CC-0012 | [7 empty] | PWG |  |  |  |  | FABRIC/VEGETATION | [37 empty] | PHw_PWG_Creek_Crossings.xlsx | 14 | [28 empty] | TRENCH | 0 | NO
PWG-AV-021 | 16317.972 |  |  | PWG | Valve | AV | PWG-AV-021 |  |  | D-DWG-PHW-024.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-EL-0033 | 16364 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0033 |  |  | D-DWG-PWG-024.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 300
PWG-TT-0088 | 16409.05 | 16429.262 | 20.212 | PWG | Trench Type | TRENCH SECTION |  | 7 | 20.212 | D-DWG-PWG-024.2 | D-DWG-PWG-024.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 196
PWG-PIPE-0139 | 16409.05 | 16429.262 | 20.212 | PWG | Pipe | PIPE | PWG-PIPE-0139 |  |  | D-DWG-PWG-024.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Pipelay Crew
PWG-RD-0015 | 16411 | 16425 | 14 | PWG | Road & Rail Crossing | MINOR ROAD CROSSING | PWG-RD-0015 |  | 14 | [5 empty] | PWG | Todd Road |  | Unsealed | 375 |  |  | DN375 PN35 DICL RRJ |  | 14 |  |  | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 27 | [28 empty] | TRENCH | 0 | NO
PWG-TT-0089 | 16429.262 | 18150.734 | 1721.472 | PWG | Trench Type | TRENCH SECTION |  | 1A | 1721.472 | D-DWG-PWG-024.2 | D-DWG-PWG-026.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 197
PWG-TB-061 | 16429.262 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-061 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 162 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3173 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-076 | 16429.262 |  |  | PWG | Bend | HOR | PWG-BND-076 |  |  | D-DWG-PHW-024.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-PIPE-0140 | 16429.262 | 16715 | 285.738 | PWG | Pipe | PIPE | PWG-PIPE-0140 |  |  | D-DWG-PWG-024.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-FN-0032 | 16520 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0032 |  |  | D-DWG-PWG-024.2 |  | D-DWG-PWG-024_C |  | Yes | PWG |  | FENCE LINE NO POSTS | [40 empty] | Forreign service raw data.xlsx | 301
PWG-PIPE-0141 | 16715 | 16725.225 | 10.225 | PWG | Pipe | PIPE | PWG-PIPE-0141 |  |  | D-DWG-PWG-024.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Pipelay Crew
PWG-PIPE-0142 | 16725.225 | 16975.581 | 250.356 | PWG | Pipe | PIPE | PWG-PIPE-0142 |  |  | D-DWG-PWG-024.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-FN-0033 | 16930 |  |  | PWG | Foreign Service | FENCE | PWG-FN-0033 |  |  | D-DWG-PWG-025.2 |  | D-DWG-PWG-025_C |  | Yes | PWG |  | FENCE LINE NO POSTS | [40 empty] | Forreign service raw data.xlsx | 302
PWG-EL-0034 | 16969 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0034 |  |  | D-DWG-PWG-025.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 303
PWG-TB-062 | 16975.581 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-062 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 163 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3142 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-077 | 16975.581 |  |  | PWG | Bend | HOR | PWG-BND-077 |  |  | D-DWG-PHW-025.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-PIPE-0143 | 16975.581 | 16982.79 | 7.209 | PWG | Pipe | PIPE | PWG-PIPE-0143 |  |  | D-DWG-PWG-024.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-CM-0044 | 16979 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0044 |  |  | D-DWG-PWG-025.2 |  |  | BYDA | Yes | PWG |  | BYDA TELSTRA COMMS DN50 | [9 empty] | Telstra |  |  | 50 | [27 empty] | Forreign service raw data.xlsx | 304
PWG-TB-063 | 16982.79 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-063 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 164 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3142 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-078 | 16982.79 |  |  | PWG | Bend | HOR | PWG-BND-078 |  |  | D-DWG-PHW-025.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-PIPE-0144 | 16982.79 | 17842.3 | 859.51 | PWG | Pipe | PIPE | PWG-PIPE-0144 |  |  | D-DWG-PWG-024.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-EL-0035 | 17006 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0035 |  |  | D-DWG-PWG-025.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 305
PWG-AV-022 | 17085.82 |  |  | PWG | Valve | AV | PWG-AV-022 |  |  | D-DWG-PHW-025.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PWG-EL-0036 | 17105 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0036 |  |  | D-DWG-PWG-025.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 306
PWG-TB-064 | 17433.278 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-064 | [7 empty] | PWG |  | Type 6 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 165 |  |  | Bend | [9 empty] | 14363 | 1 | each | 14363 | Bend | 22.5+11.25 | DICL | 375 | 3159 | 240 | Bend; 22.5+11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-079 | 17433.278 |  |  | PWG | Bend | HOR | PWG-BND-079 |  |  | D-DWG-PHW-025.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 375 | [7 empty] | 22.5 | PIPE | 0 | NO
PWG-TB-065 | 17830.527 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-065 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 166 |  |  | Bend | [9 empty] | 12690 | 1 | each | 12690 | Bend | 22.5 | DICL | 375 | 3211 | 240 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-080 | 17830.527 |  |  | PWG | Bend | HOR | PWG-BND-080 |  |  | D-DWG-PHW-025.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 375 | [7 empty] | 22.5 | PIPE | 0 | NO
PWG-PIPE-0145 | 17842.3 | 18013.63 | 171.33 | PWG | Pipe | PIPE | PWG-PIPE-0145 |  |  | D-DWG-PWG-024.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-134 | 17865.623 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-134 | [7 empty] | PWG |  | 2 x Type 13 | [12 empty] | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 235 |  |  | Pigging Station | [10 empty] | 2 | each |  | Pigging Station |  |  | 375 | 3207 | 240 | Pigging station | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-PIG-003 | 17865.623 |  |  | PWG | Valve | PIG | PWG-PIG-003 |  |  | D-DWG-PHW-025.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [13 empty] | PIPE | 0 | NO
PWG-AV-023 | 17967.012 |  |  | PWG | Valve | AV | PWG-AV-023 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-PIPE-0146 | 18013.63 | 18025 | 11.37 | PWG | Pipe | PIPE | PWG-PIPE-0146 |  |  | D-DWG-PWG-024.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Pipelay Crew
PWG-PIPE-0147 | 18025 | 18151.238 | 126.238 | PWG | Pipe | PIPE | PWG-PIPE-0147 |  |  | D-DWG-PWG-024.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-066 | 18027.533 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-066 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 167 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3206 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-081 | 18027.533 |  |  | PWG | Bend | HOR | PWG-BND-081 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-CM-0045 | 18029 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0045 |  |  | D-DWG-PWG-026.2 |  |  | BYDA | Yes | PWG |  | BYDA TELSTRA COMMS DN50 | [9 empty] | Telstra |  |  | 50 | [27 empty] | Forreign service raw data.xlsx | 307
PWG-EL-0037 | 18050 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0037 |  |  | D-DWG-PWG-026.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 308
PWG-TB-067 | 18096.401 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-067 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 168 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3217 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-082 | 18096.401 |  |  | PWG | Bend | HOR | PWG-BND-082 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-CM-0046 | 18119 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0046 |  |  | D-DWG-PWG-026.2 |  |  | PUP | Yes | PWG |  | PUP COMMS DN50 | [12 empty] | 50 | [27 empty] | Forreign service raw data.xlsx | 309
PWG-TB-068 | 18147.994 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-068 | [7 empty] | PWG |  | Type 5 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 169 |  |  | Bend | [9 empty] | 13282 | 1 | each | 13282 | Bend | 45 | DICL | 375 | 3233 | 200 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-083 | 18147.994 |  |  | PWG | Bend | HOR | PWG-BND-083 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 45° | DICL | 375 | [7 empty] | 45 | PIPE | 0 | NO
PWG-TB-114 | 18149.44 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-114 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 215 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 3233 | 200 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-SCV-018 | 18149.44 |  |  | PWG | Valve | SCV | PWG-SCV-018 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-TT-0090 | 18150.734 | 18166.781 | 16.047 | PWG | Trench Type | TRENCH SECTION |  | 8A | 16.047 | D-DWG-PWG-026.2 | D-DWG-PWG-026.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 198
PWG-TB-069 | 18150.734 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-069 | [7 empty] | PWG |  | Type 5 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 170 |  |  | Bend | [9 empty] | 13282 | 1 | each | 13282 | Bend | 45 | DICL | 375 | 3233 | 200 | Bend; 45 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-084 | 18150.734 |  |  | PWG | Bend | HOR | PWG-BND-084 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 45° | DICL | 375 | [7 empty] | 45 | PIPE | 0 | NO
PWG-RD-0016 | 18151.238 | 18166.781 | 15.543 | PWG | Road & Rail Crossing | MAJOR ROAD CROSSING | PWG-RD-0016 |  | 15.543 | [5 empty] | PWG | Cudmore Road |  | Sealed | 375 |  |  | OD457x5WT Sintalock Type 1 MSCL Carrier & OD610x9WT MS Enveloper |  |  |  |  | TRC | [15 empty] | Thrust Boring | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 28 | [28 empty] | TRENCH | 0 | NO
PWG-PIPE-0148 | 18151.238 | 18166.781 | 15.543 | PWG | Pipe | PIPE | PWG-PIPE-0148 |  |  | D-DWG-PWG-026.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 + OD610 9WT MS Enveloper | [6 empty] | MSCL | 457 | [54 empty] | Major Crossing - Trenchless | Trenchless
PWG-TT-0091 | 18166.781 | 18217.47 | 50.689 | PWG | Trench Type | TRENCH SECTION |  | 1A | 50.689 | D-DWG-PWG-026.2 | D-DWG-PWG-027.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 199
PWG-BND-085 | 18166.781 |  |  | PWG | Bend | HOR | PWG-BND-085 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 375 | [7 empty] | 22.5 | PIPE | 0 | NO
PWG-PIPE-0149 | 18166.781 | 18221.276 | 54.495 | PWG | Pipe | PIPE | PWG-PIPE-0149 |  |  | D-DWG-PWG-026.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-070 | 18181.794 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-070 | [7 empty] | PWG |  | Type 6 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 171 |  |  | Bend | [9 empty] | 14363 | 1 | each | 14363 | Bend | 22.5+11.25 | DICL | 375 | 3221 | 200 | Bend; 22.5+11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-086 | 18181.794 |  |  | PWG | Bend | HOR | PWG-BND-086 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 375 | [7 empty] | 22.5 | PIPE | 0 | NO
PWG-EL-0038 | 18184 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0038 |  |  | D-DWG-PWG-026.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 310
PWG-TB-071 | 18190.097 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-071 | [7 empty] | PWG |  | Type 6 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 172 |  |  | Bend | [9 empty] | 14363 | 1 | each | 14363 | Bend | 22.5+11.25 | DICL | 375 | 3219 | 200 | Bend; 22.5+11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-AV-024 | 18202.816 |  |  | PWG | Valve | AV | PWG-AV-024 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PWG-CM-0047 | 18216 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0047 |  |  | D-DWG-PWG-027.2 |  |  | BYDA | Yes | PWG |  | BYDA TELSTRA COMMS DN35 | [9 empty] | Telstra |  |  | 35 | [27 empty] | Forreign service raw data.xlsx | 311
PWG-TT-0092 | 18217.47 | 18231.348 | 13.878 | PWG | Trench Type | TRENCH SECTION |  | 6 | 13.878 | D-DWG-PWG-027.2 | D-DWG-PWG-027.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 200
PWG-RD-0017 | 18218 | 18225 | 7 | PWG | Road & Rail Crossing | MINOR ROAD CROSSING | PWG-RD-0017 |  | 7 | [5 empty] | PWG | Cudmore Rd / Wattsiding Road Slip Lane |  | Sealed | 375 |  |  | DN375 PN35 DICL RRJ | 7 |  |  |  | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 29 | [28 empty] | TRENCH | 0 | NO
PWG-PIPE-0150 | 18221.276 | 18230 | 8.724 | PWG | Pipe | PIPE | PWG-PIPE-0150 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Pipelay Crew
PWG-PIPE-0151 | 18230 | 18785.87 | 555.87 | PWG | Pipe | PIPE | PWG-PIPE-0151 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TT-0093 | 18231.348 | 22319.185 | 4087.837 | PWG | Trench Type | TRENCH SECTION |  | 1A | 4087.837 | D-DWG-PWG-027.2 | D-DWG-PWG-032.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 201
PWG-TB-115 | 18772.846 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-115 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 216 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 3279 | 200 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-TS-0032 | 18779.3 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0032 |  |  | D-DWG-PWG-027 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 490 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-PIPE-0152 | 18785.87 | 19511.348 | 725.478 | PWG | Pipe | PIPE | PWG-PIPE-0152 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-072 | 18785.871 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-072 | [7 empty] | PWG |  | Type 9 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 173 |  |  | Bend | [9 empty] | 12764 | 1 | each | 12764 | Bend | 11.25 | DICL | 375 | 3287 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-087 | 18785.871 |  |  | PWG | Bend | VERT | PWG-BND-087 |  |  | D-DWG-PHW-026.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-PIPE-0153 | 19511.348 | 19626.241 | 114.893 | PWG | Pipe | PIPE | PWG-PIPE-0153 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-EL-0039 | 19524 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0039 |  |  | D-DWG-PWG-028.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 312
PWG-EL-0040 | 19541 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0040 |  |  | D-DWG-PWG-028.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 313
PWG-AV-025 | 19599.346 |  |  | PWG | Valve | AV | PWG-AV-025 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-CC-0013 | 19622 | 19645 | 23 | PWG | Creek Crossing | TRENCHED CREEK CROSSING | PWG-CC-0013 | [7 empty] | PWG |  |  |  |  | FABRIC/VEGETATION | [37 empty] | PHw_PWG_Creek_Crossings.xlsx | 15 | [28 empty] | TRENCH | 0 | NO
PWG-PIPE-0154 | 19626.241 | 19659.412 | 33.171 | PWG | Pipe | PIPE | PWG-PIPE-0154 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Creek Crossings | Pipelay Crew
PWG-TB-116 | 19641.881 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-116 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 217 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 3248 | 200 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-PIPE-0155 | 19659.412 | 20070.676 | 411.264 | PWG | Pipe | PIPE | PWG-PIPE-0155 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-CM-0048 | 19765 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0048 |  |  | D-DWG-PWG-029.2 |  |  | BYDA | Yes | PWG |  | BYDA TELSTRA COMMS DN20 | [9 empty] | Telstra |  |  | 20 | [27 empty] | Forreign service raw data.xlsx | 314
PWG-TB-073 | 20066.024 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-073 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 174 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3198 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-088 | 20066.024 |  |  | PWG | Bend | HOR | PWG-BND-088 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-PIPE-0156 | 20070.676 | 20287.711 | 217.035 | PWG | Pipe | PIPE | PWG-PIPE-0156 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-AV-026 | 20149.625 |  |  | PWG | Valve | AV | PWG-AV-026 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PWG-TB-074 | 20282.529 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-074 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 175 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3222 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-TB-117 | 20287.711 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-117 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 218 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 3222 | 200 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-089 | 20287.711 |  |  | PWG | Bend | HOR | PWG-BND-089 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-PIPE-0157 | 20287.711 | 20975.564 | 687.853 | PWG | Pipe | PIPE | PWG-PIPE-0157 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-SCV-019 | 20352.907 |  |  | PWG | Valve | SCV | PWG-SCV-019 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-EL-0041 | 20818 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0041 |  |  | D-DWG-PWG-030.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 315
PWG-TB-075 | 20818.272 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-075 | [7 empty] | PWG |  | Type 6 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 176 |  |  | Bend | [9 empty] | 13283 | 1 | each | 13283 | Bend | 22.5 | DICL | 375 | 3181 | 150 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-090 | 20818.272 |  |  | PWG | Bend | HOR | PWG-BND-090 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 375 | [7 empty] | 22.5 | PIPE | 0 | NO
PWG-EL-0042 | 20947 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0042 |  |  | D-DWG-PWG-030.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 316
PWG-TB-076 | 20947.014 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-076 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 177 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3164 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-091 | 20947.014 |  |  | PWG | Bend | HOR | PWG-BND-091 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-PIPE-0158 | 20975.564 | 21325 | 349.436 | PWG | Pipe | PIPE | PWG-PIPE-0158 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Creek Crossings | Pipelay Crew
PWG-AV-027 | 21036.313 |  |  | PWG | Valve | AV | PWG-AV-027 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-PIPE-0159 | 21325 | 21330 | 5 | PWG | Pipe | PIPE | PWG-PIPE-0159 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Pipelay Crew
PWG-PIPE-0160 | 21330 | 21367.989 | 37.989 | PWG | Pipe | PIPE | PWG-PIPE-0160 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-PIPE-0161 | 21367.989 | 21473.274 | 105.285 | PWG | Pipe | PIPE | PWG-PIPE-0161 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-EL-0043 | 21376 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0043 |  |  | D-DWG-PWG-031.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 317
PWG-TB-077 | 21445.551 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-077 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 178 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3179 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-092 | 21445.551 |  |  | PWG | Bend | HOR | PWG-BND-092 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-TB-118 | 21452.237 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-118 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 219 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 3180 | 150 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-SCV-020 | 21452.237 |  |  | PWG | Valve | SCV | PWG-SCV-020 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-PIPE-0162 | 21473.274 | 21581.657 | 108.383 | PWG | Pipe | PIPE | PWG-PIPE-0162 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-EL-0044 | 21486 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0044 |  |  | D-DWG-PWG-031.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 318
PWG-VG-0016 | 21580 | 21590 | 10 | PWG | Vegetation | TREE REMOVAL | VEG_PWG016 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 103 | 74.8 | HEAVY | [26 empty] | TRENCH | 0 | NO
PWG-TB-078 | 21581.657 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-078 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 179 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3166 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-093 | 21581.657 |  |  | PWG | Bend | HOR | PWG-BND-093 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-PIPE-0163 | 21581.657 | 22065 | 483.343 | PWG | Pipe | PIPE | PWG-PIPE-0163 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-079 | 21602.601 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-079 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 180 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3165 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-094 | 21602.601 |  |  | PWG | Bend | HOR | PWG-BND-094 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-TB-080 | 21631.157 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-080 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 181 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3165 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-095 | 21631.157 |  |  | PWG | Bend | HOR | PWG-BND-095 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-AV-028 | 21714.65 |  |  | PWG | Valve | AV | PWG-AV-028 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PWG-PIPE-0164 | 22065 | 22080 | 15 | PWG | Pipe | PIPE | PWG-PIPE-0164 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-131 | 22075.201 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-131 | [7 empty] | PWG |  | Type 13 | [12 empty] | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 232 |  |  | Isolation Valve | [10 empty] | 1 | each |  | Isolation Valve |  |  | 375 | 3188 | 200 | Isolation valve | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-IV-006 | 22075.201 |  |  | PWG | Valve | IV | PWG-IV-006 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG | [55 empty] | Supplied |  | 1 | each | [9 empty] | 1 |  |  |  | PIPE | 0 | NO
PWG-PIPE-0165 | 22080 | 22319.185 | 239.185 | PWG | Pipe | PIPE | PWG-PIPE-0165 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-081 | 22176.234 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-081 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 182 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3190 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-096 | 22176.234 |  |  | PWG | Bend | HOR | PWG-BND-096 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-EL-0045 | 22272 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0045 |  |  | D-DWG-PWG-032.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 319
PWG-TB-119 | 22316.144 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-119 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 220 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 3191 | 200 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-SCV-021 | 22316.144 |  |  | PWG | Valve | SCV | PWG-SCV-021 |  |  | D-DWG-PWG-027.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-TT-0094 | 22319.185 | 22360.55 | 41.365 | PWG | Trench Type | TRENCH SECTION |  | 5 | 41.365 | D-DWG-PWG-032.2 | D-DWG-PWG-032.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 202
PWG-PIPE-0166 | 22319.185 | 22360.55 | 41.365 | PWG | Pipe | PIPE | PWG-PIPE-0166 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-BND-097 | 22337.962 |  |  | PWG | Bend | HOR | PWG-BND-097 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 17.4° | MSCL | 450 | [7 empty] | Mitred 2-cut | PIPE | 0 | NO
PWG-CC-0014 | 22350 | 22377 | 27 | PWG | Creek Crossing | TRENCHED CREEK CROSSING | PWG-CC-0014 | [7 empty] | PWG |  |  |  |  | FABRIC/VEGETATION | [37 empty] | PHw_PWG_Creek_Crossings.xlsx | 16 | [28 empty] | TRENCH | 0 | NO
PWG-TT-0095 | 22360.55 | 24944.548 | 2583.998 | PWG | Trench Type | TRENCH SECTION |  | 1A | 2583.998 | D-DWG-PWG-032.2 | D-DWG-PWG-036.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 203
PWG-PIPE-0167 | 22360.55 | 22443.57 | 83.02 | PWG | Pipe | PIPE | PWG-PIPE-0167 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Creek Crossings | Pipelay Crew
PWG-PIPE-0168 | 22443.57 | 22460 | 16.43 | PWG | Pipe | PIPE | PWG-PIPE-0168 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Pipelay Crew
PWG-PIPE-0169 | 22460 | 24407.759 | 1947.759 | PWG | Pipe | PIPE | PWG-PIPE-0169 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-EL-0046 | 22504 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0046 |  |  | D-DWG-PWG-033.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 320
PWG-TB-082 | 22504.051 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-082 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 183 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3159 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-098 | 22504.051 |  |  | PWG | Bend | HOR | PWG-BND-098 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-AV-029 | 22524.995 |  |  | PWG | Valve | AV | PWG-AV-029 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-EL-0047 | 22650 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0047 |  |  | D-DWG-PWG-033.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 321
PWG-TB-083 | 22650.05 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-083 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 184 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3170 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-099 | 22650.05 |  |  | PWG | Bend | HOR | PWG-BND-099 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-TB-120 | 22680.903 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-120 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 221 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 3170 | 200 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-SCV-022 | 22680.903 |  |  | PWG | Valve | SCV | PWG-SCV-022 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-AV-030 | 22994.685 |  |  | PWG | Valve | AV | PWG-AV-030 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-TB-084 | 23112.75 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-084 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 185 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3157 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-100 | 23112.75 |  |  | PWG | Bend | HOR | PWG-BND-100 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-TB-085 | 23373.352 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-085 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 186 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3177 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-101 | 23373.352 |  |  | PWG | Bend | HOR | PWG-BND-101 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-TB-121 | 23376.417 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-121 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 222 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 3178 | 150 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-TB-086 | 23414.166 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-086 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 187 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3177 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-SCV-023 | 23414.166 |  |  | PWG | Valve | SCV | PWG-SCV-023 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-AV-031 | 23604.486 |  |  | PWG | Valve | AV | PWG-AV-031 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-TB-087 | 23666.289 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-087 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 188 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3165 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-102 | 23666.289 |  |  | PWG | Bend | HOR | PWG-BND-102 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-TB-088 | 23999.457 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-088 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 189 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3179 | 150 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-103 | 23999.457 |  |  | PWG | Bend | HOR | PWG-BND-103 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-VG-0017 | 24010 | 24020 | 10 | PWG | Vegetation | TREE REMOVAL | VEG_PWG017 | [49 empty] | 1 SMALL TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 104 | 32.5 | LIGHT | [26 empty] | TRENCH | 0 | NO
PWG-EL-0048 | 24097 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0048 |  |  | D-DWG-PWG-035.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 322
PWG-EL-0049 | 24097 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0049 |  |  | D-DWG-PWG-035.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 323
PWG-CC-0015 | 24185 | 24208 | 23 | PWG | Creek Crossing | TRENCHED CREEK CROSSING | PWG-CC-0015 | [7 empty] | PWG |  |  |  |  | FABRIC/VEGETATION | [37 empty] | PHw_PWG_Creek_Crossings.xlsx | 17 | [28 empty] | TRENCH | 0 | NO
PWG-TB-122 | 24206.919 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-122 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 223 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 3184 | 100 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-SCV-024 | 24206.919 |  |  | PWG | Valve | SCV | PWG-SCV-024 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-PIPE-0170 | 24407.759 | 24426.9 | 19.141 | PWG | Pipe | PIPE | PWG-PIPE-0170 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Creek Crossings | Pipelay Crew
PWG-EL-0050 | 24426 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0050 |  |  | D-DWG-PWG-035.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 324
PWG-TB-089 | 24426.9 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-089 | [7 empty] | PWG |  | Type 5 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 190 |  |  | Bend | [9 empty] | 13107 | 1 | each | 13107 | Bend | 22.5 | DICL | 375 | 3172 | 100 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-104 | 24426.9 |  |  | PWG | Bend | HOR | PWG-BND-104 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 375 | [7 empty] | 22.5 | PIPE | 0 | NO
PWG-PIPE-0171 | 24426.9 | 24500 | 73.1 | PWG | Pipe | PIPE | PWG-PIPE-0171 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Creek Crossings | Pipelay Crew
PWG-CC-0016 | 24468 | 24494 | 26 | PWG | Creek Crossing | TRENCHED CREEK CROSSING | PWG-CC-0016 | [7 empty] | PWG |  |  |  |  | FABRIC/VEGETATION | [37 empty] | PHw_PWG_Creek_Crossings.xlsx | 18 | [28 empty] | TRENCH | 0 | NO
PWG-PIPE-0172 | 24500 | 24944.548 | 444.548 | PWG | Pipe | PIPE | PWG-PIPE-0172 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-EL-0051 | 24713 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0051 |  |  | D-DWG-PWG-036.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 325
PWG-TB-090 | 24713.951 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-090 | [7 empty] | PWG |  | Type 5 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 191 |  |  | Bend | [9 empty] | 13107 | 1 | each | 13107 | Bend | 22.5 | DICL | 375 | 3167 | 100 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-105 | 24713.951 |  |  | PWG | Bend | HOR | PWG-BND-105 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 375 | [7 empty] | 22.5 | PIPE | 0 | NO
PWG-VG-0018 | 24830 | 24860 | 30 | PWG | Vegetation | TREE REMOVAL | VEG_PWG018 | [49 empty] | MULTIPLE SMALL TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 105 | 176 | HEAVY | [26 empty] | TRENCH | 0 | NO
PWG-EL-0052 | 24850 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0052 |  |  | D-DWG-PWG-036.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 326
PWG-EL-0053 | 24909 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0053 |  |  | D-DWG-PWG-036.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 327
PWG-TB-091 | 24909.165 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-091 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 192 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3155 | 100 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-106 | 24909.165 |  |  | PWG | Bend | HOR | PWG-BND-106 |  |  | D-DWG-PWG-032.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-TT-0096 | 24944.548 | 24954.52 | 9.972 | PWG | Trench Type | TRENCH SECTION |  | 1B/1C | 9.972 | D-DWG-PWG-036.2 | D-DWG-PWG-036.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 204
PWG-AV-032 | 24944.548 |  |  | PWG | Valve | AV | PWG-AV-032 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PWG-PIPE-0173 | 24944.548 | 24954.52 | 9.972 | PWG | Pipe | PIPE | PWG-PIPE-0173 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TT-0097 | 24954.52 | 25018.345 | 63.825 | PWG | Trench Type | TRENCH SECTION |  | 5 | 63.825 | D-DWG-PWG-036.2 | D-DWG-PWG-036.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 205
PWG-PIPE-0174 | 24954.52 | 25018.345 | 63.825 | PWG | Pipe | PIPE | PWG-PIPE-0174 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Open Trenched Creek Crossings | Pipelay Crew
PWG-CC-0017 | 24955 | 25018 | 63 | PWG | Creek Crossing | TRENCHED CREEK CROSSING | PWG-CC-0017 | [7 empty] | PWG | EMU CREEK |  |  |  | LOOSE ROCK | A | [36 empty] | PHw_PWG_Creek_Crossings.xlsx | 19 | [28 empty] | TRENCH | 0 | NO
PWG-BND-107 | 24972.593 |  |  | PWG | Bend | VERT | PWG-BND-107 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 6° | MSCL | 450 | [7 empty] | Mitred 1-cut | PIPE | 0 | NO
PWG-TT-0098 | 25018.345 | 25052.461 | 34.116 | PWG | Trench Type | TRENCH SECTION |  | 1B/1C | 34.116 | D-DWG-PWG-036.2 | D-DWG-PWG-036.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 206
PWG-TB-123 | 25018.345 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-123 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 224 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 3159 | 100 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-PIPE-0175 | 25018.345 | 25052.461 | 34.116 | PWG | Pipe | PIPE | PWG-PIPE-0175 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TS-0033 | 25025.6 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0033 |  |  | D-DWG-PWG-036 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 491 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TS-0034 | 25039.6 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0034 |  |  | D-DWG-PWG-036 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 492 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TT-0099 | 25052.461 | 26010.44 | 957.979 | PWG | Trench Type | TRENCH SECTION |  | 1A | 957.979 | D-DWG-PWG-036.2 | D-DWG-PWG-038.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 207
PWG-PIPE-0176 | 25052.461 | 25177.723 | 125.262 | PWG | Pipe | PIPE | PWG-PIPE-0176 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TS-0035 | 25053.6 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0035 |  |  | D-DWG-PWG-036 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 493 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-TS-0036 | 25067.6 |  |  | PWG | Trench Stop & Bulkhead | TRENCH STOP | PWG-TS-0036 |  |  | D-DWG-PWG-036 | [47 empty] | Trench&Bulkheads- T2W_PIPELINE.xlsm | 494 | [12 empty] | 1112.5 | 1 | each | 1112.5 | [12 empty] | TRENCH | 0 | NO
PWG-EL-0054 | 25129 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0054 |  |  | D-DWG-PWG-036.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 328
PWG-TB-092 | 25129.481 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-092 | [7 empty] | PWG |  | Type 5 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 193 |  |  | Bend | [9 empty] | 13107 | 1 | each | 13107 | Bend | 22.5 | DICL | 375 | 3106 | 100 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-108 | 25129.481 |  |  | PWG | Bend | HOR | PWG-BND-108 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 375 | [7 empty] | 22.5 | PIPE | 0 | NO
PWG-TB-093 | 25162.559 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-093 | [7 empty] | PWG |  | Type 4 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 194 |  |  | Bend | [9 empty] | 15185 | 1 | each | 15185 | Bend | 22.5+11.25 | DICL | 375 | 3097 | 100 | Bend; 22.5+11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-109 | 25162.559 |  |  | PWG | Bend | HOR | PWG-BND-109 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 375 | [7 empty] | 22.5 | PIPE | 0 | NO
PWG-WA-0019 | 25166 |  |  | PWG | Foreign Service | WATER | PWG-WA-0019 |  |  | D-DWG-PWG-036.2 |  |  | BYDA | Yes | PWG |  | BYDA WATER DN100 | [12 empty] | 100 | [27 empty] | Forreign service raw data.xlsx | 329
PWG-TB-094 | 25169.588 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-094 | [7 empty] | PWG |  | Type 5 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 195 |  |  | Bend | [9 empty] | 13107 | 1 | each | 13107 | Bend | 22.5 | DICL | 375 | 3094 | 100 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-PIPE-0177 | 25177.723 | 25380 | 202.277 | PWG | Pipe | PIPE | PWG-PIPE-0177 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Creek Crossings | Pipelay Crew
PWG-PIPE-0178 | 25380 | 25391.145 | 11.145 | PWG | Pipe | PIPE | PWG-PIPE-0178 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Driveway crossings | Pipelay Crew
PWG-TB-095 | 25391.145 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-095 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 196 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3031 | 100 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-110 | 25391.145 |  |  | PWG | Bend | HOR | PWG-BND-110 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-PIPE-0179 | 25391.145 | 25451.56 | 60.415 | PWG | Pipe | PIPE | PWG-PIPE-0179 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-PIPE-0180 | 25451.56 | 25457 | 5.44 | PWG | Pipe | PIPE | PWG-PIPE-0180 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Driveway crossings | Pipelay Crew
PWG-PIPE-0181 | 25457 | 25563 | 106 | PWG | Pipe | PIPE | PWG-PIPE-0181 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-PIPE-0182 | 25563 | 25569 | 6 | PWG | Pipe | PIPE | PWG-PIPE-0182 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Driveway crossings | Pipelay Crew
PWG-PIPE-0183 | 25569 | 25650 | 81 | PWG | Pipe | PIPE | PWG-PIPE-0183 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-EL-0055 | 25632 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0055 |  |  | D-DWG-PWG-037.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 330
PWG-PIPE-0184 | 25650 | 25660 | 10 | PWG | Pipe | PIPE | PWG-PIPE-0184 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Driveway crossings | Pipelay Crew
PWG-PIPE-0185 | 25660 | 25748 | 88 | PWG | Pipe | PIPE | PWG-PIPE-0185 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-AV-033 | 25684.557 |  |  | PWG | Valve | AV | PWG-AV-033 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PWG-PIPE-0186 | 25748 | 25760 | 12 | PWG | Pipe | PIPE | PWG-PIPE-0186 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Driveway crossings | Pipelay Crew
PWG-PIPE-0187 | 25760 | 25792 | 32 | PWG | Pipe | PIPE | PWG-PIPE-0187 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-PIPE-0188 | 25792 | 25817.226 | 25.226 | PWG | Pipe | PIPE | PWG-PIPE-0188 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Driveway crossings | Pipelay Crew
PWG-TB-124 | 25792.787 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-124 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 225 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 3003 | 100 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-SCV-025 | 25792.787 |  |  | PWG | Valve | SCV | PWG-SCV-025 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-TB-096 | 25800.795 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-096 | [7 empty] | PWG |  | Type 5 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 197 |  |  | Bend | [9 empty] | 13107 | 1 | each | 13107 | Bend | 22.5 | DICL | 375 | 3004 | 100 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-111 | 25800.795 |  |  | PWG | Bend | HOR | PWG-BND-111 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 375 | [7 empty] | 22.5 | PIPE | 0 | NO
PWG-TB-097 | 25804.926 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-097 | [7 empty] | PWG |  | Type 5 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 198 |  |  | Bend | [9 empty] | 13107 | 1 | each | 13107 | Bend | 22.5 | DICL | 375 | 3002 | 100 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-112 | 25804.926 |  |  | PWG | Bend | HOR | PWG-BND-112 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 375 | [7 empty] | 22.5 | PIPE | 0 | NO
PWG-TB-098 | 25817.226 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-098 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 199 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 2996 | 100 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-113 | 25817.226 |  |  | PWG | Bend | HOR | PWG-BND-113 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-PIPE-0189 | 25817.226 | 25853 | 35.774 | PWG | Pipe | PIPE | PWG-PIPE-0189 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-PIPE-0190 | 25853 | 25858 | 5 | PWG | Pipe | PIPE | PWG-PIPE-0190 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Driveway crossings | Special Crossings
PWG-PIPE-0191 | 25858 | 25915 | 57 | PWG | Pipe | PIPE | PWG-PIPE-0191 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Special Crossings
PWG-AV-034 | 25892.612 |  |  | PWG | Valve | AV | PWG-AV-034 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PWG-PIPE-0192 | 25915 | 25920 | 5 | PWG | Pipe | PIPE | PWG-PIPE-0192 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Driveway crossings | Trenchless
PWG-PIPE-0193 | 25920 | 25942.81 | 22.81 | PWG | Pipe | PIPE | PWG-PIPE-0193 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-PIPE-0194 | 25942.81 | 25948 | 5.19 | PWG | Pipe | PIPE | PWG-PIPE-0194 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Driveway crossings | Pipelay Crew
PWG-PIPE-0195 | 25948 | 26015 | 67 | PWG | Pipe | PIPE | PWG-PIPE-0195 |  |  | D-DWG-PWG-036.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-WA-0020 | 26007 |  |  | PWG | Foreign Service | WATER | PWG-WA-0020 |  |  | D-DWG-PWG-038.2 |  |  | BYDA | Yes | PWG |  | BYDA WATER DN150 | [12 empty] | 150 | [27 empty] | Forreign service raw data.xlsx | 331
PWG-TT-0100 | 26010.44 | 26026.47 | 16.03 | PWG | Trench Type | TRENCH SECTION |  | 6 | 16.03 | D-DWG-PWG-038.2 | D-DWG-PWG-038.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 208
PWG-RD-0018 | 26013 | 26026 | 13 | PWG | Road & Rail Crossing | MINOR ROAD CROSSING | PWG-RD-0018 |  | 13 | [5 empty] | PWG | King Street |  | Sealed | 375 |  |  | DN375 PN35 DICL RRJ | 13 |  |  |  | TRC | [15 empty] | Open Trenching | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 30 | [28 empty] | TRENCH | 0 | NO
PWG-PIPE-0196 | 26015 | 26025 | 10 | PWG | Pipe | PIPE | PWG-PIPE-0196 |  |  | D-DWG-PWG-038.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Pipelay Crew
PWG-PIPE-0197 | 26025 | 26041.176 | 16.176 | PWG | Pipe | PIPE | PWG-PIPE-0197 |  |  | D-DWG-PWG-038.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TT-0101 | 26026.47 | 26252.108 | 225.638 | PWG | Trench Type | TRENCH SECTION |  | 1A | 225.638 | D-DWG-PWG-038.2 | D-DWG-PWG-038.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 209
PWG-TB-099 | 26038.676 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-099 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 200 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 3004 | 100 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-114 | 26038.676 |  |  | PWG | Bend | HOR | PWG-BND-114 |  |  | D-DWG-PWG-038.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-TB-125 | 26041.176 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-125 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 150 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 226 |  |  | Tee | [10 empty] | 1 | each |  | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 3004 | 100 | Tee; DN375XDN150 DIFBE SCOUR TEE | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-SCV-026 | 26041.176 |  |  | PWG | Valve | SCV | PWG-SCV-026 |  |  | D-DWG-PWG-038.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1B |  |  |  | PIPE | 0 | NO
PWG-PIPE-0198 | 26041.176 | 26097 | 55.824 | PWG | Pipe | PIPE | PWG-PIPE-0198 |  |  | D-DWG-PWG-038.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-VG-0019 | 26070 | 26080 | 10 | PWG | Vegetation | TREE REMOVAL | VEG_PWG019 | [49 empty] | 2 LARGE TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 106 | 64.7 | HEAVY | [26 empty] | TRENCH | 0 | NO
PWG-PIPE-0199 | 26097 | 26101.991 | 4.991 | PWG | Pipe | PIPE | PWG-PIPE-0199 |  |  | D-DWG-PWG-038.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Driveway crossings | Pipelay Crew
PWG-PIPE-0200 | 26101.991 | 26169 | 67.009 | PWG | Pipe | PIPE | PWG-PIPE-0200 |  |  | D-DWG-PWG-038.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-PIPE-0201 | 26169 | 26175 | 6 | PWG | Pipe | PIPE | PWG-PIPE-0201 |  |  | D-DWG-PWG-038.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Driveway crossings | Pipelay Crew
PWG-PIPE-0202 | 26175 | 26252.108 | 77.108 | PWG | Pipe | PIPE | PWG-PIPE-0202 |  |  | D-DWG-PWG-038.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TB-100 | 26195.427 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-100 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 201 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 2995 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-115 | 26195.427 |  |  | PWG | Bend | HOR | PWG-BND-115 |  |  | D-DWG-PWG-038.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-CM-0049 | 26205 |  |  | PWG | Foreign Service | COMMUNICATIONS | PWG-CM-0049 |  |  | D-DWG-PWG-038.2 |  |  | BYDA | Yes | PWG |  | BYDA TELSTRA COMMS DN100 | [9 empty] | Telstra |  |  | 100 | [27 empty] | Forreign service raw data.xlsx | 332
PWG-RD-0019 | 26252.108 | 26283.028 | 30.92 | PWG | Road & Rail Crossing | MAJOR ROAD CROSSING | PWG-RD-0019 |  | 30.92 | [5 empty] | PWG | Woodlands Rd |  | Sealed | 375 |  |  | OD457x5WT Sintalock Type 1 MSCL Carrier & OD610x9WT MS Enveloper |  |  |  |  | TRC | [15 empty] | Thrust Boring | [14 empty] | T2WRWP-05304-PTW-PPG-SCH-00002_PHW_PWG.xlsx | 31 | [28 empty] | TRENCH | 0 | NO
PWG-TT-0102 | 26252.108 | 26283.028 | 30.92 | PWG | Trench Type | TRENCH SECTION |  | 8A | 30.92 | D-DWG-PWG-038.2 | D-DWG-PWG-038.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 210
PWG-PIPE-0203 | 26252.108 | 26283.028 | 30.92 | PWG | Pipe | PIPE | PWG-PIPE-0203 |  |  | D-DWG-PWG-038.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 + OD610 9WT MS Enveloper | [6 empty] | MSCL | 457 | [54 empty] | Major Crossing - Trenchless | Trenchless
PWG-EL-0056 | 26256 |  |  | PWG | Foreign Service | ELECTRICITY | PWG-EL-0056 |  |  | D-DWG-PWG-038.2 |  |  | PUP | Yes | PWG |  | PUP ELECTRICITY | [40 empty] | Forreign service raw data.xlsx | 333
PWG-TT-0103 | 26283.028 | 26988.368 | 705.34 | PWG | Trench Type | TRENCH SECTION |  | 1A | 705.34 | D-DWG-PWG-038.2 | D-DWG-PWG-039.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 211
PWG-PIPE-0204 | 26283.028 | 26313.689 | 30.661 | PWG | Pipe | PIPE | PWG-PIPE-0204 |  |  | D-DWG-PWG-038.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-VG-0020 | 26290 | 26300 | 10 | PWG | Vegetation | TREE REMOVAL | VEG_PWG020 | [49 empty] | 2 SMALL TREES | T2W - Tree Removal TakeOff (V.1).xlsx | 107 | 23 | LIGHT | [26 empty] | TRENCH | 0 | NO
PWG-PIPE-0205 | 26313.689 | 26410.408 | 96.719 | PWG | Pipe | PIPE | PWG-PIPE-0205 |  |  | D-DWG-PWG-038.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Open Trenched Road/Carpark/Side Lane crossings | Pipelay Crew
PWG-PIPE-0206 | 26410.408 | 26668.201 | 257.793 | PWG | Pipe | PIPE | PWG-PIPE-0206 |  |  | D-DWG-PWG-038.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-VG-0021 | 26430 | 26440 | 10 | PWG | Vegetation | TREE REMOVAL | VEG_PWG021 | [49 empty] | 1 LARGE TREE | T2W - Tree Removal TakeOff (V.1).xlsx | 108 | 79 | HEAVY | [26 empty] | TRENCH | 0 | NO
PWG-WA-0021 | 26480 |  |  | PWG | Foreign Service | WATER | PWG-WA-0021 |  |  | D-DWG-PWG-038.2 |  |  | BYDA | Yes | PWG |  | BYDA WATER DN100 | [12 empty] | 100 | [27 empty] | Forreign service raw data.xlsx | 334
PWG-TB-101 | 26560.798 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-101 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 202 |  |  | Bend | [9 empty] | 12566 | 1 | each | 12566 | Bend | 11.25 | DICL | 375 | 2940 | 200 | Bend; 11.25 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-116 | 26560.798 |  |  | PWG | Bend | HOR | PWG-BND-116 |  |  | D-DWG-PWG-038.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 11.25° | DICL | 375 | [7 empty] | 11.25 | PIPE | 0 | NO
PWG-TB-102 | 26662.937 |  |  | PWG | Thrust Block | THRUST BLOCK | PWG-TB-102 | [7 empty] | PWG |  | Type 7 | [11 empty] | DICL | 375 | [27 empty] | Thrust Block Register - T2W_PIPELINE 24-8.xlsm | 203 |  |  | Bend | [9 empty] | 12690 | 1 | each | 12690 | Bend | 22.5 | DICL | 375 | 2927 | 200 | Bend; 22.5 deg | S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction |  |  |  |  | TRENCH | 0 | NO
PWG-BND-117 | 26662.937 |  |  | PWG | Bend | HOR | PWG-BND-117 |  |  | D-DWG-PWG-038.2 |  |  |  |  | PWG | [57 empty] | 1 | each |  | Bend | 22.5° | DICL | 375 | [7 empty] | 22.5 | PIPE | 0 | NO
PWG-AV-035 | 26668.201 |  |  | PWG | Valve | AV | PWG-AV-035 |  |  | D-DWG-PWG-038.2 |  |  |  |  | PWG | [57 empty] | 1 | each | [9 empty] | 1A |  |  |  | PIPE | 0 | NO
PWG-PIPE-0207 | 26668.201 | 26988 | 319.799 | PWG | Pipe | PIPE | PWG-PIPE-0207 |  |  | D-DWG-PWG-038.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-PIPE-0208 | 26988 | 27002.147 | 14.147 | PWG | Pipe | PIPE | PWG-PIPE-0208 |  |  | D-DWG-PWG-038.2 |  |  |  |  | PWG |  |  |  | 457 |  |  | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | [6 empty] | MSCL | 457 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
PWG-TT-0104 | 26988.368 | 27002.147 | 13.779 | PWG | Trench Type | TRENCH SECTION |  | 4 | 13.779 | D-DWG-PWG-039.2 | D-DWG-PWG-039.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 212
PWG-TT-0105 | 27002.147 | 27012.465 | 10.318 | PWG | Trench Type | TRENCH SECTION |  | 1A | 10.318 | D-DWG-PWG-039.2 | D-DWG-PWG-039.2 |  |  |  | PWG | [42 empty] | Trench Type Register - T2W_PIPELINE.xlsm | 213
PWG-PIPE-0209 | 27002.147 | 27012.465 | 10.318 | PWG | Pipe | PIPE | PWG-PIPE-0209 |  |  | D-DWG-PWG-039.2 |  |  |  |  | PWG |  |  |  | 375 |  |  | DN375 DICL PN 35 | [6 empty] | DICL | 375 | [54 empty] | Supply and Installation of Pipe | Pipelay Crew
RHF-TB-001 |  |  |  | RHF | Thrust Block | THRUST BLOCK | RHF-TB-001 | [7 empty] | RHF |  | RHF TYPE 1 | [40 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 114 |  |  | Facility (RHF) - not in pipeline index | [10 empty] | 1 | each | [8 empty] | Not in the thrust block index (facilities package) |  |  |  |  | TRENCH
RHF-TB-002 |  |  |  | RHF | Thrust Block | THRUST BLOCK | RHF-TB-002 | [7 empty] | RHF |  | RHF TYPE 1 | [40 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 115 |  |  | Facility (RHF) - not in pipeline index | [10 empty] | 1 | each | [8 empty] | Not in the thrust block index (facilities package) |  |  |  |  | TRENCH
RHF-TB-003 |  |  |  | RHF | Thrust Block | THRUST BLOCK | RHF-TB-003 | [7 empty] | RHF |  | RHF TYPE 3 | [40 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 116 |  |  | Facility (RHF) - not in pipeline index | [10 empty] | 1 | each | [8 empty] | Not in the thrust block index (facilities package) |  |  |  |  | TRENCH
RHF-TB-004 |  |  |  | RHF | Thrust Block | THRUST BLOCK | RHF-TB-004 | [7 empty] | RHF |  | RHF TYPE 2 | [40 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 117 |  |  | Facility (RHF) - not in pipeline index | [10 empty] | 1 | each | [8 empty] | Not in the thrust block index (facilities package) |  |  |  |  | TRENCH
RHF-TB-005 |  |  |  | RHF | Thrust Block | THRUST BLOCK | RHF-TB-005 | [7 empty] | RHF |  | RHF TYPE 1 | [40 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 118 |  |  | Facility (RHF) - not in pipeline index | [10 empty] | 1 | each | [8 empty] | Not in the thrust block index (facilities package) |  |  |  |  | TRENCH
RHF-TB-006 |  |  |  | RHF | Thrust Block | THRUST BLOCK | RHF-TB-006 | [7 empty] | RHF |  | RHF TYPE 4 | [40 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 119 |  |  | Facility (RHF) - not in pipeline index | [10 empty] | 1 | each | [8 empty] | Not in the thrust block index (facilities package) |  |  |  |  | TRENCH
RHF-TB-007 |  |  |  | RHF | Thrust Block | THRUST BLOCK | RHF-TB-007 | [7 empty] | RHF |  | RHF TYPE 4 | [40 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 120 |  |  | Facility (RHF) - not in pipeline index | [10 empty] | 1 | each | [8 empty] | Not in the thrust block index (facilities package) |  |  |  |  | TRENCH
RHF-TB-008 |  |  |  | RHF | Thrust Block | THRUST BLOCK | RHF-TB-008 | [7 empty] | RHF |  | RHF TYPE 2 | [40 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 121 |  |  | Facility (RHF) - not in pipeline index | [10 empty] | 1 | each | [8 empty] | Not in the thrust block index (facilities package) |  |  |  |  | TRENCH
RHF-TB-009 |  |  |  | RHF | Thrust Block | THRUST BLOCK | RHF-TB-009 | [7 empty] | RHF |  | RHF TYPE 1 | [40 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 122 |  |  | Facility (RHF) - not in pipeline index | [10 empty] | 1 | each | [8 empty] | Not in the thrust block index (facilities package) |  |  |  |  | TRENCH
RHF-TB-010 |  |  |  | RHF | Thrust Block | THRUST BLOCK | RHF-TB-010 | [7 empty] | RHF |  | RHF TYPE 4 | [40 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 123 |  |  | Facility (RHF) - not in pipeline index | [10 empty] | 1 | each | [8 empty] | Not in the thrust block index (facilities package) |  |  |  |  | TRENCH
RHF-TB-011 |  |  |  | RHF | Thrust Block | THRUST BLOCK | RHF-TB-011 | [7 empty] | RHF |  | RHF TYPE 4 | [40 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 124 |  |  | Facility (RHF) - not in pipeline index | [10 empty] | 1 | each | [8 empty] | Not in the thrust block index (facilities package) |  |  |  |  | TRENCH
RHF-TB-012 |  |  |  | RHF | Thrust Block | THRUST BLOCK | RHF-TB-012 | [7 empty] | RHF |  | RHF TYPE 1 | [40 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 125 |  |  | Facility (RHF) - not in pipeline index | [10 empty] | 1 | each | [8 empty] | Not in the thrust block index (facilities package) |  |  |  |  | TRENCH
RHF-TB-013 |  |  |  | RHF | Thrust Block | THRUST BLOCK | RHF-TB-013 | [7 empty] | RHF |  | TYPE 1 | [40 empty] | Thrust Block Register - T2W_PIPELINE.xlsm | 126 |  |  | Facility (RHF) - not in pipeline index | [10 empty] | 1 | each | [8 empty] | Not in the thrust block index (facilities package) |  |  |  |  | TRENCH

## Chainage Index
Records per 1 km chainage bin
Live COUNTIFS over the Master Register. Bin covers Chainage Start >= From and < To.
From (m) | To (m) | Thrust Block | Trench Type | Trench Stop & Bulkhead | Foreign Service | Creek Crossing | Road & Rail Crossing | Vegetation | Total
0 | 1000 | 23 | 16 | 97 | 11 | 1 | 3 | 22 | 173
1000 | 2000 | 18 | 18 | 71 | 23 | 1 | 4 | 15 | 150
2000 | 3000 | 16 | 23 | 40 | 50 | 0 | 6 | 16 | 151
3000 | 4000 | 7 | 5 | 22 | 16 | 3 | 0 | 5 | 58
4000 | 5000 | 9 | 8 | 16 | 11 | 1 | 1 | 2 | 48
5000 | 6000 | 10 | 4 | 81 | 3 | 1 | 0 | 3 | 102
6000 | 7000 | 3 | 11 | 56 | 15 | 2 | 2 | 1 | 90
7000 | 8000 | 19 | 16 | 8 | 26 | 1 | 3 | 0 | 73
8000 | 9000 | 17 | 20 | 13 | 27 | 1 | 5 | 5 | 88
9000 | 10000 | 10 | 12 | 33 | 7 | 3 | 1 | 4 | 70
10000 | 11000 | 10 | 8 | 1 | 18 | 2 | 2 | 2 | 43
11000 | 12000 | 10 | 8 | 12 | 8 | 3 | 2 | 1 | 44
12000 | 13000 | 5 | 7 | 3 | 17 | 0 | 3 | 0 | 35
13000 | 14000 | 8 | 6 | 5 | 22 | 0 | 2 | 2 | 45
14000 | 15000 | 9 | 15 | 7 | 14 | 3 | 2 | 2 | 52
15000 | 16000 | 2 | 2 | 0 | 18 | 1 | 1 | 1 | 25
16000 | 17000 | 3 | 5 | 0 | 6 | 2 | 1 | 0 | 17
17000 | 18000 | 6 | 3 | 0 | 3 | 1 | 0 | 0 | 13
18000 | 19000 | 13 | 6 | 1 | 13 | 1 | 2 | 1 | 37
19000 | 20000 | 4 | 2 | 19 | 6 | 1 | 0 | 3 | 35
20000 | 21000 | 5 | 0 | 0 | 2 | 0 | 0 | 0 | 7
21000 | 22000 | 5 | 0 | 0 | 2 | 0 | 0 | 1 | 8
22000 | 23000 | 6 | 2 | 0 | 3 | 1 | 0 | 0 | 12
23000 | 24000 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6
24000 | 25000 | 4 | 2 | 0 | 6 | 3 | 0 | 2 | 17
25000 | 26000 | 9 | 2 | 4 | 3 | 0 | 0 | 0 | 18
26000 | 27000 | 5 | 5 | 0 | 4 | 0 | 2 | 3 | 19
27000 | 28000 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
TOTAL |  | 242 | 207 | 489 | 334 | 32 | 42 | 91 | 1437
Note | This total counts only records that carry a chainage. 13 Thrust Block records in the RHF section have no chainage in the source and therefore fall in no bin; the Master Register holds 1,188 records in total.

## Trench Type Summary
Trench type totals
Carried across from the "Total Length Sections (m) by Trench Type" block in the Trench Type Register.
Trench Type | PWG (m) | PHW (m) | Total (m) | No. of Sections
1A | 25128.364 | 16838.593 | 41966.957 | 85
1B/1C | 134.447 | 58.129 | 192.576 | 6
1A/1B/1C | 94.046 | 143.795 | 237.841 | 7
2 | 15 | 25.754 | 40.754 | 4
4 | 432.844 | 683.233 | 1116.077 | 41
4&6 | 60.742 | 0 | 60.742 | 2
4&7 | 18.466 | 28.91 | 47.376 | 4
5 | 387.402 | 532.124 | 919.526 | 16
6 | 91.347 | 83.29 | 174.637 | 8
7 | 291.939 | 247.067 | 539.006 | 15
8A | 357.868 | 515.844 | 873.712 | 19
TOTAL | 27012.465 | 19156.739 | 46169.204 | 207
Reconciliation
Sum of (Chainage End - Chainage Start) over all 207 trench sections in the Master Register: |  |  |  |  | 46169.204
Difference against the trench-type total above (should be zero): |  |  |  |  | 0
Note | The source register carried its own "Total" and "Check: register total" lines inside this block. They are excluded from the table above so the TOTAL row is not double-counted; both stated 46,169.204 m over 207 sections, which agrees with the calculated figure.

## Rate Library
Rate Library
The single place unit rates are entered. Every cost on Cost Tracker - Linear and Cost Dashboard reads from here — change a rate here and every budget and
earned-value figure that uses it recalculates. Nothing on this sheet is calculated from anything else.
Rate is what the client is charged. Cost Rate is what it costs us. Margin is the difference, and is calculated — never typed. Both are per the unit named in the Unit column.
Lookup Key is a working column: it is what the tracker matches on. Do not type in it.
Table 1 — Trench construction, rate per metre of trench
Held SEPARATELY FOR EACH PIPELINE SECTION, because the same trench type is not built the same way in PHW as in PWG. Trench Type is written exactly as it appears in the Master Register.
Pipeline Section | Trench Type | Description | Unit | Rate | Effective From | Rate Source / Basis | Sections in register | Lookup Key | Cost Rate | Margin ($) | Margin %
PHW | 1A | PQ - remaining length (94.27% of total remaining length) | $/m | 448.79 |  | Item PHW-6110.01 (Provisional Quantity) | 41 | PHW¦1A | 353.378 | 95.412 | 21.26%
PHW | 1B/1C | PQ - remaining length (3.57% of total remaining length) | $/m | 410.3 |  | Item PHW-6110.03 (Provisional Quantity) | 1 | PHW¦1B/1C | 323.0709 | 87.2291 | 21.26%
PHW | 1A/1B/1C | PQ - remaining length (1.88% of total remaining length) | $/m | 477.6 |  | Item PHW-6110.02 (Provisional Quantity) | 4 | PHW¦1A/1B/1C | 376.063 | 101.537 | 21.26%
PHW | 2 | PQ - remaining length (0.28% of total remaining length) | $/m | 994 |  | Item PHW-6110.04 (Provisional Quantity) | 3 | PHW¦2 | 782.6772 | 211.3228 | 21.26%
PHW | 4 | Remaining length, excluding crossings | $/m | 1151.8 |  | Item PHW-6110.05 | 24 | PHW¦4 | 906.9291 | 244.8709 | 21.26%
PHW | 4&6 |  | $/m |  |  |  | 0 | PHW¦4&6 | 0
PHW | 4&7 | Sealed with concrete encasement | $/m | 1584 |  | Item PHW-6120.01 | 2 | PHW¦4&7 | 1247.2441 | 336.7559 | 21.26%
PHW | 5 | Remaining length, excluding crossings | $/m | 1597.6 |  | Item PHW-6120.02 | 9 | PHW¦5 | 1257.9528 | 339.6472 | 21.26%
PHW | 6 | Sealed without concrete encasement | $/m | 1917 |  | Item PHW-6120.02 | 4 | PHW¦6 | 1509.4488 | 407.5512 | 21.26%
PHW | 7 | Unsealed without concrete encasement | $/m | 1794.4 |  | Item PHW-6120.03 | 5 | PHW¦7 | 1412.9134 | 381.4866 | 21.26%
PHW | 8A |  | $/m |  |  |  | 9 | PHW¦8A | 0
PWG | 1A | PQ - remaining length (98.06% of total remaining length) | $/m | 369.11 |  | Item PWG-6110.01 (Provisional Quantity) | 44 | PWG¦1A | 290.6378 | 78.4722 | 21.26%
PWG | 1B/1C | PQ - remaining length (0.90% of total remaining length) | $/m | 385 |  | Item PWG-6110.03 (Provisional Quantity) | 5 | PWG¦1B/1C | 303.1496 | 81.8504 | 21.26%
PWG | 1A/1B/1C | PQ - remaining length (0.72% of total remaining length) | $/m | 398.2 |  | Item PWG-6110.02 (Provisional Quantity) | 3 | PWG¦1A/1B/1C | 313.5433 | 84.6567 | 21.26%
PWG | 2 | PQ - remaining length (0.32% of total remaining length) | $/m | 440 |  | Item PWG-6110.04 (Provisional Quantity) | 1 | PWG¦2 | 346.4567 | 93.5433 | 21.26%
PWG | 4 | Remaining length, excluding crossings | $/m | 916.6 |  | Item PWG-6110.06 | 17 | PWG¦4 | 721.7323 | 194.8677 | 21.26%
PWG | 4&6 | Sealed with concrete encasement | $/m | 2190 |  | Item PWG-6120.01 | 2 | PWG¦4&6 | 1724.4094 | 465.5906 | 21.26%
PWG | 4&7 | Unsealed with concrete encasement | $/m | 1638 |  | Item PWG-6120.02 | 2 | PWG¦4&7 | 1289.7638 | 348.2362 | 21.26%
PWG | 5 | Remaining length, excluding crossings | $/m | 1448 |  | Item PWG-6110.07 | 7 | PWG¦5 | 1140.1575 | 307.8425 | 21.26%
PWG | 6 | Sealed without concrete encasement | $/m | 984 |  | Item PWG-6120.03 | 4 | PWG¦6 | 774.8031 | 209.1969 | 21.26%
PWG | 7 | Unsealed without concrete encasement | $/m | 565.9 |  | Item PWG-6120.04 | 10 | PWG¦7 | 445.5906 | 120.3094 | 21.26%
PWG | 8A |  | $/m |  |  |  | 10 | PWG¦8A
A blank rate is NOT priced — it is left blank, never zero, so an unpriced section shows as blank instead of reading as free. "Sections in register" shows how many trench sections that section/type combination actually has; a 0 needs no rate.
Table 2 — Pipe supply and lay, rate per metre of pipe
FOUR SEPARATE PIPE ASSETS: DICL and MSCL in each pipeline section. They are held separately because the diameters differ — PHW is DN600, PWG is DN375 — so they cannot share a metre rate. Descriptions are taken from Pipe Description on the Master Register.
Pipeline Section | Pipe Type | Pipe Description | Nominal Size | Unit | Rate | Effective From | Rate Source / Basis | Lookup Key | Cost Rate | Margin ($) | Margin %
PHW | DICL | DN600 PN35 DICL RRJ | DN600 | $/m | 485.45 |  | PHW-6105.01 | PHW¦DICL
PHW | MSCL | OD660x6WT MSCL Sintalock Type 2 PN35 carrier | OD660 | $/m | 1332.7 |  | PHW-6105.02 | PHW¦MSCL
PWG | DICL | DN375 PN35 DICL RRJ | DN375 | $/m |  |  | TEST ENTRY — structure only, no rate supplied | PWG¦DICL
PWG | MSCL | OD457x5WT Sintalock Type 1 MSCL carrier | OD457 | $/m |  |  | TEST ENTRY — structure only, no rate supplied | PWG¦MSCL
These four are TEST PIPES: the rate lines exist so the mechanism can be proven, but no rate has been supplied, so the descriptions and sizes are real and the rates are blank. Enter a rate against one and every section carrying that pipe type prices immediately.
If a pipe type is later split further — a different wall thickness or an envelopered length priced apart from plain carrier — add a row here with its own Pipe Type name and choose that name in Pipe Type on the tracker. No formula needs changing.
Table 3 — Point assets, rate per item (reference only)
These are priced on the Master Register itself, in Unit Rate ($) / Quantity / Total Cost ($) — a point asset has no length, so it is not a metre rate. Restated here so every rate in the project is visible in one place. Changing a value here does NOT change the Master Register.
Asset Type | Unit | Rate | Effective From | Rate Source / Basis | Status | Cost Rate | Margin ($) | Margin %
TRENCH STOP | each | 1112.5 | 24 Aug 2026 | J. Krasnoff-Hnatjuk, 24 Aug 2026. Item detail C-DWG-PTW-105.1 Rev 1, Issued for Construction. | Applied on Master Register (442 items)
BULK HEAD | each | 20507 | 24 Aug 2026 | J. Krasnoff-Hnatjuk, 24 Aug 2026. Item detail C-DWG-PTW-105.1 Rev 1, Issued for Construction. | Applied on Master Register (47 items)
THRUST BLOCK | each |  |  |  | Superseded by Table 4 below — priced per type, not one rate for all 255
TRENCHED CREEK CROSSING | each |  |  |  | Not yet priced (32 items)
MINOR ROAD CROSSING | each |  |  |  | Not yet priced (22 items)
MAJOR ROAD CROSSING | each |  |  |  | Not yet priced (11 items)
MAJOR RAIL CROSSING | each |  |  |  | Not yet priced (3 items)
CARPARK/SIDE LANE | each |  |  |  | Not yet priced (4 items)
TREE REMOVAL | m2 |  |  |  | Not yet priced (91 records, Area (m2) held on Master Register)
Table 4 — Thrust blocks, rate per block, by section, type and fitting
Split the way the schedule of rates is written: grouped by thrust block type, and within each type a line for every fitting it is built against. A Type 4 taking a 45 deg DICL bend is not the same job as a Type 4 taking a mitred MSCL bend, so they are priced apart.
Type, fitting, angle, DN, test pressure and bearing capacity all come from the thrust block index drawings S-DWG-PTW-115 to 118. Blocks is the count in the register; a pigging station record carries two blocks.
Rate is per BLOCK. Cuts is for the mitred MSCL bends — the drawings give the angle but not the cut count, so fill it in if it changes the price.
Pipeline Section | Thrust Block Type | Item | Fitting | Angle / Size | Material | DN (mm) | Blocks | Unit | Rate | Cuts | Effective From | Rate Source / Basis | Lookup Key | Cost Rate | Margin ($) | Margin %
PHW — Thrust block Type 1
PHW | Type 1 | Bend; 45 deg | Bend | 45 | DICL | 600 | 8 | each | 114663 |  | 2026-08-27 | Item PHW-6210.01.05 (Provisional Quantity) | PHW¦Type 1¦Bend; 45 deg | 90285.8268 | 24377.1732 | 21.26%
PHW — Thrust block Type 2 | [13 empty] | 0
PHW | Type 2 | Bend; 22.5 deg | Bend | 22.5 | DICL | 600 | 1 | each | 99539 |  | 2026-08-27 | Item PHW-6210.02.02 (Provisional Quantity) | PHW¦Type 2¦Bend; 22.5 deg | 78377.1654 | 21161.8346 | 21.26%
PHW | Type 2 | Bend; 22.5+11.25 deg | Bend | 22.5+11.25 | DICL | 600 | 1 | each | 99969 |  | 2026-08-27 | Item PHW-6210.02.04 (Provisional Quantity) | PHW¦Type 2¦Bend; 22.5+11.25 deg | 78715.748 | 21253.252 | 21.26%
PHW | Type 2 | Bend; MS - 38.2° | Bend | 38.2 | MSCL | 650 | 1 | each | 104391 | 2 | 2026-08-27 | Item PHW-6210.02.10c (Provisional Quantity) | PHW¦Type 2¦Bend; MS - 38.2° | 82197.6378 | 22193.3622 | 21.26%
PHW — Thrust block Type 3 | [13 empty] | 0
PHW | Type 3 | Bend; 45 deg | Bend | 45 | DICL | 600 | 4 | each | 16755 |  | 2026-08-27 | Item PHW-6210.03.05 (Provisional Quantity) | PHW¦Type 3¦Bend; 45 deg | 13192.9134 | 3562.0866 | 21.26%
PHW | Type 3 | Bend; MS - 43.2° | Bend | 43.2 | MSCL | 650 | 1 | each | 26944 | 2 | 2026-08-27 | Item PHW-6210.03.10c (Provisional Quantity) — covers 47.1° & 43.2° cuts | PHW¦Type 3¦Bend; MS - 43.2° | 21215.748 | 5728.252 | 21.26%
PHW | Type 3 | Bend; MS - 47.1° | Bend | 47.1 | MSCL | 650 | 1 | each | 26944 | 2 | 2026-08-27 | Item PHW-6210.03.10c (Provisional Quantity) — covers 47.1° & 43.2° cuts | PHW¦Type 3¦Bend; MS - 47.1° | 21215.748 | 5728.252 | 21.26%
PHW — Thrust block Type 4 | [13 empty] | 0
PHW | Type 4 | Bend; 11.25 deg | Bend | 11.25 | DICL | 600 | 2 | each | 15563 |  | 2026-08-27 | Item PHW-6210.04.01 (Provisional Quantity) | PHW¦Type 4¦Bend; 11.25 deg | 12254.3307 | 3308.6693 | 21.26%
PHW | Type 4 | Bend; 22.5 deg | Bend | 22.5 | DICL | 600 | 4 | each | 15780 |  | 2026-08-27 | Item PHW-6210.04.02 (Provisional Quantity) | PHW¦Type 4¦Bend; 22.5 deg | 12425.1969 | 3354.8031 | 21.26%
PHW | Type 4 | Bend; 22.5+11.25 deg | Bend | 22.5+11.25 | DICL | 600 | 2 | each | 18443 |  | 2026-08-27 | Item PHW-6210.04.04 (Provisional Quantity) | PHW¦Type 4¦Bend; 22.5+11.25 deg | 14522.0472 | 3920.9528 | 21.26%
PHW | Type 4 | Bend; 45 deg | Bend | 45 | DICL | 600 | 5 | each | 16211 |  | 2026-08-27 | Item PHW-6210.04.05 (Provisional Quantity) | PHW¦Type 4¦Bend; 45 deg | 12764.5669 | 3446.4331 | 21.26%
PHW | Type 4 | Bend; MS - 13.9° | Bend | 13.9 | MSCL | 650 | 1 | each | 20678 | 2 | 2026-08-27 | Item PHW-6210.04.10c (Provisional Quantity) — covers 30° & 13.9° cuts; BoQ qty=1 vs 2 register rows — verify | PHW¦Type 4¦Bend; MS - 13.9° | 16281.8898 | 4396.1102 | 21.26%
PHW | Type 4 | Bend; MS - 30° | Bend | 30 | MSCL | 650 | 1 | each | 20678 | 2 | 2026-08-27 | Item PHW-6210.04.10c (Provisional Quantity) — covers 30° & 13.9° cuts; BoQ qty=1 vs 2 register rows — verify | PHW¦Type 4¦Bend; MS - 30° | 16281.8898 | 4396.1102 | 21.26%
PHW — Thrust block Type 5 | [13 empty] | 0
PHW | Type 5 | Bend; 22.5 deg | Bend | 22.5 | DICL | 600 | 9 | each | 14784 |  | 2026-08-27 | Item PHW-6210.05.02 (Provisional Quantity) | PHW¦Type 5¦Bend; 22.5 deg | 11640.9449 | 3143.0551 | 21.26%
PHW | Type 5 | Bend; 22.5+11.25 deg | Bend | 22.5+11.25 | DICL | 600 | 2 | each | 15214 |  | 2026-08-27 | Item PHW-6210.02.04 PQ.2 (Provisional Quantity) — listed under Type 5 in source schedule | PHW¦Type 5¦Bend; 22.5+11.25 deg | 11979.5276 | 3234.4724 | 21.26%
PHW — Thrust block Type 6 | [13 empty] | 0
PHW | Type 6 | Bend; 11.25 deg | Bend | 11.25 | DICL | 600 | 7 | each | 14743 |  | 2026-08-27 | Item PHW-6210.06.01 (Provisional Quantity) | PHW¦Type 6¦Bend; 11.25 deg | 11608.6614 | 3134.3386 | 21.26%
PHW | Type 6 | Bend; MS - 10° | Bend | 10 | MSCL | 650 | 1 | each | 19811 | 1 | 2026-08-27 | Item PHW-6210.06.10c (Provisional Quantity) | PHW¦Type 6¦Bend; MS - 10° | 15599.2126 | 4211.7874 | 21.26%
PHW | Type 6 | Tee; DN600XDN150 DIFBE SCOUR TEE | Tee | DN600xDN150 DIFBE SCOUR TEE |  | 150 | 3 | each |  |  |  |  | PHW¦Type 6¦Tee; DN600XDN150 DIFBE SCOUR TEE | 0
PHW — Thrust block Type 7 | [13 empty] | 0
PHW | Type 7 | Bend; 11.25 deg | Bend | 11.25 | DICL | 600 | 14 | each | 14150 |  | 2026-08-27 | Item PHW-6210.07.01 (Provisional Quantity) | PHW¦Type 7¦Bend; 11.25 deg | 11141.7323 | 3008.2677 | 21.26%
PHW | Type 7 | Bend; MS - 7.7° | Bend | 7.7 | MSCL | 650 | 1 | each | 19220 | 1 | 2026-08-27 | Item PHW-6210.07.10c (Provisional Quantity) — covers 9.9° & 7.7° cuts | PHW¦Type 7¦Bend; MS - 7.7° | 15133.8583 | 4086.1417 | 21.26%
PHW | Type 7 | Bend; MS - 9.1° | Bend | 9.1 | MSCL | 650 | 1 | each | 19220 | 1 | 2026-08-27 | Item PHW-6210.07.10c (Provisional Quantity) — covers 9.9° & 7.7° cuts | PHW¦Type 7¦Bend; MS - 9.1° | 15133.8583 | 4086.1417 | 21.26%
PHW | Type 7 | Tee; DN600XDN150 DIFBE SCOUR TEE | Tee | DN600xDN150 DIFBE SCOUR TEE |  | 150 | 13 | each |  |  |  |  | PHW¦Type 7¦Tee; DN600XDN150 DIFBE SCOUR TEE | 0
PHW — Thrust block Type 8 | [13 empty] | 0
PHW | Type 8 | Bend; 11.25 deg | Bend | 11.25 | DICL | 600 | 1 | each | 14024 |  | 2026-08-27 | Item PHW-6210.08.01 (Provisional Quantity) | PHW¦Type 8¦Bend; 11.25 deg | 11042.5197 | 2981.4803 | 21.26%
PHW — Thrust block Type 9 | [13 empty] | 0
PHW | Type 9 | Bend; 11.25 deg | Bend | 11.25 | DICL | 600 | 4 | each | 14347 |  | 2026-08-27 | Item PHW-6210.09.01 (Provisional Quantity) | PHW¦Type 9¦Bend; 11.25 deg | 11296.8504 | 3050.1496 | 21.26%
PHW — Thrust block Type 10 | [13 empty] | 0
PHW | Type 10 | Bend; 11.25 deg | Bend | 11.25 | DICL | 600 | 2 | each | 44440 |  | 2026-08-27 | Item PHW-6210.10.01 (Provisional Quantity) | PHW¦Type 10¦Bend; 11.25 deg | 34992.126 | 9447.874 | 21.26%
PHW | Type 10 | Bend; MS - 7.5° | Bend | 7.5 | MSCL | 650 | 1 | each | 49509 | 1 | 2026-08-27 | Item PHW-6210.10.02 (Provisional Quantity) — covers 7.5°, 8.6° & 13.9° cuts; BoQ qty=3 vs 2 register rows — verify | PHW¦Type 10¦Bend; MS - 7.5° | 38983.4646 | 10525.5354 | 21.26%
PHW | Type 10 | Bend; MS - 8.6° | Bend | 8.6 | MSCL | 650 | 1 | each | 49509 | 1 | 2026-08-27 | Item PHW-6210.10.02 (Provisional Quantity) — covers 7.5°, 8.6° & 13.9° cuts; BoQ qty=3 vs 2 register rows — verify | PHW¦Type 10¦Bend; MS - 8.6° | 38983.4646 | 10525.5354 | 21.26%
PHW — Thrust block Type 12 | [13 empty] | 0
PHW | Type 12 | Isolation valve | Isolation Valve |  |  | 600 | 5 | each |  |  |  |  | PHW¦Type 12¦Isolation valve | 0
PHW — Thrust block Type 14 | [13 empty] | 0
PHW | Type 14 | In-line | In-Line |  |  | 600 | 2 | each |  |  |  |  | PHW¦Type 14¦In-line | 0
PHW — Thrust block 2 x Type 12 | [13 empty] | 0
PHW | 2 x Type 12 | Pigging station | Pigging Station |  |  | 600 | 4 | each |  |  |  |  | PHW¦2 x Type 12¦Pigging station | 0
PPH — Thrust block Type 5 | [13 empty] | 0
PPH | Type 5 | Bend; 45 deg | Bend | 45 | DICL | 500 | 6 | each |  |  |  |  | PPH¦Type 5¦Bend; 45 deg | 0
PPH | Type 5 | Bend; 45+11.25 deg | Bend | 45+11.25 | DICL | 500 | 1 | each |  |  |  |  | PPH¦Type 5¦Bend; 45+11.25 deg | 0
PPH — Thrust block Type 6 | [13 empty] | 0
PPH | Type 6 | Tee; OD813XOD559 MSCL TEE | Tee | OD813xOD559 MSCL TEE |  | 750 | 1 | each |  |  |  |  | PPH¦Type 6¦Tee; OD813XOD559 MSCL TEE | 0
PPH — Thrust block Type 7 | [13 empty] | 0
PPH | Type 7 | Tee; DN500XDN150 DIFBE SCOUR TEE | Tee | DN500xDN150 DIFBE SCOUR TEE |  | 150 | 2 | each |  |  |  |  | PPH¦Type 7¦Tee; DN500XDN150 DIFBE SCOUR TEE | 0
PPH — Thrust block Type 13 | [13 empty] | 0
PPH | Type 13 | Isolation valve | Isolation Valve |  |  | 500 | 2 | each |  |  |  |  | PPH¦Type 13¦Isolation valve | 0
PWG — Thrust block Type 4 | [13 empty] | 0
PWG | Type 4 | Bend; 22.5+11.25 deg | Bend | 22.5+11.25 | DICL | 375 | 1 | each | 15185 |  | 2026-08-27 | Item PWG-6200.04.03 (Provisional Quantity) | PWG¦Type 4¦Bend; 22.5+11.25 deg | 11956.6929 | 3228.3071 | 21.26%
PWG | Type 4 | Bend; 45 deg | Bend | 45 | DICL | 375 | 1 | each | 14280 |  | 2026-08-27 | Item PWG-6200.04.05 (Provisional Quantity) | PWG¦Type 4¦Bend; 45 deg | 11244.0945 | 3035.9055 | 21.26%
PWG — Thrust block Type 5 | [13 empty] | 0
PWG | Type 5 | Bend; 22.5 deg | Bend | 22.5 | DICL | 375 | 6 | each | 13107 |  | 2026-08-27 | Item PWG-6200.05.02 (Provisional Quantity) | PWG¦Type 5¦Bend; 22.5 deg | 10320.4724 | 2786.5276 | 21.26%
PWG | Type 5 | Bend; 45 deg | Bend | 45 | DICL | 375 | 8 | each | 13282 |  | 2026-08-27 | Item PWG-6200.05.05 (Provisional Quantity) | PWG¦Type 5¦Bend; 45 deg | 10458.2677 | 2823.7323 | 21.26%
PWG — Thrust block Type 6 | [13 empty] | 0
PWG | Type 6 | Bend; 11.25 deg | Bend | 11.25 | DICL | 375 | 2 | each | 13159 |  | 2026-08-27 | Item PWG-6200.06.01 (Provisional Quantity) | PWG¦Type 6¦Bend; 11.25 deg | 10361.4173 | 2797.5827 | 21.26%
PWG | Type 6 | Bend; 22.5 deg | Bend | 22.5 | DICL | 375 | 3 | each | 13283 |  | 2026-08-27 | Item PWG-6200.06.02 (Provisional Quantity) | PWG¦Type 6¦Bend; 22.5 deg | 10459.0551 | 2823.9449 | 21.26%
PWG | Type 6 | Bend; 22.5+11.25 deg | Bend | 22.5+11.25 | DICL | 375 | 3 | each | 14363 |  | 2026-08-27 | Item PWG-6200.06.04 (Provisional Quantity) | PWG¦Type 6¦Bend; 22.5+11.25 deg | 11309.4488 | 3053.5512 | 21.26%
PWG | Type 6 | Bend; 45 deg | Bend | 45 | DICL | 375 | 6 | each | 13458 |  | 2026-08-27 | Item PWG-6200.06.05 (Provisional Quantity); BoQ qty=8 vs register I=6 — verify | PWG¦Type 6¦Bend; 45 deg | 10596.8504 | 2861.1496 | 21.26%
PWG | Type 6 | Bend; MS - 31.9° | Bend | 31.9 | MSCL | 450 | 1 | each | 22689 | 2 | 2026-08-27 | Item PWG-6200.06.10b (Provisional Quantity) — covers 22.6°–45° range (31.9° & 37.4° cuts) | PWG¦Type 6¦Bend; MS - 31.9° | 17865.3543 | 4823.6457 | 21.26%
PWG | Type 6 | Bend; MS - 37.4° | Bend | 37.4 | MSCL | 450 | 1 | each | 22689 | 2 | 2026-08-27 | Item PWG-6200.06.10b (Provisional Quantity) — covers 22.6°–45° range (31.9° & 37.4° cuts) | PWG¦Type 6¦Bend; MS - 37.4° | 17865.3543 | 4823.6457 | 21.26%
PWG | Type 6 | Tee; DN375XDN150 DIFBE SCOUR TEE | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 2 | each |  |  |  |  | PWG¦Type 6¦Tee; DN375XDN150 DIFBE SCOUR TEE | 0
PWG — Thrust block Type 7 | [13 empty] | 0
PWG | Type 7 | Bend; 11.25 deg | Bend | 11.25 | DICL | 375 | 46 | each | 12566 |  | 2026-08-27 | Item PWG-6200.07.01 (Provisional Quantity) | PWG¦Type 7¦Bend; 11.25 deg | 9894.4882 | 2671.5118 | 21.26%
PWG | Type 7 | Bend; 22.5 deg | Bend | 22.5 | DICL | 375 | 11 | each | 12690 |  | 2026-08-27 | Item PWG-6200.07.02 (Provisional Quantity) | PWG¦Type 7¦Bend; 22.5 deg | 9992.126 | 2697.874 | 21.26%
PWG | Type 7 | Tee; DN375XDN150 DIFBE SCOUR TEE | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 21 | each |  |  |  |  | PWG¦Type 7¦Tee; DN375XDN150 DIFBE SCOUR TEE | 0
PWG — Thrust block Type 9 | [13 empty] | 0
PWG | Type 9 | Bend; 11.25 deg | Bend | 11.25 | DICL | 375 | 4 | each | 12764 |  | 2026-08-27 | Item PWG-6200.09.01 (Provisional Quantity) | PWG¦Type 9¦Bend; 11.25 deg | 10050.3937 | 2713.6063 | 21.26%
PWG | Type 9 | Bend; MS - 8.9° | Bend | 8.9 | MSCL | 450 | 1 | each | 12887 | 1 | 2026-08-27 | Item PWG-6200.09.10a (Provisional Quantity) | PWG¦Type 9¦Bend; MS - 8.9° | 10147.2441 | 2739.7559 | 21.26%
PWG — Thrust block Type 10 | [13 empty] | 0
PWG | Type 10 | Bend; MS - 10.3° | Bend | 10.3 | MSCL | 450 | 1 | each | 49855 | 1 | 2026-08-27 | Item PWG-6200.10.10a (Provisional Quantity) — covers up to 22.5° bracket (10.3° & 10.6° cuts) | PWG¦Type 10¦Bend; MS - 10.3° | 39255.9055 | 10599.0945 | 21.26%
PWG | Type 10 | Bend; MS - 10.6° | Bend | 10.6 | MSCL | 450 | 1 | each | 49855 | 1 | 2026-08-27 | Item PWG-6200.10.10a (Provisional Quantity) — covers up to 22.5° bracket (10.3° & 10.6° cuts) | PWG¦Type 10¦Bend; MS - 10.6° | 39255.9055 | 10599.0945 | 21.26%
PWG — Thrust block Type 11 | [13 empty] | 0
PWG | Type 11 | Bend; 11.25 deg | Bend | 11.25 | DICL | 375 | 4 | each | 28674 |  | 2026-08-27 | Item PWG-6200.11.01 (Provisional Quantity); BoQ qty=3 vs register I=4 — verify | PWG¦Type 11¦Bend; 11.25 deg | 22577.9528 | 6096.0472 | 21.26%
PWG | Type 11 | Bend; MS - 10.1° | Bend | 10.1 | MSCL | 450 | 1 | each | 35673 | 1 | 2026-08-27 | Item PWG-6200.11.10a (Provisional Quantity) — covers up to 22.5° bracket (10.1° & 8.9° cuts) | PWG¦Type 11¦Bend; MS - 10.1° | 28088.9764 | 7584.0236 | 21.26%
PWG | Type 11 | Bend; MS - 8.9° | Bend | 8.9 | MSCL | 450 | 1 | each | 35673 | 1 | 2026-08-27 | Item PWG-6200.11.10a (Provisional Quantity) — covers up to 22.5° bracket (10.1° & 8.9° cuts) | PWG¦Type 11¦Bend; MS - 8.9° | 28088.9764 | 7584.0236 | 21.26%
PWG — Thrust block Type 12
PWG | Type 12 | Isolation valve | Isolation Valve |  |  | 375 | 1 | each |  |  |  |  | PWG¦Type 12¦Isolation valve
PWG — Thrust block Type 13
PWG | Type 13 | Isolation valve | Isolation Valve |  |  | 375 | 5 | each |  |  |  |  | PWG¦Type 13¦Isolation valve
PWG — Thrust block 2 x Type 13
PWG | 2 x Type 13 | Pigging station | Pigging Station |  |  | 375 | 6 | each |  |  |  |  | PWG¦2 x Type 13¦Pigging station
Off the pipeline alignment
RHF — Thrust block RHF TYPE 1
RHF | RHF TYPE 1 | Facility thrust block | Facility |  |  |  | 5 | each |  |  |  |  | RHF¦RHF TYPE 1¦Facility thrust block
RHF — Thrust block TYPE 1
RHF | TYPE 1 | Facility thrust block | Facility |  |  |  | 1 | each |  |  |  |  | RHF¦TYPE 1¦Facility thrust block
RHF — Thrust block RHF TYPE 2
RHF | RHF TYPE 2 | Facility thrust block | Facility |  |  |  | 2 | each |  |  |  |  | RHF¦RHF TYPE 2¦Facility thrust block
RHF — Thrust block RHF TYPE 3
RHF | RHF TYPE 3 | Facility thrust block | Facility |  |  |  | 1 | each |  |  |  |  | RHF¦RHF TYPE 3¦Facility thrust block
RHF — Thrust block RHF TYPE 4
RHF | RHF TYPE 4 | Facility thrust block | Facility |  |  |  | 4 | each |  |  |  |  | RHF¦RHF TYPE 4¦Facility thrust block
Blank rate = not yet priced. A blank rate gives a blank cost, never a zero.
Table 5 — Bends, rate per bend, by section and bend class
Every bend in the Bend register, priced as its own item. Jerry confirmed 27 Aug 2026 that the Table 4 thrust block rate does not cover the fitting, so a bend is billed here and its block is billed on Table 4.
DICL bends are the three standard angles the pipe is designed around — 11.25, 22.5 and 45 degrees. Every other angle is a mitred MSCL bend, priced by CUT COUNT, which is how the schedule of rates prices them (items ...10a / 10b / 10c each cover a band of angles).
The cut boundary is 12 degrees. Table 4 records 1 cut for every mitred bend up to 10.6 deg and 2 cuts for every one from 13.9 deg up, so 12 sits inside the gap and no existing block is reclassified.
Fitting Material and Fitting DN (mm) on the Master Register are DERIVED on that same rule. It was checked against the 155 bends that sit at the exact chainage of a thrust block: 138 of 138 standard-angle bends are DICL there and 14 of 14 non-standard are MSCL. No exceptions.
Pipeline Section | Bend Rate Class | Description | Material | DN (mm) | Bends | Unit | Rate | Effective From | Rate Source / Basis | Lookup Key | Cost Rate | Margin ($) | Margin %
PHW — Bends
PHW | 11.25 | Bend; 11.25 deg DICL | DICL | 600 | 27 | each |  |  | Not yet priced — enter the BoQ item and rate | PHW¦11.25
PHW | 22.5 | Bend; 22.5 deg DICL | DICL | 600 | 18 | each |  |  | Not yet priced — enter the BoQ item and rate | PHW¦22.5
PHW | 45 | Bend; 45 deg DICL | DICL | 600 | 18 | each |  |  | Not yet priced — enter the BoQ item and rate | PHW¦45
PHW | Mitred 1-cut | Bend; MSCL mitred, 1 cut (6.8–11.3 deg) | MSCL | 650 | 13 | each |  |  | Not yet priced — enter the BoQ item and rate | PHW¦Mitred 1-cut
PHW | Mitred 2-cut | Bend; MSCL mitred, 2 cuts (13.9–47.1 deg) | MSCL | 650 | 18 | each |  |  | Not yet priced — enter the BoQ item and rate | PHW¦Mitred 2-cut
PWG — Bends
PWG | 11.25 | Bend; 11.25 deg DICL | DICL | 375 | 54 | each |  |  | Not yet priced — enter the BoQ item and rate | PWG¦11.25
PWG | 22.5 | Bend; 22.5 deg DICL | DICL | 375 | 21 | each |  |  | Not yet priced — enter the BoQ item and rate | PWG¦22.5
PWG | 45 | Bend; 45 deg DICL | DICL | 375 | 16 | each |  |  | Not yet priced — enter the BoQ item and rate | PWG¦45
PWG | Mitred 1-cut | Bend; MSCL mitred, 1 cut (6–11.9 deg) | MSCL | 450 | 14 | each |  |  | Not yet priced — enter the BoQ item and rate | PWG¦Mitred 1-cut
PWG | Mitred 2-cut | Bend; MSCL mitred, 2 cuts (12.8–39.1 deg) | MSCL | 450 | 12 | each |  |  | Not yet priced — enter the BoQ item and rate | PWG¦Mitred 2-cut
Bends in register |  |  |  |  | 211 |  |  |  | Blank rate = not priced. It gives a blank cost, never zero.
Table 6 — Valves, rate per valve, by section and valve class
Every valve in the Valve register, priced as its own item, on the same basis as Table 5.
Air valves (AV) and scour valves (SCV) appear nowhere else in this workbook — they are the two that were carrying no cost at all.
Isolation valves (IV) and pigging stations (PIG) ALSO have a thrust block on Table 4, one for one: 5 PHW and 6 PWG isolation valves, 2 PHW and 3 PWG pigging stations, matching exactly. The valve is billed here and the block is billed there. If a rate is ever entered that covers both, enter it once and leave the other blank.
Valve Type is the type number off the valve schedule, carried through from the source register.
Pipeline Section | Valve Class | Valve Type | Description | DN (mm) | Valves | Unit | Rate | Effective From | Rate Source / Basis | Lookup Key | Cost Rate | Margin ($) | Margin %
PHW — Valves
PHW | AV | 1A | Air valve — type 1A | 600 | 25 | each |  |  | Not yet priced — enter the BoQ item and rate | PHW¦AV¦1A
PHW | AV | 1B | Air valve — type 1B | 600 | 4 | each |  |  | Not yet priced — enter the BoQ item and rate | PHW¦AV¦1B
PHW | AV | 2 | Air valve — type 2 | 600 | 5 | each |  |  | Not yet priced — enter the BoQ item and rate | PHW¦AV¦2
PHW | SCV | 1B | Scour valve — type 1B | 600 | 16 | each |  |  | Not yet priced — enter the BoQ item and rate | PHW¦SCV¦1B
PHW | SCV | 1E | Scour valve — type 1E | 600 | 1 | each |  |  | Not yet priced — enter the BoQ item and rate | PHW¦SCV¦1E
PHW | SCV | 2 | Scour valve — type 2 | 600 | 1 | each |  |  | Not yet priced — enter the BoQ item and rate | PHW¦SCV¦2
PHW | IV | 3 | Isolation valve — type 3 | 600 | 3 | each |  |  | Not yet priced. Also carries a Table 4 thrust block — do not price the same scope twice. | PHW¦IV¦3
PHW | IV | RHS | Isolation valve — type RHS | 600 | 1 | each |  |  | Not yet priced. Also carries a Table 4 thrust block — do not price the same scope twice. | PHW¦IV¦RHS
PHW | IV | SPECIAL | Isolation valve — type SPECIAL | 600 | 1 | each |  |  | Not yet priced. Also carries a Table 4 thrust block — do not price the same scope twice. | PHW¦IV¦SPECIAL
PHW | PIG |  | Pigging station | 600 | 2 | each |  |  | Not yet priced. Also carries a Table 4 thrust block — do not price the same scope twice. | PHW¦PIG¦
PWG — Valves
PWG | AV | 1A | Air valve — type 1A | 375 | 22 | each |  |  | Not yet priced — enter the BoQ item and rate | PWG¦AV¦1A
PWG | AV | 1B | Air valve — type 1B | 375 | 7 | each |  |  | Not yet priced — enter the BoQ item and rate | PWG¦AV¦1B
PWG | AV | 2 | Air valve — type 2 | 375 | 6 | each |  |  | Not yet priced — enter the BoQ item and rate | PWG¦AV¦2
PWG | SCV | 1B | Scour valve — type 1B | 375 | 18 | each |  |  | Not yet priced — enter the BoQ item and rate | PWG¦SCV¦1B
PWG | SCV | 1E | Scour valve — type 1E | 375 | 2 | each |  |  | Not yet priced — enter the BoQ item and rate | PWG¦SCV¦1E
PWG | SCV | 2 | Scour valve — type 2 | 375 | 6 | each |  |  | Not yet priced — enter the BoQ item and rate | PWG¦SCV¦2
PWG | IV | 1 | Isolation valve — type 1 | 375 | 1 | each |  |  | Not yet priced. Also carries a Table 4 thrust block — do not price the same scope twice. | PWG¦IV¦1
PWG | IV | 2 | Isolation valve — type 2 | 375 | 1 | each |  |  | Not yet priced. Also carries a Table 4 thrust block — do not price the same scope twice. | PWG¦IV¦2
PWG | IV | 3 | Isolation valve — type 3 | 375 | 4 | each |  |  | Not yet priced. Also carries a Table 4 thrust block — do not price the same scope twice. | PWG¦IV¦3
PWG | PIG |  | Pigging station | 375 | 3 | each |  |  | Not yet priced. Also carries a Table 4 thrust block — do not price the same scope twice. | PWG¦PIG¦
Valves in register |  |  |  |  | 129 |  |  |  | Blank rate = not priced. It gives a blank cost, never zero.

## Plant and Labour Rates
Plant and Labour Rates
An hourly rate for every resource the End of day page records. Cost Rate is what the hour costs us and is what the day’s profit is worked out from.
Charge Rate is only for work done on dayworks, where hours are billed rather than metres. Leave it blank for anything covered by the schedule of rates — charging by the metre and by the hour would count it twice.
Description must match what is typed on the End of day page. The standing crew on Settings is a good place to keep the wording consistent.
Type | Description | Unit | Charge Rate ($/h) | Cost Rate ($/h) | Margin ($/h) | Notes | Totals
Labour | Supervisor | hour | 150 | 80 | 70 |  | Resources rated | 5
Labour | Pipe crew | hour | 150 | 65 | 85 |  | Average cost $/h | 165
Labour | Welder | hour | 200 | 80 | 120
Labour | Trades assistant | hour
Labour | Traffic controller | hour
Labour | Surveyor | hour
Plant | Excavator 30t | hour | 600 | 350 | 250
Plant | Excavator 20t | hour | 400 | 250 | 150
Plant | Sideboom | hour
Plant | Padding machine | hour
Plant | Dozer | hour
Plant | Compactor | hour
Plant | Water cart | hour
Plant | Float | hour
Subcontractor |  | hour

## Cost Tracker - Linear
Cost Tracker - Linear — trench and pipe by chainage
One row per trench section, all 207 of them, in chainage order. Chainage, length and trench type are READ from the Master Register by Record Key — they are not typed here and cannot be edited here.
Rates are READ from Rate Library, keyed on pipeline section: trench by Section + Trench Type, pipe by Section + Pipe Type. Budget = full length x rate. Earned = metres complete x rate.
EDIT ONLY THE YELLOW COLUMNS: Pipe Type, Trench Complete (m), Pipe Laid (m), As At Date, Updated By, Notes. Everything else is a formula.
PIPE IS NOW TRACKED ON ITS OWN SHEET. Cost Tracker - Pipe holds all 409 pipe segments and is what Cost Dashboard reads. The pipe columns here (N to S) are kept so the End of day page keeps working, but they no longer feed any total.
Record Key | Master Row | Pipeline Section | Chainage Start (m) | Chainage End (m) | Length (m) | Trench Type | Trench Rate ($/m) | Trench Budget ($) | Trench Complete (m) | Trench % | Trench Earned ($) | Pipe Type | Pipe Rate ($/m) | Pipe Budget ($) | Pipe Laid (m) | Pipe % | Pipe Earned ($) | Total Budget ($) | Total Earned ($) | Remaining ($) | Combined % | As At Date | Updated By | Notes | Trench Front (m) | Derived - the front of continuous completed trench. A gap left behind holds it back.
PHW-TT-0001 | 1 | PHW | 0 | 327.039 | 327.039 | 1A | 448.79 | 146771.8328 | 327.039 |  |  | DICL | 485.45 | 158761.0825 | 327.039 | 0% | 0 | 305532.9154 | 0 | 305532.9154 | 0% | 2026-08-28 | Jerry KH |  | 0
PHW-TT-0002 | 35 | PHW | 327.039 | 404.862 | 77.823 | 8A |  |  | 77.823 |  |  | DICL |  |  | 77.823 | [6 empty] | 2026-08-28 | Jerry KH |  | 0
PHW-TT-0003 | 41 | PHW | 404.862 | 426.39 | 21.528 | 4 | 1151.8 | 24795.9504 | 21.528 |  |  | DICL |  |  | 15.138 |  |  | 24795.9504 |  | 24795.9504 | 0% | 2026-08-28 | Jerry KH |  | 0
PHW-TT-0004 | 43 | PHW | 426.39 | 878.592 | 452.202 | 1A | 448.79 | 202943.7356 | 33.61 | [8 empty] | 202943.7356 |  | 202943.7356 | 0% | 2026-08-28 | Jerry KH |  | 0
PHW-TT-0005 | 113 | PHW | 878.592 | 886.749 | 8.157 | 4 | 1151.8 | 9395.2326 | [9 empty] | 9395.2326 |  | 9395.2326 | 0% |  |  |  | 0
PHW-TT-0006 | 116 | PHW | 886.749 | 955.896 | 69.147 | 7 | 1794.4 | 124077.3768 | [9 empty] | 124077.3768 |  | 124077.3768 | 0% |  |  |  | 0
PHW-TT-0007 | 136 | PHW | 955.896 | 960.896 | 5 | 4&7 | 1584 | 7920 | [9 empty] | 7920 |  | 7920 | 0% |  |  |  | 0
PHW-TT-0008 | 139 | PHW | 960.896 | 1092.896 | 132 | 7 | 1794.4 | 236860.8 | [9 empty] | 236860.8 |  | 236860.8 | 0% |  |  |  | 0
PHW-TT-0009 | 175 | PHW | 1092.896 | 1116.806 | 23.91 | 4&7 | 1584 | 37873.44 | [9 empty] | 37873.44 |  | 37873.44 | 0% |  |  |  | 0
PHW-TT-0010 | 180 | PHW | 1116.806 | 1135.078 | 18.272 | 7 | 1794.4 | 32787.2768 | [9 empty] | 32787.2768 |  | 32787.2768 | 0% |  |  |  | 0
PHW-TT-0011 | 182 | PHW | 1135.078 | 1142.896 | 7.818 | 1A | 448.79 | 3508.6402 | [9 empty] | 3508.6402 |  | 3508.6402 | 0% |  |  |  | 0
PHW-TT-0012 | 186 | PHW | 1142.896 | 1182.245 | 39.349 | 4 | 1151.8 | 45322.1782 | [9 empty] | 45322.1782 |  | 45322.1782 | 0% |  |  |  | 0
PHW-TT-0013 | 189 | PHW | 1182.245 | 1217.093 | 34.848 | 1A | 448.79 | 15639.4339 | [9 empty] | 15639.4339 |  | 15639.4339 | 0% |  |  |  | 0
PHW-TT-0014 | 199 | PHW | 1217.093 | 1232.924 | 15.831 | 4 | 1151.8 | 18234.1458 | [9 empty] | 18234.1458 |  | 18234.1458 | 0% |  |  |  | 0
PHW-TT-0015 | 202 | PHW | 1232.924 | 1255.696 | 22.772 | 8A | [18 empty] | 0
PHW-TT-0016 | 207 | PHW | 1255.696 | 1733.958 | 478.262 | 1A | 448.79 | 214639.203 | [9 empty] | 214639.203 |  | 214639.203 | 0% |  |  |  | 0
PHW-TT-0017 | 270 | PHW | 1733.958 | 1787.137 | 53.179 | 5 | 1597.6 | 84958.7704 | [9 empty] | 84958.7704 |  | 84958.7704 | 0% |  |  |  | 0
PHW-TT-0018 | 278 | PHW | 1787.137 | 2036.932 | 249.795 | 1A | 448.79 | 112105.498 | [9 empty] | 112105.498 |  | 112105.498 | 0% |  |  |  | 0
PHW-TT-0019 | 308 | PHW | 2036.932 | 2038.507 | 1.575 | 4 | 1151.8 | 1814.085 | [9 empty] | 1814.085 |  | 1814.085 | 0% |  |  |  | 0
PHW-TT-0020 | 312 | PHW | 2038.507 | 2110.24 | 71.733 | 8A | [18 empty] | 0
PHW-TT-0021 | 318 | PHW | 2110.24 | 2122.834 | 12.594 | 4 | 1151.8 | 14505.7692 | [9 empty] | 14505.7692 |  | 14505.7692 | 0% |  |  |  | 0
PHW-TT-0022 | 321 | PHW | 2122.834 | 2468.34 | 345.506 | 1A | 448.79 | 155059.6377 | [9 empty] | 155059.6377 |  | 155059.6377 | 0% |  |  |  | 0
PHW-TT-0023 | 365 | PHW | 2468.34 | 2500.706 | 32.366 | 4 | 1151.8 | 37279.1588 | [9 empty] | 37279.1588 |  | 37279.1588 | 0% |  |  |  | 0
PHW-TT-0024 | 370 | PHW | 2500.706 | 2791.911 | 291.205 | 1A | 448.79 | 130689.892 | [9 empty] | 130689.892 |  | 130689.892 | 0% |  |  |  | 0
PHW-TT-0025 | 394 | PHW | 2791.911 | 2813.28 | 21.369 | 4 | 1151.8 | 24612.8142 | [9 empty] | 24612.8142 |  | 24612.8142 | 0% |  |  |  | 0
PHW-TT-0026 | 408 | PHW | 2813.28 | 2846.195 | 32.915 | 1A | 448.79 | 14771.9229 | [9 empty] | 14771.9229 |  | 14771.9229 | 0% |  |  |  | 0
PHW-TT-0027 | 412 | PHW | 2846.195 | 2881.928 | 35.733 | 4 | 1151.8 | 41157.2694 | [9 empty] | 41157.2694 |  | 41157.2694 | 0% |  |  |  | 0
PHW-TT-0028 | 414 | PHW | 2881.928 | 3534.937 | 653.009 | 1A | 448.79 | 293063.9091 | [9 empty] | 293063.9091 |  | 293063.9091 | 0% |  |  |  | 0
PHW-TT-0029 | 451 | PHW | 3534.937 | 3547.077 | 12.14 | 4 | 1151.8 | 13982.852 | [9 empty] | 13982.852 |  | 13982.852 | 0% |  |  |  | 0
PHW-TT-0030 | 460 | PHW | 3547.077 | 4416.742 | 869.665 | 1A | 448.79 | 390296.9554 | [9 empty] | 390296.9554 |  | 390296.9554 | 0% |  |  |  | 0
PHW-TT-0031 | 508 | PHW | 4416.742 | 4455.042 | 38.3 | 8A | [18 empty] | 0
PHW-TT-0032 | 516 | PHW | 4455.042 | 4534.979 | 79.937 | 4 | 1151.8 | 92071.4366 | [9 empty] | 92071.4366 |  | 92071.4366 | 0% |  |  |  | 0
PHW-TT-0033 | 522 | PHW | 4534.979 | 4663.144 | 128.165 | 1A | 448.79 | 57519.1704 | [9 empty] | 57519.1704 |  | 57519.1704 | 0% |  |  |  | 0
PHW-TT-0034 | 529 | PHW | 4663.144 | 4695.751 | 32.607 | 5 | 1597.6 | 52092.9432 | [9 empty] | 52092.9432 |  | 52092.9432 | 0% |  |  |  | 0
PHW-TT-0035 | 532 | PHW | 4695.751 | 4712.804 | 17.053 | 2 | 994 | 16950.682 | [9 empty] | 16950.682 |  | 16950.682 | 0% |  |  |  | 0
PHW-TT-0036 | 534 | PHW | 4712.804 | 4758.731 | 45.927 | 1A/1B/1C | 477.6 | 21934.7352 | [9 empty] | 21934.7352 |  | 21934.7352 | 0% |  |  |  | 0
PHW-TT-0037 | 536 | PHW | 4758.731 | 5731.564 | 972.833 | 1A | 448.79 | 436597.7221 | [9 empty] | 436597.7221 |  | 436597.7221 | 0% |  |  |  | 0
PHW-TT-0038 | 612 | PHW | 5731.564 | 5754.45 | 22.886 | 4 | 1151.8 | 26360.0948 | [9 empty] | 26360.0948 |  | 26360.0948 | 0% |  |  |  | 0
PHW-TT-0039 | 622 | PHW | 5754.45 | 6114.476 | 360.026 | 1A | 448.79 | 161576.0685 | [9 empty] | 161576.0685 |  | 161576.0685 | 0% |  |  |  | 0
PHW-TT-0040 | 685 | PHW | 6114.476 | 6160.84 | 46.364 | 4 | 1151.8 | 53402.0552 | [9 empty] | 53402.0552 |  | 53402.0552 | 0% |  |  |  | 0
PHW-TT-0041 | 690 | PHW | 6160.84 | 6368.309 | 207.469 | 1A | 448.79 | 93110.0125 | [9 empty] | 93110.0125 |  | 93110.0125 | 0% |  |  |  | 0
PHW-TT-0042 | 719 | PHW | 6368.309 | 6392.653 | 24.344 | 6 | 1917 | 46667.448 | [9 empty] | 46667.448 |  | 46667.448 | 0% |  |  |  | 0
PHW-TT-0043 | 722 | PHW | 6392.653 | 6481.011 | 88.358 | 1A | 448.79 | 39654.1868 | [9 empty] | 39654.1868 |  | 39654.1868 | 0% |  |  |  | 0
PHW-TT-0044 | 734 | PHW | 6481.011 | 6506.275 | 25.264 | 4 | 1151.8 | 29099.0752 | [9 empty] | 29099.0752 |  | 29099.0752 | 0% |  |  |  | 0
PHW-TT-0045 | 738 | PHW | 6506.275 | 6772.73 | 266.455 | 1A | 448.79 | 119582.3394 | [9 empty] | 119582.3394 |  | 119582.3394 | 0% |  |  |  | 0
PHW-TT-0046 | 745 | PHW | 6772.73 | 6792.875 | 20.145 | 5 | 1597.6 | 32183.652 | [9 empty] | 32183.652 |  | 32183.652 | 0% |  |  |  | 0
PHW-TT-0047 | 749 | PHW | 6792.875 | 6886.695 | 93.82 | 1A | 448.79 | 42105.4778 | [9 empty] | 42105.4778 |  | 42105.4778 | 0% |  |  |  | 0
PHW-TT-0048 | 753 | PHW | 6886.695 | 6934.724 | 48.029 | 5 | 1597.6 | 76731.1304 | [9 empty] | 76731.1304 |  | 76731.1304 | 0% |  |  |  | 0
PHW-TT-0049 | 757 | PHW | 6934.724 | 6980.09 | 45.366 | 1A | 448.79 | 20359.8071 | [9 empty] | 20359.8071 |  | 20359.8071 | 0% |  |  |  | 0
PHW-TT-0050 | 764 | PHW | 6980.09 | 7035.325 | 55.235 | 8A | [18 empty] | 0
PHW-TT-0051 | 778 | PHW | 7035.325 | 7046.827 | 11.502 | 4 | 1151.8 | 13248.0036 | [9 empty] | 13248.0036 |  | 13248.0036 | 0% |  |  |  | 0
PHW-TT-0052 | 780 | PHW | 7046.827 | 7819.18 | 772.353 | 1A | 448.79 | 346624.3029 | [9 empty] | 346624.3029 |  | 346624.3029 | 0% |  |  |  | 0
PHW-TT-0053 | 792 | PHW | 7819.18 | 7833.422 | 14.242 | 7 | 1794.4 | 25555.8448 | [9 empty] | 25555.8448 |  | 25555.8448 | 0% |  |  |  | 0
PHW-TT-0054 | 793 | PHW | 7833.422 | 8192.409 | 358.987 | 1A | 448.79 | 161109.7757 | [9 empty] | 161109.7757 |  | 161109.7757 | 0% |  |  |  | 0
PHW-TT-0055 | 812 | PHW | 8192.409 | 8250.538 | 58.129 | 1B/1C | 410.3 | 23850.3287 | [9 empty] | 23850.3287 |  | 23850.3287 | 0% |  |  |  | 0
PHW-TT-0056 | 817 | PHW | 8250.538 | 9069.736 | 819.198 | 1A | 448.79 | 367647.8704 | [9 empty] | 367647.8704 |  | 367647.8704 | 0% |  |  |  | 0
PHW-TT-0057 | 848 | PHW | 9069.736 | 9078.356 | 8.62 | 4 | 1151.8 | 9928.516 | [9 empty] | 9928.516 |  | 9928.516 | 0% |  |  |  | 0
PHW-TT-0058 | 851 | PHW | 9078.356 | 9087.51 | 9.154 | 1A | 448.79 | 4108.2237 | [9 empty] | 4108.2237 |  | 4108.2237 | 0% |  |  |  | 0
PHW-TT-0059 | 853 | PHW | 9087.51 | 9105.7 | 18.19 | 4 | 1151.8 | 20951.242 | [9 empty] | 20951.242 |  | 20951.242 | 0% |  |  |  | 0
PHW-TT-0060 | 855 | PHW | 9105.7 | 9330.84 | 225.14 | 1A | 448.79 | 101040.5806 | [9 empty] | 101040.5806 |  | 101040.5806 | 0% |  |  |  | 0
PHW-TT-0061 | 874 | PHW | 9330.84 | 9333.706 | 2.866 | 2 | 994 | 2848.804 | [9 empty] | 2848.804 |  | 2848.804 | 0% |  |  |  | 0
PHW-TT-0062 | 876 | PHW | 9333.706 | 9341.679 | 7.973 | 1A/1B/1C | 477.6 | 3807.9048 | [9 empty] | 3807.9048 |  | 3807.9048 | 0% |  |  |  | 0
PHW-TT-0063 | 878 | PHW | 9341.679 | 9431.212 | 89.533 | 1A | 448.79 | 40181.5151 | [9 empty] | 40181.5151 |  | 40181.5151 | 0% |  |  |  | 0
PHW-TT-0064 | 883 | PHW | 9431.212 | 9437.047 | 5.835 | 2 | 994 | 5799.99 | [9 empty] | 5799.99 |  | 5799.99 | 0% |  |  |  | 0
PHW-TT-0065 | 885 | PHW | 9437.047 | 9446.253 | 9.206 | 1A/1B/1C | 477.6 | 4396.7856 | [9 empty] | 4396.7856 |  | 4396.7856 | 0% |  |  |  | 0
PHW-TT-0066 | 888 | PHW | 9446.253 | 10080.68 | 634.427 | 1A | 448.79 | 284724.4933 | [9 empty] | 284724.4933 |  | 284724.4933 | 0% |  |  |  | 0
PHW-TT-0067 | 925 | PHW | 10080.68 | 10101.635 | 20.955 | 5 | 1597.6 | 33477.708 | [9 empty] | 33477.708 |  | 33477.708 | 0% |  |  |  | 0
PHW-TT-0068 | 928 | PHW | 10101.635 | 10347.95 | 246.315 | 1A | 448.79 | 110543.7088 | [9 empty] | 110543.7088 |  | 110543.7088 | 0% |  |  |  | 0
PHW-TT-0069 | 941 | PHW | 10347.95 | 10367.669 | 19.719 | 6 | 1917 | 37801.323 | [9 empty] | 37801.323 |  | 37801.323 | 0% |  |  |  | 0
PHW-TT-0070 | 942 | PHW | 10367.669 | 10531.389 | 163.72 | 1A | 448.79 | 73475.8988 | [9 empty] | 73475.8988 |  | 73475.8988 | 0% |  |  |  | 0
PHW-TT-0071 | 951 | PHW | 10531.389 | 10582.353 | 50.964 | 4 | 1151.8 | 58700.3352 | [9 empty] | 58700.3352 |  | 58700.3352 | 0% |  |  |  | 0
PHW-TT-0072 | 955 | PHW | 10582.353 | 10645.383 | 63.03 | 8A | [18 empty] | 0
PHW-TT-0073 | 965 | PHW | 10645.383 | 10684.369 | 38.986 | 4 | 1151.8 | 44904.0748 | [9 empty] | 44904.0748 |  | 44904.0748 | 0% |  |  |  | 0
PHW-TT-0074 | 969 | PHW | 10684.369 | 11171.188 | 486.819 | 1A | 448.79 | 218479.499 | [9 empty] | 218479.499 |  | 218479.499 | 0% |  |  |  | 0
PHW-TT-0075 | 983 | PHW | 11171.188 | 11191.258 | 20.07 | 6 | 1917 | 38474.19 | [9 empty] | 38474.19 |  | 38474.19 | 0% |  |  |  | 0
PHW-TT-0076 | 988 | PHW | 11191.258 | 11382.203 | 190.945 | 1A | 448.79 | 85694.2065 | [9 empty] | 85694.2065 |  | 85694.2065 | 0% |  |  |  | 0
PHW-TT-0077 | 997 | PHW | 11382.203 | 11427.143 | 44.94 | 4 | 1151.8 | 51761.892 | [9 empty] | 51761.892 |  | 51761.892 | 0% |  |  |  | 0
PHW-TT-0078 | 1002 | PHW | 11427.143 | 11509.11 | 81.967 | 8A | [18 empty] | 0
PHW-TT-0079 | 1004 | PHW | 11509.11 | 11589.46 | 80.35 | 5 | 1597.6 | 128367.16 | [9 empty] | 128367.16 |  | 128367.16 | 0% |  |  |  | 0
PHW-TT-0080 | 1017 | PHW | 11589.46 | 11596.46 | 7 | 1A | 448.79 | 3141.53 | [9 empty] | 3141.53 |  | 3141.53 | 0% |  |  |  | 0
PHW-TT-0081 | 1022 | PHW | 11596.46 | 11750.532 | 154.072 | 5 | 1597.6 | 246145.4272 | [9 empty] | 246145.4272 |  | 246145.4272 | 0% |  |  |  | 0
PHW-TT-0082 | 1028 | PHW | 11750.532 | 12441.199 | 690.667 | 1A | 448.79 | 309964.4429 | [9 empty] | 309964.4429 |  | 309964.4429 | 0% |  |  |  | 0
PHW-TT-0083 | 1031 | PHW | 12441.199 | 12457.644 | 16.445 | 4 | 1151.8 | 18941.351 | [9 empty] | 18941.351 |  | 18941.351 | 0% |  |  |  | 0
PHW-TT-0084 | 1034 | PHW | 12457.644 | 12471.05 | 13.406 | 7 | 1794.4 | 24055.7264 | [9 empty] | 24055.7264 |  | 24055.7264 | 0% |  |  |  | 0
PHW-TT-0085 | 1042 | PHW | 12471.05 | 13274.77 | 803.72 | 1A | 448.79 | 360701.4988 | [9 empty] | 360701.4988 |  | 360701.4988 | 0% |  |  |  | 0
PHW-TT-0086 | 1068 | PHW | 13274.77 | 13346.374 | 71.604 | 8A | [18 empty] | 0
PHW-TT-0087 | 1076 | PHW | 13346.374 | 14778.123 | 1431.749 | 1A | 448.79 | 642554.6337 | [9 empty] | 642554.6337 |  | 642554.6337 | 0% |  |  |  | 0
PHW-TT-0088 | 1124 | PHW | 14778.123 | 14806.133 | 28.01 | 4 | 1151.8 | 32261.918 | [9 empty] | 32261.918 |  | 32261.918 | 0% |  |  |  | 0
PHW-TT-0089 | 1129 | PHW | 14806.133 | 14839.513 | 33.38 | 8A | [18 empty] | 0
PHW-TT-0090 | 1134 | PHW | 14839.513 | 15743.419 | 903.906 | 1A | 448.79 | 405663.9737 | [9 empty] | 405663.9737 |  | 405663.9737 | 0% |  |  |  | 0
PHW-TT-0091 | 1151 | PHW | 15743.419 | 15762.576 | 19.157 | 6 | 1917 | 36723.969 | [9 empty] | 36723.969 |  | 36723.969 | 0% |  |  |  | 0
PHW-TT-0092 | 1156 | PHW | 15762.576 | 16145.329 | 382.753 | 1A | 448.79 | 171775.7189 | [9 empty] | 171775.7189 |  | 171775.7189 | 0% |  |  |  | 0
PHW-TT-0093 | 1160 | PHW | 16145.329 | 16226.018 | 80.689 | 1A/1B/1C | 477.6 | 38537.0664 | [9 empty] | 38537.0664 |  | 38537.0664 | 0% |  |  |  | 0
PHW-TT-0094 | 1163 | PHW | 16226.018 | 16956.128 | 730.11 | 1A | 448.79 | 327666.0669 | [9 empty] | 327666.0669 |  | 327666.0669 | 0% |  |  |  | 0
PHW-TT-0095 | 1167 | PHW | 16956.128 | 17043.684 | 87.556 | 5 | 1597.6 | 139879.4656 | [9 empty] | 139879.4656 |  | 139879.4656 | 0% |  |  |  | 0
PHW-TT-0096 | 1180 | PHW | 17043.684 | 17910.948 | 867.264 | 1A | 448.79 | 389219.4106 | [9 empty] | 389219.4106 |  | 389219.4106 | 0% |  |  |  | 0
PHW-TT-0097 | 1185 | PHW | 17910.948 | 17996.139 | 85.191 | 4 | 1151.8 | 98122.9938 | [9 empty] | 98122.9938 |  | 98122.9938 | 0% |  |  |  | 0
PHW-TT-0098 | 1189 | PHW | 17996.139 | 18075.205 | 79.066 | 1A | 448.79 | 35484.0301 | [9 empty] | 35484.0301 |  | 35484.0301 | 0% |  |  |  | 0
PHW-TT-0099 | 1195 | PHW | 18075.205 | 18080.497 | 5.292 | 4 | 1151.8 | 6095.3256 | [9 empty] | 6095.3256 |  | 6095.3256 | 0% |  |  |  | 0
PHW-TT-0100 | 1199 | PHW | 18080.497 | 19120.154 | 1039.657 | 1A | 448.79 | 466587.665 | [9 empty] | 466587.665 |  | 466587.665 | 0% |  |  |  | 0
PHW-TT-0101 | 1245 | PHW | 19120.154 | 19155.385 | 35.231 | 5 | 1597.6 | 56285.0456 | [9 empty] | 56285.0456 |  | 56285.0456 | 0% |  |  |  | 0
PHW-TT-0102 | 1265 | PHW | 19155.385 | 19156.739 | 1.354 | 1A | 448.79 | 607.6617 | [9 empty] | 607.6617 |  | 607.6617 | 0% |  |  |  | 0
PWG-TT-0001 | 1275 | PWG | 0 | 3.804 | 3.804 | 1A | 369.11 | 1404.0944 | [9 empty] | 1404.0944 |  | 1404.0944 | 0% |  |  |  | 0
PWG-TT-0002 | 1280 | PWG | 3.804 | 6.229 | 2.425 | 4 | 916.6 | 2222.755 | [9 empty] | 2222.755 |  | 2222.755 | 0% |  |  |  | 0
PWG-TT-0003 | 1281 | PWG | 6.229 | 14.172 | 7.943 | 1A | 369.11 | 2931.8407 | [9 empty] | 2931.8407 |  | 2931.8407 | 0% |  |  |  | 0
PWG-TT-0004 | 1287 | PWG | 14.172 | 42.513 | 28.341 | 7 | 565.9 | 16038.1719 | [9 empty] | 16038.1719 |  | 16038.1719 | 0% |  |  |  | 0
PWG-TT-0005 | 1292 | PWG | 42.513 | 823.6 | 781.087 | 1A | 369.11 | 288307.0226 | [9 empty] | 288307.0226 |  | 288307.0226 | 0% |  |  |  | 0
PWG-TT-0006 | 1323 | PWG | 823.6 | 889.23 | 65.63 | 5 | 1448 | 95032.24 | [9 empty] | 95032.24 |  | 95032.24 | 0% |  |  |  | 0
PWG-TT-0007 | 1325 | PWG | 889.23 | 929.856 | 40.626 | 1A/1B/1C | 398.2 | 16177.2732 | [9 empty] | 16177.2732 |  | 16177.2732 | 0% |  |  |  | 0
PWG-TT-0008 | 1330 | PWG | 929.856 | 1181.379 | 251.523 | 1A | 369.11 | 92839.6545 | [9 empty] | 92839.6545 |  | 92839.6545 | 0% |  |  |  | 0
PWG-TT-0009 | 1336 | PWG | 1181.379 | 1186.379 | 5 | 4 | 916.6 | 4583 | [9 empty] | 4583 |  | 4583 | 0% |  |  |  | 0
PWG-TT-0010 | 1339 | PWG | 1186.379 | 1488.93 | 302.551 | 1A | 369.11 | 111674.5996 | [9 empty] | 111674.5996 |  | 111674.5996 | 0% |  |  |  | 0
PWG-TT-0011 | 1351 | PWG | 1488.93 | 1507.505 | 18.575 | 7 | 565.9 | 10511.5925 | [9 empty] | 10511.5925 |  | 10511.5925 | 0% |  |  |  | 0
PWG-TT-0012 | 1357 | PWG | 1507.505 | 1856.862 | 349.357 | 1A | 369.11 | 128951.1623 | [9 empty] | 128951.1623 |  | 128951.1623 | 0% |  |  |  | 0
PWG-TT-0013 | 1370 | PWG | 1856.862 | 1876.481 | 19.619 | 7 | 565.9 | 11102.3921 | [9 empty] | 11102.3921 |  | 11102.3921 | 0% |  |  |  | 0
PWG-TT-0014 | 1376 | PWG | 1876.481 | 1888.54 | 12.059 | 1A | 369.11 | 4451.0975 | [9 empty] | 4451.0975 |  | 4451.0975 | 0% |  |  |  | 0
PWG-TT-0015 | 1380 | PWG | 1888.54 | 1902.016 | 13.476 | 4&7 | 1638 | 22073.688 | [9 empty] | 22073.688 |  | 22073.688 | 0% |  |  |  | 0
PWG-TT-0016 | 1384 | PWG | 1902.016 | 2043.24 | 141.224 | 1A | 369.11 | 52127.1906 | [9 empty] | 52127.1906 |  | 52127.1906 | 0% |  |  |  | 0
PWG-TT-0017 | 1388 | PWG | 2043.24 | 2048.591 | 5.351 | 4 | 916.6 | 4904.7266 | [9 empty] | 4904.7266 |  | 4904.7266 | 0% |  |  |  | 0
PWG-TT-0018 | 1391 | PWG | 2048.591 | 2413.402 | 364.811 | 1A | 369.11 | 134655.3882 | [9 empty] | 134655.3882 |  | 134655.3882 | 0% |  |  |  | 0
PWG-TT-0019 | 1400 | PWG | 2413.402 | 2564.395 | 150.993 | 4 | 916.6 | 138400.1838 | [9 empty] | 138400.1838 |  | 138400.1838 | 0% |  |  |  | 0
PWG-TT-0020 | 1406 | PWG | 2564.395 | 2592.076 | 27.681 | 4&6 | 2190 | 60621.39 | [9 empty] | 60621.39 |  | 60621.39 | 0% |  |  |  | 0
PWG-TT-0021 | 1411 | PWG | 2592.076 | 2631.951 | 39.875 | 1A | 369.11 | 14718.2612 | [9 empty] | 14718.2612 |  | 14718.2612 | 0% |  |  |  | 0
PWG-TT-0022 | 1417 | PWG | 2631.951 | 2691.626 | 59.675 | 7 | 565.9 | 33770.0825 | [9 empty] | 33770.0825 |  | 33770.0825 | 0% |  |  |  | 0
PWG-TT-0023 | 1420 | PWG | 2691.626 | 2739.593 | 47.967 | 6 | 984 | 47199.528 | [9 empty] | 47199.528 |  | 47199.528 | 0% |  |  |  | 0
PWG-TT-0024 | 1424 | PWG | 2739.593 | 2750.013 | 10.42 | 4 | 916.6 | 9550.972 | [9 empty] | 9550.972 |  | 9550.972 | 0% |  |  |  | 0
PWG-TT-0025 | 1427 | PWG | 2750.013 | 2783.074 | 33.061 | 4&6 | 2190 | 72403.59 | [9 empty] | 72403.59 |  | 72403.59 | 0% |  |  |  | 0
PWG-TT-0026 | 1451 | PWG | 2783.074 | 2797.815 | 14.741 | 4 | 916.6 | 13511.6006 | [9 empty] | 13511.6006 |  | 13511.6006 | 0% |  |  |  | 0
PWG-TT-0027 | 1454 | PWG | 2797.815 | 2865.366 | 67.551 | 1A | 369.11 | 24933.7496 | [9 empty] | 24933.7496 |  | 24933.7496 | 0% |  |  |  | 0
PWG-TT-0028 | 1460 | PWG | 2865.366 | 2908.821 | 43.455 | 8A | [18 empty] | 0
PWG-TT-0029 | 1464 | PWG | 2908.821 | 3071.909 | 163.088 | 1A | 369.11 | 60197.4117 | [9 empty] | 60197.4117 |  | 60197.4117 | 0% |  |  |  | 0
PWG-TT-0030 | 1468 | PWG | 3071.909 | 3151.909 | 80 | 5 | 1448 | 115840 | [9 empty] | 115840 |  | 115840 | 0% |  |  |  | 0
PWG-TT-0031 | 1471 | PWG | 3151.909 | 3991.367 | 839.458 | 1A | 369.11 | 309852.3424 | [9 empty] | 309852.3424 |  | 309852.3424 | 0% |  |  |  | 0
PWG-TT-0032 | 1479 | PWG | 3991.367 | 4014.479 | 23.112 | 1A/1B/1C | 398.2 | 9203.1984 | [9 empty] | 9203.1984 |  | 9203.1984 | 0% |  |  |  | 0
PWG-TT-0033 | 1486 | PWG | 4014.479 | 5447.953 | 1433.474 | 1A | 369.11 | 529109.5881 | [9 empty] | 529109.5881 |  | 529109.5881 | 0% |  |  |  | 0
PWG-TT-0034 | 1500 | PWG | 5447.953 | 5475.997 | 28.044 | 5 | 1448 | 40607.712 | [9 empty] | 40607.712 |  | 40607.712 | 0% |  |  |  | 0
PWG-TT-0035 | 1507 | PWG | 5475.997 | 7092.671 | 1616.674 | 1A | 369.11 | 596730.5401 | [9 empty] | 596730.5401 |  | 596730.5401 | 0% |  |  |  | 0
PWG-TT-0036 | 1518 | PWG | 7092.671 | 7122.979 | 30.308 | 1A/1B/1C | 398.2 | 12068.6456 | [9 empty] | 12068.6456 |  | 12068.6456 | 0% |  |  |  | 0
PWG-TT-0037 | 1525 | PWG | 7122.979 | 7146.681 | 23.702 | 1A | 369.11 | 8748.6452 | [9 empty] | 8748.6452 |  | 8748.6452 | 0% |  |  |  | 0
PWG-TT-0038 | 1528 | PWG | 7146.681 | 7174.681 | 28 | 4 | 916.6 | 25664.8 | [9 empty] | 25664.8 |  | 25664.8 | 0% |  |  |  | 0
PWG-TT-0039 | 1530 | PWG | 7174.681 | 7539.66 | 364.979 | 1A | 369.11 | 134717.3987 | [9 empty] | 134717.3987 |  | 134717.3987 | 0% |  |  |  | 0
PWG-TT-0040 | 1537 | PWG | 7539.66 | 7547.413 | 7.753 | 4 | 916.6 | 7106.3998 | [9 empty] | 7106.3998 |  | 7106.3998 | 0% |  |  |  | 0
PWG-TT-0041 | 1544 | PWG | 7547.413 | 7579 | 31.587 | 8A | [18 empty] | 0
PWG-TT-0042 | 1548 | PWG | 7579 | 7624.121 | 45.121 | 4 | 916.6 | 41357.9086 | [9 empty] | 41357.9086 |  | 41357.9086 | 0% |  |  |  | 0
PWG-TT-0043 | 1563 | PWG | 7624.121 | 7725.73 | 101.609 | 1A | 369.11 | 37504.898 | [9 empty] | 37504.898 |  | 37504.898 | 0% |  |  |  | 0
PWG-TT-0044 | 1574 | PWG | 7725.73 | 7742.01 | 16.28 | 7 | 565.9 | 9212.852 | [9 empty] | 9212.852 |  | 9212.852 | 0% |  |  |  | 0
PWG-TT-0045 | 1575 | PWG | 7742.01 | 7939.101 | 197.091 | 1A | 369.11 | 72748.259 | [9 empty] | 72748.259 |  | 72748.259 | 0% |  |  |  | 0
PWG-TT-0046 | 1585 | PWG | 7939.101 | 7941.464 | 2.363 | 4 | 916.6 | 2165.9258 | [9 empty] | 2165.9258 |  | 2165.9258 | 0% |  |  |  | 0
PWG-TT-0047 | 1587 | PWG | 7941.464 | 8288.124 | 346.66 | 1A | 369.11 | 127955.6726 | [9 empty] | 127955.6726 |  | 127955.6726 | 0% |  |  |  | 0
PWG-TT-0048 | 1614 | PWG | 8288.124 | 8315.201 | 27.077 | 8A | [18 empty] | 0
PWG-TT-0049 | 1623 | PWG | 8315.201 | 8323.259 | 8.058 | 1A | 369.11 | 2974.2884 | [9 empty] | 2974.2884 |  | 2974.2884 | 0% |  |  |  | 0
PWG-TT-0050 | 1625 | PWG | 8323.259 | 8335.614 | 12.355 | 4 | 916.6 | 11324.593 | [9 empty] | 11324.593 |  | 11324.593 | 0% |  |  |  | 0
PWG-TT-0051 | 1629 | PWG | 8335.614 | 8400.622 | 65.008 | 8A | [18 empty] | 0
PWG-TT-0052 | 1634 | PWG | 8400.622 | 8427.328 | 26.706 | 1A | 369.11 | 9857.4517 | [9 empty] | 9857.4517 |  | 9857.4517 | 0% |  |  |  | 0
PWG-TT-0053 | 1636 | PWG | 8427.328 | 8465.757 | 38.429 | 4 | 916.6 | 35224.0214 | [9 empty] | 35224.0214 |  | 35224.0214 | 0% |  |  |  | 0
PWG-TT-0054 | 1641 | PWG | 8465.757 | 8488.53 | 22.773 | 1A | 369.11 | 8405.742 | [9 empty] | 8405.742 |  | 8405.742 | 0% |  |  |  | 0
PWG-TT-0055 | 1654 | PWG | 8488.53 | 8542.069 | 53.539 | 8A | [18 empty] | 0
PWG-TT-0056 | 1658 | PWG | 8542.069 | 8545.354 | 3.285 | 4 | 916.6 | 3011.031 | [9 empty] | 3011.031 |  | 3011.031 | 0% |  |  |  | 0
PWG-TT-0057 | 1660 | PWG | 8545.354 | 8584.129 | 38.775 | 1A | 369.11 | 14312.2403 | [9 empty] | 14312.2403 |  | 14312.2403 | 0% |  |  |  | 0
PWG-TT-0058 | 1671 | PWG | 8584.129 | 8605.285 | 21.156 | 7 | 565.9 | 11972.1804 | [9 empty] | 11972.1804 |  | 11972.1804 | 0% |  |  |  | 0
PWG-TT-0059 | 1675 | PWG | 8605.285 | 8610.275 | 4.99 | 4&7 | 1638 | 8173.62 | [9 empty] | 8173.62 |  | 8173.62 | 0% |  |  |  | 0
PWG-TT-0060 | 1678 | PWG | 8610.275 | 8613.442 | 3.167 | 7 | 565.9 | 1792.2053 | [9 empty] | 1792.2053 |  | 1792.2053 | 0% |  |  |  | 0
PWG-TT-0061 | 1680 | PWG | 8613.442 | 8692.124 | 78.682 | 1A | 369.11 | 29042.313 | [9 empty] | 29042.313 |  | 29042.313 | 0% |  |  |  | 0
PWG-TT-0062 | 1684 | PWG | 8692.124 | 8706.792 | 14.668 | 4 | 916.6 | 13444.6888 | [9 empty] | 13444.6888 |  | 13444.6888 | 0% |  |  |  | 0
PWG-TT-0063 | 1687 | PWG | 8706.792 | 8808.151 | 101.359 | 1A | 369.11 | 37412.6205 | [9 empty] | 37412.6205 |  | 37412.6205 | 0% |  |  |  | 0
PWG-TT-0064 | 1690 | PWG | 8808.151 | 8858.11 | 49.959 | 7 | 565.9 | 28271.7981 | [9 empty] | 28271.7981 |  | 28271.7981 | 0% |  |  |  | 0
PWG-TT-0065 | 1692 | PWG | 8858.11 | 9100 | 241.89 | 1A | 369.11 | 89284.0179 | [9 empty] | 89284.0179 |  | 89284.0179 | 0% |  |  |  | 0
PWG-TT-0066 | 1697 | PWG | 9100 | 9154.955 | 54.955 | 7 | 565.9 | 31099.0345 | [9 empty] | 31099.0345 |  | 31099.0345 | 0% |  |  |  | 0
PWG-TT-0067 | 1701 | PWG | 9154.955 | 12307.423 | 3152.468 | 1A | 369.11 | 1163607.4635 | [9 empty] | 1163607.4635 |  | 1163607.4635 | 0% |  |  |  | 0
PWG-TT-0068 | 1784 | PWG | 12307.423 | 12320.895 | 13.472 | 6 | 984 | 13256.448 | [9 empty] | 13256.448 |  | 13256.448 | 0% |  |  |  | 0
PWG-TT-0069 | 1788 | PWG | 12320.895 | 12720.22 | 399.325 | 1A | 369.11 | 147394.8508 | [9 empty] | 147394.8508 |  | 147394.8508 | 0% |  |  |  | 0
PWG-TT-0070 | 1801 | PWG | 12720.22 | 12734.864 | 14.644 | 8A | [18 empty] | 0
PWG-TT-0071 | 1802 | PWG | 12734.864 | 13218.214 | 483.35 | 1A | 369.11 | 178409.3185 | [9 empty] | 178409.3185 |  | 178409.3185 | 0% |  |  |  | 0
PWG-TT-0072 | 1812 | PWG | 13218.214 | 13247.005 | 28.791 | 8A | [18 empty] | 0
PWG-TT-0073 | 1815 | PWG | 13247.005 | 13622.356 | 375.351 | 1A | 369.11 | 138545.8076 | [9 empty] | 138545.8076 |  | 138545.8076 | 0% |  |  |  | 0
PWG-TT-0074 | 1833 | PWG | 13622.356 | 13637.356 | 15 | 2 | 440 | 6600 | [9 empty] | 6600 |  | 6600 | 0% |  |  |  | 0
PWG-TT-0075 | 1835 | PWG | 13637.356 | 14060.93 | 423.574 | 1A | 369.11 | 156345.3991 | [9 empty] | 156345.3991 |  | 156345.3991 | 0% |  |  |  | 0
PWG-TT-0076 | 1837 | PWG | 14060.93 | 14076.214 | 15.284 | 1B/1C | 385 | 5884.34 | [9 empty] | 5884.34 |  | 5884.34 | 0% |  |  |  | 0
PWG-TT-0077 | 1841 | PWG | 14076.214 | 14139.442 | 63.228 | 5 | 1448 | 91554.144 | [9 empty] | 91554.144 |  | 91554.144 | 0% |  |  |  | 0
PWG-TT-0078 | 1850 | PWG | 14139.442 | 14178.758 | 39.316 | 1B/1C | 385 | 15136.66 | [9 empty] | 15136.66 |  | 15136.66 | 0% |  |  |  | 0
PWG-TT-0079 | 1857 | PWG | 14178.758 | 14224.068 | 45.31 | 5 | 1448 | 65608.88 | [9 empty] | 65608.88 |  | 65608.88 | 0% |  |  |  | 0
PWG-TT-0080 | 1866 | PWG | 14224.068 | 14259.827 | 35.759 | 1B/1C | 385 | 13767.215 | [9 empty] | 13767.215 |  | 13767.215 | 0% |  |  |  | 0
PWG-TT-0081 | 1872 | PWG | 14259.827 | 14304.298 | 44.471 | 1A | 369.11 | 16414.6908 | [9 empty] | 16414.6908 |  | 16414.6908 | 0% |  |  |  | 0
PWG-TT-0082 | 1874 | PWG | 14304.298 | 14374.64 | 70.342 | 4 | 916.6 | 64475.4772 | [9 empty] | 64475.4772 |  | 64475.4772 | 0% |  |  |  | 0
PWG-TT-0083 | 1876 | PWG | 14374.64 | 14402.293 | 27.653 | 1A | 369.11 | 10206.9988 | [9 empty] | 10206.9988 |  | 10206.9988 | 0% |  |  |  | 0
PWG-TT-0084 | 1878 | PWG | 14402.293 | 14410.112 | 7.819 | 4 | 916.6 | 7166.8954 | [9 empty] | 7166.8954 |  | 7166.8954 | 0% |  |  |  | 0
PWG-TT-0085 | 1880 | PWG | 14410.112 | 14525.498 | 115.386 | 1A | 369.11 | 42590.1265 | [9 empty] | 42590.1265 |  | 42590.1265 | 0% |  |  |  | 0
PWG-TT-0086 | 1883 | PWG | 14525.498 | 14572.298 | 46.8 | 8A | [18 empty] | 0
PWG-TT-0087 | 1885 | PWG | 14572.298 | 16409.05 | 1836.752 | 1A | 369.11 | 677963.5307 | [9 empty] | 677963.5307 |  | 677963.5307 | 0% |  |  |  | 0
PWG-TT-0088 | 1920 | PWG | 16409.05 | 16429.262 | 20.212 | 7 | 565.9 | 11437.9708 | [9 empty] | 11437.9708 |  | 11437.9708 | 0% |  |  |  | 0
PWG-TT-0089 | 1923 | PWG | 16429.262 | 18150.734 | 1721.472 | 1A | 369.11 | 635412.5299 | [9 empty] | 635412.5299 |  | 635412.5299 | 0% |  |  |  | 0
PWG-TT-0090 | 1963 | PWG | 18150.734 | 18166.781 | 16.047 | 8A | [18 empty] | 0
PWG-TT-0091 | 1968 | PWG | 18166.781 | 18217.47 | 50.689 | 1A | 369.11 | 18709.8168 | [9 empty] | 18709.8168 |  | 18709.8168 | 0% |  |  |  | 0
PWG-TT-0092 | 1977 | PWG | 18217.47 | 18231.348 | 13.878 | 6 | 984 | 13655.952 | [9 empty] | 13655.952 |  | 13655.952 | 0% |  |  |  | 0
PWG-TT-0093 | 1981 | PWG | 18231.348 | 22319.185 | 4087.837 | 1A | 369.11 | 1508861.5151 | [9 empty] | 1508861.5151 |  | 1508861.5151 | 0% |  |  |  | 0
PWG-TT-0094 | 2041 | PWG | 22319.185 | 22360.55 | 41.365 | 5 | 1448 | 59896.52 | [9 empty] | 59896.52 |  | 59896.52 | 0% |  |  |  | 0
PWG-TT-0095 | 2045 | PWG | 22360.55 | 24944.548 | 2583.998 | 1A | 369.11 | 953779.5018 | [9 empty] | 953779.5018 |  | 953779.5018 | 0% |  |  |  | 0
PWG-TT-0096 | 2092 | PWG | 24944.548 | 24954.52 | 9.972 | 1B/1C | 385 | 3839.22 | [9 empty] | 3839.22 |  | 3839.22 | 0% |  |  |  | 0
PWG-TT-0097 | 2095 | PWG | 24954.52 | 25018.345 | 63.825 | 5 | 1448 | 92418.6 | [9 empty] | 92418.6 |  | 92418.6 | 0% |  |  |  | 0
PWG-TT-0098 | 2099 | PWG | 25018.345 | 25052.461 | 34.116 | 1B/1C | 385 | 13134.66 | [9 empty] | 13134.66 |  | 13134.66 | 0% |  |  |  | 0
PWG-TT-0099 | 2104 | PWG | 25052.461 | 26010.44 | 957.979 | 1A | 369.11 | 353599.6287 | [9 empty] | 353599.6287 |  | 353599.6287 | 0% |  |  |  | 0
PWG-TT-0100 | 2148 | PWG | 26010.44 | 26026.47 | 16.03 | 6 | 984 | 15773.52 | [9 empty] | 15773.52 |  | 15773.52 | 0% |  |  |  | 0
PWG-TT-0101 | 2152 | PWG | 26026.47 | 26252.108 | 225.638 | 1A | 369.11 | 83285.2422 | [9 empty] | 83285.2422 |  | 83285.2422 | 0% |  |  |  | 0
PWG-TT-0102 | 2167 | PWG | 26252.108 | 26283.028 | 30.92 | 8A | [18 empty] | 0
PWG-TT-0103 | 2170 | PWG | 26283.028 | 26988.368 | 705.34 | 1A | 369.11 | 260348.0474 | [9 empty] | 260348.0474 |  | 260348.0474 | 0% |  |  |  | 0
PWG-TT-0104 | 2184 | PWG | 26988.368 | 27002.147 | 13.779 | 4 | 916.6 | 12629.8314 | [9 empty] | 12629.8314 |  | 12629.8314 | 0% |  |  |  | 0
PWG-TT-0105 | 2185 | PWG | 27002.147 | 27012.465 | 10.318 | 1A | 369.11 | 3808.477 | [9 empty] | 3808.477 |  | 3808.477 | 0% |  |  |  | 0
TOTAL |  |  |  |  | 46169.204 |  |  | 20707995.4865 | 0 | 0% | 0 |  |  | 158761.0825 | 0 | 0% | 0 | 20866756.5691 | 0 | 20866756.5691 | 0%
Legend
Yellow, blue text |  |  | You enter this. Pipe Type is a dropdown from Rate Library Table 2. Trench Complete (m) and Pipe Laid (m) drive every earned-value figure here and on Cost Dashboard.
Green text |  |  | Read from another sheet — Master Register (chainage, length, trench type) or Rate Library (rates). Do not type over these.
Black text |  |  | Calculated on this sheet.
Master Row |  |  | Working column: the Master Register row this record sits on, found by Record Key. Keeps the lookups on the right record even if the Master Register is re-sorted.
Assumptions
• |  |  | Progress is entered as METRES COMPLETE, not a percentage. Percentage is derived (metres / length) so a claimed percentage cannot drift away from the metres behind it.
• |  |  | Trench and pipe are tracked separately against the same chainage range: the trench is excavated before the pipe is laid in it, and the two are paid at different rates.
• |  |  | TRENCH RATES ARE PER PIPELINE SECTION. The same trench type is priced separately in PHW and in PWG because the construction differs. A rate entered against PHW 1A does not touch PWG 1A.
• |  |  | PIPE IS FOUR SEPARATE ASSETS: DICL and MSCL in each of PHW and PWG. PHW is DN600, PWG is DN375, so the four cannot share a metre rate. Pipe Type is chosen per trench section.
• |  |  | Pipe Type is BLANK on every row as delivered. A blank Pipe Type gives no pipe rate and so no pipe budget — pipe cost appears only on sections where a pipe type has been chosen. The MSCL lengths are the enveloper and casing runs; everything else is DICL carrier.
• |  |  | Length is the Master Register length (Chainage End - Chainage Start), not the Source Length (m) stated in the Trench Type Register. The two agree at 46,169.204 m over 207 sections.
• |  |  | Point assets (trench stops, bulkheads, thrust blocks, crossings) are NOT on this sheet. They are priced per item on the Master Register and rolled up separately on Cost Dashboard, so nothing is counted twice.

## Cost Tracker - Pipe
Cost Tracker - Pipe — one row per pipe segment, driven by chainage
All 409 pipe records from the Master Register, in chainage order. The pipe register is continuous: PHW runs 0 to 19,156.739 m over 200 segments and PWG 0 to 27,012.465 m over 209, with no gaps and no overlaps.
NOTHING IS TYPED ON THIS SHEET. Laid (m) is derived from the pipe front on Progress Control: a segment wholly behind the front is 100%, the segment the front sits inside is part complete, everything ahead is zero.
Pipe Type is read from the pipe description on the register, and the rate from Rate Library Table 2 on Pipeline Section and Pipe Type.
Record Key | Master Row | Section | Chainage Start (m) | Chainage End (m) | Length (m) | Pipe Description | Pipe Type | Rate ($/m) | Budget ($) | Laid (m) | Laid % | Earned ($) | Cost ($) | Margin ($) | Remaining ($) | Complete
PHW-PIPE-0001 | 2 | PHW | 0 | 150 | 150 | DN600 DICL PN35 | DICL | 485.45 | 72817.5 | 0 | 0% | 0 |  |  | 72817.5 | NO
PHW-PIPE-0002 | 10 | PHW | 150 | 225.345 | 75.345 | DN600 DICL PN35 | DICL | 485.45 | 36576.2303 | 0 | 0% | 0 |  |  | 36576.2303 | NO
PHW-PIPE-0003 | 16 | PHW | 225.345 | 236.345 | 11 | DN600 DICL PN35 | DICL | 485.45 | 5339.95 | 0 | 0% | 0 |  |  | 5339.95 | NO
PHW-PIPE-0004 | 19 | PHW | 236.345 | 321.539 | 85.194 | DN600 DICL PN35 | DICL | 485.45 | 41357.4273 | 0 | 0% | 0 |  |  | 41357.4273 | NO
PHW-PIPE-0005 | 32 | PHW | 321.539 | 327.039 | 5.5 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 7329.85 | 0 | 0% | 0 |  |  | 7329.85 | NO
PHW-PIPE-0006 | 36 | PHW | 327.039 | 404.862 | 77.823 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 + OD813 12WT MS Enveloper | MSCL | 1332.7 | 103714.7121 | 0 | 0% | 0 |  |  | 103714.7121 | NO
PHW-PIPE-0007 | 42 | PHW | 404.862 | 426.39 | 21.528 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 28690.3656 | 0 | 0% | 0 |  |  | 28690.3656 | NO
PHW-PIPE-0008 | 44 | PHW | 426.39 | 654.13 | 227.74 | DN600 DICL PN35 | DICL | 485.45 | 110556.383 | 0 | 0% | 0 |  |  | 110556.383 | NO
PHW-PIPE-0009 | 80 | PHW | 654.13 | 670.63 | 16.5 | DN600 DICL PN35 | DICL | 485.45 | 8009.925 | 0 | 0% | 0 |  |  | 8009.925 | NO
PHW-PIPE-0010 | 86 | PHW | 670.63 | 878.592 | 207.962 | DN600 DICL PN35 | DICL | 485.45 | 100955.1529 | 0 | 0% | 0 |  |  | 100955.1529 | NO
PHW-PIPE-0011 | 114 | PHW | 878.592 | 886.749 | 8.157 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 10870.8339 | 0 | 0% | 0 |  |  | 10870.8339 | NO
PHW-PIPE-0012 | 117 | PHW | 886.749 | 955.896 | 69.147 | DN600 DICL PN35 | DICL | 485.45 | 33567.4111 | 0 | 0% | 0 |  |  | 33567.4111 | NO
PHW-PIPE-0013 | 137 | PHW | 955.896 | 960.896 | 5 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 6663.5 | 0 | 0% | 0 |  |  | 6663.5 | NO
PHW-PIPE-0014 | 140 | PHW | 960.896 | 1092.896 | 132 | DN600 DICL PN35 | DICL | 485.45 | 64079.4 | 0 | 0% | 0 |  |  | 64079.4 | NO
PHW-PIPE-0015 | 176 | PHW | 1092.896 | 1116.896 | 24 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 31984.8 | 0 | 0% | 0 |  |  | 31984.8 | NO
PHW-PIPE-0016 | 181 | PHW | 1116.896 | 1135.078 | 18.182 | DN600 DICL PN35 | DICL | 485.45 | 8826.4519 | 0 | 0% | 0 |  |  | 8826.4519 | NO
PHW-PIPE-0017 | 183 | PHW | 1135.078 | 1142.896 | 7.818 | DN600 DICL PN35 | DICL | 485.45 | 3795.2481 | 0 | 0% | 0 |  |  | 3795.2481 | NO
PHW-PIPE-0018 | 187 | PHW | 1142.896 | 1182.245 | 39.349 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 52440.4123 | 0 | 0% | 0 |  |  | 52440.4123 | NO
PHW-PIPE-0019 | 190 | PHW | 1182.245 | 1217.093 | 34.848 | DN600 DICL PN35 | DICL | 485.45 | 16916.9616 | 0 | 0% | 0 |  |  | 16916.9616 | NO
PHW-PIPE-0020 | 200 | PHW | 1217.093 | 1232.924 | 15.831 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 21097.9737 | 0 | 0% | 0 |  |  | 21097.9737 | NO
PHW-PIPE-0021 | 203 | PHW | 1232.924 | 1255.696 | 22.772 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 + OD813 12WT MS Enveloper | MSCL | 1332.7 | 30348.2444 | 0 | 0% | 0 |  |  | 30348.2444 | NO
PHW-PIPE-0022 | 208 | PHW | 1255.696 | 1294.197 | 38.501 | DN600 DICL PN35 | DICL | 485.45 | 18690.3105 | 0 | 0% | 0 |  |  | 18690.3105 | NO
PHW-PIPE-0023 | 215 | PHW | 1294.197 | 1350.152 | 55.955 | DN600 DICL PN35 | DICL | 485.45 | 27163.3548 | 0 | 0% | 0 |  |  | 27163.3548 | NO
PHW-PIPE-0024 | 221 | PHW | 1350.152 | 1370.58 | 20.428 | DN600 DICL PN35 | DICL | 485.45 | 9916.7726 | 0 | 0% | 0 |  |  | 9916.7726 | NO
PHW-PIPE-0025 | 223 | PHW | 1370.58 | 1615.899 | 245.319 | DN600 DICL PN35 | DICL | 485.45 | 119090.1086 | 0 | 0% | 0 |  |  | 119090.1086 | NO
PHW-PIPE-0026 | 251 | PHW | 1615.899 | 1733.958 | 118.059 | DN600 DICL PN35 | DICL | 485.45 | 57311.7416 | 0 | 0% | 0 |  |  | 57311.7416 | NO
PHW-PIPE-0027 | 272 | PHW | 1733.958 | 1787.137 | 53.179 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 70871.6533 | 0 | 0% | 0 |  |  | 70871.6533 | NO
PHW-PIPE-0028 | 279 | PHW | 1787.137 | 1822.818 | 35.681 | DN600 DICL PN35 | DICL | 485.45 | 17321.3414 | 0 | 0% | 0 |  |  | 17321.3414 | NO
PHW-PIPE-0029 | 292 | PHW | 1822.818 | 2036.932 | 214.114 | DN600 DICL PN35 | DICL | 485.45 | 103941.6413 | 0 | 0% | 0 |  |  | 103941.6413 | NO
PHW-PIPE-0030 | 310 | PHW | 2036.932 | 2110.24 | 73.308 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 + OD813 15WT MS Enveloper | MSCL | 1332.7 | 97697.5716 | 0 | 0% | 0 |  |  | 97697.5716 | NO
PHW-PIPE-0031 | 319 | PHW | 2110.24 | 2122.834 | 12.594 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 16784.0238 | 0 | 0% | 0 |  |  | 16784.0238 | NO
PHW-PIPE-0032 | 322 | PHW | 2122.834 | 2468.34 | 345.506 | DN600 DICL PN35 | DICL | 485.45 | 167725.8877 | 0 | 0% | 0 |  |  | 167725.8877 | NO
PHW-PIPE-0033 | 366 | PHW | 2468.34 | 2500.706 | 32.366 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 43134.1682 | 0 | 0% | 0 |  |  | 43134.1682 | NO
PHW-PIPE-0034 | 372 | PHW | 2500.706 | 2561.973 | 61.267 | DN600 DICL PN35 | DICL | 485.45 | 29742.0651 | 0 | 0% | 0 |  |  | 29742.0651 | NO
PHW-PIPE-0035 | 382 | PHW | 2561.973 | 2791.911 | 229.938 | DN600 DICL PN35 | DICL | 485.45 | 111623.4021 | 0 | 0% | 0 |  |  | 111623.4021 | NO
PHW-PIPE-0036 | 395 | PHW | 2791.911 | 2813.28 | 21.369 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 28478.4663 | 0 | 0% | 0 |  |  | 28478.4663 | NO
PHW-PIPE-0037 | 409 | PHW | 2813.28 | 2846.195 | 32.915 | DN600 DICL PN35 | DICL | 485.45 | 15978.5868 | 0 | 0% | 0 |  |  | 15978.5868 | NO
PHW-PIPE-0038 | 413 | PHW | 2846.195 | 2881.928 | 35.733 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 47621.3691 | 0 | 0% | 0 |  |  | 47621.3691 | NO
PHW-PIPE-0039 | 415 | PHW | 2881.928 | 3457.556 | 575.628 | DN600 DICL PN35 | DICL | 485.45 | 279438.6126 | 0 | 0% | 0 |  |  | 279438.6126 | NO
PHW-PIPE-0040 | 448 | PHW | 3457.556 | 3487.105 | 29.549 | DN600 DICL PN35 | DICL | 485.45 | 14344.5621 | 0 | 0% | 0 |  |  | 14344.5621 | NO
PHW-PIPE-0041 | 449 | PHW | 3487.105 | 3534.937 | 47.832 | DN600 DICL PN35 | DICL | 485.45 | 23220.0444 | 0 | 0% | 0 |  |  | 23220.0444 | NO
PHW-PIPE-0042 | 453 | PHW | 3534.937 | 3547.079 | 12.142 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 16181.6434 | 0 | 0% | 0 |  |  | 16181.6434 | NO
PHW-PIPE-0043 | 461 | PHW | 3547.079 | 3785 | 237.921 | DN600 DICL PN35 | DICL | 485.45 | 115498.7495 | 0 | 0% | 0 |  |  | 115498.7495 | NO
PHW-PIPE-0044 | 471 | PHW | 3785 | 3832.98 | 47.98 | DN600 DICL PN35 | DICL | 485.45 | 23291.891 | 0 | 0% | 0 |  |  | 23291.891 | NO
PHW-PIPE-0045 | 472 | PHW | 3832.98 | 3859.762 | 26.782 | DN600 DICL PN35 | DICL | 485.45 | 13001.3219 | 0 | 0% | 0 |  |  | 13001.3219 | NO
PHW-PIPE-0046 | 484 | PHW | 3859.762 | 4085 | 225.238 | DN600 DICL PN35 | DICL | 485.45 | 109341.7871 | 0 | 0% | 0 |  |  | 109341.7871 | NO
PHW-PIPE-0047 | 487 | PHW | 4085 | 4100.183 | 15.183 | DN600 DICL PN35 | DICL | 485.45 | 7370.5873 | 0 | 0% | 0 |  |  | 7370.5873 | NO
PHW-PIPE-0048 | 488 | PHW | 4100.183 | 4111.325 | 11.142 | DN600 DICL PN35 | DICL | 485.45 | 5408.8839 | 0 | 0% | 0 |  |  | 5408.8839 | NO
PHW-PIPE-0049 | 491 | PHW | 4111.325 | 4314.51 | 203.185 | DN600 DICL PN35 | DICL | 485.45 | 98636.1583 | 0 | 0% | 0 |  |  | 98636.1583 | NO
PHW-PIPE-0050 | 498 | PHW | 4314.51 | 4339.807 | 25.297 | DN600 DICL PN35 | DICL | 485.45 | 12280.4286 | 0 | 0% | 0 |  |  | 12280.4286 | NO
PHW-PIPE-0051 | 503 | PHW | 4339.807 | 4416.742 | 76.935 | DN600 DICL PN35 | DICL | 485.45 | 37348.0958 | 0 | 0% | 0 |  |  | 37348.0958 | NO
PHW-PIPE-0052 | 509 | PHW | 4416.742 | 4455.042 | 38.3 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 + OD813 12WT MS Enveloper | MSCL | 1332.7 | 51042.41 | 0 | 0% | 0 |  |  | 51042.41 | NO
PHW-PIPE-0053 | 517 | PHW | 4455.042 | 4534.797 | 79.755 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 106289.4885 | 0 | 0% | 0 |  |  | 106289.4885 | NO
PHW-PIPE-0054 | 521 | PHW | 4534.797 | 4663.144 | 128.347 | DN600 DICL PN35 | DICL | 485.45 | 62306.0512 | 0 | 0% | 0 |  |  | 62306.0512 | NO
PHW-PIPE-0055 | 530 | PHW | 4663.144 | 4695.751 | 32.607 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 43455.3489 | 0 | 0% | 0 |  |  | 43455.3489 | NO
PHW-PIPE-0056 | 533 | PHW | 4695.751 | 4712.804 | 17.053 | DN600 DICL PN35 | DICL | 485.45 | 8278.3788 | 0 | 0% | 0 |  |  | 8278.3788 | NO
PHW-PIPE-0057 | 535 | PHW | 4712.804 | 4758.731 | 45.927 | DN600 DICL PN35 | DICL | 485.45 | 22295.2621 | 0 | 0% | 0 |  |  | 22295.2621 | NO
PHW-PIPE-0058 | 537 | PHW | 4758.731 | 4857.072 | 98.341 | DN600 DICL PN35 | DICL | 485.45 | 47739.6385 | 0 | 0% | 0 |  |  | 47739.6385 | NO
PHW-PIPE-0059 | 538 | PHW | 4857.072 | 4971.37 | 114.298 | DN600 DICL PN35 | DICL | 485.45 | 55485.9641 | 0 | 0% | 0 |  |  | 55485.9641 | NO
PHW-PIPE-0060 | 554 | PHW | 4971.37 | 5175.571 | 204.201 | DN600 DICL PN35 | DICL | 485.45 | 99129.3755 | 0 | 0% | 0 |  |  | 99129.3755 | NO
PHW-PIPE-0061 | 555 | PHW | 5175.571 | 5323.75 | 148.179 | DN600 DICL PN35 | DICL | 485.45 | 71933.4956 | 0 | 0% | 0 |  |  | 71933.4956 | NO
PHW-PIPE-0062 | 564 | PHW | 5323.75 | 5600 | 276.25 | DN600 DICL PN35 | DICL | 485.45 | 134105.5625 | 0 | 0% | 0 |  |  | 134105.5625 | NO
PHW-PIPE-0063 | 599 | PHW | 5600 | 5731.564 | 131.564 | DN600 DICL PN35 | DICL | 485.45 | 63867.7438 | 0 | 0% | 0 |  |  | 63867.7438 | NO
PHW-PIPE-0064 | 613 | PHW | 5731.564 | 5754.45 | 22.886 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 30500.1722 | 0 | 0% | 0 |  |  | 30500.1722 | NO
PHW-PIPE-0065 | 623 | PHW | 5754.45 | 5897.237 | 142.787 | DN600 DICL PN35 | DICL | 485.45 | 69315.9492 | 0 | 0% | 0 |  |  | 69315.9492 | NO
PHW-PIPE-0066 | 653 | PHW | 5897.237 | 6114.476 | 217.239 | DN600 DICL PN35 | DICL | 485.45 | 105458.6726 | 0 | 0% | 0 |  |  | 105458.6726 | NO
PHW-PIPE-0067 | 686 | PHW | 6114.476 | 6160.84 | 46.364 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 61789.3028 | 0 | 0% | 0 |  |  | 61789.3028 | NO
PHW-PIPE-0068 | 691 | PHW | 6160.84 | 6203.719 | 42.879 | DN600 DICL PN35 | DICL | 485.45 | 20815.6106 | 0 | 0% | 0 |  |  | 20815.6106 | NO
PHW-PIPE-0069 | 699 | PHW | 6203.719 | 6225 | 21.281 | DN600 DICL PN35 | DICL | 485.45 | 10330.8615 | 0 | 0% | 0 |  |  | 10330.8615 | NO
PHW-PIPE-0070 | 702 | PHW | 6225 | 6260 | 35 | DN600 DICL PN35 | DICL | 485.45 | 16990.75 | 0 | 0% | 0 |  |  | 16990.75 | NO
PHW-PIPE-0071 | 708 | PHW | 6260 | 6270 | 10 | DN600 DICL PN35 | DICL | 485.45 | 4854.5 | 0 | 0% | 0 |  |  | 4854.5 | NO
PHW-PIPE-0072 | 710 | PHW | 6270 | 6368.309 | 98.309 | DN600 DICL PN35 | DICL | 485.45 | 47724.1041 | 0 | 0% | 0 |  |  | 47724.1041 | NO
PHW-PIPE-0073 | 720 | PHW | 6368.309 | 6392.653 | 24.344 | DN600 DICL PN35 | DICL | 485.45 | 11817.7948 | 0 | 0% | 0 |  |  | 11817.7948 | NO
PHW-PIPE-0074 | 723 | PHW | 6392.653 | 6477.516 | 84.863 | DN600 DICL PN35 | DICL | 485.45 | 41196.7433 | 0 | 0% | 0 |  |  | 41196.7433 | NO
PHW-PIPE-0075 | 733 | PHW | 6477.516 | 6506.275 | 28.759 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 38327.1193 | 0 | 0% | 0 |  |  | 38327.1193 | NO
PHW-PIPE-0076 | 739 | PHW | 6506.275 | 6772.73 | 266.455 | DN600 DICL PN35 | DICL | 485.45 | 129350.5798 | 0 | 0% | 0 |  |  | 129350.5798 | NO
PHW-PIPE-0077 | 746 | PHW | 6772.73 | 6792.875 | 20.145 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 26847.2415 | 0 | 0% | 0 |  |  | 26847.2415 | NO
PHW-PIPE-0078 | 750 | PHW | 6792.875 | 6886.695 | 93.82 | DN600 DICL PN35 | DICL | 485.45 | 45544.919 | 0 | 0% | 0 |  |  | 45544.919 | NO
PHW-PIPE-0079 | 754 | PHW | 6886.695 | 6934.724 | 48.029 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 64008.2483 | 0 | 0% | 0 |  |  | 64008.2483 | NO
PHW-PIPE-0080 | 758 | PHW | 6934.724 | 6980.09 | 45.366 | DN600 DICL PN35 | DICL | 485.45 | 22022.9247 | 0 | 0% | 0 |  |  | 22022.9247 | NO
PHW-PIPE-0081 | 765 | PHW | 6980.09 | 7035.325 | 55.235 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 + OD813 12WT MS Enveloper | MSCL | 1332.7 | 73611.6845 | 0 | 0% | 0 |  |  | 73611.6845 | NO
PHW-PIPE-0082 | 779 | PHW | 7035.325 | 7046.827 | 11.502 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 15328.7154 | 0 | 0% | 0 |  |  | 15328.7154 | NO
PHW-PIPE-0083 | 781 | PHW | 7046.827 | 7328.079 | 281.252 | DN600 DICL PN35 | DICL | 485.45 | 136533.7834 | 0 | 0% | 0 |  |  | 136533.7834 | NO
PHW-PIPE-0084 | 782 | PHW | 7328.079 | 7338.213 | 10.134 | DN600 DICL PN35 | DICL | 485.45 | 4919.5503 | 0 | 0% | 0 |  |  | 4919.5503 | NO
PHW-PIPE-0085 | 785 | PHW | 7338.213 | 7795.276 | 457.063 | DN600 DICL PN35 | DICL | 485.45 | 221881.2333 | 0 | 0% | 0 |  |  | 221881.2333 | NO
PHW-PIPE-0086 | 790 | PHW | 7795.276 | 7845 | 49.724 | DN600 DICL PN35 | DICL | 485.45 | 24138.5158 | 0 | 0% | 0 |  |  | 24138.5158 | NO
PHW-PIPE-0087 | 795 | PHW | 7845 | 7882.79 | 37.79 | DN600 DICL PN35 | DICL | 485.45 | 18345.1555 | 0 | 0% | 0 |  |  | 18345.1555 | NO
PHW-PIPE-0088 | 802 | PHW | 7882.79 | 7972.409 | 89.619 | DN600 DICL PN35 | DICL | 485.45 | 43505.5435 | 0 | 0% | 0 |  |  | 43505.5435 | NO
PHW-PIPE-0089 | 809 | PHW | 7972.409 | 8192.409 | 220 | DN600 DICL PN35 | DICL | 485.45 | 106799 | 0 | 0% | 0 |  |  | 106799 | NO
PHW-PIPE-0090 | 813 | PHW | 8192.409 | 8250.538 | 58.129 | DN600 DICL PN35 | DICL | 485.45 | 28218.7231 | 0 | 0% | 0 |  |  | 28218.7231 | NO
PHW-PIPE-0091 | 818 | PHW | 8250.538 | 8375.652 | 125.114 | DN600 DICL PN35 | DICL | 485.45 | 60736.5913 | 0 | 0% | 0 |  |  | 60736.5913 | NO
PHW-PIPE-0092 | 833 | PHW | 8375.652 | 8857.962 | 482.31 | DN600 DICL PN35 | DICL | 485.45 | 234137.3895 | 0 | 0% | 0 |  |  | 234137.3895 | NO
PHW-PIPE-0093 | 840 | PHW | 8857.962 | 9053.682 | 195.72 | DN600 DICL PN35 | DICL | 485.45 | 95012.274 | 0 | 0% | 0 |  |  | 95012.274 | NO
PHW-PIPE-0094 | 843 | PHW | 9053.682 | 9069.736 | 16.054 | DN600 DICL PN35 | DICL | 485.45 | 7793.4143 | 0 | 0% | 0 |  |  | 7793.4143 | NO
PHW-PIPE-0095 | 849 | PHW | 9069.736 | 9078.356 | 8.62 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 11487.874 | 0 | 0% | 0 |  |  | 11487.874 | NO
PHW-PIPE-0096 | 852 | PHW | 9078.356 | 9087.51 | 9.154 | DN600 DICL PN35 | DICL | 485.45 | 4443.8093 | 0 | 0% | 0 |  |  | 4443.8093 | NO
PHW-PIPE-0097 | 854 | PHW | 9087.51 | 9105.7 | 18.19 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 24241.813 | 0 | 0% | 0 |  |  | 24241.813 | NO
PHW-PIPE-0098 | 856 | PHW | 9105.7 | 9330.884 | 225.184 | DN600 DICL PN35 | DICL | 485.45 | 109315.5728 | 0 | 0% | 0 |  |  | 109315.5728 | NO
PHW-PIPE-0099 | 875 | PHW | 9330.884 | 9333.706 | 2.822 | DN600 DICL PN35 | DICL | 485.45 | 1369.9399 | 0 | 0% | 0 |  |  | 1369.9399 | NO
PHW-PIPE-0100 | 877 | PHW | 9333.706 | 9341.679 | 7.973 | DN600 DICL PN35 | DICL | 485.45 | 3870.4928 | 0 | 0% | 0 |  |  | 3870.4928 | NO
PHW-PIPE-0101 | 879 | PHW | 9341.679 | 9431.212 | 89.533 | DN600 DICL PN35 | DICL | 485.45 | 43463.7948 | 0 | 0% | 0 |  |  | 43463.7948 | NO
PHW-PIPE-0102 | 884 | PHW | 9431.212 | 9437.047 | 5.835 | DN600 DICL PN35 | DICL | 485.45 | 2832.6008 | 0 | 0% | 0 |  |  | 2832.6008 | NO
PHW-PIPE-0103 | 886 | PHW | 9437.047 | 9446.253 | 9.206 | DN600 DICL PN35 | DICL | 485.45 | 4469.0527 | 0 | 0% | 0 |  |  | 4469.0527 | NO
PHW-PIPE-0104 | 889 | PHW | 9446.253 | 9510.598 | 64.345 | DN600 DICL PN35 | DICL | 485.45 | 31236.2802 | 0 | 0% | 0 |  |  | 31236.2802 | NO
PHW-PIPE-0105 | 898 | PHW | 9510.598 | 9698.209 | 187.611 | DN600 DICL PN35 | DICL | 485.45 | 91075.76 | 0 | 0% | 0 |  |  | 91075.76 | NO
PHW-PIPE-0106 | 904 | PHW | 9698.209 | 9793.567 | 95.358 | DN600 DICL PN35 | DICL | 485.45 | 46291.5411 | 0 | 0% | 0 |  |  | 46291.5411 | NO
PHW-PIPE-0107 | 907 | PHW | 9793.567 | 9808.864 | 15.297 | DN600 DICL PN35 | DICL | 485.45 | 7425.9287 | 0 | 0% | 0 |  |  | 7425.9287 | NO
PHW-PIPE-0108 | 910 | PHW | 9808.864 | 9960.086 | 151.222 | DN600 DICL PN35 | DICL | 485.45 | 73410.7199 | 0 | 0% | 0 |  |  | 73410.7199 | NO
PHW-PIPE-0109 | 916 | PHW | 9960.086 | 9997.286 | 37.2 | DN600 DICL PN35 | DICL | 485.45 | 18058.74 | 0 | 0% | 0 |  |  | 18058.74 | NO
PHW-PIPE-0110 | 924 | PHW | 9997.286 | 10080.68 | 83.394 | DN600 DICL PN35 | DICL | 485.45 | 40483.6173 | 0 | 0% | 0 |  |  | 40483.6173 | NO
PHW-PIPE-0111 | 926 | PHW | 10080.68 | 10101.635 | 20.955 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 27926.7285 | 0 | 0% | 0 |  |  | 27926.7285 | NO
PHW-PIPE-0112 | 929 | PHW | 10101.635 | 10344.417 | 242.782 | DN600 DICL PN35 | DICL | 485.45 | 117858.5219 | 0 | 0% | 0 |  |  | 117858.5219 | NO
PHW-PIPE-0113 | 940 | PHW | 10344.417 | 10367.669 | 23.252 | DN600 DICL PN35 | DICL | 485.45 | 11287.6834 | 0 | 0% | 0 |  |  | 11287.6834 | NO
PHW-PIPE-0114 | 943 | PHW | 10367.669 | 10378.599 | 10.93 | DN600 DICL PN35 | DICL | 485.45 | 5305.9685 | 0 | 0% | 0 |  |  | 5305.9685 | NO
PHW-PIPE-0115 | 947 | PHW | 10378.599 | 10531.389 | 152.79 | DN600 DICL PN35 | DICL | 485.45 | 74171.9055 | 0 | 0% | 0 |  |  | 74171.9055 | NO
PHW-PIPE-0116 | 952 | PHW | 10531.389 | 10582.353 | 50.964 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 67919.7228 | 0 | 0% | 0 |  |  | 67919.7228 | NO
PHW-PIPE-0117 | 956 | PHW | 10582.353 | 10654.383 | 72.03 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 + OD813 12WT MS Enveloper | MSCL | 1332.7 | 95994.381 | 0 | 0% | 0 |  |  | 95994.381 | NO
PHW-PIPE-0118 | 966 | PHW | 10654.383 | 10684.369 | 29.986 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 39962.3422 | 0 | 0% | 0 |  |  | 39962.3422 | NO
PHW-PIPE-0119 | 970 | PHW | 10684.369 | 10752.637 | 68.268 | DN600 DICL PN35 | DICL | 485.45 | 33140.7006 | 0 | 0% | 0 |  |  | 33140.7006 | NO
PHW-PIPE-0120 | 975 | PHW | 10752.637 | 10795 | 42.363 | DN600 DICL PN35 | DICL | 485.45 | 20565.1183 | 0 | 0% | 0 |  |  | 20565.1183 | NO
PHW-PIPE-0121 | 978 | PHW | 10795 | 10805 | 10 | DN600 DICL PN35 | DICL | 485.45 | 4854.5 | 0 | 0% | 0 |  |  | 4854.5 | NO
PHW-PIPE-0122 | 979 | PHW | 10805 | 10892.518 | 87.518 | DN600 DICL PN35 | DICL | 485.45 | 42485.6131 | 0 | 0% | 0 |  |  | 42485.6131 | NO
PHW-PIPE-0123 | 981 | PHW | 10892.518 | 10902.518 | 10 | DN600 DICL PN35 | DICL | 485.45 | 4854.5 | 0 | 0% | 0 |  |  | 4854.5 | NO
PHW-PIPE-0124 | 982 | PHW | 10902.518 | 11171.188 | 268.67 | DN600 DICL PN35 | DICL | 485.45 | 130425.8515 | 0 | 0% | 0 |  |  | 130425.8515 | NO
PHW-PIPE-0125 | 984 | PHW | 11171.188 | 11252.039 | 80.851 | DN600 DICL PN35 | DICL | 485.45 | 39249.118 | 0 | 0% | 0 |  |  | 39249.118 | NO
PHW-PIPE-0126 | 989 | PHW | 11252.039 | 11354.666 | 102.627 | DN600 DICL PN35 | DICL | 485.45 | 49820.2771 | 0 | 0% | 0 |  |  | 49820.2771 | NO
PHW-PIPE-0127 | 993 | PHW | 11354.666 | 11382.203 | 27.537 | DN600 DICL PN35 | DICL | 485.45 | 13367.8367 | 0 | 0% | 0 |  |  | 13367.8367 | NO
PHW-PIPE-0128 | 998 | PHW | 11382.203 | 11427.143 | 44.94 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 59891.538 | 0 | 0% | 0 |  |  | 59891.538 | NO
PHW-PIPE-0129 | 1003 | PHW | 11427.143 | 11509.11 | 81.967 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 + OD813 12WT MS Enveloper | MSCL | 1332.7 | 109237.4209 | 0 | 0% | 0 |  |  | 109237.4209 | NO
PHW-PIPE-0130 | 1005 | PHW | 11509.11 | 11561.518 | 52.408 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 69844.1416 | 0 | 0% | 0 |  |  | 69844.1416 | NO
PHW-PIPE-0131 | 1010 | PHW | 11561.518 | 11589.46 | 27.942 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 37238.3034 | 0 | 0% | 0 |  |  | 37238.3034 | NO
PHW-PIPE-0132 | 1019 | PHW | 11589.46 | 11596.46 | 7 | DN600 DICL PN35 | DICL | 485.45 | 3398.15 | 0 | 0% | 0 |  |  | 3398.15 | NO
PHW-PIPE-0133 | 1024 | PHW | 11596.46 | 11750.532 | 154.072 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 205331.7544 | 0 | 0% | 0 |  |  | 205331.7544 | NO
PHW-PIPE-0134 | 1029 | PHW | 11750.532 | 12441.199 | 690.667 | DN600 DICL PN35 | DICL | 485.45 | 335284.2952 | 0 | 0% | 0 |  |  | 335284.2952 | NO
PHW-PIPE-0135 | 1032 | PHW | 12441.199 | 12457.644 | 16.445 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 21916.2515 | 0 | 0% | 0 |  |  | 21916.2515 | NO
PHW-PIPE-0136 | 1035 | PHW | 12457.644 | 12471.05 | 13.406 | DN600 DICL PN35 | DICL | 485.45 | 6507.9427 | 0 | 0% | 0 |  |  | 6507.9427 | NO
PHW-PIPE-0137 | 1043 | PHW | 12471.05 | 12561.518 | 90.468 | DN600 DICL PN35 | DICL | 485.45 | 43917.6906 | 0 | 0% | 0 |  |  | 43917.6906 | NO
PHW-PIPE-0138 | 1046 | PHW | 12561.518 | 12641.845 | 80.327 | DN600 DICL PN35 | DICL | 485.45 | 38994.7421 | 0 | 0% | 0 |  |  | 38994.7421 | NO
PHW-PIPE-0139 | 1047 | PHW | 12641.845 | 12651.518 | 9.673 | DN600 DICL PN35 | DICL | 485.45 | 4695.7579 | 0 | 0% | 0 |  |  | 4695.7579 | NO
PHW-PIPE-0140 | 1049 | PHW | 12651.518 | 13230.192 | 578.674 | DN600 DICL PN35 | DICL | 485.45 | 280917.2933 | 0 | 0% | 0 |  |  | 280917.2933 | NO
PHW-PIPE-0141 | 1058 | PHW | 13230.192 | 13253 | 22.808 | DN600 DICL PN35 | DICL | 485.45 | 11072.1436 | 0 | 0% | 0 |  |  | 11072.1436 | NO
PHW-PIPE-0142 | 1065 | PHW | 13253 | 13265 | 12 | DN600 DICL PN35 | DICL | 485.45 | 5825.4 | 0 | 0% | 0 |  |  | 5825.4 | NO
PHW-PIPE-0143 | 1066 | PHW | 13265 | 13274.77 | 9.77 | DN600 DICL PN35 | DICL | 485.45 | 4742.8465 | 0 | 0% | 0 |  |  | 4742.8465 | NO
PHW-PIPE-0144 | 1069 | PHW | 13274.77 | 13346.374 | 71.604 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 + OD813 12WT MS Enveloper | MSCL | 1332.7 | 95426.6508 | 0 | 0% | 0 |  |  | 95426.6508 | NO
PHW-PIPE-0145 | 1077 | PHW | 13346.374 | 13376 | 29.626 | DN600 DICL PN35 | DICL | 485.45 | 14381.9417 | 0 | 0% | 0 |  |  | 14381.9417 | NO
PHW-PIPE-0146 | 1078 | PHW | 13376 | 13381 | 5 | DN600 DICL PN35 | DICL | 485.45 | 2427.25 | 0 | 0% | 0 |  |  | 2427.25 | NO
PHW-PIPE-0147 | 1079 | PHW | 13381 | 13515 | 134 | DN600 DICL PN35 | DICL | 485.45 | 65050.3 | 0 | 0% | 0 |  |  | 65050.3 | NO
PHW-PIPE-0148 | 1081 | PHW | 13515 | 13535.334 | 20.334 | DN600 DICL PN35 | DICL | 485.45 | 9871.1403 | 0 | 0% | 0 |  |  | 9871.1403 | NO
PHW-PIPE-0149 | 1083 | PHW | 13535.334 | 13576 | 40.666 | DN600 DICL PN35 | DICL | 485.45 | 19741.3097 | 0 | 0% | 0 |  |  | 19741.3097 | NO
PHW-PIPE-0150 | 1085 | PHW | 13576 | 13586 | 10 | DN600 DICL PN35 | DICL | 485.45 | 4854.5 | 0 | 0% | 0 |  |  | 4854.5 | NO
PHW-PIPE-0151 | 1086 | PHW | 13586 | 13620 | 34 | DN600 DICL PN35 | DICL | 485.45 | 16505.3 | 0 | 0% | 0 |  |  | 16505.3 | NO
PHW-PIPE-0152 | 1090 | PHW | 13620 | 13630 | 10 | DN600 DICL PN35 | DICL | 485.45 | 4854.5 | 0 | 0% | 0 |  |  | 4854.5 | NO
PHW-PIPE-0153 | 1092 | PHW | 13630 | 13698.342 | 68.342 | DN600 DICL PN35 | DICL | 485.45 | 33176.6239 | 0 | 0% | 0 |  |  | 33176.6239 | NO
PHW-PIPE-0154 | 1097 | PHW | 13698.342 | 13932.104 | 233.762 | DN600 DICL PN35 | DICL | 485.45 | 113479.7629 | 0 | 0% | 0 |  |  | 113479.7629 | NO
PHW-PIPE-0155 | 1098 | PHW | 13932.104 | 13965 | 32.896 | DN600 DICL PN35 | DICL | 485.45 | 15969.3632 | 0 | 0% | 0 |  |  | 15969.3632 | NO
PHW-PIPE-0156 | 1101 | PHW | 13965 | 14233.48 | 268.48 | DN600 DICL PN35 | DICL | 485.45 | 130333.616 | 0 | 0% | 0 |  |  | 130333.616 | NO
PHW-PIPE-0157 | 1109 | PHW | 14233.48 | 14242 | 8.52 | DN600 DICL PN35 | DICL | 485.45 | 4136.034 | 0 | 0% | 0 |  |  | 4136.034 | NO
PHW-PIPE-0158 | 1110 | PHW | 14242 | 14326.695 | 84.695 | DN600 DICL PN35 | DICL | 485.45 | 41115.1877 | 0 | 0% | 0 |  |  | 41115.1877 | NO
PHW-PIPE-0159 | 1115 | PHW | 14326.695 | 14335.85 | 9.155 | DN600 DICL PN35 | DICL | 485.45 | 4444.2948 | 0 | 0% | 0 |  |  | 4444.2948 | NO
PHW-PIPE-0160 | 1117 | PHW | 14335.85 | 14360 | 24.15 | DN600 DICL PN35 | DICL | 485.45 | 11723.6175 | 0 | 0% | 0 |  |  | 11723.6175 | NO
PHW-PIPE-0161 | 1119 | PHW | 14360 | 14366.236 | 6.236 | DN600 DICL PN35 | DICL | 485.45 | 3027.2662 | 0 | 0% | 0 |  |  | 3027.2662 | NO
PHW-PIPE-0162 | 1120 | PHW | 14366.236 | 14577.68 | 211.444 | DN600 DICL PN35 | DICL | 485.45 | 102645.4898 | 0 | 0% | 0 |  |  | 102645.4898 | NO
PHW-PIPE-0163 | 1121 | PHW | 14577.68 | 14589 | 11.32 | DN600 DICL PN35 | DICL | 485.45 | 5495.294 | 0 | 0% | 0 |  |  | 5495.294 | NO
PHW-PIPE-0164 | 1122 | PHW | 14589 | 14778.123 | 189.123 | DN600 DICL PN35 | DICL | 485.45 | 91809.7603 | 0 | 0% | 0 |  |  | 91809.7603 | NO
PHW-PIPE-0165 | 1125 | PHW | 14778.123 | 14806.133 | 28.01 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 37328.927 | 0 | 0% | 0 |  |  | 37328.927 | NO
PHW-PIPE-0166 | 1131 | PHW | 14806.133 | 14839.513 | 33.38 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 + OD813 12WT MS Enveloper | MSCL | 1332.7 | 44485.526 | 0 | 0% | 0 |  |  | 44485.526 | NO
PHW-PIPE-0167 | 1135 | PHW | 14839.513 | 14932.21 | 92.697 | DN600 DICL PN35 | DICL | 485.45 | 44999.7586 | 0 | 0% | 0 |  |  | 44999.7586 | NO
PHW-PIPE-0168 | 1137 | PHW | 14932.21 | 14940 | 7.79 | DN600 DICL PN35 | DICL | 485.45 | 3781.6555 | 0 | 0% | 0 |  |  | 3781.6555 | NO
PHW-PIPE-0169 | 1138 | PHW | 14940 | 15004.47 | 64.47 | DN600 DICL PN35 | DICL | 485.45 | 31296.9615 | 0 | 0% | 0 |  |  | 31296.9615 | NO
PHW-PIPE-0170 | 1140 | PHW | 15004.47 | 15011 | 6.53 | DN600 DICL PN35 | DICL | 485.45 | 3169.9885 | 0 | 0% | 0 |  |  | 3169.9885 | NO
PHW-PIPE-0171 | 1141 | PHW | 15011 | 15046.72 | 35.72 | DN600 DICL PN35 | DICL | 485.45 | 17340.274 | 0 | 0% | 0 |  |  | 17340.274 | NO
PHW-PIPE-0172 | 1142 | PHW | 15046.72 | 15072 | 25.28 | DN600 DICL PN35 | DICL | 485.45 | 12272.176 | 0 | 0% | 0 |  |  | 12272.176 | NO
PHW-PIPE-0173 | 1146 | PHW | 15072 | 15298.457 | 226.457 | DN600 DICL PN35 | DICL | 485.45 | 109933.5507 | 0 | 0% | 0 |  |  | 109933.5507 | NO
PHW-PIPE-0174 | 1149 | PHW | 15298.457 | 15743.419 | 444.962 | DN600 DICL PN35 | DICL | 485.45 | 216006.8029 | 0 | 0% | 0 |  |  | 216006.8029 | NO
PHW-PIPE-0175 | 1152 | PHW | 15743.419 | 15762.576 | 19.157 | DN600 DICL PN35 | DICL | 485.45 | 9299.7656 | 0 | 0% | 0 |  |  | 9299.7656 | NO
PHW-PIPE-0176 | 1157 | PHW | 15762.576 | 16145.329 | 382.753 | DN600 DICL PN35 | DICL | 485.45 | 185807.4439 | 0 | 0% | 0 |  |  | 185807.4439 | NO
PHW-PIPE-0177 | 1161 | PHW | 16145.329 | 16226.018 | 80.689 | DN600 DICL PN35 | DICL | 485.45 | 39170.4751 | 0 | 0% | 0 |  |  | 39170.4751 | NO
PHW-PIPE-0178 | 1164 | PHW | 16226.018 | 16956.128 | 730.11 | DN600 DICL PN35 | DICL | 485.45 | 354431.8995 | 0 | 0% | 0 |  |  | 354431.8995 | NO
PHW-PIPE-0179 | 1168 | PHW | 16956.128 | 16988.429 | 32.301 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 43047.5427 | 0 | 0% | 0 |  |  | 43047.5427 | NO
PHW-PIPE-0180 | 1174 | PHW | 16988.429 | 17043.684 | 55.255 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 73638.3385 | 0 | 0% | 0 |  |  | 73638.3385 | NO
PHW-PIPE-0181 | 1182 | PHW | 17043.684 | 17910.948 | 867.264 | DN600 DICL PN35 | DICL | 485.45 | 421013.3088 | 0 | 0% | 0 |  |  | 421013.3088 | NO
PHW-PIPE-0182 | 1186 | PHW | 17910.948 | 17996.139 | 85.191 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 113534.0457 | 0 | 0% | 0 |  |  | 113534.0457 | NO
PHW-PIPE-0183 | 1190 | PHW | 17996.139 | 18075.205 | 79.066 | DN600 DICL PN35 | DICL | 485.45 | 38382.5897 | 0 | 0% | 0 |  |  | 38382.5897 | NO
PHW-PIPE-0184 | 1196 | PHW | 18075.205 | 18080.497 | 5.292 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 7052.6484 | 0 | 0% | 0 |  |  | 7052.6484 | NO
PHW-PIPE-0185 | 1200 | PHW | 18080.497 | 18499.436 | 418.939 | DN600 DICL PN35 | DICL | 485.45 | 203373.9376 | 0 | 0% | 0 |  |  | 203373.9376 | NO
PHW-PIPE-0186 | 1203 | PHW | 18499.436 | 18545.51 | 46.074 | DN600 DICL PN35 | DICL | 485.45 | 22366.6233 | 0 | 0% | 0 |  |  | 22366.6233 | NO
PHW-PIPE-0187 | 1205 | PHW | 18545.51 | 18554 | 8.49 | DN600 DICL PN35 | DICL | 485.45 | 4121.4705 | 0 | 0% | 0 |  |  | 4121.4705 | NO
PHW-PIPE-0188 | 1206 | PHW | 18554 | 18614 | 60 | DN600 DICL PN35 | DICL | 485.45 | 29127 | 0 | 0% | 0 |  |  | 29127 | NO
PHW-PIPE-0189 | 1212 | PHW | 18614 | 18624 | 10 | DN600 DICL PN35 | DICL | 485.45 | 4854.5 | 0 | 0% | 0 |  |  | 4854.5 | NO
PHW-PIPE-0190 | 1213 | PHW | 18624 | 18752.41 | 128.41 | DN600 DICL PN35 | DICL | 485.45 | 62336.6345 | 0 | 0% | 0 |  |  | 62336.6345 | NO
PHW-PIPE-0191 | 1216 | PHW | 18752.41 | 18881.16 | 128.75 | DN600 DICL PN35 | DICL | 485.45 | 62501.6875 | 0 | 0% | 0 |  |  | 62501.6875 | NO
PHW-PIPE-0192 | 1218 | PHW | 18881.16 | 18890 | 8.84 | DN600 DICL PN35 | DICL | 485.45 | 4291.378 | 0 | 0% | 0 |  |  | 4291.378 | NO
PHW-PIPE-0193 | 1220 | PHW | 18890 | 19002.445 | 112.445 | DN600 DICL PN35 | DICL | 485.45 | 54586.4252 | 0 | 0% | 0 |  |  | 54586.4252 | NO
PHW-PIPE-0194 | 1222 | PHW | 19002.445 | 19047.78 | 45.335 | DN600 DICL PN35 | DICL | 485.45 | 22007.8757 | 0 | 0% | 0 |  |  | 22007.8757 | NO
PHW-PIPE-0195 | 1228 | PHW | 19047.78 | 19058 | 10.22 | DN600 DICL PN35 | DICL | 485.45 | 4961.299 | 0 | 0% | 0 |  |  | 4961.299 | NO
PHW-PIPE-0196 | 1230 | PHW | 19058 | 19097.802 | 39.802 | DN600 DICL PN35 | DICL | 485.45 | 19321.8809 | 0 | 0% | 0 |  |  | 19321.8809 | NO
PHW-PIPE-0197 | 1237 | PHW | 19097.802 | 19120.154 | 22.352 | DN600 DICL PN35 | DICL | 485.45 | 10850.7784 | 0 | 0% | 0 |  |  | 10850.7784 | NO
PHW-PIPE-0198 | 1247 | PHW | 19120.154 | 19138.361 | 18.207 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 24264.4689 | 0 | 0% | 0 |  |  | 24264.4689 | NO
PHW-PIPE-0199 | 1253 | PHW | 19138.361 | 19155.385 | 17.024 | OD660 MSCL 6WT SINTALOCK TYPE 2 PN35 | MSCL | 1332.7 | 22687.8848 | 0 | 0% | 0 |  |  | 22687.8848 | NO
PHW-PIPE-0200 | 1267 | PHW | 19155.385 | 19156.739 | 1.354 | OD660 MSCL 6WT RRJ PN35 | MSCL | 1332.7 | 1804.4758 | 0 | 0% | 0 |  |  | 1804.4758 | NO
PWG-PIPE-0001 | 1276 | PWG | 0 | 1.332 | 1.332 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0002 | 1278 | PWG | 1.332 | 6.229 | 4.897 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0003 | 1282 | PWG | 6.229 | 14.172 | 7.943 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0004 | 1289 | PWG | 14.172 | 42.513 | 28.341 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0005 | 1294 | PWG | 42.513 | 114.113 | 71.6 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0006 | 1297 | PWG | 114.113 | 238.728 | 124.615 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0007 | 1302 | PWG | 238.728 | 659.59 | 420.862 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0008 | 1316 | PWG | 659.59 | 836.889 | 177.299 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0009 | 1324 | PWG | 836.889 | 889.23 | 52.341 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0010 | 1326 | PWG | 889.23 | 904.59 | 15.36 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0011 | 1328 | PWG | 904.59 | 929.856 | 25.266 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0012 | 1331 | PWG | 929.856 | 1181.379 | 251.523 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0013 | 1337 | PWG | 1181.379 | 1186.379 | 5 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0014 | 1340 | PWG | 1186.379 | 1194.438 | 8.059 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0015 | 1342 | PWG | 1194.438 | 1206.954 | 12.516 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0016 | 1343 | PWG | 1206.954 | 1459 | 252.046 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0017 | 1347 | PWG | 1459 | 1466.83 | 7.83 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0018 | 1348 | PWG | 1466.83 | 1488.93 | 22.1 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0019 | 1353 | PWG | 1488.93 | 1507.505 | 18.575 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0020 | 1359 | PWG | 1507.505 | 1608.82 | 101.315 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0021 | 1363 | PWG | 1608.82 | 1614.19 | 5.37 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0022 | 1364 | PWG | 1614.19 | 1856.862 | 242.672 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0023 | 1371 | PWG | 1856.862 | 1876.481 | 19.619 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0024 | 1377 | PWG | 1876.481 | 1888.54 | 12.059 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0025 | 1381 | PWG | 1888.54 | 1902.016 | 13.476 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0026 | 1385 | PWG | 1902.016 | 2043.24 | 141.224 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0027 | 1389 | PWG | 2043.24 | 2048.591 | 5.351 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0028 | 1392 | PWG | 2048.591 | 2065.863 | 17.272 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0029 | 1395 | PWG | 2065.863 | 2413.402 | 347.539 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0030 | 1401 | PWG | 2413.402 | 2564.645 | 151.243 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0031 | 1408 | PWG | 2564.645 | 2592.076 | 27.431 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0032 | 1412 | PWG | 2592.076 | 2631.951 | 39.875 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0033 | 1418 | PWG | 2631.951 | 2691.626 | 59.675 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0034 | 1421 | PWG | 2691.626 | 2739.593 | 47.967 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0035 | 1425 | PWG | 2739.593 | 2750.013 | 10.42 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0036 | 1428 | PWG | 2750.013 | 2783.074 | 33.061 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 + OD610 9WT MS Enveloper | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0037 | 1453 | PWG | 2783.074 | 2797.815 | 14.741 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0038 | 1455 | PWG | 2797.815 | 2861.368 | 63.553 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0039 | 1457 | PWG | 2861.368 | 2865.366 | 3.998 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0040 | 1461 | PWG | 2865.366 | 2908.821 | 43.455 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 + OD610 9WT MS Enveloper | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0041 | 1465 | PWG | 2908.821 | 3071.909 | 163.088 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0042 | 1469 | PWG | 3071.909 | 3151.909 | 80 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0043 | 1473 | PWG | 3151.909 | 3991.367 | 839.458 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0044 | 1481 | PWG | 3991.367 | 4014.479 | 23.112 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0045 | 1487 | PWG | 4014.479 | 4043.508 | 29.029 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0046 | 1490 | PWG | 4043.508 | 5447.953 | 1404.445 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0047 | 1501 | PWG | 5447.953 | 5475.997 | 28.044 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0048 | 1509 | PWG | 5475.997 | 6507.647 | 1031.65 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0049 | 1514 | PWG | 6507.647 | 6666.39 | 158.743 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0050 | 1515 | PWG | 6666.39 | 7092.108 | 425.718 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0051 | 1517 | PWG | 7092.108 | 7122.979 | 30.871 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0052 | 1527 | PWG | 7122.979 | 7146.681 | 23.702 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0053 | 1529 | PWG | 7146.681 | 7174.681 | 28 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0054 | 1531 | PWG | 7174.681 | 7539.66 | 364.979 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0055 | 1538 | PWG | 7539.66 | 7547.413 | 7.753 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0056 | 1546 | PWG | 7547.413 | 7579.15 | 31.737 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 + OD610 12WT MS Enveloper | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0057 | 1549 | PWG | 7579.15 | 7624.121 | 44.971 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0058 | 1564 | PWG | 7624.121 | 7642.224 | 18.103 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0059 | 1568 | PWG | 7642.224 | 7724 | 81.776 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0060 | 1572 | PWG | 7724 | 7751 | 27 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0061 | 1576 | PWG | 7751 | 7939.101 | 188.101 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0062 | 1586 | PWG | 7939.101 | 7941.464 | 2.363 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0063 | 1588 | PWG | 7941.464 | 8045.962 | 104.498 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0064 | 1598 | PWG | 8045.962 | 8080.278 | 34.316 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0065 | 1600 | PWG | 8080.278 | 8293.259 | 212.981 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0066 | 1618 | PWG | 8293.259 | 8315.201 | 21.942 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 + OD610 9WT MS Enveloper | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0067 | 1624 | PWG | 8315.201 | 8323.259 | 8.058 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0068 | 1626 | PWG | 8323.259 | 8335.614 | 12.355 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0069 | 1630 | PWG | 8335.614 | 8400.622 | 65.008 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 + OD610 9WT MS Enveloper | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0070 | 1635 | PWG | 8400.622 | 8427.328 | 26.706 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0071 | 1637 | PWG | 8427.328 | 8465.757 | 38.429 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0072 | 1644 | PWG | 8465.757 | 8487.151 | 21.394 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0073 | 1653 | PWG | 8487.151 | 8542.069 | 54.918 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 + OD610 12WT MS Enveloper | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0074 | 1659 | PWG | 8542.069 | 8545.354 | 3.285 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0075 | 1663 | PWG | 8545.354 | 8580 | 34.646 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0076 | 1670 | PWG | 8580 | 8605.285 | 25.285 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0077 | 1676 | PWG | 8605.285 | 8610.275 | 4.99 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0078 | 1679 | PWG | 8610.275 | 8619.56 | 9.285 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0079 | 1681 | PWG | 8619.56 | 8692.124 | 72.564 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0080 | 1685 | PWG | 8692.124 | 8706.792 | 14.668 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0081 | 1688 | PWG | 8706.792 | 8808.151 | 101.359 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0082 | 1691 | PWG | 8808.151 | 8858.11 | 49.959 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0083 | 1693 | PWG | 8858.11 | 9100 | 241.89 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0084 | 1698 | PWG | 9100 | 9153.955 | 53.955 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0085 | 1700 | PWG | 9153.955 | 9473.063 | 319.108 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0086 | 1711 | PWG | 9473.063 | 9680 | 206.937 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0087 | 1716 | PWG | 9680 | 9690 | 10 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0088 | 1717 | PWG | 9690 | 10226.176 | 536.176 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0089 | 1722 | PWG | 10226.176 | 10270.319 | 44.143 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0090 | 1724 | PWG | 10270.319 | 10347.552 | 77.233 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0091 | 1727 | PWG | 10347.552 | 10664.861 | 317.309 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0092 | 1733 | PWG | 10664.861 | 10856.72 | 191.859 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0093 | 1740 | PWG | 10856.72 | 10863 | 6.28 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0094 | 1741 | PWG | 10863 | 11107.59 | 244.59 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0095 | 1743 | PWG | 11107.59 | 11129.673 | 22.083 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0096 | 1747 | PWG | 11129.673 | 11518 | 388.327 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0097 | 1755 | PWG | 11518 | 11524 | 6 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0098 | 1756 | PWG | 11524 | 11731 | 207 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0099 | 1758 | PWG | 11731 | 11737 | 6 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0100 | 1759 | PWG | 11737 | 11759.158 | 22.158 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0101 | 1762 | PWG | 11759.158 | 11773.094 | 13.936 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0102 | 1769 | PWG | 11773.094 | 11782.037 | 8.943 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0103 | 1771 | PWG | 11782.037 | 11788 | 5.963 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0104 | 1772 | PWG | 11788 | 11856.18 | 68.18 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0105 | 1773 | PWG | 11856.18 | 11862 | 5.82 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0106 | 1774 | PWG | 11862 | 12307.423 | 445.423 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0107 | 1785 | PWG | 12307.423 | 12320.895 | 13.472 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0108 | 1789 | PWG | 12320.895 | 12570.926 | 250.031 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0109 | 1793 | PWG | 12570.926 | 12582.142 | 11.216 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0110 | 1794 | PWG | 12582.142 | 12702.22 | 120.078 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0111 | 1800 | PWG | 12702.22 | 12734.864 | 32.644 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 + OD610 9WT MS Enveloper | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0112 | 1803 | PWG | 12734.864 | 13218.214 | 483.35 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0113 | 1813 | PWG | 13218.214 | 13247.005 | 28.791 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 + OD610 9WT MS Enveloper | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0114 | 1816 | PWG | 13247.005 | 13336.268 | 89.263 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0115 | 1817 | PWG | 13336.268 | 13344.268 | 8 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0116 | 1818 | PWG | 13344.268 | 13436.291 | 92.023 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0117 | 1832 | PWG | 13436.291 | 13622.356 | 186.065 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0118 | 1834 | PWG | 13622.356 | 13637.356 | 15 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0119 | 1836 | PWG | 13637.356 | 14074.214 | 436.858 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0120 | 1839 | PWG | 14074.214 | 14082.639 | 8.425 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0121 | 1844 | PWG | 14082.639 | 14101.292 | 18.653 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0122 | 1845 | PWG | 14101.292 | 14139.442 | 38.15 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0123 | 1853 | PWG | 14139.442 | 14178.758 | 39.316 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0124 | 1860 | PWG | 14178.758 | 14194.829 | 16.071 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0125 | 1863 | PWG | 14194.829 | 14224.068 | 29.239 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0126 | 1869 | PWG | 14224.068 | 14259.827 | 35.759 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0127 | 1873 | PWG | 14259.827 | 14304.298 | 44.471 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0128 | 1875 | PWG | 14304.298 | 14374.64 | 70.342 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0129 | 1877 | PWG | 14374.64 | 14402.293 | 27.653 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0130 | 1879 | PWG | 14402.293 | 14410.112 | 7.819 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0131 | 1881 | PWG | 14410.112 | 14525.498 | 115.386 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0132 | 1884 | PWG | 14525.498 | 14572.298 | 46.8 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 + OD610 9WT MS Enveloper | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0133 | 1886 | PWG | 14572.298 | 14662.048 | 89.75 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0134 | 1892 | PWG | 14662.048 | 14833.219 | 171.171 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0135 | 1893 | PWG | 14833.219 | 14883.12 | 49.901 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0136 | 1898 | PWG | 14883.12 | 15707.336 | 824.216 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0137 | 1913 | PWG | 15707.336 | 15788.534 | 81.198 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0138 | 1916 | PWG | 15788.534 | 16409.05 | 620.516 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0139 | 1921 | PWG | 16409.05 | 16429.262 | 20.212 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0140 | 1926 | PWG | 16429.262 | 16715 | 285.738 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0141 | 1928 | PWG | 16715 | 16725.225 | 10.225 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0142 | 1929 | PWG | 16725.225 | 16975.581 | 250.356 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0143 | 1934 | PWG | 16975.581 | 16982.79 | 7.209 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0144 | 1938 | PWG | 16982.79 | 17842.3 | 859.51 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0145 | 1946 | PWG | 17842.3 | 18013.63 | 171.33 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0146 | 1950 | PWG | 18013.63 | 18025 | 11.37 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0147 | 1951 | PWG | 18025 | 18151.238 | 126.238 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0148 | 1967 | PWG | 18151.238 | 18166.781 | 15.543 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 + OD610 9WT MS Enveloper | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0149 | 1970 | PWG | 18166.781 | 18221.276 | 54.495 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0150 | 1979 | PWG | 18221.276 | 18230 | 8.724 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0151 | 1980 | PWG | 18230 | 18785.87 | 555.87 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0152 | 1984 | PWG | 18785.87 | 19511.348 | 725.478 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0153 | 1987 | PWG | 19511.348 | 19626.241 | 114.893 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0154 | 1992 | PWG | 19626.241 | 19659.412 | 33.171 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0155 | 1994 | PWG | 19659.412 | 20070.676 | 411.264 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0156 | 1998 | PWG | 20070.676 | 20287.711 | 217.035 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0157 | 2003 | PWG | 20287.711 | 20975.564 | 687.853 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0158 | 2011 | PWG | 20975.564 | 21325 | 349.436 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0159 | 2013 | PWG | 21325 | 21330 | 5 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0160 | 2014 | PWG | 21330 | 21367.989 | 37.989 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0161 | 2015 | PWG | 21367.989 | 21473.274 | 105.285 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0162 | 2021 | PWG | 21473.274 | 21581.657 | 108.383 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0163 | 2026 | PWG | 21581.657 | 22065 | 483.343 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0164 | 2032 | PWG | 22065 | 22080 | 15 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0165 | 2035 | PWG | 22080 | 22319.185 | 239.185 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0166 | 2042 | PWG | 22319.185 | 22360.55 | 41.365 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0167 | 2046 | PWG | 22360.55 | 22443.57 | 83.02 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0168 | 2047 | PWG | 22443.57 | 22460 | 16.43 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0169 | 2048 | PWG | 22460 | 24407.759 | 1947.759 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0170 | 2077 | PWG | 24407.759 | 24426.9 | 19.141 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0171 | 2081 | PWG | 24426.9 | 24500 | 73.1 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0172 | 2083 | PWG | 24500 | 24944.548 | 444.548 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0173 | 2094 | PWG | 24944.548 | 24954.52 | 9.972 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0174 | 2096 | PWG | 24954.52 | 25018.345 | 63.825 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0175 | 2101 | PWG | 25018.345 | 25052.461 | 34.116 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0176 | 2105 | PWG | 25052.461 | 25177.723 | 125.262 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0177 | 2115 | PWG | 25177.723 | 25380 | 202.277 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0178 | 2116 | PWG | 25380 | 25391.145 | 11.145 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0179 | 2119 | PWG | 25391.145 | 25451.56 | 60.415 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0180 | 2120 | PWG | 25451.56 | 25457 | 5.44 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0181 | 2121 | PWG | 25457 | 25563 | 106 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0182 | 2122 | PWG | 25563 | 25569 | 6 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0183 | 2123 | PWG | 25569 | 25650 | 81 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0184 | 2125 | PWG | 25650 | 25660 | 10 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0185 | 2126 | PWG | 25660 | 25748 | 88 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0186 | 2128 | PWG | 25748 | 25760 | 12 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0187 | 2129 | PWG | 25760 | 25792 | 32 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0188 | 2130 | PWG | 25792 | 25817.226 | 25.226 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0189 | 2139 | PWG | 25817.226 | 25853 | 35.774 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0190 | 2140 | PWG | 25853 | 25858 | 5 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0191 | 2141 | PWG | 25858 | 25915 | 57 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0192 | 2143 | PWG | 25915 | 25920 | 5 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0193 | 2144 | PWG | 25920 | 25942.81 | 22.81 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0194 | 2145 | PWG | 25942.81 | 25948 | 5.19 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0195 | 2146 | PWG | 25948 | 26015 | 67 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0196 | 2150 | PWG | 26015 | 26025 | 10 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0197 | 2151 | PWG | 26025 | 26041.176 | 16.176 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0198 | 2157 | PWG | 26041.176 | 26097 | 55.824 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0199 | 2159 | PWG | 26097 | 26101.991 | 4.991 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0200 | 2160 | PWG | 26101.991 | 26169 | 67.009 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0201 | 2161 | PWG | 26169 | 26175 | 6 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0202 | 2162 | PWG | 26175 | 26252.108 | 77.108 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0203 | 2168 | PWG | 26252.108 | 26283.028 | 30.92 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 + OD610 9WT MS Enveloper | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0204 | 2171 | PWG | 26283.028 | 26313.689 | 30.661 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0205 | 2173 | PWG | 26313.689 | 26410.408 | 96.719 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0206 | 2174 | PWG | 26410.408 | 26668.201 | 257.793 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0207 | 2182 | PWG | 26668.201 | 26988 | 319.799 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0208 | 2183 | PWG | 26988 | 27002.147 | 14.147 | OD457 MSCL 5WT SINTALOCK TYPE 1 PN35 | MSCL |  |  | 0 | 0% |  |  |  |  | NO
PWG-PIPE-0209 | 2186 | PWG | 27002.147 | 27012.465 | 10.318 | DN375 DICL PN 35 | DICL |  |  | 0 | 0% |  |  |  |  | NO
TOTAL |  |  |  |  | 46169.204 |  |  |  | 10799584.9301 | 0 | 0% | 0 | 0 | 0 | 10799584.9301 | 0 of 409

## Cost Dashboard
Cost Dashboard
Every figure is a live roll-up. Nothing is typed on this sheet.
Linear work comes from Cost Tracker - Linear. Point assets come from Unit Rate x Quantity on the Master Register. The two do not overlap, so the project total is the sum of both.
Project position
| Budget ($) | Earned ($) | Remaining ($) | Complete (%)
Trench construction | 20707995.4865 | 0 | 20707995.4865 | 0%
Pipe supply and lay | 10799584.9301 | 0 | 10799584.9301 | 0% |  | From Cost Tracker - Pipe, one row per pipe segment. The pipe columns on Cost Tracker - Linear are superseded and no longer feed this sheet.
Point assets (per item, Master Register) | 5350620 | 0 | 5350620 | 0% |  | Earned is the value of every point asset whose Auto Complete reads YES on the Master Register — driven by the fronts on Progress Control.
PROJECT TOTAL | 36858200.4166 | 0 | 36858200.4166 | 0%
Trench by pipeline section and trench type
Each section/type combination is its own line, matching how the rates are held. A combination with no sections in the register is shown for completeness.
Pipeline Section | Trench Type | Rate ($/m) | Sections | Length (m) | Complete (m) | Complete (%) | Budget ($) | Earned ($) | Remaining ($)
PHW | 1A | 448.79 | 41 | 16838.593 | 0 | 0% | 7556992.1525 | 0 | 7556992.1525
PHW | 1B/1C | 410.3 | 1 | 58.129 | 0 | 0% | 23850.3287 | 0 | 23850.3287
PHW | 1A/1B/1C | 477.6 | 4 | 143.795 | 0 | 0% | 68676.492 | 0 | 68676.492
PHW | 2 | 994 | 3 | 25.754 | 0 | 0% | 25599.476 | 0 | 25599.476
PHW | 4 | 1151.8 | 24 | 683.233 | 0 | 0% | 786947.7694 | 0 | 786947.7694
PHW | 4&6 |  | 0 | 0 | 0 |  | 0 | 0 | 0
PHW | 4&7 | 1584 | 2 | 28.91 | 0 | 0% | 45793.44 | 0 | 45793.44
PHW | 5 | 1597.6 | 9 | 532.124 | 0 | 0% | 850121.3024 | 0 | 850121.3024
PHW | 6 | 1917 | 4 | 83.29 | 0 | 0% | 159666.93 | 0 | 159666.93
PHW | 7 | 1794.4 | 5 | 247.067 | 0 | 0% | 443337.0248 | 0 | 443337.0248
PHW | 8A |  | 9 | 515.844 | 0 | 0% | 0 | 0 | 0
PWG | 1A | 369.11 | 44 | 25128.364 | 0 | 0% | 9275130.436 | 0 | 9275130.436
PWG | 1B/1C | 385 | 5 | 134.447 | 0 | 0% | 51762.095 | 0 | 51762.095
PWG | 1A/1B/1C | 398.2 | 3 | 94.046 | 0 | 0% | 37449.1172 | 0 | 37449.1172
PWG | 2 | 440 | 1 | 15 | 0 | 0% | 6600 | 0 | 6600
PWG | 4 | 916.6 | 17 | 432.844 | 0 | 0% | 396744.8104 | 0 | 396744.8104
PWG | 4&6 | 2190 | 2 | 60.742 | 0 | 0% | 133024.98 | 0 | 133024.98
PWG | 4&7 | 1638 | 2 | 18.466 | 0 | 0% | 30247.308 | 0 | 30247.308
PWG | 5 | 1448 | 7 | 387.402 | 0 | 0% | 560958.096 | 0 | 560958.096
PWG | 6 | 984 | 4 | 91.347 | 0 | 0% | 89885.448 | 0 | 89885.448
PWG | 7 | 565.9 | 10 | 291.939 | 0 | 0% | 165208.2801 | 0 | 165208.2801
PWG | 8A |  | 10 | 357.868 | 0 | 0% | 0 | 0 | 0
TOTAL |  |  | 207 | 46169.204 | 0 | 0% | 20707995.4865 | 0 | 20707995.4865
Pipe by asset
One line per pipe asset, read from Cost Tracker - Pipe. Pipe Type is derived from the pipe description on each segment, so every metre of the 46,169 m is assigned — there is no unassigned remainder any more.
Pipeline Section | Pipe Type | Nominal Size | Rate ($/m) | Sections | Length (m) | Laid (m) | Laid (%) | Budget ($) | Earned ($) | Remaining ($)
PHW | DICL | DN600 | 485.45 | 152 | 17386.369 | 0 | 0% | 8440212.831 | 0 | 8440212.831
PHW | MSCL | OD660 | 1332.7 | 48 | 1770.37 | 0 | 0% | 2359372.099 | 0 | 2359372.099
PWG | DICL | DN375 |  | 166 | 25745.499 | 0 | 0% | 0 | 0 | 0
PWG | MSCL | OD457 |  | 43 | 1266.966 | 0 | 0% | 0 | 0 | 0
TOTAL |  |  |  | 409 | 46169.204 | 0 | 0% | 10799584.9301 | 0 | 10799584.9301
Segments with no pipe type identified |  |  |  |  | 0 |  | Should read zero — every pipe segment carries a description.
Combined position by pipeline section
Pipeline Section | Sections | Length (m) | Trench Complete (m) | Trench % | Pipe Laid (m) | Budget ($) | Earned ($) | Remaining ($)
PHW | 102 | 19156.739 | 0 | 0% | 0 | 20760569.8458 | 0 | 20760569.8458
PWG | 105 | 27012.465 | 0 | 0% | 0 | 10747010.5707 | 0 | 10747010.5707
TOTAL | 207 | 46169.204 | 0 | 0% | 0 | 31507580.4166 | 0 | 31507580.4166
Point assets priced on the Master Register
Complete is driven by Auto Complete, which turns YES once the front named in Completion Driver has passed the record. Bends and valves follow the PIPE front; everything else follows the TRENCH front.
Asset Type | Driver | Items rated | Items in register | Complete | Budget ($) | Earned ($)
TRENCH STOP | TRENCH | 442 | 442 | 0 | 491725 | 0
BULK HEAD | TRENCH | 47 | 47 | 0 | 963829 | 0
THRUST BLOCK | TRENCH | 255 | 255 | 0 | 3895066 | 0
TRENCHED CREEK CROSSING | TRENCH | 0 | 32 | 0 | 0 | 0
MINOR ROAD CROSSING | TRENCH | 0 | 22 | 0 | 0 | 0
MAJOR ROAD CROSSING | TRENCH | 0 | 11 | 0 | 0 | 0
MAJOR RAIL CROSSING | TRENCH | 0 | 3 | 0 | 0 | 0
CARPARK/SIDE LANE | TRENCH | 0 | 4 | 0 | 0 | 0
TREE REMOVAL | TRENCH | 0 | 91 | 0 | 0 | 0
BENDS (all types) | PIPE | 211 | 211 | 0 | 0 | 0
VALVES (all types) | PIPE | 129 | 129 | 0 | 0 | 0
TOTAL |  | 1084 | 1247 | 0 | 5350620 | 0
Notes
• | Point-asset budget is Unit Rate ($) x Quantity as held on the Master Register. A blank rate on Rate Library gives a blank budget, not zero, so every total here is partial until the remaining rates are supplied.
• | Bends and valves are counted on Register rather than Asset Type, because a bend is HOR, VERT or COMPOUND and a valve is AV, SCV, IV or PIG. Rate Library Tables 5 and 6 hold the rate lines behind them.
• | Isolation valves and pigging stations also carry a thrust block on Table 4, one for one. The valve and its block are two items; price each once.
Position at cost
Budget at the client rate against budget at the cost rate, for the work that carries both.
| Charge ($) | Cost ($) | Margin ($) | Margin %
Point assets (per item) | 5350620 |  |  |  |  | Cost per item is on Rate Library beside each rate.
Pipe supply and lay | 0 | 0 | 0 |  |  | Earned to date, charge against cost, from the pipe tracker.
Days recorded (Daily Profit) | 0 | 0 | 0

## Thrust Block Costing
Thrust Block Costing
PHW and PWG shown separately, each grouped by thrust block type and split by the fitting the block is built against. Counts and completion read live from the Master Register; rates from Rate Library Table 4.
Rate is per block. Blocks sums Quantity, so a pigging station record counts as two.
Type and fitting come from thrust block index drawings S-DWG-PTW-115 to 118 (Issued for Construction).
PHW — Toowoomba to Highfields
Item | Fitting | Angle / Size | Material | DN | Blocks | Rate ($/block) | Budget ($) | Complete | Complete (%) | Earned ($) | Remaining ($)
Thrust block Type 1
Bend; 45 deg | Bend | 45 | DICL | 600 | 8 | 114663 | 917304 | 0 | 0% | 0 | 917304
Thrust block Type 2
Bend; 22.5 deg | Bend | 22.5 | DICL | 600 | 1 | 99539 | 99539 | 0 | 0% | 0 | 99539
Bend; 22.5+11.25 deg | Bend | 22.5+11.25 | DICL | 600 | 1 | 99969 | 99969 | 0 | 0% | 0 | 99969
Bend; MS - 38.2° | Bend | 38.2 | MSCL | 650 | 1 | 104391 | 104391 | 0 | 0% | 0 | 104391
Thrust block Type 3
Bend; 45 deg | Bend | 45 | DICL | 600 | 4 | 16755 | 67020 | 0 | 0% | 0 | 67020
Bend; MS - 43.2° | Bend | 43.2 | MSCL | 650 | 1 | 26944 | 26944 | 0 | 0% | 0 | 26944
Bend; MS - 47.1° | Bend | 47.1 | MSCL | 650 | 1 | 26944 | 26944 | 0 | 0% | 0 | 26944
Thrust block Type 4
Bend; 11.25 deg | Bend | 11.25 | DICL | 600 | 2 | 15563 | 31126 | 0 | 0% | 0 | 31126
Bend; 22.5 deg | Bend | 22.5 | DICL | 600 | 4 | 15780 | 63120 | 0 | 0% | 0 | 63120
Bend; 22.5+11.25 deg | Bend | 22.5+11.25 | DICL | 600 | 2 | 18443 | 36886 | 0 | 0% | 0 | 36886
Bend; 45 deg | Bend | 45 | DICL | 600 | 5 | 16211 | 81055 | 0 | 0% | 0 | 81055
Bend; MS - 13.9° | Bend | 13.9 | MSCL | 650 | 1 | 20678 | 20678 | 0 | 0% | 0 | 20678
Bend; MS - 30° | Bend | 30 | MSCL | 650 | 1 | 20678 | 20678 | 0 | 0% | 0 | 20678
Thrust block Type 5
Bend; 22.5 deg | Bend | 22.5 | DICL | 600 | 9 | 14784 | 133056 | 0 | 0% | 0 | 133056
Bend; 22.5+11.25 deg | Bend | 22.5+11.25 | DICL | 600 | 2 | 15214 | 30428 | 0 | 0% | 0 | 30428
Thrust block Type 6
Bend; 11.25 deg | Bend | 11.25 | DICL | 600 | 7 | 14743 | 103201 | 0 | 0% | 0 | 103201
Bend; MS - 10° | Bend | 10 | MSCL | 650 | 1 | 19811 | 19811 | 0 | 0% | 0 | 19811
Tee; DN600XDN150 DIFBE SCOUR TEE | Tee | DN600xDN150 DIFBE SCOUR TEE |  | 150 | 3 |  |  | 0 | 0%
Thrust block Type 7
Bend; 11.25 deg | Bend | 11.25 | DICL | 600 | 14 | 14150 | 198100 | 0 | 0% | 0 | 198100
Bend; MS - 7.7° | Bend | 7.7 | MSCL | 650 | 1 | 19220 | 19220 | 0 | 0% | 0 | 19220
Bend; MS - 9.1° | Bend | 9.1 | MSCL | 650 | 1 | 19220 | 19220 | 0 | 0% | 0 | 19220
Tee; DN600XDN150 DIFBE SCOUR TEE | Tee | DN600xDN150 DIFBE SCOUR TEE |  | 150 | 13 |  |  | 0 | 0%
Thrust block Type 8
Bend; 11.25 deg | Bend | 11.25 | DICL | 600 | 1 | 14024 | 14024 | 0 | 0% | 0 | 14024
Thrust block Type 9
Bend; 11.25 deg | Bend | 11.25 | DICL | 600 | 4 | 14347 | 57388 | 0 | 0% | 0 | 57388
Thrust block Type 10
Bend; 11.25 deg | Bend | 11.25 | DICL | 600 | 2 | 44440 | 88880 | 0 | 0% | 0 | 88880
Bend; MS - 7.5° | Bend | 7.5 | MSCL | 650 | 1 | 49509 | 49509 | 0 | 0% | 0 | 49509
Bend; MS - 8.6° | Bend | 8.6 | MSCL | 650 | 1 | 49509 | 49509 | 0 | 0% | 0 | 49509
Thrust block Type 12
Isolation valve | Isolation Valve |  |  | 600 | 5 |  |  | 0 | 0%
Thrust block Type 14
In-line | In-Line |  |  | 600 | 2 |  |  | 0 | 0%
Thrust block 2 x Type 12
Pigging station | Pigging Station |  |  | 600 | 4 |  |  | 0 | 0%
Subtotal PHW |  |  |  |  | 103 |  | 2378000 | 0 | 0% | 0 | 2378000
PWG — Highfields to Warwick
Item | Fitting | Angle / Size | Material | DN | Blocks | Rate ($/block) | Budget ($) | Complete | Complete (%) | Earned ($) | Remaining ($)
Thrust block Type 4
Bend; 22.5+11.25 deg | Bend | 22.5+11.25 | DICL | 375 | 1 | 15185 | 15185 | 0 | 0% | 0 | 15185
Bend; 45 deg | Bend | 45 | DICL | 375 | 1 | 14280 | 14280 | 0 | 0% | 0 | 14280
Thrust block Type 5
Bend; 22.5 deg | Bend | 22.5 | DICL | 375 | 6 | 13107 | 78642 | 0 | 0% | 0 | 78642
Bend; 45 deg | Bend | 45 | DICL | 375 | 8 | 13282 | 106256 | 0 | 0% | 0 | 106256
Thrust block Type 6
Bend; 11.25 deg | Bend | 11.25 | DICL | 375 | 2 | 13159 | 26318 | 0 | 0% | 0 | 26318
Bend; 22.5 deg | Bend | 22.5 | DICL | 375 | 3 | 13283 | 39849 | 0 | 0% | 0 | 39849
Bend; 22.5+11.25 deg | Bend | 22.5+11.25 | DICL | 375 | 3 | 14363 | 43089 | 0 | 0% | 0 | 43089
Bend; 45 deg | Bend | 45 | DICL | 375 | 6 | 13458 | 80748 | 0 | 0% | 0 | 80748
Bend; MS - 31.9° | Bend | 31.9 | MSCL | 450 | 1 | 22689 | 22689 | 0 | 0% | 0 | 22689
Bend; MS - 37.4° | Bend | 37.4 | MSCL | 450 | 1 | 22689 | 22689 | 0 | 0% | 0 | 22689
Tee; DN375XDN150 DIFBE SCOUR TEE | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 2 |  |  | 0 | 0%
Thrust block Type 7
Bend; 11.25 deg | Bend | 11.25 | DICL | 375 | 46 | 12566 | 578036 | 0 | 0% | 0 | 578036
Bend; 22.5 deg | Bend | 22.5 | DICL | 375 | 11 | 12690 | 139590 | 0 | 0% | 0 | 139590
Tee; DN375XDN150 DIFBE SCOUR TEE | Tee | DN375xDN150 DIFBE SCOUR TEE |  | 150 | 21 |  |  | 0 | 0%
Thrust block Type 9
Bend; 11.25 deg | Bend | 11.25 | DICL | 375 | 4 | 12764 | 51056 | 0 | 0% | 0 | 51056
Bend; MS - 8.9° | Bend | 8.9 | MSCL | 450 | 1 | 12887 | 12887 | 0 | 0% | 0 | 12887
Thrust block Type 10
Bend; MS - 10.3° | Bend | 10.3 | MSCL | 450 | 1 | 49855 | 49855 | 0 | 0% | 0 | 49855
Bend; MS - 10.6° | Bend | 10.6 | MSCL | 450 | 1 | 49855 | 49855 | 0 | 0% | 0 | 49855
Thrust block Type 11
Bend; 11.25 deg | Bend | 11.25 | DICL | 375 | 4 | 28674 | 114696 | 0 | 0% | 0 | 114696
Bend; MS - 10.1° | Bend | 10.1 | MSCL | 450 | 1 | 35673 | 35673 | 0 | 0% | 0 | 35673
Bend; MS - 8.9° | Bend | 8.9 | MSCL | 450 | 1 | 35673 | 35673 | 0 | 0% | 0 | 35673
Thrust block Type 12
Isolation valve | Isolation Valve |  |  | 375 | 1 |  |  | 0 | 0%
Thrust block Type 13
Isolation valve | Isolation Valve |  |  | 375 | 5 |  |  | 0 | 0%
Thrust block 2 x Type 13
Pigging station | Pigging Station |  |  | 375 | 6 |  |  | 0 | 0%
Subtotal PWG |  |  |  |  | 137 |  | 1517066 | 0 | 0% | 0 | 1517066
PPH — Pittsworth to Highfields
In this register and in the index drawings, so priced the same way. A separate package: kept out of the PHW and PWG subtotals.
Item | Fitting | Angle / Size | Material | DN | Blocks | Rate ($/block) | Budget ($) | Complete | Complete (%) | Earned ($) | Remaining ($)
Thrust block Type 5
Bend; 45 deg | Bend | 45 | DICL | 500 | 6 |  |  | 0 | 0%
Bend; 45+11.25 deg | Bend | 45+11.25 | DICL | 500 | 1 |  |  | 0 | 0%
Thrust block Type 6
Tee; OD813XOD559 MSCL TEE | Tee | OD813xOD559 MSCL TEE |  | 750 | 0 |  |  | 0
Thrust block Type 7
Tee; DN500XDN150 DIFBE SCOUR TEE | Tee | DN500xDN150 DIFBE SCOUR TEE |  | 150 | 0 |  |  | 0
Thrust block Type 13
Isolation valve | Isolation Valve |  |  | 500 | 0 |  |  | 0
Subtotal PPH |  |  |  |  | 7 |  | 0 | 0 | 0% | 0 | 0
Off the pipeline alignment
RHF facility thrust blocks. Note 4 on the index drawings excludes facilities packages, so these carry no type or fitting from the index and are counted here only.
Item | Fitting | Angle / Size | Material | DN | Blocks | Rate ($/block) | Budget ($) | Complete | Complete (%) | Earned ($) | Remaining ($)
RHF — RHF TYPE 1 | Facility |  |  |  | 5
RHF — TYPE 1 | Facility |  |  |  | 1
RHF — RHF TYPE 2 | Facility |  |  |  | 2
RHF — RHF TYPE 3 | Facility |  |  |  | 1
RHF — RHF TYPE 4 | Facility |  |  |  | 4
Subtotal off alignment |  |  |  |  | 13
ALL THRUST BLOCKS |  |  |  |  | 260 |  | 3895066 | 0 | 0% | 0 | 3895066
Reading this sheet
• | Green figures are read from elsewhere: rates from Rate Library Table 4, counts and completion from the Master Register. Nothing on this sheet is typed.
• | A blank rate gives a blank budget, never a zero, so an unpriced line shows as blank rather than reading as free.
• | Mitred MSCL bends are listed by angle. The drawings give the angle but not the number of cuts, so if the cut count changes the price, record it in the Cuts column on Rate Library Table 4.

## Daily Progress
Daily Progress
One row per pipeline section per day, written by the End of day page. Append only: a row is what was reported that day, so a correction goes in as a later row rather than an overtype.
Earned is at the client rate. Our Cost is the same quantities at the cost rate. Gross Margin is the difference and takes no account of plant and labour — that is a day-level figure and lives on Daily Profit.
Date | Recorded By | Shift | Pipeline Section | Trench From Ch (m) | Trench To Ch (m) | Trench m Today | Pipe From Ch (m) | Pipe To Ch (m) | Pipe m Today | Point Assets Complete | Earned Today ($) | Our Cost Today ($) | Gross Margin Today ($) | Weather | Downtime (hrs) | Notes | Totals to date
2026-08-28 | Jerry Kh | Day | PHW | 100 | 125 | 25 | 45 | 55 | 10 | 0 | 16074.25 | 8834.4488 | 7239.8012 | Fine |  |  | Trench m | 0
2026-08-29 | Jerry Kh | Day | PHW | 125 | 325 | 200 | 0 | 150 | 150 | 2 | 164800.5 | 70675.5906 | 94124.9094 | Fine |  |  | Pipe m | 0
2026-08-30 | Jerry Kh | Day | PHW | 325 | 450 | 125 | 150 | 250 | 100 | 4 | 85964.4651 | 28588.1615 | 57376.3036 | Fine |  |  | Point assets | 0
2026-08-31 | Jerry Kh | Day | PHW | 450 | 460 | 10 | 250 | 420 | 170 | 1 | 87014.4 | 3533.7795 | 83480.6205 | Fine |  |  | Earned ($) | 0
[17 empty] | Our cost ($) | 0
[17 empty] | Gross margin ($) | 0
[17 empty] | Days recorded | 0

## Daily Plant and Labour
Daily Plant and Labour
One row per resource per day. The End of day page carries the previous day forward, so an unchanged crew needs no typing at all — only what changed.
Hours are worked hours. Standby is time on site but not producing: weather, access, waiting on a hold point.
Date | Recorded By | Type | Description | Number | Hours | Standby Hours | Notes | Totals to date
2026-08-28 | Jerry Kh | Labour | Supervisor | 1 | 10 |  |  | Hours worked | 0
2026-08-28 | Jerry Kh | Labour | Pipe crew | 6 | 10 |  |  | Standby hours | 0
2026-08-28 | Jerry Kh | Plant | Excavator 30t | 1 | 9 |  |  | Days recorded | 0
2026-08-28 | Jerry Kh | Plant | Sideboom | 1 | 9
2026-08-29 | Jerry Kh | Labour | Supervisor | 1 | 10 |  |  | Append only. Written by the End of day page; a correction goes in as a later row.
2026-08-29 | Jerry Kh | Labour | Pipe crew | 6 | 10
2026-08-29 | Jerry Kh | Plant | Excavator 30t | 1 | 9
2026-08-29 | Jerry Kh | Plant | Sideboom | 1 | 9
2026-08-30 | Jerry Kh | Labour | Supervisor | 1 | 10
2026-08-30 | Jerry Kh | Labour | Pipe crew | 8 | 10
2026-08-30 | Jerry Kh | Plant | Excavator 30t | 1 | 9
2026-08-30 | Jerry Kh | Plant | Sideboom | 1 | 9
2026-08-31 | Jerry Kh | Labour | Supervisor | 1 | 10
2026-08-31 | Jerry Kh | Labour | Pipe crew | 8 | 10
2026-08-31 | Jerry Kh | Plant | Excavator 30t | 1 | 9
2026-08-31 | Jerry Kh | Plant | Sideboom | 1 | 9

## Daily Safety
Daily Safety
One row per day. Nil is a real answer and is recorded as one, so a quiet day is on the record rather than missing from it.
Date | Recorded By | Toolbox Held | Toolbox Topic | Personnel On Site | Incident Class | Incident Detail | Lost Time (hrs) | Totals to date
2026-08-28 | Jerry Kh | Yes |  | 7 | Nil |  |  | Personnel-days | 0
2026-08-29 | Jerry Kh | Yes |  | 7 | Nil |  |  | Lost time hours | 0
2026-08-30 | Jerry Kh | Yes |  | 9 | Nil |  |  | Days recorded | 0
2026-08-31 | Jerry Kh | Yes |  | 9 | Nil
Append only. Written by the End of day page; a correction goes in as a later row.

## Daily Hold Points
Daily Hold Points
One row per hold point movement. A hold point raised on one day and released on another gets a row for each, so the history reads in order rather than being overwritten.
Record Key ties it to an asset in the Master Register where there is one.
Date | Recorded By | Reference | Description | Status | Record Key | Notes | Totals to date
[7 empty] | Days recorded | 0
Append only. Written by the End of day page; a correction goes in as a later row.

## Daily Profit
Daily Profit
One row per day: what the day earned, what it cost, and what was left. Written by the End of day page from the rates in force when the day was saved.
Earned and Direct Cost are the same quantities at the client rate and the cost rate. Plant and Labour is the hours recorded that day at the cost rate on Plant and Labour Rates.
Profit = Earned − Direct Cost − Plant and Labour. A claim position for review, not certified accounts.
Date | Recorded By | Shift | Earned ($) | Direct Cost ($) | Plant and Labour ($) | Total Cost ($) | Profit ($) | Margin % | Trench m | Pipe m | Crew Hours | Notes | Totals to date
2026-08-28 | Jerry Kh | Day | 16074.25 | 8834.4488 | 7850 | 16684.4488 | -610.1988 | -3.796% | 25 | 10 | 88 |  | Earned ($) | 0
2026-08-29 | Jerry Kh | Day | 164800.5 | 70675.5906 | 7850 | 78525.5906 | 86274.9094 | 52.35% | 200 | 150 | 88 |  | Direct cost ($) | 0
2026-08-30 | Jerry Kh | Day | 85964.4651 | 28588.1615 | 9150 | 37738.1615 | 48226.3036 | 56.1% | 125 | 100 | 108 |  | Plant and labour ($) | 0
2026-08-31 | Jerry Kh | Day | 87014.4 | 3533.7795 | 9150 | 12683.7795 | 74330.6205 | 85.42% | 10 | 170 | 108 |  | Total cost ($) | 0
[13 empty] | Profit ($) | 0
[13 empty] | Crew hours | 0
Margin to date

## Data Quality
Data quality exceptions
Every change made to the source data during consolidation, plus anomalies found and left untouched for review.
Register | Source row(s) | Issue | Resolution | Detail
Thrust Block | 305 | Template residue | ROW REMOVED | Entire row is residual data from the Jemena Port Kembla pipeline template (Operator PKCT, Design Drawing GAS-554-MA-AL-001, DBYD 31981590, chainage 9.92387015996201 km-scale). Not a T2W asset.
Thrust Block | 306 | Template residue | ROW REMOVED | Entire row is residual data from the Jemena Port Kembla pipeline template (Operator UNKNOWN, Design Drawing GAS-554-MA-AL-001, DBYD 31981590, chainage 9.96169594877122 km-scale). Not a T2W asset.
Thrust Block | 307 | Template residue | ROW REMOVED | Entire row is residual data from the Jemena Port Kembla pipeline template (Operator PKCT, Design Drawing GAS-554-MA-AL-001, DBYD 31981590, chainage 9.99952173758052 km-scale). Not a T2W asset.
Thrust Block | 308 | Template residue | ROW REMOVED | Entire row is residual data from the Jemena Port Kembla pipeline template (Operator PKCT, Design Drawing GAS-554-MA-AL-001, DBYD 31981590, chainage 10.0373475263898 km-scale). Not a T2W asset.
Thrust Block | 309 | Template residue | ROW REMOVED | Entire row is residual data from the Jemena Port Kembla pipeline template (Operator PKCT, Design Drawing GAS-554-MA-AL-001, DBYD 31981590, chainage 10.075173315199 km-scale). Not a T2W asset.
Thrust Block | 310 | Template residue | ROW REMOVED | Entire row is residual data from the Jemena Port Kembla pipeline template (Operator PKCT, Design Drawing GAS-554-MA-AL-002, DBYD 31981590, chainage 10.1129991040083 km-scale). Not a T2W asset.
Thrust Block | 311 | Template residue | ROW REMOVED | Entire row is residual data from the Jemena Port Kembla pipeline template (Operator PKCT, Design Drawing GAS-554-MA-AL-002, DBYD 31981590, chainage 10.1508248928175 km-scale). Not a T2W asset.
Thrust Block | 312 | Template residue | ROW REMOVED | Entire row is residual data from the Jemena Port Kembla pipeline template (Operator PKCT, Design Drawing GAS-554-MA-AL-002, DBYD 31981590, chainage 10.1886506816268 km-scale). Not a T2W asset.
Trench Stop & Bulkhead | 309 | Template residue | SURVEY CELLS CLEARED | Asset PHW-TS-0270 is genuine, but columns E-L of this row carried Port Kembla residue (Surveyors PtNo Surveyors PtNo, Actual Chainage Actual Chainage). Those cells cleared; asset data retained.
Trench Stop & Bulkhead | 310 | Template residue | SURVEY CELLS CLEARED | Asset PHW-TS-0271 is genuine, but columns E-L of this row carried Port Kembla residue (Surveyors PtNo 2050364410.23209, Actual Chainage 9923.87015996201). Those cells cleared; asset data retained.
Trench Stop & Bulkhead | 311 | Template residue | SURVEY CELLS CLEARED | Asset PHW-TS-0272 is genuine, but columns E-L of this row carried Port Kembla residue (Surveyors PtNo 2058981476.64782, Actual Chainage 9961.6959487713). Those cells cleared; asset data retained.
Trench Stop & Bulkhead | 312 | Template residue | SURVEY CELLS CLEARED | Asset PHW-TS-0273 is genuine, but columns E-L of this row carried Port Kembla residue (Surveyors PtNo 2067598543.06356, Actual Chainage 9999.5217375805). Those cells cleared; asset data retained.
Trench Stop & Bulkhead | 313 | Template residue | SURVEY CELLS CLEARED | Asset PHW-BS-0035 is genuine, but columns E-L of this row carried Port Kembla residue (Surveyors PtNo 2076215609.4793, Actual Chainage 10037.3475263898). Those cells cleared; asset data retained.
Trench Stop & Bulkhead | 314 | Template residue | SURVEY CELLS CLEARED | Asset PHW-TS-0274 is genuine, but columns E-L of this row carried Port Kembla residue (Surveyors PtNo 2084832675.89504, Actual Chainage 10075.173315199). Those cells cleared; asset data retained.
Trench Stop & Bulkhead | 315 | Template residue | SURVEY CELLS CLEARED | Asset PHW-TS-0275 is genuine, but columns E-L of this row carried Port Kembla residue (Surveyors PtNo 2093449742.31077, Actual Chainage 10112.9991040083). Those cells cleared; asset data retained.
Trench Stop & Bulkhead | 316 | Template residue | SURVEY CELLS CLEARED | Asset PHW-TS-0276 is genuine, but columns E-L of this row carried Port Kembla residue (Surveyors PtNo 2102066808.72651, Actual Chainage 10150.8248928175). Those cells cleared; asset data retained.
Trench Stop & Bulkhead | 318 | Template residue | SURVEY CELLS CLEARED | Asset PHW-TS-0278 is genuine, but columns E-L of this row carried Port Kembla residue (Surveyors PtNo 2110683875.14225, Actual Chainage 10188.6506816268). Those cells cleared; asset data retained.
Trench Stop & Bulkhead | 316 | Malformed drawing-sheet ref | FLAGGED - not changed | Value "9,9" does not match the n.n pattern used elsewhere in this column.
Trench Stop & Bulkhead | 317 | Malformed drawing-sheet ref | FLAGGED - not changed | Value "9.9.1" does not match the n.n pattern used elsewhere in this column.
Thrust Block | 114-126 | No chainage assigned | RETAINED - sorted to end | 13 record(s) have no value in the chainage column: RHF-TB-001, RHF-TB-002, RHF-TB-003, RHF-TB-004, RHF-TB-005, RHF-TB-006, RHF-TB-007, RHF-TB-008, RHF-TB-009, RHF-TB-010, RHF-TB-011, RHF-TB-012, RHF-TB-013. They are genuine assets and are kept in the Master Register with a blank Chainage Start, sorted after all located records. Chainage needs to be assigned before this register can be relied on for setout.
Creek Crossing | 3-19 | No chainage assigned | RETAINED - sorted to end | 32 record(s) have no value in the chainage column: PHW-CC-0001, PWG-CC-0001, PHW-CC-0002, PWG-CC-0002, PHW-CC-0003, PWG-CC-0003, PHW-CC-0004, PWG-CC-0004, PHW-CC-0005, PWG-CC-0005, PHW-CC-0006, PWG-CC-0006, PHW-CC-0007, PWG-CC-0007, PHW-CC-0008, PWG-CC-0008, PHW-CC-0009, PWG-CC-0009, PHW-CC-0010, PWG-CC-0010, PHW-CC-0011, PWG-CC-0011, PHW-CC-0012, PWG-CC-0012, PHW-CC-0013, PWG-CC-0013, PHW-CC-0014, PWG-CC-0014, PHW-CC-0015, PWG-CC-0015, PWG-CC-0016, PWG-CC-0017. They are genuine assets and are kept in the Master Register with a blank Chainage Start, sorted after all located records. Chainage needs to be assigned before this register can be relied on for setout.
Road & Rail Crossing | 6-31 | No chainage assigned | RETAINED - sorted to end | 42 record(s) have no value in the chainage column: PHW-PT-0001, PHW-RD-0001, PHW-RD-0002, PHW-RL-0001, PHW-RD-0003, PHW-RD-0004, PHW-RD-0005, PHW-RD-0006, PHW-RD-0007, PHW-RD-0008, PHW-RD-0009, PHW-RD-0010, PHW-RD-0011, PHW-RD-0012, PHW-RD-0013, PHW-RD-0014, PWG-RD-0001, PWG-RD-0002, PWG-RD-0003, PWG-RD-0004, PWG-RD-0005, PWG-CP-0001, PWG-RD-0006, PWG-RD-0007, PWG-RD-0008, PWG-RL-0001, PWG-RD-0009, PWG-RD-0010, PWG-PT-0001, PWG-RL-0002, PWG-CP-0002, PWG-CP-0003, PWG-CP-0004, PWG-RD-0011, PWG-RD-0012, PWG-RD-0013, PWG-RD-0014, PWG-RD-0015, PWG-RD-0016, PWG-RD-0017, PWG-RD-0018, PWG-RD-0019. They are genuine assets and are kept in the Master Register with a blank Chainage Start, sorted after all located records. Chainage needs to be assigned before this register can be relied on for setout.
Foreign Service | 176 | Spelling in description | FLAGGED - raw text unchanged | "BDYA" appears on 1 row(s); read as "BYDA" when deriving Utility Type / Operator / Info Source. The description column still holds the original wording.
Foreign Service | 149 | Spelling in description | FLAGGED - raw text unchanged | "BYD" appears on 1 row(s); read as "BYDA" when deriving Utility Type / Operator / Info Source. The description column still holds the original wording.
Foreign Service | 197 | Spelling in description | FLAGGED - raw text unchanged | "ELECTRICITYELD" appears on 1 row(s); read as "ELECTRICITY ELD" when deriving Utility Type / Operator / Info Source. The description column still holds the original wording.
Foreign Service | 68, 105 | Spelling in description | FLAGGED - raw text unchanged | "NO POST" appears on 2 row(s); read as "NO POSTS" when deriving Utility Type / Operator / Info Source. The description column still holds the original wording.
Foreign Service | 129 | Spelling in description | FLAGGED - raw text unchanged | "TELSTA" appears on 1 row(s); read as "TELSTRA" when deriving Utility Type / Operator / Info Source. The description column still holds the original wording.
Foreign Service | 100, 101 | Spelling in description | FLAGGED - raw text unchanged | "TELSTRA COMS" appears on 2 row(s); read as "TELSTRA COMMS" when deriving Utility Type / Operator / Info Source. The description column still holds the original wording.
Foreign Service | 262 | Spelling in description | FLAGGED - raw text unchanged | "TELSTRACOMMS" appears on 1 row(s); read as "TELSTRA COMMS" when deriving Utility Type / Operator / Info Source. The description column still holds the original wording.
Foreign Service | 219 | Spelling in description | FLAGGED - raw text unchanged | "UNKNOW" appears on 1 row(s); read as "UNKNOWN" when deriving Utility Type / Operator / Info Source. The description column still holds the original wording.
Foreign Service | 215 | Spelling in description | FLAGGED - raw text unchanged | "WIRES ON" appears on 1 row(s); read as "WIRES ONLY (truncated)" when deriving Utility Type / Operator / Info Source. The description column still holds the original wording.
Foreign Service | 18 | Contradictory status | FLAGGED - not changed | "Included in Current Plan" is Yes but the comment reads "Not Included in Rev 2". Needs resolving before the register is issued.
Foreign Service | 90-96 | Not a utility | RETAINED - typed SURVEY LEVEL | 7 records are described only as "DG LEVEL" or "EUD LEVEL" and appear to be survey level references rather than foreign services. Retained but typed SURVEY LEVEL so they can be filtered out.
Foreign Service | 236 records | Asset owner not stated | FLAGGED - left blank | 236 of 334 records name no owner in either the description or the comments, so Operator is blank. Owner is needed for permit and notification purposes.
Foreign Service | 335 | No alignment sheet | FLAGGED - not changed | No value in "New Drawing Number (Alignment Sheet)", so the crossing cannot be traced to a drawing.
Foreign Service | 43 of 334 records | Superseded drawing sparse | INFORMATION ONLY | The superseded drawing number is populated on only 43 records. Not an error, but it cannot be used to cross-check the remainder against the earlier revision.
Foreign Service | 29, 30 | Possible duplicate crossing | FLAGGED - not changed | 2 identical records at PHW chainage 2,793 m: "BYDA WATER". Either a genuine pair of parallel services or a double entry.
Foreign Service | 62, 63 | Possible duplicate crossing | FLAGGED - not changed | 2 identical records at PHW chainage 5,494 m: "BYDA TELSTRA COMMS". Either a genuine pair of parallel services or a double entry.
Foreign Service | 71, 72 | Possible duplicate crossing | FLAGGED - not changed | 2 identical records at PHW chainage 6,993 m: "FENCE LINE NO POSTS". Either a genuine pair of parallel services or a double entry.
Foreign Service | 74, 75 | Possible duplicate crossing | FLAGGED - not changed | 2 identical records at PHW chainage 6,996 m: "BYDA TELSTRA COMMSTUD". Either a genuine pair of parallel services or a double entry.
Foreign Service | 78, 79 | Possible duplicate crossing | FLAGGED - not changed | 2 identical records at PHW chainage 7,021 m: "BYDA NBN COMMS". Either a genuine pair of parallel services or a double entry.
Foreign Service | 107, 108 | Possible duplicate crossing | FLAGGED - not changed | 2 identical records at PHW chainage 12,470 m: "PUP ELECTRICITY". Either a genuine pair of parallel services or a double entry.
Foreign Service | 118, 119 | Possible duplicate crossing | FLAGGED - not changed | 2 identical records at PHW chainage 13,278 m: "PUP COMMS DN100". Either a genuine pair of parallel services or a double entry.
Foreign Service | 185, 186 | Possible duplicate crossing | FLAGGED - not changed | 2 identical records at PWG chainage 2,754 m: "BYDA TELSTRA COMMS DN100". Either a genuine pair of parallel services or a double entry.
Foreign Service | 187, 188, 189, 190, 191, 192 | Possible duplicate crossing | FLAGGED - not changed | 6 identical records at PWG chainage 2,754 m: "BYDA NBN COMMS DN30". Either a genuine pair of parallel services or a double entry.
Foreign Service | 193, 196 | Possible duplicate crossing | FLAGGED - not changed | 2 identical records at PWG chainage 2,763 m: "PUP ELECTRICITY". Either a genuine pair of parallel services or a double entry.
Foreign Service | 220, 221 | Possible duplicate crossing | FLAGGED - not changed | 2 identical records at PWG chainage 7,826 m: "PUP ELECTRICITY". Either a genuine pair of parallel services or a double entry.
Foreign Service | 256, 257 | Possible duplicate crossing | FLAGGED - not changed | 2 identical records at PWG chainage 9,585 m: "PUP ELECTRICITY". Either a genuine pair of parallel services or a double entry.
Foreign Service | 272, 273 | Possible duplicate crossing | FLAGGED - not changed | 2 identical records at PWG chainage 12,307 m: "BYDA NBN COMMS DN30". Either a genuine pair of parallel services or a double entry.
Foreign Service | 275, 276, 277 | Possible duplicate crossing | FLAGGED - not changed | 3 identical records at PWG chainage 12,322 m: "BYDA NBN COMMS DN30". Either a genuine pair of parallel services or a double entry.
Foreign Service | 279, 280, 281 | Possible duplicate crossing | FLAGGED - not changed | 3 identical records at PWG chainage 13,375 m: "FENCE LINE NO POSTS - WIRES ONLY". Either a genuine pair of parallel services or a double entry.
Foreign Service | 286, 287 | Possible duplicate crossing | FLAGGED - not changed | 2 identical records at PWG chainage 15,528 m: "FENCE LINE NO POSTS - WIRES ONLY". Either a genuine pair of parallel services or a double entry.
Foreign Service | 295, 296 | Possible duplicate crossing | FLAGGED - not changed | 2 identical records at PWG chainage 15,663 m: "BYDA NBN COMMS DN30". Either a genuine pair of parallel services or a double entry.
Foreign Service | 322, 323 | Possible duplicate crossing | FLAGGED - not changed | 2 identical records at PWG chainage 24,097 m: "PUP ELECTRICITY". Either a genuine pair of parallel services or a double entry.
Foreign Service | 30 chainages | Multiple services at one chainage | INFORMATION ONLY | 30 chainage values carry more than one foreign service. Expected where services run in a common trench, but each needs its own crossing treatment.
Creek Crossing | 23 records | Watercourse not named | FLAGGED - left blank | 23 of 32 trenched creek crossings have no watercourse name in the source (e.g. PWG-CC-0001, PHW-CC-0002, PHW-CC-0003, PWG-CC-0003). Only 9 are named. Names are needed for waterway barrier works approvals.
Creek Crossing | PWG-CC-0004 | Treatment refers to a missing note | FLAGGED - not changed | Creek Bed Treatment Type reads "NOTE 1", but the source table supplied no notes. The referenced Table 2 and Table 3 were not provided with the file, so the treatment cannot be resolved from this register alone.
Road & Rail Crossing | various | Trailing whitespace | NORMALISED | Method of Construction appears as ['Open Trenching '] as well as the clean value. Trimmed when loading so the column groups correctly; the source cell is unchanged.
Road & Rail Crossing | PHW-PT-0001 | Chainage disagrees with Trench Type register | FLAGGED - not changed | PHW-PT-0001 (Trees - Kieman Road) end chainage 404.867 m against the nearest Trench Type boundary 404.862 m - 5 mm apart. The schedule states it is the source of truth for open trenched crossing chainages, so the Trench Type register is the one to correct.
Road & Rail Crossing | PHW-RD-0001 | Chainage disagrees with Trench Type register | FLAGGED - not changed | PHW-RD-0001 (Access Track - Kieman Road) end chainage 1,135.000 m against the nearest Trench Type boundary 1,135.078 m - 78 mm apart. The schedule states it is the source of truth for open trenched crossing chainages, so the Trench Type register is the one to correct.
Road & Rail Crossing | PHW-RD-0003 | Chainage disagrees with Trench Type register | ROUNDING ONLY | PHW-RD-0003 (Morris Road) start chainage 4,416.743 m against the nearest Trench Type boundary 4,416.742 m - 1 mm apart. A 1-2 mm difference, so almost certainly rounding rather than a real disagreement.
Road & Rail Crossing | PHW-RD-0003 | Chainage disagrees with Trench Type register | ROUNDING ONLY | PHW-RD-0003 (Morris Road) end chainage 4,455.043 m against the nearest Trench Type boundary 4,455.042 m - 1 mm apart. A 1-2 mm difference, so almost certainly rounding rather than a real disagreement.
Road & Rail Crossing | PHW-RD-0010 | Chainage disagrees with Trench Type register | ROUNDING ONLY | PHW-RD-0010 (Second Range Crossing) start chainage 11,427.142 m against the nearest Trench Type boundary 11,427.143 m - 1 mm apart. A 1-2 mm difference, so almost certainly rounding rather than a real disagreement.
Road & Rail Crossing | PHW-RD-0012 | Chainage disagrees with Trench Type register | ROUNDING ONLY | PHW-RD-0012 (Toowoomba Cecil Plains Road) end chainage 13,346.373 m against the nearest Trench Type boundary 13,346.374 m - 1 mm apart. A 1-2 mm difference, so almost certainly rounding rather than a real disagreement.
Road & Rail Crossing | PWG-RD-0003 | Chainage disagrees with Trench Type register | FLAGGED - not changed | PWG-RD-0003 (Crockers Road) start chainage 1,857.000 m against the nearest Trench Type boundary 1,856.862 m - 138 mm apart. The schedule states it is the source of truth for open trenched crossing chainages, so the Trench Type register is the one to correct.
Road & Rail Crossing | PWG-RL-0001 | Chainage disagrees with Trench Type register | FLAGGED - not changed | PWG-RL-0001 (South Western System) end chainage 7,579.150 m against the nearest Trench Type boundary 7,579.000 m - 150 mm apart. The schedule states it is the source of truth for open trenched crossing chainages, so the Trench Type register is the one to correct.
Road & Rail Crossing | PWG-RD-0018 | Chainage disagrees with Trench Type register | FLAGGED - not changed | PWG-RD-0018 (King Street) end chainage 26,026.000 m against the nearest Trench Type boundary 26,026.470 m - 470 mm apart. The schedule states it is the source of truth for open trenched crossing chainages, so the Trench Type register is the one to correct.
Trench Stop & Bulkhead | PWG-TS-0001 to PWG-TS-0036, PWG-BS-0001 | New records in updated source | LOADED | The Trench&Bulkheads- T2W_PIPELINE.xlsm source was reissued 2026-08-17 with 37 PWG trench stop and bulkhead records that were not in the previous load. All 452 existing records are unchanged (differences are floating-point noise below 1e-11 and trailing spaces only). No records were removed from the source.
Trench Stop & Bulkhead | PHW-BS-0001 to PHW-BS-0046 | Trailing space on Utility Type | NORMALISED IN MASTER REGISTER | The reissued source writes "Bulk Head " with a trailing space on 46 bulkhead rows. Asset Type is stored trimmed in the Master Register; the Src sheet keeps the source text.
Vegetation | Sheet1 rows 15-236 | Chainage stated in kilometres | CONVERTED TO METRES | The takeoff states chainage in kilometres (0.06, 24.61) where every other register in this workbook uses metres. The takeoff's own SC(m)/EC(m) columns on the 70 PHW rows confirm the factor of 1000 (0.01 km -> 10 m). All 91 loaded records were multiplied by 1000. The Src - Tree Removal sheet keeps the kilometre values as stated.
Vegetation | Sheet1 rows 15-17 and 228-230 | Duplicate Pipe ID in source | FLAGGED - not loaded | The takeoff numbers PAE trees VEG_PAE001 to VEG_PAE003 twice, once at rows 15-17 (ch 0.06-0.51 km) and again at rows 228-230 (ch 7.13-7.25 km), so three IDs identify two assets each. PAE is not a section in this register so none of these rows were loaded; the collision must be resolved in the source before PAE can be brought in.
Vegetation | Sheet1 rows 15-17, 131-236 | Sections not present in this register | NOT LOADED | The takeoff covers PAE (12), PLG (24), PLE (32) and PEL (63) in addition to PHW and PWG. This register covers PHW, PWG, PPH and RHF only, so those 131 rows were held back. They are on the Src - Tree Removal sheet in full and can be loaded once the sections are confirmed as in scope.
Trench Stop & Bulkhead / Vegetation | 5 cells | Float storage precision on reload | NOTED - no practical effect | Five source cells hold values such as 235.00000000000003 and 1575.9999999999995, which store as 235 and 1576 when the Src sheet is written. The largest difference is 3.6e-12 m. The values are arithmetic noise in the source, not measurements.
Vegetation | Sheet1 rows 15-236 | Register totals cover all six sections | NOTED | The summary block at the top of the takeoff totals 222 points and 44,867.94 m2 across six sections. The 91 records loaded here total 13,250.24 m2 (PHW 8,329.04 + PWG 4,921.20). The register will not reconcile to the takeoff total until the other four sections are loaded.
Thrust Block | PWG-TB-026 to PWG-TB-134, PHW-TB-077 to PHW-TB-101 | New records in updated source | LOADED | The Thrust Block Register was reissued 24-8 carrying 134 records that were not in the previous load: 109 PWG and 25 PHW. Every one has a chainage. All 121 previously loaded records are unchanged - a field-by-field comparison of all 38 shared columns found zero differences. No record was removed. Asset IDs continue the existing three-digit numbering and none collides.
Thrust Block | Column AP, all 255 rows | New column in source: Thrust Block Category | LOADED - column added | The reissued register adds a Thrust Block Category column classifying each block as Bend (185), Tee (39), Isolation Valve (11), Pigging Station (5), In-Line (2) or Facility (RHF) (13). The column did not exist in the previous source, so it was added to the Master Register and populated for all 255 thrust blocks, including the 121 already held. Each backfilled value is logged individually on the Edit Log.
Thrust Block | RHF-TB-001 to RHF-TB-013 | Missing chainage now explained | RESOLVED - no chainage expected | The 13 RHF records have carried no chainage since the baseline and were flagged as a gap. The new Thrust Block Category column classifies them as "Facility (RHF) - not in pipeline index", so they sit within the Regional Header Facility and are not positioned on the pipeline chainage. The blank is correct and is not missing data. They continue to sort to the end of the Master Register and remain outside the Chainage Index count.
Thrust Block | Sheets 'Master Register - GIS rev E' and 'GIS - rev F' | Template residue sheets | NOT LOADED | Both GIS sheets in this workbook hold Jemena Port Kembla data (KGMS TO EGP, Eastern Gas Pipeline, drawing GAS-556-MA-AL-020) and carry no asset IDs. Neither is T2W data and neither has ever been loaded. Rows 294-312 of the LandPartners sheet, the colour legend and the eight Port Kembla survey rows, are hidden in this revision and remain excluded.
Trench Stop & Bulkhead | 442 records | Unit rate applied | RATED | Trench stops rated at $1,112.50 each. Rate supplied by J. Krasnoff-Hnatjuk on 24 Aug 2026. The rate is per trench stop, not per metre of trench: it pairs with the bulkhead rate and matches the two details on C-DWG-PTW-105.1 Rev 1, Issued for Construction, which shows a sand/hessian bag trench stop and a reinforced concrete bulkhead as separate items.
Trench Stop & Bulkhead | 47 records | Unit rate applied | RATED | Concrete bulkheads rated at $20,507.00 each. Rate supplied by J. Krasnoff-Hnatjuk on 24 Aug 2026. Detail on C-DWG-PTW-105.1 Rev 1, Issued for Construction: N32 concrete keyed into the trench walls and floor with N12 reinforcement, which is consistent with a rate an order of magnitude above a bagged trench stop.
All other registers | 961 records | No rate supplied | LEFT BLANK - not zero | Thrust blocks, trench sections, foreign services, creek crossings, road and rail crossings and vegetation carry no rate yet. Unit Rate, Quantity, Unit and Total Cost are deliberately blank on those rows rather than set to zero, so any total taken off this register is visibly incomplete rather than wrong.
Cost columns | Total Cost ($) | Derived, not entered | FORMULA | Total Cost is =Unit Rate x Quantity on every rated row, so changing either input updates the total. Quantity is 1 on all rated rows because both rates are per item. If a rate later moves to a length or area basis, Quantity is where that goes.
Cost formulas | Rev 5.5–5.7 sheets | Lookup ranges stopped at Master Register row 1638 | FIXED — extended to 2600 | The pipe, bend and valve registers were inserted in chainage order, not appended, so 562 existing records moved past the end of every cost range. 52 trench sections (18,546.7 m, about $7.13M), 29 trench stops and 103 thrust blocks were invisible to Cost Tracker - Linear, Cost Dashboard and Thrust Block Costing. Any figure read off those sheets before 28 Aug 2026 was understated.
Master Register | Column K, rows 1452+ | Drawing (Start) returned a no-match error on 223 records | FIXED — extended to 2600 | The array formula searched rows 2:1451 for the trench section covering the chainage. 173 pipe, 30 bend and 20 valve records in PWG sat beyond it. All resolve now.
Bend | All 211 records | Fitting Material and Fitting DN empty in the source | DERIVED — not source data | Material is DICL where the bend angle is one of the three standard design angles (11.25, 22.5, 45 deg) and MSCL otherwise. Verified against the 155 bends that sit at the exact chainage of a thrust block, which carry the material from the index drawings: 138 of 138 standard-angle bends are DICL and 14 of 14 non-standard are MSCL. DN follows the section — DICL 600 (PHW) / 375 (PWG), MSCL 650 / 450. If a bend is ever found that breaks the rule, correct the two cells and log it.
Bend / Valve / Thrust Block | Cross-register | Overlapping scope between registers | FLAGGED — left for pricing to resolve | Isolation valves and pigging stations match Table 4 thrust blocks one for one (5 and 6 isolation valves, 2 and 3 pigging stations, PHW and PWG). 145 of 211 bends sit at the exact chainage of a bend thrust block. Confirmed 27 Aug 2026 that the Table 4 rate is the block only, so the fitting is priced separately on Tables 5 and 6. If a rate covering the whole assembly is ever supplied, enter it once and leave the matching line blank.
Valve | AV and SCV records | 69 air valves and 44 scour valves carried no cost anywhere | RATE LINES CREATED — still unpriced | These are the only new assets with no representation at all in the previous cost structure. Rate Library Table 6 now holds a line for each section and valve type; every rate is blank until the BoQ items are supplied.

## Src - Thrust Block
|  | Located | C&G | TRENCH | Surveyors PtNo | E | N | Z | Survey Code | Actual Chainage | Asset Id | KP | Pipeline Section | Utility Type | Utility Description | Operator | Location | Material | Size (mm) | ID | Proven to Underside of Service | Test Point | C&G Code | Trench Code | Proposed Crossing Method | Parallel or Crossed | Design Drawing | DBYD SEQ | Separation (m) (Minimum 600mm clearance to underside of asset to TOP) | Asset DOC (m) | Pipeline DOC (m) | Depth to Underside of Asset (m) | Crossover | Within | Permit to Excavate Near Assets Required? | Permit/Notification Date | Crossing Permit Required? | Permit/Notification Date | Comments | Thrust Block Category
[11 empty] | PPH-TB-001 | 63.236 | PPH | THRUST BLOCK | Type 5 |  |  | DICL | 500 | [20 empty] | Bend
[11 empty] | PPH-TB-002 | 81.352 | PPH | THRUST BLOCK | Type 5 |  |  | DICL | 500 | [20 empty] | Bend
[11 empty] | PPH-TB-003 | 94.039 | PPH | THRUST BLOCK | Type 5 |  |  | DICL | 500 | [20 empty] | Bend
[11 empty] | PPH-TB-004 | 833.013 | PPH | THRUST BLOCK | Type 5 |  |  | DICL | 500 | [20 empty] | Bend
[11 empty] | PPH-TB-005 | 871.821 | PPH | THRUST BLOCK | Type 5 |  |  | DICL | 500 | [20 empty] | Bend
[11 empty] | PPH-TB-006 | 988.07 | PPH | THRUST BLOCK | Type 5 |  |  | DICL | 500 | [20 empty] | Bend
[11 empty] | PPH-TB-007 | 992.261 | PPH | THRUST BLOCK | Type 5 |  |  | DICL | 500 | [20 empty] | Bend
[11 empty] | PHW-TB-001 | 18.832 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-002 | 848.792 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-003 | 899.995 | PHW | THRUST BLOCK | Type 6 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-004 | 1086.423 | PHW | THRUST BLOCK | Type 6 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-005 | 1137.626 | PHW | THRUST BLOCK | Type 3 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-006 | 1256.696 | PHW | THRUST BLOCK | Type 3 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-007 | 1265.039 | PHW | THRUST BLOCK | Type 1 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-008 | 1451.029 | PHW | THRUST BLOCK | Type 1 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-009 | 1471.052 | PHW | THRUST BLOCK | Type 8 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-010 | 1675.935 | PHW | THRUST BLOCK | Type 10 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-011 | 1733.958 | PHW | THRUST BLOCK | Type 10 |  |  | MSCL | 650 | [20 empty] | Bend
[11 empty] | PHW-TB-012 | 1802.818 | PHW | THRUST BLOCK | Type 1 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-013 | 1870.316 | PHW | THRUST BLOCK | Type 2 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-014 | 1878.593 | PHW | THRUST BLOCK | Type 3 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-015 | 2029.495 | PHW | THRUST BLOCK | Type 3 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-016 | 2036.932 | PHW | THRUST BLOCK | Type 2 |  |  | MSCL | 650 | [20 empty] | Bend
[11 empty] | PHW-TB-017 | 2336.958 | PHW | THRUST BLOCK | Type 2 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-018 | 2500.706 | PHW | THRUST BLOCK | Type 6 |  |  | MSCL | 650 | [20 empty] | Bend
[11 empty] | PHW-TB-019 | 2536.539 | PHW | THRUST BLOCK | Type 5 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-020 | 2667.545 | PHW | THRUST BLOCK | Type 4 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-021 | 2679.259 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-022 | 2793.96 | PHW | THRUST BLOCK | Type 4 |  |  | MSCL | 650 | [20 empty] | Bend
[11 empty] | PHW-TB-023 | 2802.89 | PHW | THRUST BLOCK | Type 5 |  |  | MSCL | 650 | [20 empty] | Bend
[11 empty] | PHW-TB-024 | 2819.519 | PHW | THRUST BLOCK | Type 6 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-025 | 3354.973 | PHW | THRUST BLOCK | Type 3 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-026 | 3534.937 | PHW | THRUST BLOCK | Type 4 |  |  | MSCL | 650 | [20 empty] | Bend
[11 empty] | PHW-TB-027 | 3549.714 | PHW | THRUST BLOCK | Type 5 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-028 | 3833.98 | PHW | THRUST BLOCK | Type 9 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-029 | 3843.886 | PHW | THRUST BLOCK | Type 5 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-030 | 3858.762 | PHW | THRUST BLOCK | Type 6 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-031 | 4304.94 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-032 | 4409.494 | PHW | THRUST BLOCK | Type 4 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-033 | 4413.12 | PHW | THRUST BLOCK | Type 9 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-034 | 4859.322 | PHW | THRUST BLOCK | Type 5 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-035 | 5356.119 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-036 | 5386.241 | PHW | THRUST BLOCK | Type 5 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-037 | 5498.469 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-038 | 5641.654 | PHW | THRUST BLOCK | Type 9 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-039 | 5719.91 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-040 | 5823.561 | PHW | THRUST BLOCK | Type 9 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-041 | 5851.91 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-042 | 5909.993 | PHW | THRUST BLOCK | Type 5 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-043 | 6101.187 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-044 | 6181.401 | PHW | THRUST BLOCK | Type 7 |  |  | MSCL | 650 | [20 empty] | Bend
[11 empty] | PHW-TB-045 | 7780.848 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-046 | 7936.403 | PHW | THRUST BLOCK | Type 4 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-047 | 8345.315 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-048 | 8350.305 | PHW | THRUST BLOCK | Type 5 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-049 | 8676.185 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-050 | 8768.417 | PHW | THRUST BLOCK | Type 5 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-051 | 9056.494 | PHW | THRUST BLOCK | Type 5 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-052 | 9146.86 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-053 | 9411.852 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-054 | 9422.385 | PHW | THRUST BLOCK | Type 4 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-055 | 9885.483 | PHW | THRUST BLOCK | Type 10 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-056 | 9979.18 | PHW | THRUST BLOCK | Type 6 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-057 | 9984.731 | PHW | THRUST BLOCK | Type 4 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-058 | 10177.634 | PHW | THRUST BLOCK | Type 4 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-059 | 10319.973 | PHW | THRUST BLOCK | Type 4 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-060 | 10337.161 | PHW | THRUST BLOCK | Type 6 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-061 | 10378.599 | PHW | THRUST BLOCK | Type 4 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-062 | 10459.505 | PHW | THRUST BLOCK | Type 1 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-063 | 10699.881 | PHW | THRUST BLOCK | Type 3 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-064 | 11370.095 | PHW | THRUST BLOCK | Type 6 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-065 | 11382.203 | PHW | THRUST BLOCK | Type 4 |  |  | MSCL | 650 | [20 empty] | Bend
[11 empty] | PHW-TB-066 | 11589.46 | PHW | THRUST BLOCK | Type 4 |  |  | MSCL | 650 | [20 empty] | Bend
[11 empty] | PHW-TB-067 | 13230.192 | PHW | THRUST BLOCK | Type 4 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-068 | 13238.609 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-069 | 13674.348 | PHW | THRUST BLOCK | Type 1 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-070 | 14107.829 | PHW | THRUST BLOCK | Type 1 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-071 | 14119.348 | PHW | THRUST BLOCK | Type 10 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-072 | 17043.684 | PHW | THRUST BLOCK | Type 1 |  |  | MSCL | 650 | [20 empty] | Bend
[11 empty] | PHW-TB-073 | 18060.322 | PHW | THRUST BLOCK | Type 1 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-074 | 18066.852 | PHW | THRUST BLOCK | Type 4 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-075 | 18577.023 | PHW | THRUST BLOCK | Type 4 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PHW-TB-076 | 18590.921 | PHW | THRUST BLOCK | Type 11 |  |  | DICL | 600 | [20 empty] | Bend
[11 empty] | PWG-TB-001 | 0.548 | PWG | THRUST BLOCK | Type 9 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-002 | 14.172 | PWG | THRUST BLOCK | Type 5 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-003 | 42.513 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-004 | 228.027 | PWG | THRUST BLOCK | Type 6 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-005 | 323.528 | PWG | THRUST BLOCK | Type 6 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-006 | 424.209 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-007 | 611.583 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-008 | 700.553 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-009 | 995.153 | PWG | THRUST BLOCK | Type 5 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-010 | 1488.93 | PWG | THRUST BLOCK | Type 5 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-011 | 1507.505 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-012 | 1570.993 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-013 | 1630.183 | PWG | THRUST BLOCK | Type 5 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-014 | 1906.136 | PWG | THRUST BLOCK | Type 6 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-015 | 2596.042 | PWG | THRUST BLOCK | Type 6 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-016 | 2691.626 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-017 | 2916.826 | PWG | THRUST BLOCK | Type 9 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-018 | 4005.999 | PWG | THRUST BLOCK | Type 11 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-019 | 5442.668 | PWG | THRUST BLOCK | Type 11 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-020 | 5475.997 | PWG | THRUST BLOCK | Type 7 |  |  | MSCL | 450 | [20 empty] | Bend
[11 empty] | PWG-TB-021 | 7122.979 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-022 | 7177.914 | PWG | THRUST BLOCK | Type 6 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-023 | 7542.564 | PWG | THRUST BLOCK | Type 6 |  |  | MSCL | 450 | [20 empty] | Bend
[11 empty] | PWG-TB-024 | 7546.037 | PWG | THRUST BLOCK | Type 6 |  |  | MSCL | 450 | [20 empty] | Bend
[11 empty] | PWG-TB-025 | 7583.581 | PWG | THRUST BLOCK | Type 6 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | RHF-TB-001 |  | RHF | THRUST BLOCK | RHF TYPE 1 | [24 empty] | Facility (RHF) - not in pipeline index
[11 empty] | RHF-TB-002 |  | RHF | THRUST BLOCK | RHF TYPE 1 | [24 empty] | Facility (RHF) - not in pipeline index
[11 empty] | RHF-TB-003 |  | RHF | THRUST BLOCK | RHF TYPE 3 | [24 empty] | Facility (RHF) - not in pipeline index
[11 empty] | RHF-TB-004 |  | RHF | THRUST BLOCK | RHF TYPE 2 | [24 empty] | Facility (RHF) - not in pipeline index
[11 empty] | RHF-TB-005 |  | RHF | THRUST BLOCK | RHF TYPE 1 | [24 empty] | Facility (RHF) - not in pipeline index
[11 empty] | RHF-TB-006 |  | RHF | THRUST BLOCK | RHF TYPE 4 | [24 empty] | Facility (RHF) - not in pipeline index
[11 empty] | RHF-TB-007 |  | RHF | THRUST BLOCK | RHF TYPE 4 | [24 empty] | Facility (RHF) - not in pipeline index
| + | [9 empty] | RHF-TB-008 |  | RHF | THRUST BLOCK | RHF TYPE 2 | [24 empty] | Facility (RHF) - not in pipeline index
[11 empty] | RHF-TB-009 |  | RHF | THRUST BLOCK | RHF TYPE 1 | [24 empty] | Facility (RHF) - not in pipeline index
[11 empty] | RHF-TB-010 |  | RHF | THRUST BLOCK | RHF TYPE 4 | [24 empty] | Facility (RHF) - not in pipeline index
[11 empty] | RHF-TB-011 |  | RHF | THRUST BLOCK | RHF TYPE 4 | [24 empty] | Facility (RHF) - not in pipeline index
[11 empty] | RHF-TB-012 |  | RHF | THRUST BLOCK | RHF TYPE 1 | [24 empty] | Facility (RHF) - not in pipeline index
[11 empty] | RHF-TB-013 |  | RHF | THRUST BLOCK | TYPE 1 | [24 empty] | Facility (RHF) - not in pipeline index
[11 empty] | PWG-TB-026 | 7587.138 | PWG | THRUST BLOCK | Type 6 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-027 | 7618.704 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-028 | 7619.979 | PWG | THRUST BLOCK | Type 11 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-029 | 7646.073 | PWG | THRUST BLOCK | Type 11 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-030 | 7862.684 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-031 | 7910.66 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-032 | 7957.939 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-033 | 7973.15 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-034 | 8109.465 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-035 | 8202.694 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-036 | 8245.381 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-037 | 8288.124 | PWG | THRUST BLOCK | Type 6 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-038 | 8465.757 | PWG | THRUST BLOCK | Type 9 |  |  | MSCL | 450 | [20 empty] | Bend
[11 empty] | PWG-TB-039 | 8481.865 | PWG | THRUST BLOCK | Type 4 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-040 | 8485.834 | PWG | THRUST BLOCK | Type 6 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-041 | 8545.354 | PWG | THRUST BLOCK | Type 6 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-042 | 8547.89 | PWG | THRUST BLOCK | Type 6 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-043 | 9455.661 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-044 | 10741.055 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-045 | 10780.713 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-046 | 11468.159 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-047 | 11759.158 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-048 | 11768.094 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-049 | 11773.094 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-050 | 11782.037 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-051 | 12099.939 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-052 | 12694.713 | PWG | THRUST BLOCK | Type 5 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-053 | 12747.863 | PWG | THRUST BLOCK | Type 5 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-054 | 12782.914 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-055 | 13394.686 | PWG | THRUST BLOCK | Type 9 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-056 | 13416.368 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-057 | 14076.214 | PWG | THRUST BLOCK | Type 11 |  |  | MSCL | 450 | [20 empty] | Bend
[11 empty] | PWG-TB-058 | 14139.442 | PWG | THRUST BLOCK | Type 10 |  |  | MSCL | 450 | [20 empty] | Bend
[11 empty] | PWG-TB-059 | 14178.758 | PWG | THRUST BLOCK | Type 10 |  |  | MSCL | 450 | [20 empty] | Bend
[11 empty] | PWG-TB-060 | 14883.12 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-061 | 16429.262 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-062 | 16975.581 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-063 | 16982.79 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-064 | 17433.278 | PWG | THRUST BLOCK | Type 6 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-065 | 17830.527 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-066 | 18027.533 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-067 | 18096.401 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-068 | 18147.994 | PWG | THRUST BLOCK | Type 5 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-069 | 18150.734 | PWG | THRUST BLOCK | Type 5 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-070 | 18181.794 | PWG | THRUST BLOCK | Type 6 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-071 | 18190.097 | PWG | THRUST BLOCK | Type 6 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-072 | 18785.871 | PWG | THRUST BLOCK | Type 9 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-073 | 20066.024 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-074 | 20282.529 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-075 | 20818.272 | PWG | THRUST BLOCK | Type 6 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-076 | 20947.014 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-077 | 21445.551 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-078 | 21581.657 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-079 | 21602.601 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-080 | 21631.157 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-081 | 22176.234 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-082 | 22504.051 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-083 | 22650.05 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-084 | 23112.75 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-085 | 23373.352 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-086 | 23414.166 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-087 | 23666.289 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-088 | 23999.457 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-089 | 24426.9 | PWG | THRUST BLOCK | Type 5 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-090 | 24713.951 | PWG | THRUST BLOCK | Type 5 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-091 | 24909.165 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-092 | 25129.481 | PWG | THRUST BLOCK | Type 5 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-093 | 25162.559 | PWG | THRUST BLOCK | Type 4 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-094 | 25169.588 | PWG | THRUST BLOCK | Type 5 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-095 | 25391.145 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-096 | 25800.795 | PWG | THRUST BLOCK | Type 5 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-097 | 25804.926 | PWG | THRUST BLOCK | Type 5 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-098 | 25817.226 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-099 | 26038.676 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-100 | 26195.427 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-101 | 26560.798 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-102 | 26662.937 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 375 | [20 empty] | Bend
[11 empty] | PWG-TB-103 | 230.031 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-104 | 702.553 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-105 | 7092.671 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-106 | 8908.151 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-107 | 9473.063 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-108 | 10553.492 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-109 | 12687.754 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-110 | 13188.911 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-111 | 14143.438 | PWG | THRUST BLOCK | Type 6 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-112 | 14224.068 | PWG | THRUST BLOCK | Type 6 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-113 | 15788.534 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-114 | 18149.44 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-115 | 18772.846 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-116 | 19641.881 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-117 | 20287.711 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-118 | 21452.237 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-119 | 22316.144 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-120 | 22680.903 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-121 | 23376.417 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-122 | 24206.919 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-123 | 25018.345 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-124 | 25792.787 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-125 | 26041.176 | PWG | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PWG-TB-126 | 4040.672 | PWG | THRUST BLOCK | Type 12 |  |  |  | 375 | [20 empty] | Isolation Valve
[11 empty] | PWG-TB-127 | 7536.828 | PWG | THRUST BLOCK | Type 13 |  |  |  | 375 | [20 empty] | Isolation Valve
[11 empty] | PWG-TB-128 | 8475.323 | PWG | THRUST BLOCK | Type 13 |  |  |  | 375 | [20 empty] | Isolation Valve
[11 empty] | PWG-TB-129 | 8562.951 | PWG | THRUST BLOCK | Type 13 |  |  |  | 375 | [20 empty] | Isolation Valve
[11 empty] | PWG-TB-130 | 13366.211 | PWG | THRUST BLOCK | Type 13 |  |  |  | 375 | [20 empty] | Isolation Valve
[11 empty] | PWG-TB-131 | 22075.201 | PWG | THRUST BLOCK | Type 13 |  |  |  | 375 | [20 empty] | Isolation Valve
[11 empty] | PWG-TB-132 | 99.181 | PWG | THRUST BLOCK | 2 x Type 13 |  |  |  | 375 | [20 empty] | Pigging Station
[11 empty] | PWG-TB-133 | 7595.718 | PWG | THRUST BLOCK | 2 x Type 13 |  |  |  | 375 | [20 empty] | Pigging Station
[11 empty] | PWG-TB-134 | 17865.623 | PWG | THRUST BLOCK | 2 x Type 13 |  |  |  | 375 | [20 empty] | Pigging Station
[11 empty] | PHW-TB-077 | 1261.832 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PHW-TB-078 | 1727.817 | PHW | THRUST BLOCK | Type 6 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PHW-TB-079 | 2746.277 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PHW-TB-080 | 3558.423 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PHW-TB-081 | 4470 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PHW-TB-082 | 4661.417 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PHW-TB-083 | 4961.176 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PHW-TB-084 | 6796.976 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PHW-TB-085 | 8197.671 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PHW-TB-086 | 10103.635 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PHW-TB-087 | 11396.642 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PHW-TB-088 | 11596.46 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PHW-TB-089 | 13125.991 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PHW-TB-090 | 15248.457 | PHW | THRUST BLOCK | Type 7 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PHW-TB-091 | 17038.094 | PHW | THRUST BLOCK | Type 6 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PHW-TB-092 | 17984.612 | PHW | THRUST BLOCK | Type 6 |  |  | DICL | 150 | [20 empty] | Tee
[11 empty] | PHW-TB-093 | 842.62 | PHW | THRUST BLOCK | Type 12 |  |  |  | 600 | [20 empty] | Isolation Valve
[11 empty] | PHW-TB-094 | 2019.495 | PHW | THRUST BLOCK | Type 12 |  |  |  | 600 | [20 empty] | Isolation Valve
[11 empty] | PHW-TB-095 | 2140.173 | PHW | THRUST BLOCK | Type 12 |  |  |  | 600 | [20 empty] | Isolation Valve
[11 empty] | PHW-TB-096 | 7335.153 | PHW | THRUST BLOCK | Type 12 |  |  |  | 600 | [20 empty] | Isolation Valve
[11 empty] | PHW-TB-097 | 14323.567 | PHW | THRUST BLOCK | Type 12 |  |  |  | 600 | [20 empty] | Isolation Valve
[11 empty] | PHW-TB-098 | 19120.153 | PHW | THRUST BLOCK | Type 14 |  |  |  | 600 | [20 empty] | In-Line
[11 empty] | PHW-TB-099 | 19155.385 | PHW | THRUST BLOCK | Type 14 |  |  |  | 600 | [20 empty] | In-Line
[11 empty] | PHW-TB-100 | 9801.143 | PHW | THRUST BLOCK | 2 x Type 12 |  |  |  | 600 | [20 empty] | Pigging Station
[11 empty] | PHW-TB-101 | 19097.802 | PHW | THRUST BLOCK | 2 x Type 12 |  |  |  | 600 | [20 empty] | Pigging Station
Verbatim rows from Thrust Block Register - T2W_PIPELINE 24-8.xlsm, sheet 'Master Register - LandPartners', rows 6-260. Reloaded 24 Aug 2026; the previous load (121 rows) is preserved in the dated backup. Rows 294-312 of the source (colour legend and the Jemena Port Kembla template residue) are excluded, as in every prior load.

## Src - Trench Type
Located | C&G | TRENCH | Surveyors PtNo | E | N | Z | Survey Code | Actual Chainage | Drawing (START) | Drawing (END) | KP (START) | KP (END) | Trench Type | Total Length Sections (m) | Pipeline Section | Utility Description | Operator | Location | Material | Size (mm) | ID | Proven to Underside of Service | Test Point | C&G Code | Trench Code | Proposed Crossing Method | Parallel or Crossed | Design Drawing | DBYD SEQ | Separation (m) (Minimum 600mm clearance to underside of asset to TOP) | Asset DOC (m) | Pipeline DOC (m) | Depth to Underside of Asset (m) | Crossover | Within | Permit to Excavate Near Assets Required? | Permit/Notification Date | Crossing Permit Required? | Permit/Notification Date (2) | Comments | Trench Type (2) | PWG | PHW | Total (m) | No. of Sections | Source Row
[9 empty] | D-DWG-PHW-001.2 | D-DWG-PHW-001.2 | 0 | 327.039 | 1A | 327.039 | PHW | [25 empty] | 1A | 25128.364 | 16838.593 | 41966.957 | 85 | 6
[9 empty] | D-DWG-PHW-001.2 | D-DWG-PHW-001.2 | 327.039 | 404.862 | 8A | 77.823 | PHW | [25 empty] | 1B/1C | 134.447 | 58.129 | 192.576 | 6 | 7
[9 empty] | D-DWG-PHW-001.2 | D-DWG-PHW-001.2 | 404.862 | 426.39 | 4 | 21.528 | PHW | [25 empty] | 1A/1B/1C | 94.046 | 143.795 | 237.841 | 7 | 8
[9 empty] | D-DWG-PHW-001.2 | D-DWG-PHW-002.2 | 426.39 | 878.592 | 1A | 452.202 | PHW | [25 empty] | 2 | 15 | 25.754 | 40.754 | 4 | 9
[9 empty] | D-DWG-PHW-002.2 | D-DWG-PHW-002.2 | 878.592 | 886.749 | 4 | 8.157 | PHW | [25 empty] | 4 | 432.844 | 683.233 | 1116.077 | 41 | 10
[9 empty] | D-DWG-PHW-002.2 | D-DWG-PHW-002.2 | 886.749 | 955.896 | 7 | 69.147 | PHW | [25 empty] | 4&6 | 60.742 | 0 | 60.742 | 2 | 11
[9 empty] | D-DWG-PHW-002.2 | D-DWG-PHW-002.2 | 955.896 | 960.896 | 4&7 | 5 | PHW | [25 empty] | 4&7 | 18.466 | 28.91 | 47.376 | 4 | 12
[9 empty] | D-DWG-PHW-002.2 | D-DWG-PHW-002.2 | 960.896 | 1092.896 | 7 | 132 | PHW | [25 empty] | 5 | 387.402 | 532.124 | 919.526 | 16 | 13
[9 empty] | D-DWG-PHW-002.2 | D-DWG-PHW-002.2 | 1092.896 | 1116.806 | 4&7 | 23.91 | PHW | [25 empty] | 6 | 91.347 | 83.29 | 174.637 | 8 | 14
[9 empty] | D-DWG-PHW-002.2 | D-DWG-PHW-002.2 | 1116.806 | 1135.078 | 7 | 18.272 | PHW | [25 empty] | 7 | 291.939 | 247.067 | 539.006 | 15 | 15
[9 empty] | D-DWG-PHW-002.2 | D-DWG-PHW-002.2 | 1135.078 | 1142.896 | 1A | 7.818 | PHW | [25 empty] | 8A | 357.868 | 515.844 | 873.712 | 19 | 16
[9 empty] | D-DWG-PHW-002.2 | D-DWG-PHW-002.2 | 1142.896 | 1182.245 | 4 | 39.349 | PHW | [25 empty] | Total | 27012.465 | 19156.739 | 46169.204 | 207 | 17
[9 empty] | D-DWG-PHW-002.2 | D-DWG-PHW-002.2 | 1182.245 | 1217.093 | 1A | 34.848 | PHW | [25 empty] | Check: register total |  |  | 46169.204 | 207 | 18
[9 empty] | D-DWG-PHW-002.2 | D-DWG-PHW-002.2 | 1217.093 | 1232.924 | 4 | 15.831 | PHW | [30 empty] | 19
[9 empty] | D-DWG-PHW-002.2 | D-DWG-PHW-002.2 | 1232.924 | 1255.696 | 8A | 22.772 | PHW | [30 empty] | 20
[9 empty] | D-DWG-PHW-002.2 | D-DWG-PHW-003.2 | 1255.696 | 1733.958 | 1A | 478.262 | PHW | [30 empty] | 21
[9 empty] | D-DWG-PHW-003.2 | D-DWG-PHW-003.2 | 1733.958 | 1787.137 | 5 | 53.179 | PHW | [30 empty] | 22
[9 empty] | D-DWG-PHW-003.2 | D-DWG-PHW-003.2 | 1787.137 | 2036.932 | 1A | 249.795 | PHW | [30 empty] | 23
[9 empty] | D-DWG-PHW-003.2 | D-DWG-PHW-003.2 | 2036.932 | 2038.507 | 4 | 1.575 | PHW | [30 empty] | 24
[9 empty] | D-DWG-PHW-003.2 | D-DWG-PHW-004.2 | 2038.507 | 2110.24 | 8A | 71.733 | PHW | [30 empty] | 25
[9 empty] | D-DWG-PHW-004.2 | D-DWG-PHW-004.2 | 2110.24 | 2122.834 | 4 | 12.594 | PHW | [30 empty] | 26
[9 empty] | D-DWG-PHW-004.2 | D-DWG-PHW-004.2 | 2122.834 | 2468.34 | 1A | 345.506 | PHW | [30 empty] | 27
[9 empty] | D-DWG-PHW-004.2 | D-DWG-PHW-004.2 | 2468.34 | 2500.706 | 4 | 32.366 | PHW | [30 empty] | 28
[9 empty] | D-DWG-PHW-004.2 | D-DWG-PHW-004.2 | 2500.706 | 2791.911 | 1A | 291.205 | PHW | [30 empty] | 29
[9 empty] | D-DWG-PHW-004.2 | D-DWG-PHW-005.2 | 2791.911 | 2813.28 | 4 | 21.369 | PHW | [30 empty] | 30
[9 empty] | D-DWG-PHW-005.2 | D-DWG-PHW-005.2 | 2813.28 | 2846.195 | 1A | 32.915 | PHW | [30 empty] | 31
[9 empty] | D-DWG-PHW-005.2 | D-DWG-PHW-005.2 | 2846.195 | 2881.928 | 4 | 35.733 | PHW | [30 empty] | 32
[9 empty] | D-DWG-PHW-005.2 | D-DWG-PHW-006.2 | 2881.928 | 3534.937 | 1A | 653.009 | PHW | [30 empty] | 33
[9 empty] | D-DWG-PHW-006.2 | D-DWG-PHW-006.2 | 3534.937 | 3547.077 | 4 | 12.14 | PHW | [30 empty] | 34
[9 empty] | D-DWG-PHW-006.2 | D-DWG-PHW-007.2 | 3547.077 | 4416.742 | 1A | 869.665 | PHW | [30 empty] | 35
[9 empty] | D-DWG-PHW-007.2 | D-DWG-PHW-007.2 | 4416.742 | 4455.042 | 8A | 38.3 | PHW | [30 empty] | 36
[9 empty] | D-DWG-PHW-007.2 | D-DWG-PHW-007.2 | 4455.042 | 4534.979 | 4 | 79.937 | PHW | [30 empty] | 37
[9 empty] | D-DWG-PHW-007.2 | D-DWG-PHW-007.2 | 4534.979 | 4663.144 | 1A | 128.165 | PHW | [30 empty] | 38
[9 empty] | D-DWG-PHW-007.2 | D-DWG-PHW-007.2 | 4663.144 | 4695.751 | 5 | 32.607 | PHW | [30 empty] | 39
[9 empty] | D-DWG-PHW-007.2 | D-DWG-PHW-007.2 | 4695.751 | 4712.804 | 2 | 17.053 | PHW | [30 empty] | 40
[9 empty] | D-DWG-PHW-007.2 | D-DWG-PHW-007.2 | 4712.804 | 4758.731 | 1A/1B/1C | 45.927 | PHW | [30 empty] | 41
[9 empty] | D-DWG-PHW-007.2 | D-DWG-PHW-009.2 | 4758.731 | 5731.564 | 1A | 972.833 | PHW | [30 empty] | 42
[9 empty] | D-DWG-PHW-009.2 | D-DWG-PHW-009.2 | 5731.564 | 5754.45 | 4 | 22.886 | PHW | [30 empty] | 43
[9 empty] | D-DWG-PHW-009.2 | D-DWG-PHW-009.2 | 5754.45 | 6114.476 | 1A | 360.026 | PHW | [30 empty] | 44
[9 empty] | D-DWG-PHW-009.2 | D-DWG-PHW-009.2 | 6114.476 | 6160.84 | 4 | 46.364 | PHW | [30 empty] | 45
[9 empty] | D-DWG-PHW-009.2 | D-DWG-PHW-010.2 | 6160.84 | 6368.309 | 1A | 207.469 | PHW | [30 empty] | 46
[9 empty] | D-DWG-PHW-010.2 | D-DWG-PHW-010.2 | 6368.309 | 6392.653 | 6 | 24.344 | PHW | [30 empty] | 47
[9 empty] | D-DWG-PHW-010.2 | D-DWG-PHW-010.2 | 6392.653 | 6481.011 | 1A | 88.358 | PHW | [30 empty] | 48
[9 empty] | D-DWG-PHW-010.2 | D-DWG-PHW-010.2 | 6481.011 | 6506.275 | 4 | 25.264 | PHW | [30 empty] | 49
[9 empty] | D-DWG-PHW-010.2 | D-DWG-PHW-010.2 | 6506.275 | 6772.73 | 1A | 266.455 | PHW | [30 empty] | 50
[9 empty] | D-DWG-PHW-010.2 | D-DWG-PHW-010.2 | 6772.73 | 6792.875 | 5 | 20.145 | PHW | [30 empty] | 51
[9 empty] | D-DWG-PHW-010.2 | D-DWG-PHW-010.2 | 6792.875 | 6886.695 | 1A | 93.82 | PHW | [30 empty] | 52
[9 empty] | D-DWG-PHW-010.2 | D-DWG-PHW-010.2 | 6886.695 | 6934.724 | 5 | 48.029 | PHW | [30 empty] | 53
[9 empty] | D-DWG-PHW-010.2 | D-DWG-PHW-010.2 | 6934.724 | 6980.09 | 1A | 45.366 | PHW | [30 empty] | 54
[9 empty] | D-DWG-PHW-010.2 | D-DWG-PHW-011.2 | 6980.09 | 7035.325 | 8A | 55.235 | PHW | [30 empty] | 55
[9 empty] | D-DWG-PHW-011.2 | D-DWG-PHW-011.2 | 7035.325 | 7046.827 | 4 | 11.502 | PHW | [30 empty] | 56
[9 empty] | D-DWG-PHW-011.2 | D-DWG-PHW-012.2 | 7046.827 | 7819.18 | 1A | 772.353 | PHW | [30 empty] | 57
[9 empty] | D-DWG-PHW-012.2 | D-DWG-PHW-012.2 | 7819.18 | 7833.422 | 7 | 14.242 | PHW | [30 empty] | 58
[9 empty] | D-DWG-PHW-012.2 | D-DWG-PHW-012.2 | 7833.422 | 8192.409 | 1A | 358.987 | PHW | [30 empty] | 59
[9 empty] | D-DWG-PHW-012.2 | D-DWG-PHW-012.2 | 8192.409 | 8250.538 | 1B/1C | 58.129 | PHW | [30 empty] | 60
[9 empty] | D-DWG-PHW-012.2 | D-DWG-PHW-013.2 | 8250.538 | 9069.736 | 1A | 819.198 | PHW | [30 empty] | 61
[9 empty] | D-DWG-PHW-013.2 | D-DWG-PHW-013.2 | 9069.736 | 9078.356 | 4 | 8.62 | PHW | [30 empty] | 62
[9 empty] | D-DWG-PHW-013.2 | D-DWG-PHW-013.2 | 9078.356 | 9087.51 | 1A | 9.154 | PHW | [30 empty] | 63
[9 empty] | D-DWG-PHW-013.2 | D-DWG-PHW-014.2 | 9087.51 | 9105.7 | 4 | 18.19 | PHW | [30 empty] | 64
[9 empty] | D-DWG-PHW-014.2 | D-DWG-PHW-014.2 | 9105.7 | 9330.84 | 1A | 225.14 | PHW | [30 empty] | 65
[9 empty] | D-DWG-PHW-014.2 | D-DWG-PHW-014.2 | 9330.84 | 9333.706 | 2 | 2.866 | PHW | [30 empty] | 66
[9 empty] | D-DWG-PHW-014.2 | D-DWG-PHW-014.2 | 9333.706 | 9341.679 | 1A/1B/1C | 7.973 | PHW | [30 empty] | 67
[9 empty] | D-DWG-PHW-014.2 | D-DWG-PHW-014.2 | 9341.679 | 9431.212 | 1A | 89.533 | PHW | [30 empty] | 68
[9 empty] | D-DWG-PHW-014.2 | D-DWG-PHW-014.2 | 9431.212 | 9437.047 | 2 | 5.835 | PHW | [30 empty] | 69
[9 empty] | D-DWG-PHW-014.2 | D-DWG-PHW-014.2 | 9437.047 | 9446.253 | 1A/1B/1C | 9.206 | PHW | [30 empty] | 70
[9 empty] | D-DWG-PHW-014.2 | D-DWG-PHW-015.2 | 9446.253 | 10080.68 | 1A | 634.427 | PHW | [30 empty] | 71
[9 empty] | D-DWG-PHW-015.2 | D-DWG-PHW-015.2 | 10080.68 | 10101.635 | 5 | 20.955 | PHW | [30 empty] | 72
[9 empty] | D-DWG-PHW-015.2 | D-DWG-PHW-015.2 | 10101.635 | 10347.95 | 1A | 246.315 | PHW | [30 empty] | 73
[9 empty] | D-DWG-PHW-015.2 | D-DWG-PHW-015.2 | 10347.95 | 10367.669 | 6 | 19.719 | PHW | [30 empty] | 74
[9 empty] | D-DWG-PHW-015.2 | D-DWG-PHW-016.2 | 10367.669 | 10531.389 | 1A | 163.72 | PHW | [30 empty] | 75
[9 empty] | D-DWG-PHW-016.2 | D-DWG-PHW-016.2 | 10531.389 | 10582.353 | 4 | 50.964 | PHW | [30 empty] | 76
[9 empty] | D-DWG-PHW-016.2 | D-DWG-PHW-016.2 | 10582.353 | 10645.383 | 8A | 63.03 | PHW | [30 empty] | 77
[9 empty] | D-DWG-PHW-016.2 | D-DWG-PHW-016.2 | 10645.383 | 10684.369 | 4 | 38.986 | PHW | [30 empty] | 78
[9 empty] | D-DWG-PHW-016.2 | D-DWG-PHW-016.2 | 10684.369 | 11171.188 | 1A | 486.819 | PHW | [30 empty] | 79
[9 empty] | D-DWG-PHW-016.2 | D-DWG-PHW-016.2 | 11171.188 | 11191.258 | 6 | 20.07 | PHW | [30 empty] | 80
[9 empty] | D-DWG-PHW-016.2 | D-DWG-PHW-017.2 | 11191.258 | 11382.203 | 1A | 190.945 | PHW | [30 empty] | 81
[9 empty] | D-DWG-PHW-017.2 | D-DWG-PHW-017.2 | 11382.203 | 11427.143 | 4 | 44.94 | PHW | [30 empty] | 82
[9 empty] | D-DWG-PHW-017.2 | D-DWG-PHW-017.2 | 11427.143 | 11509.11 | 8A | 81.967 | PHW | [30 empty] | 83
[9 empty] | D-DWG-PHW-017.2 | D-DWG-PHW-017.2 | 11509.11 | 11589.46 | 5 | 80.35 | PHW | [30 empty] | 84
[9 empty] | D-DWG-PHW-017.2 | D-DWG-PHW-017.2 | 11589.46 | 11596.46 | 1A | 7 | PHW | [30 empty] | 85
[9 empty] | D-DWG-PHW-017.2 | D-DWG-PHW-017.2 | 11596.46 | 11750.532 | 5 | 154.072 | PHW | [30 empty] | 86
[9 empty] | D-DWG-PHW-017.2 | D-DWG-PHW-018.2 | 11750.532 | 12441.199 | 1A | 690.667 | PHW | [30 empty] | 87
[9 empty] | D-DWG-PHW-018.2 | D-DWG-PHW-018.2 | 12441.199 | 12457.644 | 4 | 16.445 | PHW | [30 empty] | 88
[9 empty] | D-DWG-PHW-018.2 | D-DWG-PHW-018.2 | 12457.644 | 12471.05 | 7 | 13.406 | PHW | [30 empty] | 89
[9 empty] | D-DWG-PHW-018.2 | D-DWG-PHW-019.2 | 12471.05 | 13274.77 | 1A | 803.72 | PHW | [30 empty] | 90
[9 empty] | D-DWG-PHW-019.2 | D-DWG-PHW-020.2 | 13274.77 | 13346.374 | 8A | 71.604 | PHW | [30 empty] | 91
[9 empty] | D-DWG-PHW-020.2 | D-DWG-PHW-022.2 | 13346.374 | 14778.123 | 1A | 1431.749 | PHW | [30 empty] | 92
[9 empty] | D-DWG-PHW-022.2 | D-DWG-PHW-022.2 | 14778.123 | 14806.133 | 4 | 28.01 | PHW | [30 empty] | 93
[9 empty] | D-DWG-PHW-022.2 | D-DWG-PHW-022.2 | 14806.133 | 14839.513 | 8A | 33.38 | PHW | [30 empty] | 94
[9 empty] | D-DWG-PHW-022.2 | D-DWG-PHW-023.2 | 14839.513 | 15743.419 | 1A | 903.906 | PHW | [30 empty] | 95
[9 empty] | D-DWG-PHW-023.2 | D-DWG-PHW-023.2 | 15743.419 | 15762.576 | 6 | 19.157 | PHW | [30 empty] | 96
[9 empty] | D-DWG-PHW-023.2 | D-DWG-PHW-024.2 | 15762.576 | 16145.329 | 1A | 382.753 | PHW | [30 empty] | 97
[9 empty] | D-DWG-PHW-024.2 | D-DWG-PHW-024.2 | 16145.329 | 16226.018 | 1A/1B/1C | 80.689 | PHW | [30 empty] | 98
[9 empty] | D-DWG-PHW-024.2 | D-DWG-PHW-025.2 | 16226.018 | 16956.128 | 1A | 730.11 | PHW | [30 empty] | 99
[9 empty] | D-DWG-PHW-025.2 | D-DWG-PHW-025.2 | 16956.128 | 17043.684 | 5 | 87.556 | PHW | [30 empty] | 100
[9 empty] | D-DWG-PHW-025.2 | D-DWG-PHW-026.2 | 17043.684 | 17910.948 | 1A | 867.264 | PHW | [30 empty] | 101
[9 empty] | D-DWG-PHW-026.2 | D-DWG-PHW-026.2 | 17910.948 | 17996.139 | 4 | 85.191 | PHW | [30 empty] | 102
[9 empty] | D-DWG-PHW-026.2 | D-DWG-PHW-026.2 | 17996.139 | 18075.205 | 1A | 79.066 | PHW | [30 empty] | 103
[9 empty] | D-DWG-PHW-026.2 | D-DWG-PHW-026.2 | 18075.205 | 18080.497 | 4 | 5.292 | PHW | [30 empty] | 104
[9 empty] | D-DWG-PHW-026.2 | D-DWG-PHW-028.2 | 18080.497 | 19120.154 | 1A | 1039.657 | PHW | [30 empty] | 105
[9 empty] | D-DWG-PHW-028.2 | D-DWG-PHW-028.2 | 19120.154 | 19155.385 | 5 | 35.231 | PHW | [30 empty] | 106
[9 empty] | D-DWG-PHW-028.2 | D-DWG-PHW-028.2 | 19155.385 | 19156.739 | 1A | 1.354 | PHW | [30 empty] | 107
[9 empty] | D-DWG-PWG-001.2 | D-DWG-PWG-001.2 | 0 | 3.804 | 1A | 3.804 | PWG | [30 empty] | 109
[9 empty] | D-DWG-PWG-001.2 | D-DWG-PWG-001.2 | 3.804 | 6.229 | 4 | 2.425 | PWG | [30 empty] | 110
[9 empty] | D-DWG-PWG-001.2 | D-DWG-PWG-001.2 | 6.229 | 14.172 | 1A | 7.943 | PWG | [30 empty] | 111
[9 empty] | D-DWG-PWG-001.2 | D-DWG-PWG-001.2 | 14.172 | 42.513 | 7 | 28.341 | PWG | [30 empty] | 112
[9 empty] | D-DWG-PWG-001.2 | D-DWG-PWG-002.2 | 42.513 | 823.6 | 1A | 781.087 | PWG | [30 empty] | 113
[9 empty] | D-DWG-PWG-002.2 | D-DWG-PWG-002.2 | 823.6 | 889.23 | 5 | 65.63 | PWG | [30 empty] | 114
[9 empty] | D-DWG-PWG-002.2 | D-DWG-PWG-002.2 | 889.23 | 929.856 | 1A/1B/1C | 40.626 | PWG | [30 empty] | 115
[9 empty] | D-DWG-PWG-002.2 | D-DWG-PWG-002.2 | 929.856 | 1181.379 | 1A | 251.523 | PWG | [30 empty] | 116
[9 empty] | D-DWG-PWG-002.2 | D-DWG-PWG-002.2 | 1181.379 | 1186.379 | 4 | 5 | PWG | [30 empty] | 117
[9 empty] | D-DWG-PWG-002.2 | D-DWG-PWG-003.2 | 1186.379 | 1488.93 | 1A | 302.551 | PWG | [30 empty] | 118
[9 empty] | D-DWG-PWG-003.2 | D-DWG-PWG-003.2 | 1488.93 | 1507.505 | 7 | 18.575 | PWG | [30 empty] | 119
[9 empty] | D-DWG-PWG-003.2 | D-DWG-PWG-003.2 | 1507.505 | 1856.862 | 1A | 349.357 | PWG | [30 empty] | 120
[9 empty] | D-DWG-PWG-003.2 | D-DWG-PWG-003.2 | 1856.862 | 1876.481 | 7 | 19.619 | PWG | [30 empty] | 121
[9 empty] | D-DWG-PWG-003.2 | D-DWG-PWG-003.2 | 1876.481 | 1888.54 | 1A | 12.059 | PWG | [30 empty] | 122
[9 empty] | D-DWG-PWG-003.2 | D-DWG-PWG-003.2 | 1888.54 | 1902.016 | 4&7 | 13.476 | PWG | [30 empty] | 123
[9 empty] | D-DWG-PWG-003.2 | D-DWG-PWG-003.2 | 1902.016 | 2043.24 | 1A | 141.224 | PWG | [30 empty] | 124
[9 empty] | D-DWG-PWG-003.2 | D-DWG-PWG-003.2 | 2043.24 | 2048.591 | 4 | 5.351 | PWG | [30 empty] | 125
[9 empty] | D-DWG-PWG-003.2 | D-DWG-PWG-004.2 | 2048.591 | 2413.402 | 1A | 364.811 | PWG | [30 empty] | 126
[9 empty] | D-DWG-PWG-004.2 | D-DWG-PWG-004.2 | 2413.402 | 2564.395 | 4 | 150.993 | PWG | [30 empty] | 127
[9 empty] | D-DWG-PWG-004.2 | D-DWG-PWG-004.2 | 2564.395 | 2592.076 | 4&6 | 27.681 | PWG | [30 empty] | 128
[9 empty] | D-DWG-PWG-004.2 | D-DWG-PWG-004.2 | 2592.076 | 2631.951 | 1A | 39.875 | PWG | [30 empty] | 129
[9 empty] | D-DWG-PWG-004.2 | D-DWG-PWG-004.2 | 2631.951 | 2691.626 | 7 | 59.675 | PWG | [30 empty] | 130
[9 empty] | D-DWG-PWG-004.2 | D-DWG-PWG-004.2 | 2691.626 | 2739.593 | 6 | 47.967 | PWG | [30 empty] | 131
[9 empty] | D-DWG-PWG-004.2 | D-DWG-PWG-004.2 | 2739.593 | 2750.013 | 4 | 10.42 | PWG | [30 empty] | 132
[9 empty] | D-DWG-PWG-004.2 | D-DWG-PWG-004.2 | 2750.013 | 2783.074 | 4&6 | 33.061 | PWG | [30 empty] | 133
[9 empty] | D-DWG-PWG-004.2 | D-DWG-PWG-004.2 | 2783.074 | 2797.815 | 4 | 14.741 | PWG | [30 empty] | 134
[9 empty] | D-DWG-PWG-004.2 | D-DWG-PWG-005.2 | 2797.815 | 2865.366 | 1A | 67.551 | PWG | [30 empty] | 135
[9 empty] | D-DWG-PWG-005.2 | D-DWG-PWG-005.2 | 2865.366 | 2908.821 | 8A | 43.455 | PWG | [30 empty] | 136
[9 empty] | D-DWG-PWG-005.2 | D-DWG-PWG-005.2 | 2908.821 | 3071.909 | 1A | 163.088 | PWG | [30 empty] | 137
[9 empty] | D-DWG-PWG-005.2 | D-DWG-PWG-005.2 | 3071.909 | 3151.909 | 5 | 80 | PWG | [30 empty] | 138
[9 empty] | D-DWG-PWG-005.2 | D-DWG-PWG-006.2 | 3151.909 | 3991.367 | 1A | 839.458 | PWG | [30 empty] | 139
[9 empty] | D-DWG-PWG-006.2 | D-DWG-PWG-006.2 | 3991.367 | 4014.479 | 1A/1B/1C | 23.112 | PWG | [30 empty] | 140
[9 empty] | D-DWG-PWG-006.2 | D-DWG-PWG-008.2 | 4014.479 | 5447.953 | 1A | 1433.474 | PWG | [30 empty] | 141
[9 empty] | D-DWG-PWG-008.2 | D-DWG-PWG-008.2 | 5447.953 | 5475.997 | 5 | 28.044 | PWG | [30 empty] | 142
[9 empty] | D-DWG-PWG-008.2 | D-DWG-PWG-011.2 | 5475.997 | 7092.671 | 1A | 1616.674 | PWG | [30 empty] | 143
[9 empty] | D-DWG-PWG-011.2 | D-DWG-PWG-011.2 | 7092.671 | 7122.979 | 1A/1B/1C | 30.308 | PWG | [30 empty] | 144
[9 empty] | D-DWG-PWG-011.2 | D-DWG-PWG-011.2 | 7122.979 | 7146.681 | 1A | 23.702 | PWG | [30 empty] | 145
[9 empty] | D-DWG-PWG-011.2 | D-DWG-PWG-011.2 | 7146.681 | 7174.681 | 4 | 28 | PWG | [30 empty] | 146
[9 empty] | D-DWG-PWG-011.2 | D-DWG-PWG-011.2 | 7174.681 | 7539.66 | 1A | 364.979 | PWG | [30 empty] | 147
[9 empty] | D-DWG-PWG-011.2 | D-DWG-PWG-011.2 | 7539.66 | 7547.413 | 4 | 7.753 | PWG | [30 empty] | 148
[9 empty] | D-DWG-PWG-011.2 | D-DWG-PWG-011.2 | 7547.413 | 7579 | 8A | 31.587 | PWG | [30 empty] | 149
[9 empty] | D-DWG-PWG-011.2 | D-DWG-PWG-011.2 | 7579 | 7624.121 | 4 | 45.121 | PWG | [30 empty] | 150
[9 empty] | D-DWG-PWG-011.2 | D-DWG-PWG-012.2 | 7624.121 | 7725.73 | 1A | 101.609 | PWG | [30 empty] | 151
[9 empty] | D-DWG-PWG-012.2 | D-DWG-PWG-012.2 | 7725.73 | 7742.01 | 7 | 16.28 | PWG | [30 empty] | 152
[9 empty] | D-DWG-PWG-012.2 | D-DWG-PWG-012.2 | 7742.01 | 7939.101 | 1A | 197.091 | PWG | [30 empty] | 153
[9 empty] | D-DWG-PWG-012.2 | D-DWG-PWG-012.2 | 7939.101 | 7941.464 | 4 | 2.363 | PWG | [30 empty] | 154
[9 empty] | D-DWG-PWG-012.2 | D-DWG-PWG-012.2 | 7941.464 | 8288.124 | 1A | 346.66 | PWG | [30 empty] | 155
[9 empty] | D-DWG-PWG-012.2 | D-DWG-PWG-012.2 | 8288.124 | 8315.201 | 8A | 27.077 | PWG | [30 empty] | 156
[9 empty] | D-DWG-PWG-012.2 | D-DWG-PWG-012.2 | 8315.201 | 8323.259 | 1A | 8.058 | PWG | [30 empty] | 157
[9 empty] | D-DWG-PWG-012.2 | D-DWG-PWG-012.2 | 8323.259 | 8335.614 | 4 | 12.355 | PWG | [30 empty] | 158
[9 empty] | D-DWG-PWG-012.2 | D-DWG-PWG-013.2 | 8335.614 | 8400.622 | 8A | 65.008 | PWG | [30 empty] | 159
[9 empty] | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 | 8400.622 | 8427.328 | 1A | 26.706 | PWG | [30 empty] | 160
[9 empty] | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 | 8427.328 | 8465.757 | 4 | 38.429 | PWG | [30 empty] | 161
[9 empty] | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 | 8465.757 | 8488.53 | 1A | 22.773 | PWG | [30 empty] | 162
[9 empty] | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 | 8488.53 | 8542.069 | 8A | 53.539 | PWG | [30 empty] | 163
[9 empty] | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 | 8542.069 | 8545.354 | 4 | 3.285 | PWG | [30 empty] | 164
[9 empty] | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 | 8545.354 | 8584.129 | 1A | 38.775 | PWG | [30 empty] | 165
[9 empty] | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 | 8584.129 | 8605.285 | 7 | 21.156 | PWG | [30 empty] | 166
[9 empty] | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 | 8605.285 | 8610.275 | 4&7 | 4.99 | PWG | [30 empty] | 167
[9 empty] | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 | 8610.275 | 8613.442 | 7 | 3.167 | PWG | [30 empty] | 168
[9 empty] | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 | 8613.442 | 8692.124 | 1A | 78.682 | PWG | [30 empty] | 169
[9 empty] | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 | 8692.124 | 8706.792 | 4 | 14.668 | PWG | [30 empty] | 170
[9 empty] | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 | 8706.792 | 8808.151 | 1A | 101.359 | PWG | [30 empty] | 171
[9 empty] | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 | 8808.151 | 8858.11 | 7 | 49.959 | PWG | [30 empty] | 172
[9 empty] | D-DWG-PWG-013.2 | D-DWG-PWG-013.2 | 8858.11 | 9100 | 1A | 241.89 | PWG | [30 empty] | 173
[9 empty] | D-DWG-PWG-014.2 | D-DWG-PWG-014.2 | 9100 | 9154.955 | 7 | 54.955 | PWG | [30 empty] | 174
[9 empty] | D-DWG-PWG-014.2 | D-DWG-PWG-018.2 | 9154.955 | 12307.423 | 1A | 3152.468 | PWG | [30 empty] | 175
[9 empty] | D-DWG-PWG-018.2 | D-DWG-PWG-018.2 | 12307.423 | 12320.895 | 6 | 13.472 | PWG | [30 empty] | 176
[9 empty] | D-DWG-PWG-018.2 | D-DWG-PWG-019.2 | 12320.895 | 12720.22 | 1A | 399.325 | PWG | [30 empty] | 177
[9 empty] | D-DWG-PWG-019.2 | D-DWG-PWG-019.2 | 12720.22 | 12734.864 | 8A | 14.644 | PWG | [30 empty] | 178
[9 empty] | D-DWG-PWG-019.2 | D-DWG-PWG-019.2 | 12734.864 | 13218.214 | 1A | 483.35 | PWG | [30 empty] | 179
[9 empty] | D-DWG-PWG-019.2 | D-DWG-PWG-019.2 | 13218.214 | 13247.005 | 8A | 28.791 | PWG | [30 empty] | 180
[9 empty] | D-DWG-PWG-019.2 | D-DWG-PWG-020.2 | 13247.005 | 13622.356 | 1A | 375.351 | PWG | [30 empty] | 181
[9 empty] | D-DWG-PWG-020.2 | D-DWG-PWG-020.2 | 13622.356 | 13637.356 | 2 | 15 | PWG | [30 empty] | 182
[9 empty] | D-DWG-PWG-020.2 | D-DWG-PWG-021.2 | 13637.356 | 14060.93 | 1A | 423.574 | PWG | [30 empty] | 183
[9 empty] | D-DWG-PWG-021.2 | D-DWG-PWG-021.2 | 14060.93 | 14076.214 | 1B/1C | 15.284 | PWG | [30 empty] | 184
[9 empty] | D-DWG-PWG-021.2 | D-DWG-PWG-021.2 | 14076.214 | 14139.442 | 5 | 63.228 | PWG | [30 empty] | 185
[9 empty] | D-DWG-PWG-021.2 | D-DWG-PWG-021.2 | 14139.442 | 14178.758 | 1B/1C | 39.316 | PWG | [30 empty] | 186
[9 empty] | D-DWG-PWG-021.2 | D-DWG-PWG-021.2 | 14178.758 | 14224.068 | 5 | 45.31 | PWG | [30 empty] | 187
[9 empty] | D-DWG-PWG-021.2 | D-DWG-PWG-021.2 | 14224.068 | 14259.827 | 1B/1C | 35.759 | PWG | [30 empty] | 188
[9 empty] | D-DWG-PWG-021.2 | D-DWG-PWG-021.2 | 14259.827 | 14304.298 | 1A | 44.471 | PWG | [30 empty] | 189
[9 empty] | D-DWG-PWG-021.2 | D-DWG-PWG-021.2 | 14304.298 | 14374.64 | 4 | 70.342 | PWG | [30 empty] | 190
[9 empty] | D-DWG-PWG-021.2 | D-DWG-PWG-021.2 | 14374.64 | 14402.293 | 1A | 27.653 | PWG | [30 empty] | 191
[9 empty] | D-DWG-PWG-021.2 | D-DWG-PWG-021.2 | 14402.293 | 14410.112 | 4 | 7.819 | PWG | [30 empty] | 192
[9 empty] | D-DWG-PWG-021.2 | D-DWG-PWG-021.2 | 14410.112 | 14525.498 | 1A | 115.386 | PWG | [30 empty] | 193
[9 empty] | D-DWG-PWG-021.2 | D-DWG-PWG-021.2 | 14525.498 | 14572.298 | 8A | 46.8 | PWG | [30 empty] | 194
[9 empty] | D-DWG-PWG-021.2 | D-DWG-PWG-024.2 | 14572.298 | 16409.05 | 1A | 1836.752 | PWG | [30 empty] | 195
[9 empty] | D-DWG-PWG-024.2 | D-DWG-PWG-024.2 | 16409.05 | 16429.262 | 7 | 20.212 | PWG | [30 empty] | 196
[9 empty] | D-DWG-PWG-024.2 | D-DWG-PWG-026.2 | 16429.262 | 18150.734 | 1A | 1721.472 | PWG | [30 empty] | 197
[9 empty] | D-DWG-PWG-026.2 | D-DWG-PWG-026.2 | 18150.734 | 18166.781 | 8A | 16.047 | PWG | [30 empty] | 198
[9 empty] | D-DWG-PWG-026.2 | D-DWG-PWG-027.2 | 18166.781 | 18217.47 | 1A | 50.689 | PWG | [30 empty] | 199
[9 empty] | D-DWG-PWG-027.2 | D-DWG-PWG-027.2 | 18217.47 | 18231.348 | 6 | 13.878 | PWG | [30 empty] | 200
[9 empty] | D-DWG-PWG-027.2 | D-DWG-PWG-032.2 | 18231.348 | 22319.185 | 1A | 4087.837 | PWG | [30 empty] | 201
[9 empty] | D-DWG-PWG-032.2 | D-DWG-PWG-032.2 | 22319.185 | 22360.55 | 5 | 41.365 | PWG | [30 empty] | 202
[9 empty] | D-DWG-PWG-032.2 | D-DWG-PWG-036.2 | 22360.55 | 24944.548 | 1A | 2583.998 | PWG | [30 empty] | 203
[9 empty] | D-DWG-PWG-036.2 | D-DWG-PWG-036.2 | 24944.548 | 24954.52 | 1B/1C | 9.972 | PWG | [30 empty] | 204
[9 empty] | D-DWG-PWG-036.2 | D-DWG-PWG-036.2 | 24954.52 | 25018.345 | 5 | 63.825 | PWG | [30 empty] | 205
[9 empty] | D-DWG-PWG-036.2 | D-DWG-PWG-036.2 | 25018.345 | 25052.461 | 1B/1C | 34.116 | PWG | [30 empty] | 206
[9 empty] | D-DWG-PWG-036.2 | D-DWG-PWG-038.2 | 25052.461 | 26010.44 | 1A | 957.979 | PWG | [30 empty] | 207
[9 empty] | D-DWG-PWG-038.2 | D-DWG-PWG-038.2 | 26010.44 | 26026.47 | 6 | 16.03 | PWG | [30 empty] | 208
[9 empty] | D-DWG-PWG-038.2 | D-DWG-PWG-038.2 | 26026.47 | 26252.108 | 1A | 225.638 | PWG | [30 empty] | 209
[9 empty] | D-DWG-PWG-038.2 | D-DWG-PWG-038.2 | 26252.108 | 26283.028 | 8A | 30.92 | PWG | [30 empty] | 210
[9 empty] | D-DWG-PWG-038.2 | D-DWG-PWG-039.2 | 26283.028 | 26988.368 | 1A | 705.34 | PWG | [30 empty] | 211
[9 empty] | D-DWG-PWG-039.2 | D-DWG-PWG-039.2 | 26988.368 | 27002.147 | 4 | 13.779 | PWG | [30 empty] | 212
[9 empty] | D-DWG-PWG-039.2 | D-DWG-PWG-039.2 | 27002.147 | 27012.465 | 1A | 10.318 | PWG | [30 empty] | 213

## Src - Trench Stop & BH
|  | Located | C&G | TRENCH | Surveyors PtNo | E | N | Z | Survey Code | Actual Chainage |  | Asset Id | Drawing # | Pipeline Section | KP | Utility Type | Notes , Not on Plan | Operator | Location | Material | Size (mm) | ID | Proven to Underside of Service | Test Point | C&G Code | Trench Code | Proposed Crossing Method | Parallel or Crossed | Design Drawing | DBYD SEQ | Separation (m) (Minimum 600mm clearance to underside of asset to TOP) | Asset DOC (m) | Pipeline DOC (m) | Depth to Underside of Asset (m) | Crossover | Within | Permit to Excavate Near Assets Required? | Permit/Notification Date
[11 empty] | PHW | PHW-TS-0001 | D-DWG-PHW-001 | 1.1 | 188 | Trench Stop
[11 empty] | PHW | PHW-TS-0002 | D-DWG-PHW-001 | 1.1 | 197.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0003 | D-DWG-PHW-001 | 1.1 | 206.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0004 | D-DWG-PHW-001 | 1.1 | 216.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0005 | D-DWG-PHW-001 | 1.1 | 225.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0006 | D-DWG-PHW-001 | 1.1 | 235 | Trench Stop
[11 empty] | PHW | PHW-TS-0007 | D-DWG-PHW-001 | 1.1 | 244.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0008 | D-DWG-PHW-001 | 1.1 | 253.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0009 | D-DWG-PHW-001 | 1.1 | 259 | Trench Stop
[11 empty] | PHW | PHW-TS-0010 | D-DWG-PHW-001 | 1.1 | 266.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0011 | D-DWG-PHW-001 | 1.1 | 274 | Trench Stop
[11 empty] | PHW | PHW-TS-0012 | D-DWG-PHW-001 | 1.1 | 281.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0013 | D-DWG-PHW-001 | 1.1 | 289 | Trench Stop
[11 empty] | PHW | PHW-TS-0014 | D-DWG-PHW-001 | 1.1 | 296.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0015 | D-DWG-PHW-001 | 1.1 | 304 | Trench Stop
[11 empty] | PHW | PHW-TS-0016 | D-DWG-PHW-001 | 1.1 | 311.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0017 | D-DWG-PHW-001 | 1.1 | 319 | Trench Stop
[11 empty] | PHW | PHW-TS-0018 | D-DWG-PHW-001 | 1.1 | 326.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0019 | D-DWG-PHW-001 | 1.2 | 448 | Trench Stop
[11 empty] | PHW | PHW-TS-0020 | D-DWG-PHW-001 | 1.3 | 463 | Trench Stop
[11 empty] | PHW | PHW-TS-0021 | D-DWG-PHW-001 | 1.3 | 471.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0022 | D-DWG-PHW-001 | 1.3 | 479.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0023 | D-DWG-PHW-001 | 1.4 | 486.1 | Trench Stop
[11 empty] | PHW | PHW-BS-0001 | D-DWG-PHW-001 | 1.4 | 492.5 | Bulk Head
[11 empty] | PHW | PHW-TS-0024 | D-DWG-PHW-001 | 1.4 | 498.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0025 | D-DWG-PHW-001 | 1.4 | 505.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0026 | D-DWG-PHW-001 | 1.4 | 511.7 | Trench Stop
[11 empty] | PHW | PHW-BS-0002 | D-DWG-PHW-001 | 1.4 | 518.1 | Bulk Head
[11 empty] | PHW | PHW-TS-0027 | D-DWG-PHW-001 | 1.4 | 524.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0028 | D-DWG-PHW-001 | 1.5 | 531.2 | Trench Stop
[11 empty] | PHW | PHW-BS-0003 | D-DWG-PHW-001 | 1.5 | 536.1 | Bulk Head
[11 empty] | PHW | PHW-TS-0029 | D-DWG-PHW-001 | 1.5 | 541 | Trench Stop
[11 empty] | PHW | PHW-TS-0030 | D-DWG-PHW-001 | 1.5 | 545.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0031 | D-DWG-PHW-001 | 1.5 | 550.8 | Trench Stop
[11 empty] | PHW | PHW-BS-0004 | D-DWG-PHW-001 | 1.5 | 553.25 | Bulk Head
[11 empty] | PHW | PHW-TS-0032 | D-DWG-PHW-001 | 1.5 | 555.7 | Trench Stop
[11 empty] | PHW | PHW-TS-0033 | D-DWG-PHW-001 | 1.5 | 560.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0034 | D-DWG-PHW-001 | 1.5 | 565.5 | Trench Stop
[11 empty] | PHW | PHW-BS-0005 | D-DWG-PHW-001 | 1.5 | 570.4 | Bulk Head
[11 empty] | PHW | PHW-TS-0035 | D-DWG-PHW-001 | 1.5 | 575.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0036 | D-DWG-PHW-001 | 1.6 | 577 | Trench Stop
[11 empty] | PHW | PHW-TS-0037 | D-DWG-PHW-001 | 1.6 | 582.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0038 | D-DWG-PHW-001 | 1.6 | 588.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0039 | D-DWG-PHW-001 | 1.7 | 608.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0040 | D-DWG-PHW-001 | 1.7 | 618.7 | Trench Stop
[11 empty] | PHW | PHW-TS-0041 | D-DWG-PHW-001 | 1.7 | 628.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0042 | D-DWG-PHW-001 | 1.8 | 635.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0043 | D-DWG-PHW-001 | 1.8 | 642.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0044 | D-DWG-PHW-001 | 1.8 | 649.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0045 | D-DWG-PHW-001 | 1.8 | 655.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0046 | D-DWG-PHW-001 | 1.9 | 662 | Trench Stop
[11 empty] | PHW | PHW-BS-0006 | D-DWG-PHW-001 | 1.9 | 666.3 | Bulk Head
[11 empty] | PHW | PHW-TS-0047 | D-DWG-PHW-001 | 1.9 | 670.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0048 | D-DWG-PHW-001 | 1.9 | 674.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0049 | D-DWG-PHW-001 | 1.9 | 679.2 | Trench Stop
[11 empty] | PHW | PHW-BS-0007 | D-DWG-PHW-001 | 1.9 | 681.35 | Bulk Head
[11 empty] | PHW | PHW-TS-0050 | D-DWG-PHW-001 | 1.9 | 683.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0051 | D-DWG-PHW-001 | 1.9 | 687.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0052 | D-DWG-PHW-001 | 1.9 | 692.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0053 | D-DWG-PHW-001 | 1.9 | 696.4 | Trench Stop
[11 empty] | PHW | PHW-BS-0008 | D-DWG-PHW-002 | 1.9 | 700.7 | Bulk Head
[11 empty] | PHW | PHW-TS-0054 | D-DWG-PHW-002 | 1.9 | 705 | Trench Stop
[11 empty] | PHW | PHW-TS-0055 | D-DWG-PHW-002 | 1.9 | 709.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0056 | D-DWG-PHW-002 | 1.9 | 713.6 | Trench Stop
[11 empty] | PHW | PHW-BS-0009 | D-DWG-PHW-002 | 1.9 | 717.9 | Bulk Head
[11 empty] | PHW | PHW-TS-0057 | D-DWG-PHW-002 | 1.9 | 722.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0058 | D-DWG-PHW-002 | 2.1 | 729 | Trench Stop
[11 empty] | PHW | PHW-BS-0010 | D-DWG-PHW-002 | 2.1 | 731.5 | Bulk Head
[11 empty] | PHW | PHW-TS-0059 | D-DWG-PHW-002 | 2.1 | 734 | Trench Stop
[11 empty] | PHW | PHW-TS-0060 | D-DWG-PHW-002 | 2.3 | 742 | Trench Stop
[11 empty] | PHW | PHW-TS-0061 | D-DWG-PHW-002 | 2.3 | 749 | Trench Stop
[11 empty] | PHW | PHW-TS-0062 | D-DWG-PHW-002 | 2.4 | 892 | Trench Stop
[11 empty] | PHW | PHW-TS-0063 | D-DWG-PHW-002 | 2.5 | 899 | Trench Stop
[11 empty] | PHW | PHW-TS-0064 | D-DWG-PHW-002 | 2.5 | 903.6 | Trench Stop
[11 empty] | PHW | PHW-BS-0011 | D-DWG-PHW-002 | 2.5 | 908.2 | Bulk Head
[11 empty] | PHW | PHW-TS-0065 | D-DWG-PHW-002 | 2.5 | 912.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0066 | D-DWG-PHW-002 | 2.5 | 917.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0067 | D-DWG-PHW-002 | 2.5 | 922 | Trench Stop
[11 empty] | PHW | PHW-BS-0012 | D-DWG-PHW-002 | 2.5 | 926.6 | Bulk Head
[11 empty] | PHW | PHW-TS-0068 | D-DWG-PHW-002 | 2.5 | 931.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0069 | D-DWG-PHW-002 | 2.5 | 935.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0070 | D-DWG-PHW-002 | 2.5 | 940.4 | Trench Stop
[11 empty] | PHW | PHW-BS-0013 | D-DWG-PHW-002 | 2.5 | 945 | Bulk Head
[11 empty] | PHW | PHW-TS-0071 | D-DWG-PHW-002 | 2.5 | 949.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0072 | D-DWG-PHW-002 | 2.5 | 954.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0073 | D-DWG-PHW-002 |  | 964 | Trench Stop
[11 empty] | PHW | PHW-TS-0074 | D-DWG-PHW-002 |  | 967.6 | Trench Stop
[11 empty] | PHW | PHW-BS-0014 | D-DWG-PHW-002 |  | 971.2 | Bulk Head
[11 empty] | PHW | PHW-TS-0075 | D-DWG-PHW-002 |  | 974.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0076 | D-DWG-PHW-002 |  | 978.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0077 | D-DWG-PHW-002 |  | 982 | Trench Stop
[11 empty] | PHW | PHW-BS-0015 | D-DWG-PHW-002 |  | 985.6 | Bulk Head
[11 empty] | PHW | PHW-TS-0078 | D-DWG-PHW-002 |  | 989.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0079 | D-DWG-PHW-002 |  | 992.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0080 | D-DWG-PHW-002 |  | 1000.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0081 | D-DWG-PHW-002 |  | 1005 | Trench Stop
[11 empty] | PHW | PHW-BS-0016 | D-DWG-PHW-002 |  | 1007.25 | Bulk Head
[11 empty] | PHW | PHW-TS-0082 | D-DWG-PHW-002 |  | 1009.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0083 | D-DWG-PHW-002 |  | 1014 | Trench Stop
[11 empty] | PHW | PHW-TS-0084 | D-DWG-PHW-002 |  | 1020.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0085 | D-DWG-PHW-002 |  | 1024.9 | Trench Stop
[11 empty] | PHW | PHW-BS-0017 | D-DWG-PHW-002 |  | 1029.3 | Bulk Head
[11 empty] | PHW | PHW-TS-0086 | D-DWG-PHW-002 |  | 1033.7 | Trench Stop
[11 empty] | PHW | PHW-TS-0087 | D-DWG-PHW-002 |  | 1038.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0088 | D-DWG-PHW-002 |  | 1042.5 | Trench Stop
[11 empty] | PHW | PHW-BS-0018 | D-DWG-PHW-002 |  | 1046.9 | Bulk Head
[11 empty] | PHW | PHW-TS-0089 | D-DWG-PHW-002 |  | 1051.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0090 | D-DWG-PHW-002 |  | 1055.7 | Trench Stop
[11 empty] | PHW | PHW-TS-0091 | D-DWG-PHW-002 |  | 1060 | Trench Stop
[11 empty] | PHW | PHW-BS-0019 | D-DWG-PHW-002 |  | 1065 | Bulk Head
[11 empty] | PHW | PHW-TS-0092 | D-DWG-PHW-002 |  | 1070 | Trench Stop
[11 empty] | PHW | PHW-TS-0093 | D-DWG-PHW-002 |  | 1075 | Trench Stop
[11 empty] | PHW | PHW-TS-0094 | D-DWG-PHW-002 |  | 1080 | Trench Stop
[11 empty] | PHW | PHW-BS-0020 | D-DWG-PHW-002 |  | 1085 | Bulk Head
[11 empty] | PHW | PHW-TS-0095 | D-DWG-PHW-002 |  | 1185 | Trench Stop
[11 empty] | PHW | PHW-TS-0096 | D-DWG-PHW-002 |  | 1192 | Trench Stop
[11 empty] | PHW | PHW-TS-0097 | D-DWG-PHW-002 |  | 1199 | Trench Stop
[11 empty] | PHW | PHW-TS-0098 | D-DWG-PHW-002 |  | 1206 | Trench Stop
[11 empty] | PHW | PHW-TS-0099 | D-DWG-PHW-002 |  | 1211 | Trench Stop
[11 empty] | PHW | PHW-BS-0021 | D-DWG-PHW-002 |  | 1212.55 | Bulk Head
| + | [9 empty] | PHW | PHW-TS-0100 | D-DWG-PHW-002 |  | 1214.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0101 | D-DWG-PHW-002 |  | 1302 | Trench Stop
[11 empty] | PHW | PHW-TS-0102 | D-DWG-PHW-002 |  | 1317.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0103 | D-DWG-PHW-002 |  | 1332.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0104 | D-DWG-PHW-002 |  | 1347.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0105 | D-DWG-PHW-002 |  | 1363.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0106 | D-DWG-PHW-003 |  | 1484.7 | Trench Stop
[11 empty] | PHW | PHW-TS-0107 | D-DWG-PHW-003 |  | 1488.25 | Trench Stop
[11 empty] | PHW | PHW-TS-0108 | D-DWG-PHW-003 |  | 1493 | Trench Stop
[11 empty] | PHW | PHW-TS-0109 | D-DWG-PHW-003 |  | 1497.15 | Trench Stop
[11 empty] | PHW | PHW-TS-0110 | D-DWG-PHW-003 |  | 1501.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0111 | D-DWG-PHW-003 |  | 1506.05 | Trench Stop
[11 empty] | PHW | PHW-TS-0112 | D-DWG-PHW-003 |  | 1509.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0113 | D-DWG-PHW-003 |  | 1517.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0114 | D-DWG-PHW-003 |  | 1526.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0115 | D-DWG-PHW-003 |  | 1534.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0116 | D-DWG-PHW-003 |  | 1542.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0117 | D-DWG-PHW-003 |  | 1551.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0118 | D-DWG-PHW-003 |  | 1559.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0119 | D-DWG-PHW-003 |  | 1567.7 | Trench Stop
[11 empty] | PHW | PHW-TS-0120 | D-DWG-PHW-003 |  | 1576 | Trench Stop
[11 empty] | PHW | PHW-TS-0121 | D-DWG-PHW-003 |  | 1584.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0122 | D-DWG-PHW-003 |  | 1592.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0123 | D-DWG-PHW-003 |  | 1600.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0124 | D-DWG-PHW-003 |  | 1615 | Trench Stop
[11 empty] | PHW | PHW-TS-0125 | D-DWG-PHW-003 |  | 1621.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0126 | D-DWG-PHW-003 |  | 1628.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0127 | D-DWG-PHW-003 |  | 1635.7 | Trench Stop
[11 empty] | PHW | PHW-TS-0128 | D-DWG-PHW-003 |  | 1643.25 | Trench Stop
[11 empty] | PHW | PHW-BS-0022 | D-DWG-PHW-003 |  | 1647.95 | Bulk Head
[11 empty] | PHW | PHW-TS-0129 | D-DWG-PHW-003 |  | 1652.65 | Trench Stop
[11 empty] | PHW | PHW-TS-0130 | D-DWG-PHW-003 |  | 1657.35 | Trench Stop
[11 empty] | PHW | PHW-TS-0131 | D-DWG-PHW-003 |  | 1662.05 | Trench Stop
[11 empty] | PHW | PHW-BS-0023 | D-DWG-PHW-003 |  | 1666.75 | Bulk Head
[11 empty] | PHW | PHW-TS-0132 | D-DWG-PHW-003 |  | 1671.45 | Trench Stop
[11 empty] | PHW | PHW-TS-0133 | D-DWG-PHW-003 |  | 1679.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0134 | D-DWG-PHW-003 |  | 1688.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0135 | D-DWG-PHW-003 |  | 1788 | Trench Stop
[11 empty] | PHW | PHW-TS-0136 | D-DWG-PHW-003 |  | 1791.2 | Trench Stop
[11 empty] | PHW | PHW-BS-0024 | D-DWG-PHW-003 |  | 1792.8 | Bulk Head
[11 empty] | PHW | PHW-TS-0137 | D-DWG-PHW-003 |  | 1794.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0138 | D-DWG-PHW-003 |  | 1797.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0139 | D-DWG-PHW-003 |  | 1809 | Trench Stop
[11 empty] | PHW | PHW-TS-0140 | D-DWG-PHW-003 |  | 1819 | Trench Stop
[11 empty] | PHW | PHW-TS-0141 | D-DWG-PHW-004 |  | 2125 | Trench Stop
[11 empty] | PHW | PHW-TS-0142 | D-DWG-PHW-004 |  | 2131 | Trench Stop
[11 empty] | PHW | PHW-TS-0143 | D-DWG-PHW-004 |  | 2146 | Trench Stop
[11 empty] | PHW | PHW-TS-0144 | D-DWG-PHW-004 |  | 2157.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0145 | D-DWG-PHW-004 |  | 2169 | Trench Stop
[11 empty] | PHW | PHW-TS-0146 | D-DWG-PHW-004 |  | 2180.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0147 | D-DWG-PHW-004 |  | 2192 | Trench Stop
[11 empty] | PHW | PHW-TS-0148 | D-DWG-PHW-004 |  | 2203.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0149 | D-DWG-PHW-004 |  | 2215 | Trench Stop
[11 empty] | PHW | PHW-TS-0150 | D-DWG-PHW-004 |  | 2226.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0151 | D-DWG-PHW-004 |  | 2238 | Trench Stop
[11 empty] | PHW | PHW-TS-0152 | D-DWG-PHW-004 |  | 2249.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0153 | D-DWG-PHW-004 |  | 2261 | Trench Stop
[11 empty] | PHW | PHW-TS-0154 | D-DWG-PHW-004 |  | 2272.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0155 | D-DWG-PHW-004 |  | 2284 | Trench Stop
[11 empty] | PHW | PHW-TS-0156 | D-DWG-PHW-004 |  | 2295.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0157 | D-DWG-PHW-004 |  | 2307 | Trench Stop
[11 empty] | PHW | PHW-TS-0158 | D-DWG-PHW-004 |  | 2318.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0159 | D-DWG-PHW-004 |  | 2330 | Trench Stop
[11 empty] | PHW | PHW-TS-0160 | D-DWG-PHW-004 |  | 2339.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0161 | D-DWG-PHW-004 |  | 2350.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0162 | D-DWG-PHW-004 |  | 2360.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0163 | D-DWG-PHW-004 |  | 2371.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0164 | D-DWG-PHW-004 |  | 2381.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0165 | D-DWG-PHW-004 |  | 2392.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0166 | D-DWG-PHW-004 |  | 2402.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0167 | D-DWG-PHW-004 |  | 2413.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0168 | D-DWG-PHW-004 |  | 2423.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0169 | D-DWG-PHW-004 |  | 2434.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0170 | D-DWG-PHW-004 |  | 2444.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0171 | D-DWG-PHW-004 |  | 2521.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0172 | D-DWG-PHW-004 |  | 2537 | Trench Stop
[11 empty] | PHW | PHW-TS-0173 | D-DWG-PHW-004 |  | 2552.7 | Trench Stop
[11 empty] | PHW | PHW-TS-0174 | D-DWG-PHW-005 |  | 2930 | Trench Stop
[11 empty] | PHW | PHW-TS-0175 | D-DWG-PHW-005 |  | 2945.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0176 | D-DWG-PHW-005 |  | 2961 | Trench Stop
[11 empty] | PHW | PHW-TS-0177 | D-DWG-PHW-005 |  | 2976.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0178 | D-DWG-PHW-005 |  | 2988.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0179 | D-DWG-PHW-005 |  | 3000.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0180 | D-DWG-PHW-005 |  | 3011.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0181 | D-DWG-PHW-005 |  | 3023.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0182 | D-DWG-PHW-005 |  | 3035 | Trench Stop
[11 empty] | PHW | PHW-TS-0183 | D-DWG-PHW-005 |  | 3046.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0184 | D-DWG-PHW-005 |  | 3058.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0185 | D-DWG-PHW-005 |  | 3069.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0186 | D-DWG-PHW-005 |  | 3081.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0187 | D-DWG-PHW-005 |  | 3093 | Trench Stop
[11 empty] | PHW | PHW-TS-0188 | D-DWG-PHW-005 |  | 3104.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0189 | D-DWG-PHW-005 |  | 3116.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0190 | D-DWG-PHW-005 |  | 3127.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0191 | D-DWG-PHW-005 |  | 3139.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0192 | D-DWG-PHW-005 |  | 3151 | Trench Stop
[11 empty] | PHW | PHW-TS-0193 | D-DWG-PHW-005 |  | 3162.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0194 | D-DWG-PHW-005 |  | 3174.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0195 | D-DWG-PHW-005 |  | 3185.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0196 | D-DWG-PHW-005 |  | 3197.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0197 | D-DWG-PHW-005 |  | 3432.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0198 | D-DWG-PHW-005 |  | 3449.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0199 | D-DWG-PHW-006 |  | 3836.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0200 | D-DWG-PHW-006 |  | 3841.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0201 | D-DWG-PHW-006 |  | 4105.75 | Trench Stop
[11 empty] | PHW | PHW-TS-0202 | D-DWG-PHW-007 | 7.1 | 4318.7 | Trench Stop
[11 empty] | PHW | PHW-TS-0203 | D-DWG-PHW-007 | 7.1 | 4327.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0204 | D-DWG-PHW-007 | 7.1 | 4335.7 | Trench Stop
[11 empty] | PHW | PHW-TS-0205 | D-DWG-PHW-007 | 7.2 | 4613.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0206 | D-DWG-PHW-007 | 7.2 | 4629.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0207 | D-DWG-PHW-007 | 7.3 | 4859.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0208 | D-DWG-PHW-007 | 7.3 | 4864.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0209 | D-DWG-PHW-007 | 7.3 | 4869.7 | Trench Stop
[11 empty] | PHW | PHW-TS-0210 | D-DWG-PHW-007 | 7.3 | 4876.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0211 | D-DWG-PHW-007 | 7.3 | 4886.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0212 | D-DWG-PHW-007 | 7.3 | 4895.7 | Trench Stop
[11 empty] | PHW | PHW-TS-0213 | D-DWG-PHW-008 |  | 4905.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0214 | D-DWG-PHW-008 |  | 4914.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0215 | D-DWG-PHW-008 |  | 4954.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0216 | D-DWG-PHW-008 |  | 5182.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0217 | D-DWG-PHW-008 |  | 5195.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0218 | D-DWG-PHW-008 |  | 5209.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0219 | D-DWG-PHW-008 |  | 5222.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0220 | D-DWG-PHW-008 |  | 5236.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0221 | D-DWG-PHW-008 |  | 5249.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0222 | D-DWG-PHW-008 |  | 5263.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0223 | D-DWG-PHW-008 |  | 5359.75 | Trench Stop
[11 empty] | PHW | PHW-TS-0224 | D-DWG-PHW-008 |  | 5367.35 | Trench Stop
[11 empty] | PHW | PHW-TS-0225 | D-DWG-PHW-008 |  | 5374.95 | Trench Stop
[11 empty] | PHW | PHW-TS-0226 | D-DWG-PHW-008 |  | 5382.55 | Trench Stop
[11 empty] | PHW | PHW-TS-0227 | D-DWG-PHW-008 |  | 5390.7 | Trench Stop
[11 empty] | PHW | PHW-TS-0228 | D-DWG-PHW-008 |  | 5401 | Trench Stop
[11 empty] | PHW | PHW-TS-0229 | D-DWG-PHW-008 |  | 5411.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0230 | D-DWG-PHW-008 |  | 5421.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0231 | D-DWG-PHW-008 |  | 5431.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0232 | D-DWG-PHW-008 |  | 5442.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0233 | D-DWG-PHW-008 |  | 5452.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0234 | D-DWG-PHW-008 |  | 5462.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0235 | D-DWG-PHW-008 |  | 5473.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0236 | D-DWG-PHW-008 |  | 5483.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0237 | D-DWG-PHW-008 |  | 5493.7 | Trench Stop
[11 empty] | PHW | PHW-TS-0238 | D-DWG-PHW-008 |  | 5501.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0239 | D-DWG-PHW-008 |  | 5508.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0240 | D-DWG-PHW-008 |  | 5515.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0241 | D-DWG-PHW-008 |  | 5522 | Trench Stop
[11 empty] | PHW | PHW-TS-0242 | D-DWG-PHW-008 |  | 5527.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0243 | D-DWG-PHW-008 |  | 5536 | Trench Stop
[11 empty] | PHW | PHW-TS-0244 | D-DWG-PHW-008 |  | 5544.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0245 | D-DWG-PHW-008 |  | 5552.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0246 | D-DWG-PHW-008 |  | 5561.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0247 | D-DWG-PHW-008 |  | 5569.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0248 | D-DWG-PHW-009 | 9.1 | 5671.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0249 | D-DWG-PHW-009 | 9.1 | 5682.7 | Trench Stop
[11 empty] | PHW | PHW-TS-0250 | D-DWG-PHW-009 | 9.1 | 5694.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0251 | D-DWG-PHW-009 | 9.1 | 5705.7 | Trench Stop
[11 empty] | PHW | PHW-TS-0252 | D-DWG-PHW-009 | 9.1 | 5717.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0253 | D-DWG-PHW-009 | 9.2 | 5723.75 | Trench Stop
[11 empty] | PHW | PHW-BS-0025 | D-DWG-PHW-009 | 9.2 | 5726.4 | Bulk Head
[11 empty] | PHW | PHW-TS-0254 | D-DWG-PHW-009 | 9.2 | 5729.05 | Trench Stop
[11 empty] | PHW | PHW-BS-0026 | D-DWG-PHW-009 | 9.3 | 5733 | Bulk Head
[11 empty] | PHW | PHW-BS-0027 | D-DWG-PHW-009 | 9.3 | 5736 | Bulk Head
[11 empty] | PHW | PHW-BS-0028 | D-DWG-PHW-009 | 9.3 | 5739 | Bulk Head
[11 empty] | PHW | PHW-BS-0029 | D-DWG-PHW-009 | 9.3 | 5742 | Bulk Head
[11 empty] | PHW | PHW-BS-0030 | D-DWG-PHW-009 | 9.3 | 5745 | Bulk Head
[11 empty] | PHW | PHW-BS-0031 | D-DWG-PHW-009 | 9.3 | 5748 | Bulk Head
[11 empty] | PHW | PHW-BS-0032 | D-DWG-PHW-009 | 9.3 | 5751 | Bulk Head
[11 empty] | PHW | PHW-BS-0033 | D-DWG-PHW-009 | 9.3 | 5754 | Bulk Head
[11 empty] | PHW | PHW-TS-0255 | D-DWG-PHW-009 | 9.4 | 5756.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0256 | D-DWG-PHW-009 | 9.4 | 5761 | Trench Stop
[11 empty] | PHW | PHW-TS-0257 | D-DWG-PHW-009 | 9.4 | 5765.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0258 | D-DWG-PHW-009 | 9.4 | 5769.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0259 | D-DWG-PHW-009 | 9.5 | 5775.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0260 | D-DWG-PHW-009 | 9.5 | 5783.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0261 | D-DWG-PHW-009 | 9.5 | 5791.7 | Trench Stop
[11 empty] | PHW | PHW-TS-0262 | D-DWG-PHW-009 | 9.5 | 5799.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0263 | D-DWG-PHW-009 | 9.5 | 5808.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0264 | D-DWG-PHW-009 | 9.5 | 5816.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0265 | D-DWG-PHW-009 | 9.6 | 5825.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0266 | D-DWG-PHW-009 | 9.6 | 5835.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0267 | D-DWG-PHW-009 | 9.6 | 5845.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0268 | D-DWG-PHW-009 | 9.7 | 5852.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0269 | D-DWG-PHW-009 | 9.7 | 5855.6 | Trench Stop
[11 empty] | PHW | PHW-BS-0034 | D-DWG-PHW-009 | 9.7 | 5857.25 | Bulk Head
[11 empty] | PHW | PHW-TS-0270 | D-DWG-PHW-009 | 9.7 | 5858.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0271 | D-DWG-PHW-009 | 9.7 | 5862.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0272 | D-DWG-PHW-009 | 9.8 | 5870 | Trench Stop
[11 empty] | PHW | PHW-TS-0273 | D-DWG-PHW-009 | 9.8 | 5875 | Trench Stop
[11 empty] | PHW | PHW-BS-0035 | D-DWG-PHW-009 | 9.8 | 5877.5 | Bulk Head
[11 empty] | PHW | PHW-TS-0274 | D-DWG-PHW-009 | 9.8 | 5880 | Trench Stop
[11 empty] | PHW | PHW-TS-0275 | D-DWG-PHW-009 | 9.8 | 5885 | Trench Stop
[11 empty] | PHW | PHW-TS-0276 | D-DWG-PHW-009 | 9,9 | 5893.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0277 | D-DWG-PHW-009 | 9.9.1 | 5914.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0278 | D-DWG-PHW-009 | 9.1 | 5952.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0279 | D-DWG-PHW-009 | 9.1 | 5959.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0280 | D-DWG-PHW-009 | 9.1 | 5966.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0281 | D-DWG-PHW-009 | 9.1 | 5973.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0282 | D-DWG-PHW-009 | 9.1 | 5980.7 | Trench Stop
[11 empty] | PHW | PHW-TS-0283 | D-DWG-PHW-009 | 9.1 | 5987.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0284 | D-DWG-PHW-009 | 9.1 | 5994.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0285 | D-DWG-PHW-009 | 9.1 | 6002 | Trench Stop
[11 empty] | PHW | PHW-TS-0286 | D-DWG-PHW-009 | 9.1 | 6009.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0287 | D-DWG-PHW-009 | 9.1 | 6016.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0288 | D-DWG-PHW-009 | 9.1 | 6023.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0289 | D-DWG-PHW-009 | 9.1 | 6030.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0290 | D-DWG-PHW-009 | 9.1 | 6037.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0291 | D-DWG-PHW-009 | 9.11 | 6042.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0292 | D-DWG-PHW-009 | 9.11 | 6048.1 | Trench Stop
[11 empty] | PHW | PHW-BS-0036 | D-DWG-PHW-009 | 9.11 | 6053.7 | Bulk Head
[11 empty] | PHW | PHW-TS-0293 | D-DWG-PHW-009 | 9.11 | 6059.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0294 | D-DWG-PHW-009 | 9.11 | 6064.9 | Trench Stop
[11 empty] | PHW | PHW-BS-0037 | D-DWG-PHW-009 | 9.11 | 6070.5 | Bulk Head
[11 empty] | PHW | PHW-TS-0295 | D-DWG-PHW-009 | 9.11 | 6076.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0296 | D-DWG-PHW-009 | 9.11 | 6081.7 | Trench Stop
[11 empty] | PHW | PHW-BS-0038 | D-DWG-PHW-009 | 9.11 | 6087.3 | Bulk Head
[11 empty] | PHW | PHW-TS-0297 | D-DWG-PHW-009 | 9.11 | 6092.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0298 | D-DWG-PHW-009 | 9.11 | 6098.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0299 | D-DWG-PHW-009 | 9.12 | 6104 | Trench Stop
[11 empty] | PHW | PHW-TS-0300 | D-DWG-PHW-009 | 9.12 | 6111.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0301 | D-DWG-PHW-009 | 9.13 | 6160.84 | Trench Stop
[11 empty] | PHW | PHW-TS-0302 | D-DWG-PHW-009 | 9.13 | 6169.24 | Trench Stop
[11 empty] | PHW | PHW-TS-0303 | D-DWG-PHW-009 | 9.13 | 6177.64 | Trench Stop
[11 empty] | PHW | PHW-TS-0304 | D-DWG-PHW-009 | 9.13 | 6186.04 | Trench Stop
[11 empty] | PHW | PHW-TS-0305 | D-DWG-PHW-009 | 9.13 | 6194.44 | Trench Stop
[11 empty] | PHW | PHW-TS-0306 | D-DWG-PHW-009 | 9.13 | 6202.84 | Trench Stop
[11 empty] | PHW | PHW-TS-0307 | D-DWG-PHW-009 | 9.13 | 6211.24 | Trench Stop
[11 empty] | PHW | PHW-TS-0308 | D-DWG-PHW-009 | 9.13 | 6219.64 | Trench Stop
[11 empty] | PHW | PHW-TS-0309 | D-DWG-PHW-009 | 9.13 | 6228.04 | Trench Stop
[11 empty] | PHW | PHW-TS-0310 | D-DWG-PHW-009 | 9.13 | 6236.44 | Trench Stop
[11 empty] | PHW | PHW-TS-0311 | D-DWG-PHW-009 | 9.13 | 6244.84 | Trench Stop
[11 empty] | PHW | PHW-TS-0312 | D-DWG-PHW-009 | 9.13 | 6253.24 | Trench Stop
[11 empty] | PHW | PHW-TS-0313 | D-DWG-PHW-009 | 9.13 | 6261.64 | Trench Stop
[11 empty] | PHW | PHW-TS-0314 | D-DWG-PHW-009 | 9.14 | 6270.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0315 | D-DWG-PHW-009 | 9.14 | 6287.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0316 | D-DWG-PHW-010 | 9.14 | 6303.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0317 | D-DWG-PHW-010 | 9.14 | 6320.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0318 | D-DWG-PHW-010 |  | 6337 | Trench Stop
[11 empty] | PHW | PHW-TS-0319 | D-DWG-PHW-010 |  | 6350.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0320 | D-DWG-PHW-010 |  | 6366.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0321 | D-DWG-PHW-010 |  | 6381.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0322 | D-DWG-PHW-010 |  | 6397.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0323 | D-DWG-PHW-010 |  | 6419.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0324 | D-DWG-PHW-010 |  | 6426.4 | Trench Stop
[11 empty] | PHW | PHW-BS-0039 | D-DWG-PHW-010 |  | 6429.35 | Bulk Head
[11 empty] | PHW | PHW-TS-0325 | D-DWG-PHW-010 |  | 6432.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0326 | D-DWG-PHW-010 |  | 6452.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0327 | D-DWG-PHW-010 |  | 6459.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0328 | D-DWG-PHW-010 |  | 6466.5 | Trench Stop
[11 empty] | PHW | PHW-BS-0040 | D-DWG-PHW-010 |  | 6474 | Bulk Head
[11 empty] | PHW | PHW-TS-0329 | D-DWG-PHW-010 |  | 6525.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0330 | D-DWG-PHW-010 |  | 6545.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0331 | D-DWG-PHW-010 |  | 6564.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0332 | D-DWG-PHW-010 |  | 6937.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0333 | D-DWG-PHW-010 |  | 6947.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0334 | D-DWG-PHW-010 |  | 6956.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0335 | D-DWG-PHW-010 |  | 6965.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0336 | D-DWG-PHW-012 |  | 7839.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0337 | D-DWG-PHW-012 |  | 7851.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0338 | D-DWG-PHW-012 |  | 7864.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0339 | D-DWG-PHW-012 |  | 7876.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0340 | D-DWG-PHW-012 |  | 7937.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0341 | D-DWG-PHW-012 |  | 7948.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0342 | D-DWG-PHW-012 |  | 7959.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0343 | D-DWG-PHW-012 |  | 7970.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0344 | D-DWG-PHW-012 |  | 8192.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0345 | D-DWG-PHW-012 |  | 8210 | Trench Stop
[11 empty] | PHW | PHW-TS-0346 | D-DWG-PHW-012 |  | 8285.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0347 | D-DWG-PHW-012 |  | 8296.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0348 | D-DWG-PHW-012 |  | 8307.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0349 | D-DWG-PHW-012 |  | 8317.7 | Trench Stop
[11 empty] | PHW | PHW-TS-0350 | D-DWG-PHW-012 |  | 8328.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0351 | D-DWG-PHW-012 |  | 8338.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0352 | D-DWG-PHW-012 |  | 8349.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0353 | D-DWG-PHW-012 |  | 8360.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0354 | D-DWG-PHW-012 |  | 8370.7 | Trench Stop
[11 empty] | PHW | PHW-TS-0355 | D-DWG-PHW-013 |  | 9059.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0356 | D-DWG-PHW-013 |  | 9067.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0357 | D-DWG-PHW-013 |  | 9075.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0358 | D-DWG-PHW-014 |  | 9126.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0359 | D-DWG-PHW-014 |  | 9138.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0360 | D-DWG-PHW-014 |  | 9150.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0361 | D-DWG-PHW-014 |  | 9162 | Trench Stop
[11 empty] | PHW | PHW-TS-0362 | D-DWG-PHW-014 |  | 9173.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0363 | D-DWG-PHW-014 |  | 9185.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0364 | D-DWG-PHW-014 |  | 9197.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0365 | D-DWG-PHW-014 |  | 9209.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0366 | D-DWG-PHW-014 |  | 9221 | Trench Stop
[11 empty] | PHW | PHW-TS-0367 | D-DWG-PHW-014 |  | 9232.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0368 | D-DWG-PHW-014 |  | 9244.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0369 | D-DWG-PHW-014 |  | 9256.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0370 | D-DWG-PHW-014 |  | 9441.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0371 | D-DWG-PHW-014 |  | 9452 | Trench Stop
[11 empty] | PHW | PHW-TS-0372 | D-DWG-PHW-014 |  | 9462.8 | Trench Stop
[11 empty] | PHW | PHW-TS-0373 | D-DWG-PHW-014 |  | 9473.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0374 | D-DWG-PHW-014 |  | 9484.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0375 | D-DWG-PHW-014 |  | 9495.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0376 | D-DWG-PHW-014 |  | 9506 | Trench Stop
[11 empty] | PHW | PHW-TS-0377 | D-DWG-PHW-015 |  | 9840.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0378 | D-DWG-PHW-015 |  | 9852.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0379 | D-DWG-PHW-015 |  | 9981.4 | Trench Stop
[11 empty] | PHW | PHW-TS-0380 | D-DWG-PHW-015 |  | 9987.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0381 | D-DWG-PHW-015 |  | 9993.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0382 | D-DWG-PHW-015 |  | 10373.15 | Trench Stop
[11 empty] | PHW | PHW-TS-0383 | D-DWG-PHW-017 |  | 11279.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0384 | D-DWG-PHW-017 |  | 11328.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0385 | D-DWG-PHW-017 |  | 11345.9 | Trench Stop
[11 empty] | PHW | PHW-TS-0386 | D-DWG-PHW-017 |  | 11581 | Trench Stop
[11 empty] | PHW | PHW-TS-0387 | D-DWG-PHW-017 |  | 11584.3 | Trench Stop
[11 empty] | PHW | PHW-TS-0388 | D-DWG-PHW-017 |  | 11587.6 | Trench Stop
[11 empty] | PHW | PHW-TS-0389 | D-DWG-PHW-018 |  | 12461 | Trench Stop
[11 empty] | PHW | PHW-TS-0390 | D-DWG-PHW-018 |  | 12468 | Trench Stop
[11 empty] | PHW | PHW-TS-0391 | D-DWG-PHW-019 |  | 12646.7 | Trench Stop
[11 empty] | PHW | PHW-TS-0392 | D-DWG-PHW-019 |  | 13242.2 | Trench Stop
[11 empty] | PHW | PHW-TS-0393 | D-DWG-PHW-019 |  | 13249.7 | Trench Stop
[11 empty] | PHW | PHW-TS-0394 | D-DWG-PHW-028 |  | 19009.5 | Trench Stop
[11 empty] | PHW | PHW-TS-0395 | D-DWG-PHW-028 |  | 19022.1 | Trench Stop
[11 empty] | PHW | PHW-TS-0396 | D-DWG-PHW-028 |  | 19039.67 | Trench Stop
[11 empty] | PHW | PHW-TS-0397 | D-DWG-PHW-028 |  | 19047.47 | Trench Stop
[11 empty] | PHW | PHW-TS-0398 | D-DWG-PHW-028 |  | 19055.27 | Trench Stop
[11 empty] | PHW | PHW-TS-0399 | D-DWG-PHW-028 |  | 19063.07 | Trench Stop
[11 empty] | PHW | PHW-TS-0400 | D-DWG-PHW-028 |  | 19070.87 | Trench Stop
[11 empty] | PHW | PHW-TS-0401 | D-DWG-PHW-028 |  | 19078.67 | Trench Stop
[11 empty] | PHW | PHW-TS-0402 | D-DWG-PHW-028 |  | 19086.47 | Trench Stop
[11 empty] | PHW | PHW-TS-0403 | D-DWG-PHW-028 |  | 19094.27 | Trench Stop
[11 empty] | PHW | PHW-TS-0404 | D-DWG-PHW-028 |  | 19102.07 | Trench Stop
[11 empty] | PHW | PHW-TS-0405 | D-DWG-PHW-028 |  | 19109.87 | Trench Stop
[11 empty] | PHW | PHW-TS-0406 | D-DWG-PHW-028 |  | 19111 | Trench Stop
[11 empty] | PHW | PHW-BS-0041 | D-DWG-PHW-028 |  | 19139.744 | Bulk Head
[11 empty] | PHW | PHW-BS-0042 | D-DWG-PHW-028 |  | 19141.144 | Bulk Head
[11 empty] | PHW | PHW-BS-0043 | D-DWG-PHW-028 |  | 19142.544 | Bulk Head
[11 empty] | PHW | PHW-BS-0044 | D-DWG-PHW-028 |  | 19143.944 | Bulk Head
[11 empty] | PHW | PHW-BS-0045 | D-DWG-PHW-028 |  | 19145.344 | Bulk Head
[11 empty] | PHW | PHW-BS-0046 | D-DWG-PHW-028 |  | 19146.744 | Bulk Head
[11 empty] | PWG | PWG-TS-0001 | D-DWG-PWG-001 |  | 2 | Trench Stop
[11 empty] | PWG | PWG-BS-0001 | D-DWG-PWG-001 |  | 7 | Bulk Head
[11 empty] | PWG | PWG-TS-0002 | D-DWG-PWG-001 |  | 12 | Trench Stop
[11 empty] | PWG | PWG-TS-0003 | D-DWG-PWG-002 |  | 1190.9 | Trench Stop
[11 empty] | PWG | PWG-TS-0004 | D-DWG-PWG-003 |  | 2052.9 | Trench Stop
[11 empty] | PWG | PWG-TS-0005 | D-DWG-PWG-003 |  | 2061.5 | Trench Stop
[11 empty] | PWG | PWG-TS-0006 | D-DWG-PWG-006 |  | 4010.3 | Trench Stop
[11 empty] | PWG | PWG-TS-0007 | D-DWG-PWG-008 |  | 5445.3 | Trench Stop
[11 empty] | PWG | PWG-TS-0008 | D-DWG-PWG-013 |  | 8669.8 | Trench Stop
[11 empty] | PWG | PWG-TS-0009 | D-DWG-PWG-013 |  | 8677 | Trench Stop
[11 empty] | PWG | PWG-TS-0010 | D-DWG-PWG-014 |  | 9344.9 | Trench Stop
[11 empty] | PWG | PWG-TS-0011 | D-DWG-PWG-014 |  | 9358.4 | Trench Stop
[11 empty] | PWG | PWG-TS-0012 | D-DWG-PWG-014 |  | 9371.9 | Trench Stop
[11 empty] | PWG | PWG-TS-0013 | D-DWG-PWG-015 |  | 9810.2 | Trench Stop
[11 empty] | PWG | PWG-TS-0014 | D-DWG-PWG-015 |  | 9825.8 | Trench Stop
[11 empty] | PWG | PWG-TS-0015 | D-DWG-PWG-015 |  | 9841.4 | Trench Stop
[11 empty] | PWG | PWG-TS-0016 | D-DWG-PWG-016 |  | 11111.31 | Trench Stop
[11 empty] | PWG | PWG-TS-0017 | D-DWG-PWG-016 |  | 11118.61 | Trench Stop
[11 empty] | PWG | PWG-TS-0018 | D-DWG-PWG-016 |  | 11125.91 | Trench Stop
[11 empty] | PWG | PWG-TS-0019 | D-DWG-PWG-017 |  | 11305.8 | Trench Stop
[11 empty] | PWG | PWG-TS-0020 | D-DWG-PWG-017 |  | 11318.5 | Trench Stop
[11 empty] | PWG | PWG-TS-0021 | D-DWG-PWG-017 |  | 11331.2 | Trench Stop
[11 empty] | PWG | PWG-TS-0022 | D-DWG-PWG-020 |  | 13376.5 | Trench Stop
[11 empty] | PWG | PWG-TS-0023 | D-DWG-PWG-020 |  | 13384.4 | Trench Stop
[11 empty] | PWG | PWG-TS-0024 | D-DWG-PWG-020 |  | 13392.3 | Trench Stop
[11 empty] | PWG | PWG-TS-0025 | D-DWG-PWG-021 |  | 14244.2 | Trench Stop
[11 empty] | PWG | PWG-TS-0026 | D-DWG-PWG-021 |  | 14254.6 | Trench Stop
[11 empty] | PWG | PWG-TS-0027 | D-DWG-PWG-021 |  | 14577.5 | Trench Stop
[11 empty] | PWG | PWG-TS-0028 | D-DWG-PWG-021 |  | 14588.8 | Trench Stop
[11 empty] | PWG | PWG-TS-0029 | D-DWG-PWG-021 |  | 14600.1 | Trench Stop
[11 empty] | PWG | PWG-TS-0030 | D-DWG-PWG-021 |  | 14611.4 | Trench Stop
[11 empty] | PWG | PWG-TS-0031 | D-DWG-PWG-021 |  | 14622.7 | Trench Stop
[11 empty] | PWG | PWG-TS-0032 | D-DWG-PWG-027 |  | 18779.3 | Trench Stop
[11 empty] | PWG | PWG-TS-0033 | D-DWG-PWG-036 |  | 25025.6 | Trench Stop
[11 empty] | PWG | PWG-TS-0034 | D-DWG-PWG-036 |  | 25039.6 | Trench Stop
[11 empty] | PWG | PWG-TS-0035 | D-DWG-PWG-036 |  | 25053.6 | Trench Stop
[11 empty] | PWG | PWG-TS-0036 | D-DWG-PWG-036 |  | 25067.6 | Trench Stop
Verbatim rows from Trench&Bulkheads- T2W_PIPELINE.xlsm, sheet 'Master Register - LandPartners', source revision dated 2026-08-17. Reloaded 24 Aug 2026; the previous load (452 rows) is preserved in the dated backup.

## Src - Foreign Service
Asset Id | Pipeline Section | KP | Utility Description | Utility Type | Operator | Size (mm) | Info Source | Drawing # | Drawing (superseded) | Included in Current Plan | Comments | Source Row
PHW-FN-0001 | PHW | 15 | FENCE LINE NO POSTS | FENCE |  |  |  | D-DWG-PHW-001.2 | D-DWG-PHW-001_C | Yes |  | 2
PHW-CM-0001 | PHW | 38 | BYDA TELSTRA COMMSTUD | COMMUNICATIONS | Telstra |  | BYDA | D-DWG-PHW-001.2 | D-DWG-PHW-001_C | Yes |  | 3
PHW-CM-0002 | PHW | 44 | BYDA TELSTRA COMMSTUD | COMMUNICATIONS | Telstra |  | BYDA | D-DWG-PHW-001.2 | D-DWG-PHW-001_C | Yes |  | 4
PHW-CM-0003 | PHW | 361 | BYDA TELSTRA COMMSTUD | COMMUNICATIONS | Telstra |  | BYDA | D-DWG-PHW-001.2 | D-DWG-PHW-001_C | Yes |  | 5
PHW-EL-0001 | PHW | 364 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-001.2 |  | Yes |  | 6
PHW-FN-0002 | PHW | 671 | FENCE LINE NO POSTS | FENCE |  |  |  | D-DWG-PHW-001.2 | D-DWG-PHW-001_C | Yes |  | 7
PHW-DR-0001 | PHW | 1105 | PUP DRAINAGE DN375 | DRAINAGE |  | 375 | PUP | D-DWG-PHW-002.2 |  | Yes |  | 8
PHW-SW-0001 | PHW | 1242 | BYDA TRC SEWER | SEWER | Toowoomba Regional Council |  | BYDA | D-DWG-PHW-002.2 | D-DWG-PHW-002_C | Yes | DEPTH OF DUAL SEWER MAINS NOT KNOWN AT EXACT CROSSING LOCATION. CONTRACTOR TO CONFIRM PRIOR TO D&C DESIGN. | 9
PHW-SW-0002 | PHW | 1243 | PUP SEWER DN375 | SEWER |  | 375 | PUP | D-DWG-PHW-002.2 |  | Yes | DEPTH OF DUAL SEWER MAINS NOT KNOWN AT EXACT CROSSING LOCATION. CONTRACTOR TO CONFIRM PRIOR TO D&C DESIGN. | 10
PHW-EL-0002 | PHW | 1459 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-003.2 | D-DWG-PHW-003_C | Yes |  | 11
PHW-FN-0003 | PHW | 1462 | FENCE LINE NO POSTS | FENCE |  |  |  | D-DWG-PHW-003.2 | D-DWG-PHW-003_C | Yes |  | 12
PHW-FN-0004 | PHW | 1534 | FENCE LINE NO POSTS | FENCE |  |  |  | D-DWG-PHW-003.2 | D-DWG-PHW-003_C | Yes |  | 13
PHW-FN-0005 | PHW | 1736 | FENCE LINE NO POSTS | FENCE |  |  |  | D-DWG-PHW-003.2 | D-DWG-PHW-003_C | Yes |  | 14
PHW-FN-0006 | PHW | 1820 | FENCE CHAINWIRE | FENCE |  |  |  | D-DWG-PHW-003.2 | D-DWG-PHW-003_C | Yes |  | 15
PHW-FN-0007 | PHW | 1868 | FENCE LINE NO POSTS | FENCE |  |  |  | D-DWG-PHW-003.2 | D-DWG-PHW-003_C | Yes |  | 16
PHW-FN-0008 | PHW | 1897 | FENCE LINE NO POSTS | FENCE |  |  |  | D-DWG-PHW-003.2 | D-DWG-PHW-003_C | Yes |  | 17
PHW-FN-0009 | PHW | 1915 | FENCE LINE NO POSTS | FENCE |  |  |  | D-DWG-PHW-003.2 | D-DWG-PHW-003_C | Yes | Not Included in Rev 2 | 18
PHW-FN-0010 | PHW | 2062 | FENCE CHAINWIRE | FENCE |  |  |  | D-DWG-PHW-003.2 | D-DWG-PHW-003_C | Yes |  | 19
PHW-FN-0011 | PHW | 2062 | FENCE LINE NO POSTS | FENCE |  |  |  | D-DWG-PHW-003.2 | D-DWG-PHW-003_C | Yes |  | 20
PHW-CM-0004 | PHW | 2093 | BYDA TELSTRA COMMSTUD | COMMUNICATIONS | Telstra |  | BYDA | D-DWG-PHW-003.2 | D-DWG-PHW-003_C | Yes |  | 21
PHW-RW-0001 | PHW | 2104 | BYDA RECYCLED WATER | WATER - RECYCLED |  |  | BYDA | D-DWG-PHW-004.2 |  | Yes |  | 22
PHW-CM-0005 | PHW | 2108 | BYDA TELSTRA COMMSTUD | COMMUNICATIONS | Telstra |  | BYDA | D-DWG-PHW-004.2 | D-DWG-PHW-004_C | Yes |  | 23
PHW-FN-0012 | PHW | 2123 | FENCE CHAINWIRE | FENCE |  |  |  | D-DWG-PHW-004.2 |  | Yes |  | 24
PHW-WA-0001 | PHW | 2340 | BYDA WATER | WATER |  |  | BYDA | D-DWG-PHW-004.2 |  | Yes |  | 25
PHW-CM-0006 | PHW | 2506 | BYDA COMMS DN35 | COMMUNICATIONS |  | 35 | BYDA | D-DWG-PHW-004.2 |  | Yes |  | 26
PHW-WA-0002 | PHW | 2507 | BYDA WATER | WATER |  |  | BYDA | D-DWG-PHW-004.2 | D-DWG-PHW-004_C | Yes |  | 27
PHW-CM-0007 | PHW | 2560 | BYDA TELSTRA COMMSTUD | COMMUNICATIONS | Telstra |  | BYDA | D-DWG-PHW-004.2 |  | Yes |  | 28
PHW-WA-0003 | PHW | 2793 | BYDA WATER | WATER |  |  | BYDA | D-DWG-PHW-004.2 |  | Yes |  | 29
PHW-WA-0004 | PHW | 2793 | BYDA WATER | WATER |  |  | BYDA | D-DWG-PHW-004.2 |  | Yes |  | 30
PHW-FN-0013 | PHW | 2796 | FENCE CHAINWIRE | FENCE |  |  |  | D-DWG-PHW-004.2 |  | Yes |  | 31
PHW-WA-0005 | PHW | 2810 | BYDA WATER | WATER |  |  | BYDA | D-DWG-PHW-005.2 |  | Yes |  | 32
PHW-WA-0006 | PHW | 2813 | BYDA WATER DN450 | WATER |  | 450 | BYDA | D-DWG-PHW-005.2 |  | Yes |  | 33
PHW-CM-0008 | PHW | 2813 | BYDA COMMS DN15 | COMMUNICATIONS |  | 15 | BYDA | D-DWG-PHW-005.2 |  | Yes |  | 34
PHW-FN-0014 | PHW | 2923 | FENCE CHAINWIRE | FENCE |  |  |  | D-DWG-PHW-005.2 | D-DWG-PHW-005_C | Yes |  | 35
PHW-FN-0015 | PHW | 2923 | FENCE LINE NO POSTS | FENCE |  |  |  | D-DWG-PHW-005.2 | D-DWG-PHW-005_C | Yes |  | 36
PHW-EL-0004 | PHW | 3000 | PUP ELECTRICITY | ELECTRICITY | Ergon Energy |  | PUP | D-DWG-PHW-005.2 |  | Yes | POWER POLE TO BE RELOCATED BY OTHERS (ERGON) PRIOR TO CONSTRUCTION | 37
PHW-EL-0005 | PHW | 3350 | PUP ELECTRICITY | ELECTRICITY | Ergon Energy |  | PUP | D-DWG-PHW-005.2 |  | Yes | POWER POLE TO BE RELOCATED BY OTHERS (ERGON) PRIOR TO CONSTRUCTION | 38
PHW-WA-0007 | PHW | 3537 | BYDA WATER DN450 | WATER |  | 450 | BYDA | D-DWG-PHW-005.2 |  | Yes |  | 39
PHW-WA-0009 | PHW | 3544 | BYDA WATER DN450 | WATER |  | 450 | BYDA | D-DWG-PHW-005.2 |  | Yes |  | 40
PHW-CM-0009 | PHW | 3545 | BYDA COMMS DN15 | COMMUNICATIONS |  | 15 | BYDA | D-DWG-PHW-005.2 |  | Yes |  | 41
PHW-WA-0008 | PHW | 3538 | BYDA WATER DN450 | WATER |  | 450 | BYDA | D-DWG-PHW-006.2 |  | Yes |  | 42
PHW-WA-0010 | PHW | 3545 | BYDA WATER DN450 | WATER |  | 450 | BYDA | D-DWG-PHW-006.2 |  | Yes |  | 43
PHW-CM-0010 | PHW | 3546 | BYDA COMMS DN15 | COMMUNICATIONS |  | 15 | BYDA | D-DWG-PHW-006.2 |  | Yes |  | 44
PHW-EL-0006 | PHW | 3559 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-006.2 |  | Yes |  | 45
PHW-EL-0007 | PHW | 3560 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-006.2 |  | Yes |  | 46
PHW-CM-0011 | PHW | 3762 | BYDA TELSTRA COMMSTUD | COMMUNICATIONS | Telstra |  | BYDA | D-DWG-PHW-006.2 | D-DWG-PHW-006_C | Yes |  | 47
PHW-EL-0008 | PHW | 3762 | BYDA ELECTRICITY LV | ELECTRICITY |  |  | BYDA | D-DWG-PHW-006.2 | D-DWG-PHW-006_C | Yes |  | 48
PHW-CM-0012 | PHW | 3845 | BYDA COMMS DN15 | COMMUNICATIONS |  | 15 | BYDA | D-DWG-PHW-006.2 |  | Yes |  | 49
PHW-WA-0011 | PHW | 3847 | BYDA WATER DN450 | WATER |  | 450 | BYDA | D-DWG-PHW-006.2 |  | Yes |  | 50
PHW-WA-0012 | PHW | 3855 | BYDA WATER DN450 | WATER |  | 450 | BYDA | D-DWG-PHW-006.2 |  | Yes |  | 51
PHW-EL-0009 | PHW | 4102 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-006.2 |  | Yes |  | 52
PHW-WA-0013 | PHW | 4119 | BYDA WATER | WATER |  |  | BYDA | D-DWG-PHW-006.2 |  | Yes |  | 53
PHW-CM-0013 | PHW | 4178 | BYDA TELSTRA COMMS DN35 | COMMUNICATIONS | Telstra | 35 | BYDA | D-DWG-PHW-006.2 |  | Yes |  | 54
PHW-EL-0010 | PHW | 4178 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-006.2 |  | Yes |  | 55
PHW-EL-0011 | PHW | 4317 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-007.2 |  | Yes |  | 56
PHW-WA-0014 | PHW | 4417 | BYDA WATER DN450 | WATER |  | 450 | BYDA | D-DWG-PHW-007.2 |  | Yes |  | 57
PHW-CM-0014 | PHW | 4417 | BYDA COMMS DN15 | COMMUNICATIONS |  | 15 | BYDA | D-DWG-PHW-007.2 |  | Yes |  | 58
PHW-CM-0015 | PHW | 4435 | BYDA TELSTRA COMMS DN20 | COMMUNICATIONS | Telstra | 20 | BYDA | D-DWG-PHW-007.2 |  | Yes |  | 59
PHW-CM-0016 | PHW | 4437 | BYDA TELSTRA COMMSTUD | COMMUNICATIONS | Telstra |  | BYDA | D-DWG-PHW-007.2 | D-DWG-PHW-007_C | Yes |  | 60
PHW-SW-0003 | PHW | 4448 | BYDA TRC SEWER | SEWER | Toowoomba Regional Council |  | BYDA | D-DWG-PHW-007.2 | D-DWG-PHW-007_C | Yes |  | 61
PHW-CM-0017 | PHW | 5494 | BYDA TELSTRA COMMS | COMMUNICATIONS | Telstra |  | BYDA | D-DWG-PHW-008.2 |  | Yes |  | 62
PHW-CM-0018 | PHW | 5494 | BYDA TELSTRA COMMS | COMMUNICATIONS | Telstra |  | BYDA | D-DWG-PHW-008.2 |  | Yes |  | 63
PHW-GA-0001 | PHW | 6125 | BYDA GAS DN400 | GAS | APA Group | 400 | BYDA | D-DWG-PHW-009.2 |  | Yes | LOCATION/DEPTH OF DUAL APA GAS MAINS NOT KNOWN. CONTRACTOR TO CONFIRM PRIOR TO CONSTRUCTION. | 64
PHW-GA-0002 | PHW | 6141 | BYDA GAS DN400 | GAS |  | 400 | BYDA | D-DWG-PHW-009.2 |  | Yes |  | 65
PHW-GA-0003 | PHW | 6194 | BYDA GAS DN400 | GAS |  | 400 | BYDA | D-DWG-PHW-009.2 |  | Yes |  | 66
PHW-EL-0012 | PHW | 6237 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-009.2 | D-DWG-PHW-009_C | Yes |  | 67
PHW-FN-0016 | PHW | 6486 | FENCE LINE NO POST - WIRE ONLY | FENCE |  |  |  | D-DWG-PHW-010.2 |  | Yes |  | 68
PHW-GA-0004 | PHW | 6488 | PUP GAS DN250 | GAS | APA Group | 250 | PUP | D-DWG-PHW-010.2 |  | Yes | LOCATION/DEPTH OF DUAL APA GAS MAINS NOT KNOWN. CONTRACTOR TO CONFIRM PRIOR TO CONSTRUCTION. | 69
PHW-GA-0005 | PHW | 6494 | PUP GAS DN400 | GAS | APA Group | 400 | PUP | D-DWG-PHW-010.2 |  | Yes | LOCATION/DEPTH OF DUAL APA GAS MAINS NOT KNOWN. CONTRACTOR TO CONFIRM PRIOR TO CONSTRUCTION. | 70
PHW-FN-0017 | PHW | 6993 | FENCE LINE NO POSTS | FENCE |  |  |  | D-DWG-PHW-010.2 |  | Yes |  | 71
PHW-FN-0018 | PHW | 6993 | FENCE LINE NO POSTS | FENCE |  |  |  | D-DWG-PHW-010.2 |  | Yes |  | 72
PHW-CM-0019 | PHW | 6995 | BYDA TELSTRA COMMSTUD | COMMUNICATIONS | Telstra |  | BYDA | D-DWG-PHW-010.2 |  | Yes |  | 73
PHW-CM-0020 | PHW | 6996 | BYDA TELSTRA COMMSTUD | COMMUNICATIONS | Telstra |  | BYDA | D-DWG-PHW-010.2 |  | Yes |  | 74
PHW-CM-0021 | PHW | 6996 | BYDA TELSTRA COMMSTUD | COMMUNICATIONS | Telstra |  | BYDA | D-DWG-PHW-010.2 |  | Yes |  | 75
PHW-CM-0022 | PHW | 6997 | BYDA TELSTRA COMMSTUD | COMMUNICATIONS | Telstra |  | BYDA | D-DWG-PHW-010.2 |  | Yes |  | 76
PHW-CM-0023 | PHW | 6998 | BYDA NEXTGEN | COMMUNICATIONS | Nextgen |  | BYDA | D-DWG-PHW-010.2 |  | Yes |  | 77
PHW-CM-0024 | PHW | 7021 | BYDA NBN COMMS | COMMUNICATIONS | NBN Co |  | BYDA | D-DWG-PHW-011.2 | D-DWG-PHW-011_C | Yes |  | 78
PHW-CM-0025 | PHW | 7021 | BYDA NBN COMMS | COMMUNICATIONS | NBN Co |  | BYDA | D-DWG-PHW-011.2 | D-DWG-PHW-011_C | Yes |  | 79
PHW-WA-0015 | PHW | 7030 | BYDA TRC WATER | WATER | Toowoomba Regional Council |  | BYDA | D-DWG-PHW-011.2 | D-DWG-PHW-011_C | Yes |  | 80
PHW-EL-0013 | PHW | 7032 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-011.2 | D-DWG-PHW-011_C | Yes |  | 81
PHW-CM-0026 | PHW | 7033 | BYDA TELSTRA COMMS | COMMUNICATIONS | Telstra |  | BYDA | D-DWG-PHW-011.2 |  | Yes |  | 82
PHW-EL-0014 | PHW | 7481 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-011.2 |  | Yes |  | 83
PHW-CM-0027 | PHW | 7860 | BYDA TELSTRA COMMS DN50 | COMMUNICATIONS | Telstra | 50 | BYDA | D-DWG-PHW-012.2 |  | Yes |  | 84
PHW-EL-0015 | PHW | 7867 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-012.2 |  | Yes |  | 85
PHW-WA-0016 | PHW | 7882 | BYDA TRC WATER DN 375 | WATER | Toowoomba Regional Council | 375 | BYDA | D-DWG-PHW-012.2 |  | Yes | LOCATION/DEPTH OF WATER SERVICE NOT KNOWN. CONTRACTOR TO CONFIRM PRIOR TO CONSTRUCTION | 86
PHW-CM-0028 | PHW | 7903 | BYDA TELSTRA COMMS | COMMUNICATIONS | Telstra |  | BYDA | D-DWG-PHW-012.2 |  | Yes |  | 87
PHW-CM-0029 | PHW | 9476 | BYDA COMMS DN50 | COMMUNICATIONS |  | 50 | BYDA | D-DWG-PHW-014.2 |  | Yes |  | 88
PHW-CM-0030 | PHW | 9698 | BYDA COMMS DN50 | COMMUNICATIONS |  | 50 | BYDA | D-DWG-PHW-014.2 |  | Yes |  | 89
| PHW | 10595 | EUD LEVEL | SURVEY LEVEL |  |  |  | D-DWG-PHW-016.2 |  | Yes | UNKOWN ASSET | 90
| PHW | 10597 | DG LEVEL | SURVEY LEVEL |  |  |  | D-DWG-PHW-016.2 |  | Yes | UNKOWN ASSET | 91
| PHW | 10598 | DG LEVEL | SURVEY LEVEL |  |  |  | D-DWG-PHW-016.2 |  | Yes | UNKOWN ASSET | 92
| PHW | 10599 | DG LEVEL | SURVEY LEVEL |  |  |  | D-DWG-PHW-016.2 |  | Yes | UNKOWN ASSET | 93
| PHW | 10609 | EUD LEVEL | SURVEY LEVEL |  |  |  | D-DWG-PHW-016.2 |  | Yes | UNKOWN ASSET | 94
| PHW | 10610 | DG LEVEL | SURVEY LEVEL |  |  |  | D-DWG-PHW-016.2 |  | Yes | UNKOWN ASSET | 95
| PHW | 10632 | EUD LEVEL | SURVEY LEVEL |  |  |  | D-DWG-PHW-016.2 |  | Yes | UNKOWN ASSET | 96
PHW-CM-0031 | PHW | 10642 | BYDA TELSTRA COMMS DN100 | COMMUNICATIONS | Telstra | 100 | BYDA | D-DWG-PHW-016.2 |  | Yes |  | 97
PHW-EL-0016 | PHW | 10676 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-016.2 | D-DWG-PHW-016_C | Yes |  | 98
PHW-EL-0017 | PHW | 10691 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-016.2 | D-DWG-PHW-016_C | Yes |  | 99
PHW-CM-0032 | PHW | 10692 | BYDA TELSTRA COMS | COMMUNICATIONS | Telstra |  | BYDA | D-DWG-PHW-016.2 |  | Yes |  | 100
PHW-CM-0033 | PHW | 10775 | BYDA TELSTRA COMS DN50 | COMMUNICATIONS | Telstra | 50 | BYDA | D-DWG-PHW-016.2 |  | Yes |  | 101
PHW-EL-0018 | PHW | 10793 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-016.2 |  | Yes |  | 102
PHW-CM-0034 | PHW | 11188 | BYDA TELSTRA COMMS | COMMUNICATIONS | Telstra |  | BYDA | D-DWG-PHW-016.2 |  | Yes |  | 103
PHW-EL-0019 | PHW | 11379 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-017.2 |  | Yes |  | 104
PHW-FN-0019 | PHW | 11735 | FENCE LINE NO POST - WIRES ONLY | FENCE |  |  |  | D-DWG-PHW-017.2 |  | Yes |  | 105
PHW-CM-0035 | PHW | 12452 | BYDA TELSTRA COMMS DN100 | COMMUNICATIONS | Telstra | 100 | BYDA | D-DWG-PHW-018.2 |  | Yes |  | 106
PHW-EL-0020 | PHW | 12470 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-018.2 |  | Yes |  | 107
PHW-EL-0021 | PHW | 12470 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-018.2 |  | Yes |  | 108
PHW-CM-0036 | PHW | 12470 | BYDA COMMS DN100 | COMMUNICATIONS |  | 100 | BYDA | D-DWG-PHW-018.2 |  | Yes |  | 109
PHW-EL-0022 | PHW | 12507 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-018.2 |  | Yes |  | 110
PHW-CM-0037 | PHW | 12528 | BYDA TELSTRA COMMS DN100 | COMMUNICATIONS | Telstra | 100 | BYDA | D-DWG-PHW-018.2 |  | Yes |  | 111
PHW-EL-0023 | PHW | 12915 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-019.2 |  | Yes |  | 112
PHW-CM-0038 | PHW | 12969 | BYDA TELSTRA COMMS | COMMUNICATIONS | Telstra |  | BYDA | D-DWG-PHW-019.2 |  | Yes |  | 113
PHW-EL-0024 | PHW | 13024 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-019.2 |  | Yes |  | 114
PHW-WA-0017 | PHW | 13236 | BYDA TRC WATER DN300 | WATER | Toowoomba Regional Council | 300 | BYDA | D-DWG-PHW-019.2 |  | Yes | LOCATION/DEPTH OF WATER SERVICE NOT KNOWN.CONTRACTOR TO CONFIRM PRIOR TO CONSTRUCTION | 115
PHW-EL-0025 | PHW | 13243 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-019.2 |  | Yes |  | 116
PHW-CM-0039 | PHW | 13275 | PUP COMMS DN100 | COMMUNICATIONS |  | 100 | PUP | D-DWG-PHW-019.2 |  | Yes |  | 117
PHW-CM-0040 | PHW | 13278 | PUP COMMS DN100 | COMMUNICATIONS |  | 100 | PUP | D-DWG-PHW-019.2 |  | Yes |  | 118
PHW-CM-0041 | PHW | 13278 | PUP COMMS DN100 | COMMUNICATIONS |  | 100 | PUP | D-DWG-PHW-019.2 |  | Yes |  | 119
PHW-CM-0042 | PHW | 13278 | BYDA NBN COMMS DN100 | COMMUNICATIONS | NBN Co | 100 | BYDA | D-DWG-PHW-019.2 |  | Yes |  | 120
PHW-EL-0026 | PHW | 13287 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-019.2 |  | Yes |  | 121
PHW-CM-0043 | PHW | 13323 | BYDA TELSTRA COMMS DN100 | COMMUNICATIONS | Telstra | 100 | BYDA | D-DWG-PHW-020.2 |  | Yes |  | 122
PHW-EL-0027 | PHW | 13395 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-020.2 |  | Yes |  | 123
PHW-EL-0028 | PHW | 13556 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-020.2 |  | Yes |  | 124
PHW-EL-0029 | PHW | 13606 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-020.2 |  | Yes |  | 125
PHW-EL-0030 | PHW | 13613 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-020.2 |  | Yes |  | 126
PHW-EL-0031 | PHW | 13628 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-020.2 |  | Yes |  | 127
PHW-WA-0018 | PHW | 13644 | BYDA TRC WATER DN375 | WATER | Toowoomba Regional Council | 375 | BYDA | D-DWG-PHW-020.2 |  | Yes | LOCATION/DEPTH OF WATER SERVICE NOT KNOWN.CONTRACTOR TO CONFIRM PRIOR TO CONSTRUCTION | 128
PHW-CM-0044 | PHW | 13650 | BYDA TELSTA COMMS DN100 | COMMUNICATIONS | Telstra | 100 | BYDA | D-DWG-PHW-020.2 |  | Yes |  | 129
PHW-EL-0032 | PHW | 13950 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-020.2 |  | Yes |  | 130
PHW-CM-0045 | PHW | 14114 | BYDA NBN COMMS DN100 | COMMUNICATIONS | NBN Co | 100 | BYDA | D-DWG-PHW-021.2 |  | Yes |  | 131
PHW-CM-0046 | PHW | 14116 | BYDA TELSTRA COMMS DN35 | COMMUNICATIONS | Telstra | 35 | BYDA | D-DWG-PHW-021.2 |  | Yes |  | 132
PHW-EL-0033 | PHW | 14192 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-021.2 |  | Yes |  | 133
PHW-EL-0034 | PHW | 14335 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-021.2 |  | Yes |  | 134
PHW-CM-0047 | PHW | 14630 | BYDA TELSTRA COMMS DN35 | COMMUNICATIONS | Telstra | 35 | BYDA | D-DWG-PHW-021.2 |  | Yes |  | 135
PHW-SW-0004 | PHW | 14803 | BYDA TRC SEWER | SEWER | Toowoomba Regional Council |  | BYDA | D-DWG-PHW-022.2 | D-DWG-PHW-022_C | Yes |  | 136
PHW-EL-0035 | PHW | 14830 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-022.2 |  | Yes |  | 137
PHW-CM-0048 | PHW | 14832 | PUP COMMS DN100 | COMMUNICATIONS |  | 100 | PUP | D-DWG-PHW-022.2 |  | Yes |  | 138
PHW-EL-0036 | PHW | 14925 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-022.2 |  | Yes |  | 139
PHW-EL-0037 | PHW | 15049 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-022.2 |  | Yes |  | 140
PHW-EL-0038 | PHW | 15052 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-022.2 |  | Yes |  | 141
PHW-CM-0049 | PHW | 15054 | BYDA TELSTRA COMMS DN50 | COMMUNICATIONS | Telstra | 50 | BYDA | D-DWG-PHW-022.2 |  | Yes |  | 142
PHW-CM-0050 | PHW | 15758 | BYDA TELSTRA COMMS DN50 | COMMUNICATIONS | Telstra | 50 | BYDA | D-DWG-PHW-023.2 |  | Yes |  | 143
PHW-CM-0051 | PHW | 15763 | BYDA TELSTRA COMMS DN50 | COMMUNICATIONS | Telstra | 50 | BYDA | D-DWG-PHW-023.2 |  | Yes |  | 144
PHW-EL-0039 | PHW | 15769 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-023.2 |  | Yes |  | 145
PHW-EL-0040 | PHW | 16590 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-024.2 |  | Yes |  | 146
PHW-SW-0005 | PHW | 17031 | PUP SEWER DN375 | SEWER |  | 375 | PUP | D-DWG-PHW-025.2 |  | Yes |  | 147
PHW-SW-0006 | PHW | 18078 | BYDA SEWER DN375 | SEWER |  | 375 | BYDA | D-DWG-PHW-026.2 |  | Yes |  | 148
PHW-CM-0052 | PHW | 18079 | BYD TELSTRA COMMS | COMMUNICATIONS | Telstra |  | BYDA | D-DWG-PHW-026.2 |  | Yes |  | 149
PHW-FN-0020 | PHW | 18452 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PHW-027.2 |  | Yes |  | 150
PHW-FN-0021 | PHW | 18507 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PHW-027.2 |  | Yes |  | 151
PHW-EL-0041 | PHW | 18601 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-027.2 |  | Yes |  | 152
PHW-CM-0053 | PHW | 18717 | BYDA TELSTRA COMMSTUD | COMMUNICATIONS | Telstra |  | BYDA | D-DWG-PHW-027.2 |  | Yes | LOCATION OF TELECOMS SERVICE NOT KNOWN.CONTRACTOR TO CONFIRM PRIOR TO CONSTRUCTION | 153
PHW-CM-0054 | PHW | 18828 | BYDA TELSTRA COMMS DN35 | COMMUNICATIONS | Telstra | 35 | BYDA | D-DWG-PHW-027.2 |  | Yes |  | 154
PHW-EL-0042 | PHW | 18889 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PHW-027.2 |  | Yes |  | 155
PHW-CM-0055 | PHW | 19123 | BYDA TELSTRA COMMS DN20 | COMMUNICATIONS | Telstra | 20 | BYDA | D-DWG-PHW-028.2 |  | Yes | CONTRACTOR TO LOCATE EXISTING TELECOMS AND ENSURE PIGGING STATION DOES NOT CLASH | 156
PHW-FN-0022 | PHW | 19124 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PHW-028.2 |  | Yes |  | 157
PHW-FN-0023 | PHW | 19155 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PHW-028.2 |  | Yes |  | 158
PWG-CM-0001 | PWG | 12 | BYDA TELSTRA COMMS DN20 | COMMUNICATIONS | Telstra | 20 | BYDA | D-DWG-PWG-001.2 |  | Yes |  | 159
PWG-FN-0001 | PWG | 635 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PWG-001.2 |  | Yes |  | 160
PWG-FN-0002 | PWG | 653 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PWG-001.2 |  | Yes |  | 161
PWG-FN-0003 | PWG | 755 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PWG-002.2 |  | Yes |  | 162
PWG-FN-0004 | PWG | 905 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PWG-002.2 | D-DWG-PWG-002_C | Yes |  | 163
PWG-SW-0001 | PWG | 1183 | BYDA SEWER DN375 | SEWER |  | 375 | BYDA | D-DWG-PWG-002.2 |  | Yes |  | 164
PWG-EL-0001 | PWG | 1403 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-003.2 |  | Yes |  | 165
PWG-CM-0002 | PWG | 1425 | BYDA TELSTRA COMMS | COMMUNICATIONS | Telstra |  | BYDA | D-DWG-PWG-003.2 |  | Yes |  | 166
PWG-CM-0003 | PWG | 1469 | PUP COMMS DN50 | COMMUNICATIONS |  | 50 | PUP | D-DWG-PWG-003.2 | D-DWG-PWG-003_C | Yes |  | 167
PWG-EL-0002 | PWG | 1494 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-003.2 |  | Yes |  | 168
PWG-EL-0003 | PWG | 1788 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-003.2 |  | Yes |  | 169
PWG-EL-0004 | PWG | 1839 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-003.2 |  | Yes |  | 170
PWG-CM-0004 | PWG | 1867 | PUP COMMS DN100 | COMMUNICATIONS |  | 100 | PUP | D-DWG-PWG-003.2 |  | Yes |  | 171
PWG-CM-0005 | PWG | 1871 | BYDA NBN COMMS DN30 | COMMUNICATIONS | NBN Co | 30 | BYDA | D-DWG-PWG-003.2 |  | Yes |  | 172
PWG-CM-0006 | PWG | 1872 | PUP COMMS DN35 | COMMUNICATIONS |  | 35 | PUP | D-DWG-PWG-003.2 |  | Yes |  | 173
PWG-DR-0001 | PWG | 1894 | PUP DRAINAGE DN1200x450 | DRAINAGE |  | 1200 x 450 | PUP | D-DWG-PWG-003.2 |  | Yes |  | 174
PWG-SW-0002 | PWG | 1900 | BYDA SEWER DN250 | SEWER |  | 250 | BYDA | D-DWG-PWG-003.2 |  | Yes |  | 175
PWG-SW-0003 | PWG | 2046 | BDYA TRC SEWER DN 150 | SEWER | Toowoomba Regional Council | 150 | BYDA | D-DWG-PWG-003.2 |  | Yes |  | 176
PWG-EL-0005 | PWG | 2186 | BYDA ELECTRICITY UGD DN100 | ELECTRICITY |  | 100 | BYDA | D-DWG-PWG-004.2 |  | Yes |  | 177
PWG-DR-0002 | PWG | 2217 | PUP DRAINAGE DN900x450 | DRAINAGE |  | 900 x 450 | PUP | D-DWG-PWG-004.2 |  | Yes |  | 178
PWG-DR-0003 | PWG | 2494 | PUP DRAINAGE DN450 | DRAINAGE |  | 450 | PUP | D-DWG-PWG-004.2 |  | Yes |  | 179
PWG-SW-0004 | PWG | 2556 | BYDA SEWER DN250 | SEWER |  | 250 | BYDA | D-DWG-PWG-004.2 |  | Yes |  | 180
PWG-DR-0004 | PWG | 2560 | PUP DRAINAGE DN600 | DRAINAGE |  | 600 | PUP | D-DWG-PWG-004.2 |  | Yes |  | 181
PWG-WA-0001 | PWG | 2578 | BYDA WATER DN150 | WATER |  | 150 | BYDA | D-DWG-PWG-004.2 |  | Yes |  | 182
PWG-EL-0006 | PWG | 2744 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-004.2 | D-DWG-PWG-004_C | Yes |  | 183
PWG-WA-0002 | PWG | 2754 | BYDA TRC WATER DN100 | WATER | Toowoomba Regional Council | 100 | BYDA | D-DWG-PWG-004.2 |  | Yes |  | 184
PWG-CM-0007 | PWG | 2754 | BYDA TELSTRA COMMS DN100 | COMMUNICATIONS | Telstra | 100 | BYDA | D-DWG-PWG-004.2 |  | Yes |  | 185
PWG-CM-0008 | PWG | 2754 | BYDA TELSTRA COMMS DN100 | COMMUNICATIONS | Telstra | 100 | BYDA | D-DWG-PWG-004.2 |  | Yes |  | 186
PWG-CM-0009 | PWG | 2754 | BYDA NBN COMMS DN30 | COMMUNICATIONS | NBN Co | 30 | BYDA | D-DWG-PWG-004.2 |  | Yes |  | 187
PWG-CM-0010 | PWG | 2754 | BYDA NBN COMMS DN30 | COMMUNICATIONS | NBN Co | 30 | BYDA | D-DWG-PWG-004.2 |  | Yes |  | 188
PWG-CM-0011 | PWG | 2754 | BYDA NBN COMMS DN30 | COMMUNICATIONS | NBN Co | 30 | BYDA | D-DWG-PWG-004.2 |  | Yes |  | 189
PWG-CM-0012 | PWG | 2754 | BYDA NBN COMMS DN30 | COMMUNICATIONS | NBN Co | 30 | BYDA | D-DWG-PWG-004.2 |  | Yes |  | 190
PWG-CM-0013 | PWG | 2754 | BYDA NBN COMMS DN30 | COMMUNICATIONS | NBN Co | 30 | BYDA | D-DWG-PWG-004.2 |  | Yes |  | 191
PWG-CM-0014 | PWG | 2754 | BYDA NBN COMMS DN30 | COMMUNICATIONS | NBN Co | 30 | BYDA | D-DWG-PWG-004.2 |  | Yes |  | 192
PWG-EL-0007 | PWG | 2763 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-004.2 |  | Yes |  | 193
PWG-WA-0003 | PWG | 2763 | BYDA WATER DN200 | WATER |  | 200 | BYDA | D-DWG-PWG-004.2 |  | Yes |  | 194
PWG-WA-0004 | PWG | 2763 | BYDA TRC WATER | WATER | Toowoomba Regional Council |  | BYDA | D-DWG-PWG-004.2 |  | Yes |  | 195
PWG-EL-0008 | PWG | 2763 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-004.2 |  | Yes |  | 196
PWG-EL-0009 | PWG | 2768 | BYDA ELECTRICITYELD LV | ELECTRICITY |  |  | BYDA | D-DWG-PWG-004.2 | D-DWG-PWG-004_C | Yes |  | 197
PWG-SW-0005 | PWG | 2771 | BYDA TRC SEWER DN110 | SEWER | Toowoomba Regional Council | 110 | BYDA | D-DWG-PWG-004.2 |  | Yes |  | 198
PWG-EL-0010 | PWG | 2771 | BYDA ELECTRICITY UGD DN50 | ELECTRICITY |  | 50 | BYDA | D-DWG-PWG-004.2 |  | Yes |  | 199
PWG-SW-0006 | PWG | 2773 | BYDA TRC SEWER DN63 | SEWER | Toowoomba Regional Council | 63 | BYDA | D-DWG-PWG-004.2 |  | Yes |  | 200
PWG-SW-0007 | PWG | 2775 | BYDA SEWER DN315 | SEWER |  | 315 | BYDA | D-DWG-PWG-004.2 |  | Yes |  | 201
PWG-SW-0008 | PWG | 2777 | PUP SEWER DN150 | SEWER |  | 150 | PUP | D-DWG-PWG-004.2 |  | Yes |  | 202
PWG-CM-0015 | PWG | 2781 | PUP COMMS DN100 | COMMUNICATIONS |  | 100 | PUP | D-DWG-PWG-004.2 |  | Yes |  | 203
PWG-CM-0016 | PWG | 2805 | PUP COMMS DN50 | COMMUNICATIONS |  | 50 | PUP | D-DWG-PWG-005.2 |  | Yes |  | 204
PWG-SW-0009 | PWG | 2868 | PUP SEWER DN150 | SEWER |  | 150 | PUP | D-DWG-PWG-005.2 |  | Yes |  | 205
PWG-FN-0005 | PWG | 2908 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PWG-005.2 |  | Yes |  | 206
PWG-FN-0006 | PWG | 3368 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PWG-005.2 |  | Yes |  | 207
PWG-FN-0007 | PWG | 4640 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PWG-007.2 | D-DWG-PWG-007_C | Yes |  | 208
PWG-FN-0008 | PWG | 5448 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PWG-008.2 |  | Yes |  | 209
PWG-FN-0009 | PWG | 6505 | FENCE LINE NO POSTS | FENCE |  |  |  | D-DWG-PWG-010.2 | D-DWG-PWG-010_C | Yes |  | 210
PWG-CM-0017 | PWG | 7079 | BYDA NEXTGEN COMMS DN50 | COMMUNICATIONS | Nextgen | 50 | BYDA | D-DWG-PWG-011.2 |  | Yes |  | 211
PWG-FN-0010 | PWG | 7098 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PWG-011.2 |  | Yes |  | 212
PWG-FN-0011 | PWG | 7116 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PWG-011.2 |  | Yes |  | 213
PWG-FN-0012 | PWG | 7260 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PWG-011.2 | D-DWG-PWG-011_C | Yes |  | 214
PWG-FN-0013 | PWG | 7577 | FENCE LINE NO POSTS - WIRES ON | FENCE |  |  |  | D-DWG-PWG-011.2 |  | Yes |  | 215
PWG-WA-0005 | PWG | 7609 | BYDA WATER | WATER |  |  | BYDA | D-DWG-PWG-011.2 |  | Yes |  | 216
PWG-EL-0011 | PWG | 7609 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-011.2 |  | Yes |  | 217
PWG-OI-0001 | PWG | 7633 | BYDA OIL | OIL |  |  | BYDA | D-DWG-PWG-011.2 |  | Yes |  | 218
PWG-WA-0006 | PWG | 7820 | UNKNOW WATER | WATER |  |  |  | D-DWG-PWG-012.2 |  | Yes |  | 219
PWG-EL-0012 | PWG | 7826 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-012.2 |  | Yes |  | 220
PWG-EL-0013 | PWG | 7826 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-012.2 |  | Yes |  | 221
PWG-WA-0007 | PWG | 7854 | BYDA WATER DN375 | WATER |  | 375 | BYDA | D-DWG-PWG-012.2 |  | Yes |  | 222
PWG-WA-0008 | PWG | 7915 | BYDA WATER DN375 | WATER |  | 375 | BYDA | D-DWG-PWG-012.2 |  | Yes |  | 223
PWG-WA-0009 | PWG | 7953 | BYDA WATER DN150 | WATER |  | 150 | BYDA | D-DWG-PWG-012.2 |  | Yes |  | 224
PWG-DR-0005 | PWG | 7953 | PUP DRAINAGE DN200x500 | DRAINAGE |  | 200 x 500 | PUP | D-DWG-PWG-012.2 |  | Yes |  | 225
PWG-EL-0014 | PWG | 7958 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-012.2 |  | Yes |  | 226
PWG-EL-0015 | PWG | 8041 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-012.2 |  | Yes |  | 227
PWG-EL-0016 | PWG | 8042 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-012.2 |  | Yes |  | 228
PWG-WA-0010 | PWG | 8067 | BYDA WATER DN150 | WATER |  | 150 | BYDA | D-DWG-PWG-012.2 |  | Yes |  | 229
PWG-WA-0011 | PWG | 8117 | BYDA WATER | WATER |  |  | BYDA | D-DWG-PWG-012.2 |  | Yes |  | 230
PWG-WA-0012 | PWG | 8220 | BYDA WATER | WATER |  |  | BYDA | D-DWG-PWG-012.2 | D-DWG-PWG-012_C | Yes |  | 231
PWG-EL-0017 | PWG | 8234 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-012.2 |  | Yes |  | 232
PWG-WA-0013 | PWG | 8257 | BYDA WATER | WATER |  |  | BYDA | D-DWG-PWG-012.2 |  | Yes |  | 233
PWG-EL-0018 | PWG | 8266 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-012.2 |  | Yes |  | 234
PWG-WA-0014 | PWG | 8278 | BYDA WATER DN150 | WATER |  | 150 | BYDA | D-DWG-PWG-012.2 |  | Yes |  | 235
PWG-CM-0018 | PWG | 8289 | PUP COMMS DN300 | COMMUNICATIONS |  | 300 | PUP | D-DWG-PWG-012.2 |  | Yes |  | 236
PWG-EL-0019 | PWG | 8306 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-012.2 |  | Yes |  | 237
PWG-WA-0015 | PWG | 8306 | BYDA WATER | WATER |  |  | BYDA | D-DWG-PWG-012.2 |  | Yes |  | 238
PWG-EL-0020 | PWG | 8310 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-012.2 |  | Yes |  | 239
PWG-CM-0019 | PWG | 8358 | BYDA COMMS DN100 | COMMUNICATIONS |  | 100 | BYDA | D-DWG-PWG-012.2 |  | Yes |  | 240
PWG-CM-0020 | PWG | 8370 | BYDA TELSTRA COMMS DN100 | COMMUNICATIONS | Telstra | 100 | BYDA | D-DWG-PWG-012.2 |  | Yes |  | 241
PWG-CM-0021 | PWG | 8372 | BYDA TELSTRA COMMS DN30 | COMMUNICATIONS | Telstra | 30 | BYDA | D-DWG-PWG-012.2 |  | Yes |  | 242
PWG-WA-0016 | PWG | 8442 | BYDA WATER "SIZE TBC" | WATER |  | TBC | BYDA | D-DWG-PWG-013.2 |  | Yes |  | 243
PWG-WA-0017 | PWG | 8487 | BYDA WATER | WATER |  |  | BYDA | D-DWG-PWG-013.2 |  | Yes |  | 244
PWG-CM-0022 | PWG | 8489 | BYDA TELSTRA COMMS DN100 | COMMUNICATIONS | Telstra | 100 | BYDA | D-DWG-PWG-013.2 |  | Yes |  | 245
PWG-FN-0014 | PWG | 8491 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PWG-013.2 |  | Yes |  | 246
PWG-CM-0023 | PWG | 8532 | PUP COMMS DN200 PVC | COMMUNICATIONS |  | 200 | PUP | D-DWG-PWG-013.2 |  | Yes |  | 247
PWG-CM-0024 | PWG | 8577 | BYDA NBN COMMS DN30 | COMMUNICATIONS | NBN Co | 30 | BYDA | D-DWG-PWG-013.2 |  | Yes |  | 248
PWG-CM-0025 | PWG | 8596 | BYDA NBN COMMS | COMMUNICATIONS | NBN Co |  | BYDA | D-DWG-PWG-013.2 |  | Yes |  | 249
PWG-CM-0026 | PWG | 8597 | PUP COMMS PVC | COMMUNICATIONS |  |  | PUP | D-DWG-PWG-013.2 |  | Yes |  | 250
PWG-WA-0018 | PWG | 8603 | BYDA WATER DN150 | WATER |  | 150 | BYDA | D-DWG-PWG-013.2 |  | Yes |  | 251
PWG-SW-0010 | PWG | 8607 | PUP SEWER DN150 | SEWER |  | 150 | PUP | D-DWG-PWG-013.2 |  | Yes |  | 252
PWG-SW-0011 | PWG | 8697 | PUP SEWER DN315 | SEWER |  | 315 | PUP | D-DWG-PWG-013.2 |  | Yes |  | 253
PWG-CM-0027 | PWG | 9243 | BYDA TELSTRA COMMS DN50 CONC COVER | COMMUNICATIONS | Telstra | 50 | BYDA | D-DWG-PWG-014.2 |  | Yes |  | 254
PWG-EL-0021 | PWG | 9561 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-014.2 |  | Yes |  | 255
PWG-EL-0022 | PWG | 9585 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-014.2 |  | Yes |  | 256
PWG-EL-0023 | PWG | 9585 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-014.2 |  | Yes |  | 257
PWG-EL-0024 | PWG | 9788 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-014.2 |  | Yes |  | 258
PWG-EL-0025 | PWG | 10298 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-015.2 |  | Yes |  | 259
PWG-CM-0028 | PWG | 10433 | BYDA TELSTRA COMMS DN50 CONC COVER | COMMUNICATIONS | Telstra | 50 | BYDA | D-DWG-PWG-015.2 |  | Yes |  | 260
PWG-CM-0029 | PWG | 10433 | BYDA NBN COMMS DN30 | COMMUNICATIONS | NBN Co | 30 | BYDA | D-DWG-PWG-015.2 |  | Yes |  | 261
PWG-CM-0030 | PWG | 10433 | BYDA TELSTRACOMMS DN30 | COMMUNICATIONS | Telstra | 30 | BYDA | D-DWG-PWG-015.2 |  | Yes |  | 262
PWG-EL-0026 | PWG | 10905 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-016.2 |  | Yes |  | 263
PWG-EL-0027 | PWG | 11179 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-016.2 |  | Yes |  | 264
PWG-EL-0028 | PWG | 11482 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-017.2 |  | Yes |  | 265
PWG-CM-0031 | PWG | 11771 | BYDA TELSTRA COMMS DN50 CONC COVER | COMMUNICATIONS | Telstra | 50 | BYDA | D-DWG-PWG-017.2 |  | Yes |  | 266
PWG-EL-0029 | PWG | 11771 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-017.2 |  | Yes |  | 267
PWG-EL-0030 | PWG | 11969 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-018.2 |  | Yes |  | 268
PWG-EL-0031 | PWG | 12094 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-018.2 |  | Yes |  | 269
PWG-FN-0015 | PWG | 12214 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PWG-018.2 |  | Yes |  | 270
PWG-FN-0016 | PWG | 12273 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PWG-018.2 |  | Yes |  | 271
PWG-CM-0032 | PWG | 12307 | BYDA NBN COMMS DN30 | COMMUNICATIONS | NBN Co | 30 | BYDA | D-DWG-PWG-018.2 |  | Yes |  | 272
PWG-CM-0033 | PWG | 12307 | BYDA NBN COMMS DN30 | COMMUNICATIONS | NBN Co | 30 | BYDA | D-DWG-PWG-018.2 |  | Yes |  | 273
PWG-CM-0034 | PWG | 12320 | BYDA TELSTRA COMMS DN35 | COMMUNICATIONS | Telstra | 35 | BYDA | D-DWG-PWG-018.2 |  | Yes |  | 274
PWG-CM-0035 | PWG | 12322 | BYDA NBN COMMS DN30 | COMMUNICATIONS | NBN Co | 30 | BYDA | D-DWG-PWG-018.2 |  | Yes |  | 275
PWG-CM-0036 | PWG | 12322 | BYDA NBN COMMS DN30 | COMMUNICATIONS | NBN Co | 30 | BYDA | D-DWG-PWG-018.2 |  | Yes |  | 276
PWG-CM-0037 | PWG | 12322 | BYDA NBN COMMS DN30 | COMMUNICATIONS | NBN Co | 30 | BYDA | D-DWG-PWG-018.2 |  | Yes |  | 277
PWG-CM-0038 | PWG | 13228 | BYDA TELSTRA COMMS DN50 | COMMUNICATIONS | Telstra | 50 | BYDA | D-DWG-PWG-019.2 |  | Yes |  | 278
PWG-FN-0017 | PWG | 13375 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PWG-020.2 |  | Yes |  | 279
PWG-FN-0018 | PWG | 13375 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PWG-020.2 |  | Yes |  | 280
PWG-FN-0019 | PWG | 13375 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PWG-020.2 |  | Yes |  | 281
PWG-EL-0032 | PWG | 13380 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-020.2 |  | Yes |  | 282
PWG-FN-0020 | PWG | 14071 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PWG-021.2 |  | Yes |  | 283
PWG-FN-0021 | PWG | 14136 | FENCE - CHAINWIRE | FENCE |  |  |  | D-DWG-PWG-021.2 |  | Yes |  | 284
PWG-FN-0022 | PWG | 14214 | FENCE - CHAINWIRE | FENCE |  |  |  | D-DWG-PWG-021.2 |  | Yes |  | 285
PWG-FN-0027 | PWG | 15528 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PWG-021.2 |  | Yes |  | 286
PWG-FN-0028 | PWG | 15528 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PWG-021.2 |  | Yes |  | 287
PWG-CM-0040 | PWG | 15533 | BYDA TELSTRA COMMS DN20 | COMMUNICATIONS | Telstra | 20 | BYDA | D-DWG-PWG-021.2 |  | Yes |  | 288
PWG-CM-0041 | PWG | 15566 | BYDA TELSTRA COMMS DN20 | COMMUNICATIONS | Telstra | 20 | BYDA | D-DWG-PWG-021.2 |  | Yes |  | 289
PWG-FN-0030 | PWG | 15571 | FENCE LINE NO POSTS - WIRES ONLY | FENCE |  |  |  | D-DWG-PWG-021.2 |  | Yes |  | 290
PWG-CM-0039 | PWG | 14877 | BYDA TELSTRA COMMS DN20 | COMMUNICATIONS | Telstra | 20 | BYDA | D-DWG-PWG-022.2 |  | Yes |  | 291
PWG-FN-0023 | PWG | 14883 | FENCE - CHAINWIRE | FENCE |  |  |  | D-DWG-PWG-022.2 |  | Yes |  | 292
PWG-FN-0024 | PWG | 15016 | FENCE - CHAINWIRE | FENCE |  |  |  | D-DWG-PWG-022.2 |  | Yes |  | 293
PWG-FN-0025 | PWG | 15340 | FENCE - CHAINWIRE | FENCE |  |  |  | D-DWG-PWG-022.2 |  | Yes |  | 294
PWG-CM-0042 | PWG | 15663 | BYDA NBN COMMS DN30 | COMMUNICATIONS | NBN Co | 30 | BYDA | D-DWG-PWG-022.2 |  | Yes |  | 295
PWG-CM-0043 | PWG | 15663 | BYDA NBN COMMS DN30 | COMMUNICATIONS | NBN Co | 30 | BYDA | D-DWG-PWG-022.2 |  | Yes |  | 296
PWG-FN-0026 | PWG | 15475 | FENCE CHAINWIRE | FENCE |  |  |  | D-DWG-PWG-023.2 |  | Yes |  | 297
PWG-FN-0029 | PWG | 15542 | FENCE CHAINWIRE | FENCE |  |  |  | D-DWG-PWG-023.2 |  | Yes |  | 298
PWG-FN-0031 | PWG | 15593 | FENCE CHAINWIRE | FENCE |  |  |  | D-DWG-PWG-023.2 |  | Yes |  | 299
PWG-EL-0033 | PWG | 16364 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-024.2 |  | Yes |  | 300
PWG-FN-0032 | PWG | 16520 | FENCE LINE NO POSTS | FENCE |  |  |  | D-DWG-PWG-024.2 | D-DWG-PWG-024_C | Yes |  | 301
PWG-FN-0033 | PWG | 16930 | FENCE LINE NO POSTS | FENCE |  |  |  | D-DWG-PWG-025.2 | D-DWG-PWG-025_C | Yes |  | 302
PWG-EL-0034 | PWG | 16969 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-025.2 |  | Yes |  | 303
PWG-CM-0044 | PWG | 16979 | BYDA TELSTRA COMMS DN50 | COMMUNICATIONS | Telstra | 50 | BYDA | D-DWG-PWG-025.2 |  | Yes |  | 304
PWG-EL-0035 | PWG | 17006 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-025.2 |  | Yes |  | 305
PWG-EL-0036 | PWG | 17105 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-025.2 |  | Yes |  | 306
PWG-CM-0045 | PWG | 18029 | BYDA TELSTRA COMMS DN50 | COMMUNICATIONS | Telstra | 50 | BYDA | D-DWG-PWG-026.2 |  | Yes |  | 307
PWG-EL-0037 | PWG | 18050 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-026.2 |  | Yes |  | 308
PWG-CM-0046 | PWG | 18119 | PUP COMMS DN50 | COMMUNICATIONS |  | 50 | PUP | D-DWG-PWG-026.2 |  | Yes |  | 309
PWG-EL-0038 | PWG | 18184 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-026.2 |  | Yes |  | 310
PWG-CM-0047 | PWG | 18216 | BYDA TELSTRA COMMS DN35 | COMMUNICATIONS | Telstra | 35 | BYDA | D-DWG-PWG-027.2 |  | Yes |  | 311
PWG-EL-0039 | PWG | 19524 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-028.2 |  | Yes |  | 312
PWG-EL-0040 | PWG | 19541 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-028.2 |  | Yes |  | 313
PWG-CM-0048 | PWG | 19765 | BYDA TELSTRA COMMS DN20 | COMMUNICATIONS | Telstra | 20 | BYDA | D-DWG-PWG-029.2 |  | Yes |  | 314
PWG-EL-0041 | PWG | 20818 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-030.2 |  | Yes |  | 315
PWG-EL-0042 | PWG | 20947 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-030.2 |  | Yes |  | 316
PWG-EL-0043 | PWG | 21376 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-031.2 |  | Yes |  | 317
PWG-EL-0044 | PWG | 21486 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-031.2 |  | Yes |  | 318
PWG-EL-0045 | PWG | 22272 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-032.2 |  | Yes |  | 319
PWG-EL-0046 | PWG | 22504 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-033.2 |  | Yes |  | 320
PWG-EL-0047 | PWG | 22650 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-033.2 |  | Yes |  | 321
PWG-EL-0048 | PWG | 24097 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-035.2 |  | Yes |  | 322
PWG-EL-0049 | PWG | 24097 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-035.2 |  | Yes |  | 323
PWG-EL-0050 | PWG | 24426 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-035.2 |  | Yes |  | 324
PWG-EL-0051 | PWG | 24713 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-036.2 |  | Yes |  | 325
PWG-EL-0052 | PWG | 24850 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-036.2 |  | Yes |  | 326
PWG-EL-0053 | PWG | 24909 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-036.2 |  | Yes |  | 327
PWG-EL-0054 | PWG | 25129 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-036.2 |  | Yes |  | 328
PWG-WA-0019 | PWG | 25166 | BYDA WATER DN100 | WATER |  | 100 | BYDA | D-DWG-PWG-036.2 |  | Yes |  | 329
PWG-EL-0055 | PWG | 25632 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-037.2 |  | Yes |  | 330
PWG-WA-0020 | PWG | 26007 | BYDA WATER DN150 | WATER |  | 150 | BYDA | D-DWG-PWG-038.2 |  | Yes |  | 331
PWG-CM-0049 | PWG | 26205 | BYDA TELSTRA COMMS DN100 | COMMUNICATIONS | Telstra | 100 | BYDA | D-DWG-PWG-038.2 |  | Yes |  | 332
PWG-EL-0056 | PWG | 26256 | PUP ELECTRICITY | ELECTRICITY |  |  | PUP | D-DWG-PWG-038.2 |  | Yes |  | 333
PWG-WA-0021 | PWG | 26480 | BYDA WATER DN100 | WATER |  | 100 | BYDA | D-DWG-PWG-038.2 |  | Yes |  | 334
PHW-EL-0003 | PHW | 2792 | BYDA ELECTRICITY | ELECTRICITY |  |  | BYDA |  |  | Yes |  | 335

## Src - Creek Crossings
Asset Id | Pipeline Section | KP (START) | KP (END) | Feature Name | Embankment Treatment | Creek Bed Treatment | Source Row
PHW-CC-0001 | PHW | 1734 | 1787 | GOWRIE CREEK | LOOSE ROCK | C | 3
PWG-CC-0001 | PWG | 903 | 912 |  | FABRIC/VEGETATION |  | 3
PHW-CC-0002 | PHW | 3457 | 3489 |  | FABRIC/VEGETATION |  | 4
PWG-CC-0002 | PWG | 3072 | 3152 | WESTBROOK CREEK | LOOSE ROCK | B | 4
PHW-CC-0003 | PHW | 4663 | 4696 |  | LOOSE ROCK | A | 5
PWG-CC-0003 | PWG | 3992 | 4014 |  | FABRIC/VEGETATION |  | 5
PHW-CC-0004 | PHW | 6773 | 6793 |  | LOOSE ROCK | A | 6
PWG-CC-0004 | PWG | 5448 | 5476 | DRY CHANNEL | GABION/MATRESS | NOTE 1 | 6
PHW-CC-0005 | PHW | 6887 | 6935 |  | LOOSE ROCK | A | 7
PWG-CC-0005 | PWG | 7097 | 7115 |  | FABRIC/VEGETATION |  | 7
PHW-CC-0006 | PHW | 8187 | 8212 |  | FABRIC/VEGETATION |  | 8
PWG-CC-0006 | PWG | 9456 | 9480 |  | FABRIC/VEGETATION |  | 8
PHW-CC-0007 | PHW | 9258 | 9438 |  | FABRIC/VEGETATION |  | 9
PWG-CC-0007 | PWG | 10243 | 10260 |  | FABRIC/VEGETATION |  | 9
PHW-CC-0008 | PHW | 9781 | 9809 |  | FABRIC/VEGETATION |  | 10
PWG-CC-0008 | PWG | 11558 | 11574 |  | FABRIC/VEGETATION |  | 10
PHW-CC-0009 | PHW | 10081 | 10102 |  | LOOSE ROCK | A | 11
PWG-CC-0009 | PWG | 14076 | 14139 | HODGSON CREEK | LOOSE ROCK | B | 11
PHW-CC-0010 | PHW | 11532 | 11589 | DRY CREEK | LOOSE ROCK | C | 12
PWG-CC-0010 | PWG | 14179 | 14224 | HODGSON CREEK ARM | LOOSE ROCK | A | 12
PHW-CC-0011 | PHW | 11735 | 11765 | DRY CREEK ARM | LOOSE ROCK |  | 13
PWG-CC-0011 | PWG | 14224 | 14423 |  | FABRIC/VEGETATION |  | 13
PHW-CC-0012 | PHW | 16180 | 16191 |  | FABRIC/VEGETATION |  | 14
PWG-CC-0012 | PWG | 15810 | 15826 |  | FABRIC/VEGETATION |  | 14
PHW-CC-0013 | PHW | 16978 | 17002 | SPRING CREEK | LOOSE ROCK | A | 15
PWG-CC-0013 | PWG | 19622 | 19645 |  | FABRIC/VEGETATION |  | 15
PHW-CC-0014 | PHW | 17900 | 18040 |  | FABRIC/VEGETATION |  | 16
PWG-CC-0014 | PWG | 22350 | 22377 |  | FABRIC/VEGETATION |  | 16
PHW-CC-0015 | PHW | 18469 | 18539 |  | FABRIC/VEGETATION |  | 17
PWG-CC-0015 | PWG | 24185 | 24208 |  | FABRIC/VEGETATION |  | 17
PWG-CC-0016 | PWG | 24468 | 24494 |  | FABRIC/VEGETATION |  | 18
PWG-CC-0017 | PWG | 24955 | 25018 | EMU CREEK | LOOSE ROCK | A | 19

## Src - Road & Rail Xings
Asset Id | Pipeline Section | KP (START) | KP (END) | Utility Type | Surface | Pipeline DN | Total Length Sections (m) | Feature Name | Operator | Proposed Crossing Method | Pipe Description | Type 6 (m) | Type 7 (m) | Type 4 & 7 (m) | Type 4 & 6 (m) | Source Row
PHW-PT-0001 | PHW | 327.039 | 404.867 | SIGNIFICANT PROTECTED TREES | N/A | 600 | 77.828 | Trees - Kieman Road | TRC | Thrust Boring | OD660x6WT MSCL Sintalock Type 2 PN35 Carrier & OD813x12WT MS Enveloper |  |  |  |  | 6
PHW-RD-0001 | PHW | 886 | 1135 | MINOR ROAD CROSSING | Unsealed | 600 | 249 | Access Track - Kieman Road | TRC | Open Trenching | DN600 PN35 DICL RRJ |  | 219.2 | 29.8 |  | 7
PHW-RD-0002 | PHW | 1232.924 | 1255.696 | MAJOR ROAD CROSSING | Sealed | 600 | 22.772 | Old Goombungee Road | TRC | Thrust Boring | OD660x6WT MSCL Sintalock Type 2 PN35 Carrier & OD813x12WT MS Enveloper |  |  |  |  | 8
PHW-RL-0001 | PHW | 2038.507 | 2110.24 | MAJOR RAIL CROSSING | Rail | 600 | 71.733 | West Moreton System | QLD Rail | Thrust Boring | OD660x6WT MSCL Sintalock Type 2 PN35 Carrier & OD813x15WT MS Enveloper |  |  |  |  | 9
PHW-RD-0003 | PHW | 4416.743 | 4455.043 | MINOR ROAD CROSSING | Sealed | 600 | 38.3 | Morris Road | TRC | Thrust Boring | OD660x6WT MSCL Sintalock Type 2 PN35 Carrier & OD813x12WT MS Enveloper |  |  |  |  | 10
PHW-RD-0004 | PHW | 6368.309 | 6385.309 | MINOR ROAD CROSSING | Sealed | 600 | 17 | Ganzer Road | TRC | Open Trenching | DN600 PN35 DICL RRJ | 17 |  |  |  | 11
PHW-RD-0005 | PHW | 6980.09 | 7035.325 | MAJOR ROAD CROSSING | Sealed | 600 | 55.235 | Gowrie Junction road | TRC | Thrust Boring | OD660x6WT MSCL Sintalock Type 2 PN35 Carrier & OD813x12WT MS Enveloper |  |  |  |  | 12
PHW-RD-0006 | PHW | 7811.422 | 7833.422 | MINOR ROAD CROSSING | Unsealed | 600 | 22 | Holmes Road | TRC | Open Trenching | DN600 PN35 DICL RRJ |  | 22 |  |  | 13
PHW-RD-0007 | PHW | 10342 | 10364 | MINOR ROAD CROSSING | Sealed | 600 | 22 | Khurt Court | TRC | Open Trenching | DN600 PN35 DICL RRJ | 22 |  |  |  | 14
PHW-RD-0008 | PHW | 10582.353 | 10645.383 | MAJOR ROAD CROSSING | Sealed | 600 | 63.03 | Toowoomba Connection Road / Warrego Highway | TMR | Thrust Boring | OD660x6WT MSCL Sintalock Type 2 PN35 Carrier & OD813x12WT MS Enveloper |  |  |  |  | 15
PHW-RD-0009 | PHW | 11174 | 11181 | MINOR ROAD CROSSING | Sealed | 600 | 7 | Wirth Road | TRC | Open Trenching | DN600 PN35 DICL RRJ | 7 |  |  |  | 16
PHW-RD-0010 | PHW | 11427.142 | 11509.11 | MAJOR ROAD CROSSING | Sealed | 600 | 81.968 | Second Range Crossing | TMR | Thrust Boring | OD660x6WT MSCL Sintalock Type 2 PN35 Carrier & OD813x12WT MS Enveloper |  |  |  |  | 17
PHW-RD-0011 | PHW | 12461 | 12469 | MINOR ROAD CROSSING | Unsealed | 600 | 8 | Carrington Road | TRC | Open Trenching | DN600 PN35 DICL RRJ |  | 8 |  |  | 18
PHW-RD-0012 | PHW | 13274.77 | 13346.373 | MAJOR ROAD CROSSING | Sealed | 600 | 71.603 | Toowoomba Cecil Plains Road | TMR | Thrust Boring | OD660x6WT MSCL Sintalock Type 2 PN35 Carrier & OD813x12WT MS Enveloper |  |  |  |  | 19
PHW-RD-0013 | PHW | 14806.133 | 14839.513 | MAJOR ROAD CROSSING | Sealed | 600 | 33.38 | Drayton Wellcamp Road | TRC | Thrust Boring | OD660x6WT MSCL Sintalock Type 2 PN35 Carrier & OD813x12WT MS Enveloper |  |  |  |  | 20
PHW-RD-0014 | PHW | 15762 | 15777 | MINOR ROAD CROSSING | Sealed | 600 | 15 | Max Smith Road | TRC | Open Trenching | DN600 PN35 DICL RRJ | 15 |  |  |  | 21
PWG-RD-0001 | PWG | 16 | 27 | MINOR ROAD CROSSING | Unsealed | 375 | 11 | E. Drews Road | TRC | Open Trenching | DN375 PN35 DICL RRJ |  | 11 |  |  | 6
PWG-RD-0002 | PWG | 1490 | 1501 | MINOR ROAD CROSSING | Unsealed | 375 | 11 | Keding Road | TRC | Open Trenching | DN375 PN35 DICL RRJ |  | 11 |  |  | 7
PWG-RD-0003 | PWG | 1857 | 1880 | MINOR ROAD CROSSING | Unsealed | 375 | 23 | Crockers Road | TRC | Open Trenching | DN375 PN35 DICL RRJ |  | 23 |  |  | 8
PWG-RD-0004 | PWG | 1888.54 | 1900 | MINOR ROAD CROSSING | Unsealed | 375 | 11.46 | Keding Road | TRC | Open Trenching | OD457x5WT Sintalock Type 1 MSCL |  |  | 11.46 |  | 9
PWG-RD-0005 | PWG | 2572 | 2596 | MINOR ROAD CROSSING | Sealed | 375 | 24 | Gore Street | TRC | Open Trenching | OD457x5WT Sintalock Type 1 MSCL | 3.9 |  |  | 20.1 | 10
PWG-CP-0001 | PWG | 2626 | 2694 | CARPARK/SIDE LANE | Unsealed | 375 | 68 | Progress Avenue | TRC | Open Trenching | DN375 PN35 DICL RRJ |  | 68 |  |  | 11
PWG-RD-0006 | PWG | 2694 | 2739 | MINOR ROAD CROSSING | Sealed | 375 | 45 | Progress Avenue | TRC | Open Trenching | DN375 PN35 DICL RRJ | 45 |  |  |  | 12
PWG-RD-0007 | PWG | 2763 | 2777 | MINOR ROAD CROSSING | Sealed | 375 | 14 | Main Street | TRC | Open Trenching | OD457x5WT Sintalock Type 1 MSCL |  |  |  | 14 | 13
PWG-RD-0008 | PWG | 2865.366 | 2908.821 | MAJOR ROAD CROSSING | Sealed | 375 | 43.455 | Toowoomba-Athol Road | TMR | Thrust Boring | OD457x5WT Sintalock Type 1 MSCL Carrier & OD610x9WT MS Enveloper |  |  |  |  | 14
PWG-RL-0001 | PWG | 7547.413 | 7579.15 | MAJOR RAIL CROSSING | Rail | 375 | 31.737 | South Western System | QLD Rail | Thrust Boring | OD457x5WT Sintalock Type 1 MSCL Carrier & OD610x12WT MS Enveloper |  |  |  |  | 15
PWG-RD-0009 | PWG | 7725 | 7743 | MINOR ROAD CROSSING | Unsealed | 375 | 18 | Hartvigsen Street | TRC | Open Trenching | DN375 PN35 DICL RRJ |  | 18 |  |  | 16
PWG-RD-0010 | PWG | 8293.647 | 8315.201 | MAJOR ROAD CROSSING | Sealed | 375 | 21.554 | Umbiram Road | TRC | Thrust Boring | OD457x5WT Sintalock Type 1 MSCL Carrier & OD610x9WT MS Enveloper |  |  |  |  | 17
PWG-PT-0001 | PWG | 8335.614 | 8400.622 | SIGNIFICANT PROTECTED TREES | N/A | 375 | 65.008 | Wyreema Memorial Park | TRC | Thrust Boring | OD457x5WT Sintalock Type 1 MSCL Carrier & OD610x9WT MS Enveloper |  |  |  |  | 18
PWG-RL-0002 | PWG | 8487.151 | 8542.069 | MAJOR RAIL CROSSING | Rail | 375 | 54.918 | South Western System | QLD Rail | Thrust Boring | OD457x5WT Sintalock Type 1 MSCL Carrier & OD610x12WT MS Enveloper |  |  |  |  | 19
PWG-CP-0002 | PWG | 8578 | 8622 | CARPARK/SIDE LANE | Unsealed | 375 | 44 | Wyreema Cambooya Road Side Bay | TRC | Open Trenching | DN375 PN35 DICL RRJ |  | 39.01 | 4.99 |  | 20
PWG-CP-0003 | PWG | 8780 | 8840 | CARPARK/SIDE LANE | Unsealed | 375 | 60 | Wyreema Cambooya Road Side Bay | TRC | Open Trenching | DN375 PN35 DICL RRJ |  | 60 |  |  | 21
PWG-CP-0004 | PWG | 9115 | 9157 | CARPARK/SIDE LANE | Unsealed | 375 | 42 | Wyreema Cambooya Road Side Bay | TRC | Open Trenching | DN375 PN35 DICL RRJ |  | 42 |  |  | 22
PWG-RD-0011 | PWG | 12310 | 12320 | MINOR ROAD CROSSING | Sealed | 375 | 10 | Bourne Road | TRC | Open Trenching | DN375 PN35 DICL RRJ | 10 |  |  |  | 23
PWG-RD-0012 | PWG | 12702.22 | 12734.864 | MINOR ROAD CROSSING | Sealed | 375 | 32.644 | Wyreema Cambooya Road | TRC | Thrust Boring | OD457x5WT Sintalock Type 1 MSCL Carrier & OD610x9WT MS Enveloper |  |  |  |  | 24
PWG-RD-0013 | PWG | 13218.214 | 13247.005 | MINOR ROAD CROSSING | Sealed | 375 | 28.791 | Cambooya Felton Road | TRC | Thrust Boring | OD457x5WT Sintalock Type 1 MSCL Carrier & OD610x9WT MS Enveloper |  |  |  |  | 25
PWG-RD-0014 | PWG | 14525.498 | 14572.298 | MAJOR ROAD CROSSING | Sealed | 375 | 46.8 | William Street / Toowoomba Karara Road | TMR | Thrust Boring | OD457x5WT Sintalock Type 1 MSCL Carrier & OD610x9WT MS Enveloper |  |  |  |  | 26
PWG-RD-0015 | PWG | 16411 | 16425 | MINOR ROAD CROSSING | Unsealed | 375 | 14 | Todd Road | TRC | Open Trenching | DN375 PN35 DICL RRJ |  | 14 |  |  | 27
PWG-RD-0016 | PWG | 18151.238 | 18166.781 | MAJOR ROAD CROSSING | Sealed | 375 | 15.543 | Cudmore Road | TRC | Thrust Boring | OD457x5WT Sintalock Type 1 MSCL Carrier & OD610x9WT MS Enveloper |  |  |  |  | 28
PWG-RD-0017 | PWG | 18218 | 18225 | MINOR ROAD CROSSING | Sealed | 375 | 7 | Cudmore Rd / Wattsiding Road Slip Lane | TRC | Open Trenching | DN375 PN35 DICL RRJ | 7 |  |  |  | 29
PWG-RD-0018 | PWG | 26013 | 26026 | MINOR ROAD CROSSING | Sealed | 375 | 13 | King Street | TRC | Open Trenching | DN375 PN35 DICL RRJ | 13 |  |  |  | 30
PWG-RD-0019 | PWG | 26252.108 | 26283.028 | MAJOR ROAD CROSSING | Sealed | 375 | 30.92 | Woodlands Rd | TRC | Thrust Boring | OD457x5WT Sintalock Type 1 MSCL Carrier & OD610x9WT MS Enveloper |  |  |  |  | 31

## Src - Tree Removal
Pipe ID | Pipeline | Start Chainage | End Chainage | SC(m) | EC (m) | Area m2 | Timber Density HEAVY/LIGHT/TRIM | Other Information | Loaded to Master Register?
VEG_PAE001 | PAE | 0.06 | 0.07 |  |  | 90.3 | LIGHT | MULTIPLE SMALL TREES | NOT LOADED - section not in register
VEG_PAE002 | PAE | 0.15 | 0.21 |  |  | 503 | TRIM | BRANCHES HANGING OVER PIPE | NOT LOADED - section not in register
VEG_PAE003 | PAE | 0.51 | 0.52 |  |  | 90.4 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PHW001 | PHW | 0.01 | 0.02 | 10 | 20 | 195 | HEAVY | 1 LARGE TREE, MULTIPLE SMALL TREES | LOADED
VEG_PHW002 | PHW | 0.06 | 0.2 | 60 | 200 | 658 | LIGHT | MULTIPLE SMALL TREES | LOADED
VEG_PHW003 | PHW | 0.25 | 0.27 | 250 | 270 | 110 | HEAVY | 1 LARGE TREE | LOADED
VEG_PHW004 | PHW | 0.33 | 0.37 | 330 | 370 | 486 | HEAVY | 2 LARGE TREES | LOADED
VEG_PHW005 | PHW | 0.38 | 0.41 | 380 | 410 | 145 | HEAVY | 2 LARGE TREES | LOADED
VEG_PHW006 | PHW | 0.45 | 0.46 | 450 | 460 | 18.7 | TRIM | BRANCHES HANGING OVER PIPE | LOADED
VEG_PHW007 | PHW | 0.51 | 0.53 | 510 | 530 | 85.9 | TRIM | 3 SMALL TREES | LOADED
VEG_PHW008 | PHW | 0.54 | 0.56 | 540 | 560 | 147 | HEAVY | 2 LARGE TREES | LOADED
VEG_PHW009 | PHW | 0.62 | 0.64 | 620 | 640 | 108 | HEAVY | 1 LARGE TREE, 1 SMALL TREE | LOADED
VEG_PHW010 | PHW | 0.67 | 0.69 | 670 | 690 | 110 | HEAVY | 2 LARGE TREES | LOADED
VEG_PHW011 | PHW | 0.73 | 0.74 | 730 | 740 | 62.9 | HEAVY | 1 LARGE TREE | LOADED
VEG_PHW012 | PHW | 0.77 | 0.8 | 770 | 800 | 262 | HEAVY | 3 LARGE TREES | LOADED
VEG_PHW013 | PHW | 0.89 | 0.9 | 890 | 900 | 24.2 | LIGHT | 1 SMALL TREE | LOADED
VEG_PHW014 | PHW | 0.92 | 0.93 | 920 | 930 | 66.5 | HEAVY | 2 LARGE TREES | LOADED
VEG_PHW015 | PHW | 0.95 | 0.95 | 950 | 950 | 9.64 | LIGHT | 1 SMALL TREE | LOADED
VEG_PHW016 | PHW | 0.96 | 0.98 | 960 | 980 | 123 | HEAVY | 2 LARGE TREES, TRIMMING NEEDED | LOADED
VEG_PHW017 | PHW | 1 | 1.01 | 1000 | 1010 | 55.6 | TRIM | BRANCHES HANGING OVER PIPE | LOADED
VEG_PHW018 | PHW | 1.01 | 1.02 | 1010 | 1020 | 57.9 | HEAVY | 2 LARGE TREES | LOADED
VEG_PHW019 | PHW | 1.04 | 1.05 | 1040 | 1050 | 23 | LIGHT | 2 SMALL TREES | LOADED
VEG_PHW020 | PHW | 1.07 | 1.08 | 1070 | 1080 | 85.4 | HEAVY | 2 LARGE TREES | LOADED
VEG_PHW021 | PHW | 1.1 | 1.13 | 1100 | 1130 | 117 | HEAVY | 3 LARGE TREES | LOADED
VEG_PHW022 | PHW | 1.14 | 1.15 | 1140 | 1150 | 82 | HEAVY | 1 LARGE TREE | LOADED
VEG_PHW023 | PHW | 1.17 | 1.19 | 1170 | 1190 | 46.3 | TRIM | BRANCHES HANGING OVER PIPE | LOADED
VEG_PHW024 | PHW | 1.21 | 1.22 | 1210 | 1220 | 12.4 | TRIM | BRANCHES HANGING OVER PIPE | LOADED
VEG_PHW025 | PHW | 1.25 | 1.25 | 1250 | 1250 | 54 | LIGHT | 1 SMALL TREE | LOADED
VEG_PHW026 | PHW | 1.32 | 1.33 | 1320 | 1330 | 66 | LIGHT | 1 SMALL TREE | LOADED
VEG_PHW027 | PHW | 1.74 | 1.78 | 1740 | 1780 | 402 | HEAVY | 2 LARGE TREES, 2 SMALL TREES | LOADED
VEG_PHW028 | PHW | 1.81 | 1.83 | 1810 | 1830 | 271 | HEAVY | 1 LARGE TREE | LOADED
VEG_PHW029 | PHW | 1.98 | 2.01 | 1980 | 2010 | 380 | HEAVY | 1 LARGE TREE, 2 SMALL TREES | LOADED
VEG_PHW030 | PHW | 2.03 | 2.04 | 2030 | 2040 | 99 | LIGHT | 2 SMALL TREES | LOADED
VEG_PHW031 | PHW | 2.32 | 2.33 | 2320 | 2330 | 44.8 | LIGHT | 1 SMALL TREE | LOADED
VEG_PHW032 | PHW | 2.36 | 2.38 | 2360 | 2380 | 141 | TRIM | 1 LARGE TREE, 1 SMALL TREE | LOADED
VEG_PHW033 | PHW | 2.36 | 2.37 | 2360 | 2370 | 94 | TRIM | 1 LARGE TREE | LOADED
VEG_PHW034 | PHW | 2.4 | 2.42 | 2400 | 2420 | 138 | HEAVY | 1 LARGE TREE | LOADED
VEG_PHW035 | PHW | 2.46 | 2.48 | 2460 | 2480 | 132 | HEAVY | 1 LARGE TREE | LOADED
VEG_PHW036 | PHW | 2.48 | 2.49 | 2480 | 2490 | 37.7 | LIGHT | 2 SMALL TREES | LOADED
VEG_PHW037 | PHW | 2.5 | 2.51 | 2500 | 2510 | 17 | LIGHT | 1 SMALL TREE | LOADED
VEG_PHW038 | PHW | 2.56 | 2.58 | 2560 | 2580 | 117 | HEAVY | 2 LARGE TREES | LOADED
VEG_PHW039 | PHW | 2.62 | 2.62 | 2620 | 2620 | 29 | HEAVY | 1 LARGE TREE | LOADED
VEG_PHW040 | PHW | 2.71 | 2.72 | 2710 | 2720 | 43.3 | LIGHT | 3 SMALL TREES | LOADED
VEG_PHW041 | PHW | 2.75 | 2.75 | 2750 | 2750 | 32.5 | TRIM | BRANCHES HANGING OVER PIPE | LOADED
VEG_PHW042 | PHW | 2.77 | 2.79 | 2770 | 2790 | 86.4 | HEAVY | 1 LARGE TREE, 1 SMALL TREE | LOADED
VEG_PHW043 | PHW | 2.81 | 2.81 | 2810 | 2810 | 41.4 | LIGHT | 1 SMALL TREE | LOADED
VEG_PHW044 | PHW | 3.93 | 3.94 | 3930 | 3940 | 283 | HEAVY | 1 LARGE TREE | LOADED
VEG_PHW045 | PHW | 3.95 | 3.96 | 3950 | 3960 | 99 | LIGHT | 1 SMALL TREE | LOADED
VEG_PHW046 | PHW | 4.9 | 4.91 | 4900 | 4910 | 309 | HEAVY | 1 LARGE TREE | LOADED
VEG_PHW047 | PHW | 5.39 | 5.41 | 5390 | 5410 | 142 | HEAVY | 1 LARGE TREE | LOADED
VEG_PHW048 | PHW | 5.84 | 5.85 | 5840 | 5850 | 85.2 | LIGHT | 1 SMALL TREE | LOADED
VEG_PHW049 | PHW | 5.97 | 5.99 | 5970 | 5990 | 212 | HEAVY | 2 LARGE TREES | LOADED
VEG_PHW050 | PHW | 6.62 | 6.63 | 6620 | 6630 | 27 | LIGHT | 1 SMALL TREE | LOADED
VEG_PHW051 | PHW | 8.31 | 8.32 | 8310 | 8320 | 188 | HEAVY | 1 LARGE TREE | LOADED
VEG_PHW052 | PHW | 8.35 | 8.36 | 8350 | 8360 | 54.8 | HEAVY | 1 LARGE TREE | LOADED
VEG_PHW053 | PHW | 8.46 | 8.47 | 8460 | 8470 | 56 | TRIM | 1 LARGE TREE | LOADED
VEG_PHW054 | PHW | 8.95 | 8.96 | 8950 | 8960 | 88.8 | HEAVY | 1 LARGE TREE | LOADED
VEG_PHW055 | PHW | 8.97 | 8.98 | 8970 | 8980 | 5 | LIGHT | 1 SMALL TREE | LOADED
VEG_PHW056 | PHW | 9.14 | 9.15 | 9140 | 9150 | 164 | HEAVY | 1 LARGE TREE | LOADED
VEG_PHW057 | PHW | 9.22 | 9.23 | 9220 | 9230 | 40 | LIGHT | 3 SMALL TREES | LOADED
VEG_PHW058 | PHW | 9.46 | 9.47 | 9460 | 9470 | 48 | HEAVY | 1 LARGE TREE | LOADED
VEG_PHW059 | PHW | 9.59 | 9.6 | 9590 | 9600 | 29 | LIGHT | 1 SMALL TREE | LOADED
VEG_PHW060 | PHW | 10.32 | 10.33 | 10320 | 10330 | 65.7 | HEAVY | 1 LARGE TREE | LOADED
VEG_PHW061 | PHW | 11.18 | 11.19 | 11180 | 11190 | 23.8 | LIGHT | 1 SMALL TREE | LOADED
VEG_PHW062 | PHW | 13.59 | 13.61 | 13590 | 13610 | 90 | LIGHT | 4 SMALL TREE | LOADED
VEG_PHW063 | PHW | 13.96 | 13.98 | 13960 | 13980 | 73 | TRIM | 3 LARGE TREES | LOADED
VEG_PHW064 | PHW | 14.25 | 14.26 | 14250 | 14260 | 21.5 | LIGHT | 1 SMALL TREE | LOADED
VEG_PHW065 | PHW | 14.35 | 14.36 | 14350 | 14360 | 29 | TRIM | 1 LARGE TREE | LOADED
VEG_PHW066 | PHW | 15.76 | 15.77 | 15760 | 15770 | 43 | TRIM | 1 LARGE TREE | LOADED
VEG_PHW067 | PHW | 18.99 | 19 | 18990 | 19000 | 63.7 | LIGHT | 1 SMALL TREE | LOADED
VEG_PHW068 | PHW | 19.01 | 19.06 | 19010 | 19060 | 593 | HEAVY | 6 LARGE TREES | LOADED
VEG_PHW069 | PHW | 19.11 | 19.12 | 19110 | 19120 | 105 | HEAVY | 2 LARGE TREES | LOADED
VEG_PHW070 | PHW | 19.132 | 19.132 | 19132 | 19132 | 73 | HEAVY | 1 LARGE TREES | LOADED
VEG_PWG001 | PWG | 0.4 | 0.43 |  |  | 234 | HEAVY | 4 SMALL TREES | LOADED
VEG_PWG002 | PWG | 0.44 | 0.45 |  |  | 113 | LIGHT | 2 SMALL TREES | LOADED
VEG_PWG003 | PWG | 0.49 | 0.53 |  |  | 273 | HEAVY | MULTIPLE SMALL TREES | LOADED
VEG_PWG004 | PWG | 0.59 | 0.74 |  |  | 1550 | HEAVY | MULTIPLE LARGE & SMALL TREES | LOADED
VEG_PWG005 | PWG | 0.76 | 0.88 |  |  | 1520 | HEAVY | MULTIPLE LARGE & SMALL TREES | LOADED
VEG_PWG006 | PWG | 0.99 | 1 |  |  | 56.6 | LIGHT | 1 SMALL TREE | LOADED
VEG_PWG007 | PWG | 1.04 | 1.05 |  |  | 27 | LIGHT | 1 SMALL TREE | LOADED
VEG_PWG008 | PWG | 1.43 | 1.46 |  |  | 215 | HEAVY | MULTIPLE SMALL TREES & 1 LARGE TREE | LOADED
VEG_PWG009 | PWG | 2.21 | 2.22 |  |  | 80 | HEAVY | MULTIPLE SMALL TREES | LOADED
VEG_PWG010 | PWG | 2.37 | 2.38 |  |  | 50 | LIGHT | 2 SMALL TREES | LOADED
VEG_PWG011 | PWG | 3.25 | 3.26 |  |  | 31.4 | LIGHT | 1 SMALL TREE | LOADED
VEG_PWG012 | PWG | 3.54 | 3.56 |  |  | 145 | HEAVY | 1 LARGE TREE | LOADED
VEG_PWG013 | PWG | 3.59 | 3.6 |  |  | 13.6 | LIGHT | 1 SMALL TREE | LOADED
VEG_PWG014 | PWG | 4.08 | 4.09 |  |  | 46.6 | LIGHT | 1 SMALL TREE | LOADED
VEG_PWG015 | PWG | 10.68 | 10.69 |  |  | 116 | HEAVY | MULTIPLE SMALL TREES | LOADED
VEG_PWG016 | PWG | 21.58 | 21.59 |  |  | 74.8 | HEAVY | 1 LARGE TREE | LOADED
VEG_PWG017 | PWG | 24.01 | 24.02 |  |  | 32.5 | LIGHT | 1 SMALL TREE | LOADED
VEG_PWG018 | PWG | 24.83 | 24.86 |  |  | 176 | HEAVY | MULTIPLE SMALL TREES | LOADED
VEG_PWG019 | PWG | 26.07 | 26.08 |  |  | 64.7 | HEAVY | 2 LARGE TREES | LOADED
VEG_PWG020 | PWG | 26.29 | 26.3 |  |  | 23 | LIGHT | 2 SMALL TREES | LOADED
VEG_PWG021 | PWG | 26.43 | 26.44 |  |  | 79 | HEAVY | 1 LARGE TREE | LOADED
VEG_PLG001 | PLG | 0.22 | 0.23 |  |  | 21.8 | LIGHT | 1 SMALL TREE | NOT LOADED - section not in register
VEG_PLG002 | PLG | 0.69 | 0.71 |  |  | 135 | HEAVY | 2 LARGE TREES | NOT LOADED - section not in register
VEG_PLG003 | PLG | 1.5 | 1.52 |  |  | 114 | HEAVY | MULTIPLE LARGE & SMALL TREES | NOT LOADED - section not in register
VEG_PLG004 | PLG | 4.71 | 4.74 |  |  | 187 | HEAVY | MULTIPLE SMALL TREES | NOT LOADED - section not in register
VEG_PLG005 | PLG | 5.97 | 5.99 |  |  | 80.1 | HEAVY | 1 LARGE TREE & 2 SMALL TREES | NOT LOADED - section not in register
VEG_PLG006 | PLG | 7.65 | 7.66 |  |  | 215 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PLG007 | PLG | 7.69 | 7.71 |  |  | 161 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PLG008 | PLG | 7.73 | 7.76 |  |  | 266 | HEAVY | MULTIPLE LARGE TREES | NOT LOADED - section not in register
VEG_PLG009 | PLG | 7.77 | 7.78 |  |  | 199 | HEAVY | MULTIPLE LARGE TREES | NOT LOADED - section not in register
VEG_PLG010 | PLG | 7.8 | 7.83 |  |  | 380 | HEAVY | MULTIPLE LARGE TREES | NOT LOADED - section not in register
VEG_PLG011 | PLG | 8.6 | 8.61 |  |  | 22.4 | LIGHT | 1 SMALL TREE | NOT LOADED - section not in register
VEG_PLG012 | PLG | 15.78 | 15.78 |  |  | 32.5 | LIGHT | 1 SMALL TREE | NOT LOADED - section not in register
VEG_PLG013 | PLG | 15.82 | 15.82 |  |  | 32.9 | LIGHT | 1 SMALL TREE | NOT LOADED - section not in register
VEG_PLG014 | PLG | 15.91 | 15.91 |  |  | 39.4 | LIGHT | 1 SMALL TREE | NOT LOADED - section not in register
VEG_PLG015 | PLG | 15.96 | 15.96 |  |  | 28.7 | LIGHT | 1 SMALL TREE | NOT LOADED - section not in register
VEG_PLG016 | PLG | 15.99 | 16 |  |  | 20.4 | LIGHT | 1 SMALL TREE | NOT LOADED - section not in register
VEG_PLG017 | PLG | 16.03 | 16.04 |  |  | 38.9 | LIGHT | 1 SMALL TREE | NOT LOADED - section not in register
VEG_PLG018 | PLG | 16.09 | 16.09 |  |  | 42.9 | LIGHT | 1 SMALL TREE | NOT LOADED - section not in register
VEG_PLG019 | PLG | 16.23 | 16.24 |  |  | 129 | HEAVY | 2 LARGE TREES | NOT LOADED - section not in register
VEG_PLG020 | PLG | 16.31 | 16.37 |  |  | 340 | HEAVY | MULTIPLE LARGE TREES | NOT LOADED - section not in register
VEG_PLG021 | PLG | 16.98 | 17 |  |  | 196 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PLG022 | PLG | 17.45 | 17.49 |  |  | 281 | HEAVY | MULTIPLE LARGE & SMALL TREES | NOT LOADED - section not in register
VEG_PLG023 | PLG | 18.05 | 18.06 |  |  | 58 | TRIM | BRANCHES HANGING OVER PIPE | NOT LOADED - section not in register
VEG_PLG024 | PLG | 23.6 | 23.657 |  |  | 563 | HEAVY | MULTIPLE SMALL TREES | NOT LOADED - section not in register
VEG_PLE001 | PLE | 0.63 | 0.64 |  |  | 83 | TRIM | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PLE002 | PLE | 1.79 | 1.81 |  |  | 188 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PLE003 | PLE | 1.84 | 1.85 |  |  | 237 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PLE004 | PLE | 2.04 | 2.06 |  |  | 357 | HEAVY | 4 LARGE TREES | NOT LOADED - section not in register
VEG_PLE005 | PLE | 2.15 | 2.16 |  |  | 268 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PLE006 | PLE | 2.43 | 2.44 |  |  | 76.5 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PLE007 | PLE | 2.46 | 2.46 |  |  | 22 | LIGHT | 1 SMALL TREE | NOT LOADED - section not in register
VEG_PLE008 | PLE | 4.97 | 4.98 |  |  | 241 | HEAVY | 2 LARGE TREES | NOT LOADED - section not in register
VEG_PLE009 | PLE | 4.98 | 5.01 |  |  | 306 | HEAVY | 3 LARGE TREES | NOT LOADED - section not in register
VEG_PLE010 | PLE | 5.03 | 5.04 |  |  | 140 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PLE011 | PLE | 5.08 | 5.09 |  |  | 182 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PLE012 | PLE | 5.13 | 5.13 |  |  | 60 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PLE013 | PLE | 5.14 | 5.18 |  |  | 322 | HEAVY | MULTIPLE LARGE TREES | NOT LOADED - section not in register
VEG_PLE014 | PLE | 5.21 | 5.23 |  |  | 150 | HEAVY | 2 LARGE TREES | NOT LOADED - section not in register
VEG_PLE015 | PLE | 5.25 | 5.26 |  |  | 131 | HEAVY | 2 LARGE TREES | NOT LOADED - section not in register
VEG_PLE016 | PLE | 5.38 | 5.39 |  |  | 149 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PLE017 | PLE | 5.4 | 5.56 |  |  | 1793 | HEAVY | MULTIPLE LARGE TREES | NOT LOADED - section not in register
VEG_PLE018 | PLE | 5.57 | 5.73 |  |  | 1341 | HEAVY | MULTIPLE LARGE TREES | NOT LOADED - section not in register
VEG_PLE019 | PLE | 5.82 | 5.84 |  |  | 188 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PLE020 | PLE | 6.08 | 6.09 |  |  | 101 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PLE021 | PLE | 6.56 | 6.57 |  |  | 212 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PLE022 | PLE | 6.72 | 6.73 |  |  | 146 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PLE023 | PLE | 6.75 | 6.77 |  |  | 223 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PLE024 | PLE | 6.78 | 6.81 |  |  | 279 | HEAVY | 4 LARGE TREES | NOT LOADED - section not in register
VEG_PLE025 | PLE | 6.85 | 6.88 |  |  | 375 | HEAVY | MULTIPLE LARGE TREES | NOT LOADED - section not in register
VEG_PLE026 | PLE | 6.91 | 6.93 |  |  | 299 | HEAVY | MULTIPLE LARGE TREES | NOT LOADED - section not in register
VEG_PLE027 | PLE | 7.89 | 7.31 |  |  | 119 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PLE028 | PLE | 8.12 | 8.13 |  |  | 19.3 | LIGHT | 1 SMALL TREE | NOT LOADED - section not in register
VEG_PLE029 | PLE | 8.2 | 8.22 |  |  | 125 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PLE030 | PLE | 8.45 | 8.47 |  |  | 159 | HEAVY | 3 LARGE TREES | NOT LOADED - section not in register
VEG_PLE031 | PLE | 8.82 | 8.83 |  |  | 136 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PLE032 | PLE | 8.87 | 8.88 |  |  | 90.4 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL001 | PEL | 0.15 | 0.18 |  |  | 97.1 | TRIM | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL002 | PEL | 0.36 | 0.42 |  |  | 1081 | HEAVY | 3 LARGE TREES | NOT LOADED - section not in register
VEG_PEL003 | PEL | 4.58 | 4.59 |  |  | 208 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL004 | PEL | 4.87 | 4.91 |  |  | 288 | HEAVY | 2 LARGE TREES | NOT LOADED - section not in register
VEG_PEL005 | PEL | 5.71 | 5.74 |  |  | 195 | TRIM | 3 LARGE TREES | NOT LOADED - section not in register
VEG_PEL006 | PEL | 8.38 | 8.4 |  |  | 228 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL007 | PEL | 8.49 | 8.52 |  |  | 171 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL008 | PEL | 8.53 | 8.55 |  |  | 167 | TRIM | 3 LARGE TREES | NOT LOADED - section not in register
VEG_PEL009 | PEL | 8.58 | 8.59 |  |  | 142 | HEAVY | 1 LARGE TREE, 1 SMALL TREE | NOT LOADED - section not in register
VEG_PEL010 | PEL | 8.67 | 8.73 |  |  | 308 | TRIM | 2 LARGE TREES | NOT LOADED - section not in register
VEG_PEL011 | PEL | 8.75 | 8.77 |  |  | 75.9 | TRIM | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL012 | PEL | 9.91 | 9.95 |  |  | 466 | TRIM | 3 LARGE TREES | NOT LOADED - section not in register
VEG_PEL013 | PEL | 9.96 | 10 |  |  | 259 | TRIM | 2 LARGE TREES | NOT LOADED - section not in register
VEG_PEL014 | PEL | 10.1 | 10.4 |  |  | 234 | TRIM | 2 LARGE TREES | NOT LOADED - section not in register
VEG_PEL015 | PEL | 13.15 | 13.16 |  |  | 253 | HEAVY | 2 LARGE TREES | NOT LOADED - section not in register
VEG_PEL016 | PEL | 13.2 | 13.21 |  |  | 36.6 | TRIM | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL017 | PEL | 13.61 | 13.62 |  |  | 116 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL018 | PEL | 13.98 | 14 |  |  | 118 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL019 | PEL | 14.07 | 14.08 |  |  | 135 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL020 | PEL | 14.16 | 14.18 |  |  | 130 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL021 | PEL | 14.19 | 14.23 |  |  | 186 | HEAVY | 3 LARGE TREES | NOT LOADED - section not in register
VEG_PEL022 | PEL | 14.26 | 14.27 |  |  | 81 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL023 | PEL | 17.09 | 17.11 |  |  | 124 | TRIM | 2 LARGE TREES | NOT LOADED - section not in register
VEG_PEL024 | PEL | 17.13 | 17.15 |  |  | 152 | HEAVY | 2 LARGE TREES | NOT LOADED - section not in register
VEG_PEL025 | PEL | 17.17 | 17.19 |  |  | 153 | HEAVY | 2 LARGE TREES | NOT LOADED - section not in register
VEG_PEL026 | PEL | 18.14 | 18.16 |  |  | 91 | TRIM | 2 LARGE TREES | NOT LOADED - section not in register
VEG_PEL027 | PEL | 18.5 | 18.2 |  |  | 101 | HEAVY | 2 LARGE TREES | NOT LOADED - section not in register
VEG_PEL028 | PEL | 18.59 | 18.64 |  |  | 177 | TRIM | 3 LARGE TREES | NOT LOADED - section not in register
VEG_PEL029 | PEL | 19.97 | 19.98 |  |  | 91.5 | HEAVY | 2 LARGE TREES | NOT LOADED - section not in register
VEG_PEL030 | PEL | 21.22 | 21.27 |  |  | 461 | TRIM | 5 LARGE TREES | NOT LOADED - section not in register
VEG_PEL031 | PEL | 21.28 | 21.51 |  |  | 2380 | HEAVY | MULTIPLE LARGE TREES | NOT LOADED - section not in register
VEG_PEL032 | PEL | 21.65 | 21.68 |  |  | 430 | HEAVY | MULTIPLE LARGE TREES | NOT LOADED - section not in register
VEG_PEL033 | PEL | 21.86 | 21.89 |  |  | 229 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL034 | PEL | 21.92 | 21.93 |  |  | 132 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL035 | PEL | 22.25 | 22.28 |  |  | 188 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL036 | PEL | 22.29 | 22.31 |  |  | 85.7 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL037 | PEL | 22.34 | 22.36 |  |  | 375 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL038 | PEL | 22.37 | 22.39 |  |  | 119 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL039 | PEL | 22.58 | 22.59 |  |  | 149 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL040 | PEL | 22.86 | 22.88 |  |  | 329 | HEAVY | 2 LARGE TREES | NOT LOADED - section not in register
VEG_PEL041 | PEL | 22.9 | 22.91 |  |  | 180 | HEAVY | 1 SMALL TREE | NOT LOADED - section not in register
VEG_PEL042 | PEL | 22.97 | 23 |  |  | 501 | HEAVY | 1 LARGE TREE & 1 SMALL TREE | NOT LOADED - section not in register
VEG_PEL043 | PEL | 23.18 | 23.2 |  |  | 117 | LIGHT | 1 SMALL TREE | NOT LOADED - section not in register
VEG_PEL044 | PEL | 23.23 | 23.24 |  |  | 63.8 | LIGHT | 1 SMALL TREE | NOT LOADED - section not in register
VEG_PEL045 | PEL | 23.26 | 23.29 |  |  | 614 | HEAVY | 2 LARGE TREES | NOT LOADED - section not in register
VEG_PEL046 | PEL | 23.32 | 23.33 |  |  | 120 | TRIM | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL047 | PEL | 23.54 | 23.55 |  |  | 336 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL048 | PEL | 23.6 | 23.62 |  |  | 603 | HEAVY | 2 LARGE TREE & 1 SMALL TREE | NOT LOADED - section not in register
VEG_PEL049 | PEL | 23.65 | 23.67 |  |  | 473 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL050 | PEL | 23.73 | 23.82 |  |  | 2062 | HEAVY | MULTIPLE LARGE TREES | NOT LOADED - section not in register
VEG_PEL051 | PEL | 23.87 | 23.87 |  |  | 33.6 | LIGHT | 1 SMALL TREE | NOT LOADED - section not in register
VEG_PEL052 | PEL | 23.9 | 23.91 |  |  | 173 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL053 | PEL | 23.96 | 23.98 |  |  | 304 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL054 | PEL | 24.01 | 24.02 |  |  | 162 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL055 | PEL | 24.08 | 24.09 |  |  | 102 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL056 | PEL | 24.14 | 24.15 |  |  | 294 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL057 | PEL | 24.31 | 24.32 |  |  | 84 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL058 | PEL | 24.33 | 24.34 |  |  | 393 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL059 | PEL | 24.4 | 24.41 |  |  | 85 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL060 | PEL | 24.48 | 24.49 |  |  | 108 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PEL061 | PEL | 24.61 | 24.62 |  |  | 27 | LIGHT | 1 SMALL TREE | NOT LOADED - section not in register
VEG_PEL062 | PEL | 24.64 | 24.64 |  |  | 18.2 | LIGHT | 1 SMALL TREE | NOT LOADED - section not in register
VEG_PEL063 | PEL | 24.73 | 24.758 |  |  | 527 | HEAVY | 2 LARGE TREES | NOT LOADED - section not in register
VEG_PAE001 | PAE | 7.25 | 7.26 |  |  | 42.5 | TRIM | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PAE002 | PAE | 7.17 | 7.2 |  |  | 286 | HEAVY | 3 LARGE TREES | NOT LOADED - section not in register
VEG_PAE003 | PAE | 7.13 | 7.14 |  |  | 90.8 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PAE004 | PAE | 7.09 | 7.1 |  |  | 85.3 | HEAVY | 2 LARGE TREES | NOT LOADED - section not in register
VEG_PAE005 | PAE | 6.94 | 6.95 |  |  | 98.8 | HEAVY | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PAE006 | PAE | 6.75 | 6.75 |  |  | 13.2 | LIGHT | 1 SMALL TREE | NOT LOADED - section not in register
VEG_PAE007 | PAE | 1.35 | 1.36 |  |  | 34.7 | TRIM | 2 LARGE TREES | NOT LOADED - section not in register
VEG_PAE008 | PAE | 1.2 | 1.21 |  |  | 17.8 | TRIM | 1 LARGE TREE | NOT LOADED - section not in register
VEG_PAE009 | PAE | 0.6 | 0.61 |  |  | 39.3 | TRIM | 1 LARGE TREE | NOT LOADED - section not in register
Verbatim rows from T2W - Tree Removal TakeOff (V.1).xlsx, sheet 'Sheet1' rows 15-236. Chainage is in KILOMETRES here, as in the source; the Master Register holds the same values converted to metres.

## Edit Log
Edit log
Every change made to the Master Register is appended here — one row per field changed, with who made it, when, and the value it replaced. Rows are written when an edit is applied, not by hand. The Src - sheets are never edited, so they remain the record of what each source file originally said.
Timestamp | Edited by | Record Key | Asset ID | Field | Previous value | New value | Sheet cell
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | (schema) |  | new column |  | Area (m2) | Master Register!BI1
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | (schema) |  | new column |  | Timber Density | Master Register!BJ1
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0001 | PWG-TS-0001 | RECORD ADDED |  | Trench Stop & Bulkhead @ 2 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 458
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-BS-0001 | PWG-BS-0001 | RECORD ADDED |  | Trench Stop & Bulkhead @ 7 m (BULK HEAD) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 459
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0002 | PWG-TS-0002 | RECORD ADDED |  | Trench Stop & Bulkhead @ 12 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 460
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0003 | PWG-TS-0003 | RECORD ADDED |  | Trench Stop & Bulkhead @ 1190.9 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 461
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0004 | PWG-TS-0004 | RECORD ADDED |  | Trench Stop & Bulkhead @ 2052.9 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 462
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0005 | PWG-TS-0005 | RECORD ADDED |  | Trench Stop & Bulkhead @ 2061.5 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 463
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0006 | PWG-TS-0006 | RECORD ADDED |  | Trench Stop & Bulkhead @ 4010.3 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 464
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0007 | PWG-TS-0007 | RECORD ADDED |  | Trench Stop & Bulkhead @ 5445.3 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 465
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0008 | PWG-TS-0008 | RECORD ADDED |  | Trench Stop & Bulkhead @ 8669.8 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 466
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0009 | PWG-TS-0009 | RECORD ADDED |  | Trench Stop & Bulkhead @ 8677 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 467
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0010 | PWG-TS-0010 | RECORD ADDED |  | Trench Stop & Bulkhead @ 9344.9 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 468
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0011 | PWG-TS-0011 | RECORD ADDED |  | Trench Stop & Bulkhead @ 9358.4 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 469
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0012 | PWG-TS-0012 | RECORD ADDED |  | Trench Stop & Bulkhead @ 9371.9 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 470
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0013 | PWG-TS-0013 | RECORD ADDED |  | Trench Stop & Bulkhead @ 9810.2 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 471
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0014 | PWG-TS-0014 | RECORD ADDED |  | Trench Stop & Bulkhead @ 9825.8 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 472
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0015 | PWG-TS-0015 | RECORD ADDED |  | Trench Stop & Bulkhead @ 9841.4 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 473
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0016 | PWG-TS-0016 | RECORD ADDED |  | Trench Stop & Bulkhead @ 11111.31 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 474
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0017 | PWG-TS-0017 | RECORD ADDED |  | Trench Stop & Bulkhead @ 11118.61 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 475
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0018 | PWG-TS-0018 | RECORD ADDED |  | Trench Stop & Bulkhead @ 11125.91 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 476
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0019 | PWG-TS-0019 | RECORD ADDED |  | Trench Stop & Bulkhead @ 11305.8 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 477
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0020 | PWG-TS-0020 | RECORD ADDED |  | Trench Stop & Bulkhead @ 11318.5 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 478
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0021 | PWG-TS-0021 | RECORD ADDED |  | Trench Stop & Bulkhead @ 11331.2 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 479
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0022 | PWG-TS-0022 | RECORD ADDED |  | Trench Stop & Bulkhead @ 13376.5 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 480
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0023 | PWG-TS-0023 | RECORD ADDED |  | Trench Stop & Bulkhead @ 13384.4 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 481
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0024 | PWG-TS-0024 | RECORD ADDED |  | Trench Stop & Bulkhead @ 13392.3 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 482
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0025 | PWG-TS-0025 | RECORD ADDED |  | Trench Stop & Bulkhead @ 14244.2 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 483
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0026 | PWG-TS-0026 | RECORD ADDED |  | Trench Stop & Bulkhead @ 14254.6 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 484
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0027 | PWG-TS-0027 | RECORD ADDED |  | Trench Stop & Bulkhead @ 14577.5 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 485
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0028 | PWG-TS-0028 | RECORD ADDED |  | Trench Stop & Bulkhead @ 14588.8 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 486
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0029 | PWG-TS-0029 | RECORD ADDED |  | Trench Stop & Bulkhead @ 14600.1 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 487
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0030 | PWG-TS-0030 | RECORD ADDED |  | Trench Stop & Bulkhead @ 14611.4 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 488
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0031 | PWG-TS-0031 | RECORD ADDED |  | Trench Stop & Bulkhead @ 14622.7 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 489
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0032 | PWG-TS-0032 | RECORD ADDED |  | Trench Stop & Bulkhead @ 18779.3 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 490
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0033 | PWG-TS-0033 | RECORD ADDED |  | Trench Stop & Bulkhead @ 25025.6 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 491
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0034 | PWG-TS-0034 | RECORD ADDED |  | Trench Stop & Bulkhead @ 25039.6 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 492
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0035 | PWG-TS-0035 | RECORD ADDED |  | Trench Stop & Bulkhead @ 25053.6 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 493
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-TS-0036 | PWG-TS-0036 | RECORD ADDED |  | Trench Stop & Bulkhead @ 25067.6 m (TRENCH STOP) | Trench&Bulkheads- T2W_PIPELINE.xlsm row 494
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0001 | VEG_PHW001 | RECORD ADDED |  | Vegetation @ 10.0-20.0 m, 195 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 18
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0002 | VEG_PHW002 | RECORD ADDED |  | Vegetation @ 60.0-200.0 m, 658 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 19
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0003 | VEG_PHW003 | RECORD ADDED |  | Vegetation @ 250.0-270.0 m, 110 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 20
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0004 | VEG_PHW004 | RECORD ADDED |  | Vegetation @ 330.0-370.0 m, 486 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 21
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0005 | VEG_PHW005 | RECORD ADDED |  | Vegetation @ 380.0-410.0 m, 145 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 22
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0006 | VEG_PHW006 | RECORD ADDED |  | Vegetation @ 450.0-460.0 m, 18.7 m2 TRIM | T2W - Tree Removal TakeOff (V.1).xlsx row 23
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0007 | VEG_PHW007 | RECORD ADDED |  | Vegetation @ 510.0-530.0 m, 85.9 m2 TRIM | T2W - Tree Removal TakeOff (V.1).xlsx row 24
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0008 | VEG_PHW008 | RECORD ADDED |  | Vegetation @ 540.0-560.0 m, 147 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 25
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0009 | VEG_PHW009 | RECORD ADDED |  | Vegetation @ 620.0-640.0 m, 108 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 26
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0010 | VEG_PHW010 | RECORD ADDED |  | Vegetation @ 670.0-690.0 m, 110 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 27
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0011 | VEG_PHW011 | RECORD ADDED |  | Vegetation @ 730.0-740.0 m, 62.9 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 28
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0012 | VEG_PHW012 | RECORD ADDED |  | Vegetation @ 770.0-800.0 m, 262 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 29
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0013 | VEG_PHW013 | RECORD ADDED |  | Vegetation @ 890.0-900.0 m, 24.2 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 30
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0014 | VEG_PHW014 | RECORD ADDED |  | Vegetation @ 920.0-930.0 m, 66.5 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 31
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0015 | VEG_PHW015 | RECORD ADDED |  | Vegetation @ 950.0-950.0 m, 9.64 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 32
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0016 | VEG_PHW016 | RECORD ADDED |  | Vegetation @ 960.0-980.0 m, 123 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 33
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0017 | VEG_PHW017 | RECORD ADDED |  | Vegetation @ 1000-1010.0 m, 55.6 m2 TRIM | T2W - Tree Removal TakeOff (V.1).xlsx row 34
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0018 | VEG_PHW018 | RECORD ADDED |  | Vegetation @ 1010.0-1020.0 m, 57.9 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 35
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0019 | VEG_PHW019 | RECORD ADDED |  | Vegetation @ 1040.0-1050.0 m, 23 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 36
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0020 | VEG_PHW020 | RECORD ADDED |  | Vegetation @ 1070.0-1080.0 m, 85.4 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 37
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0021 | VEG_PHW021 | RECORD ADDED |  | Vegetation @ 1100.0-1130.0 m, 117 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 38
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0022 | VEG_PHW022 | RECORD ADDED |  | Vegetation @ 1140.0-1150.0 m, 82 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 39
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0023 | VEG_PHW023 | RECORD ADDED |  | Vegetation @ 1170.0-1190.0 m, 46.3 m2 TRIM | T2W - Tree Removal TakeOff (V.1).xlsx row 40
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0024 | VEG_PHW024 | RECORD ADDED |  | Vegetation @ 1210.0-1220.0 m, 12.4 m2 TRIM | T2W - Tree Removal TakeOff (V.1).xlsx row 41
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0025 | VEG_PHW025 | RECORD ADDED |  | Vegetation @ 1250.0-1250.0 m, 54 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 42
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0026 | VEG_PHW026 | RECORD ADDED |  | Vegetation @ 1320.0-1330.0 m, 66 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 43
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0027 | VEG_PHW027 | RECORD ADDED |  | Vegetation @ 1740.0-1780.0 m, 402 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 44
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0028 | VEG_PHW028 | RECORD ADDED |  | Vegetation @ 1810.0-1830.0 m, 271 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 45
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0029 | VEG_PHW029 | RECORD ADDED |  | Vegetation @ 1980.0-2010.0 m, 380 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 46
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0030 | VEG_PHW030 | RECORD ADDED |  | Vegetation @ 2030.0-2040.0 m, 99 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 47
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0031 | VEG_PHW031 | RECORD ADDED |  | Vegetation @ 2320.0-2330.0 m, 44.8 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 48
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0032 | VEG_PHW032 | RECORD ADDED |  | Vegetation @ 2360.0-2380.0 m, 141 m2 TRIM | T2W - Tree Removal TakeOff (V.1).xlsx row 49
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0033 | VEG_PHW033 | RECORD ADDED |  | Vegetation @ 2360.0-2370.0 m, 94 m2 TRIM | T2W - Tree Removal TakeOff (V.1).xlsx row 50
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0034 | VEG_PHW034 | RECORD ADDED |  | Vegetation @ 2400.0-2420.0 m, 138 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 51
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0035 | VEG_PHW035 | RECORD ADDED |  | Vegetation @ 2460.0-2480.0 m, 132 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 52
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0036 | VEG_PHW036 | RECORD ADDED |  | Vegetation @ 2480.0-2490.0 m, 37.7 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 53
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0037 | VEG_PHW037 | RECORD ADDED |  | Vegetation @ 2500.0-2510.0 m, 17 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 54
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0038 | VEG_PHW038 | RECORD ADDED |  | Vegetation @ 2560.0-2580.0 m, 117 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 55
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0039 | VEG_PHW039 | RECORD ADDED |  | Vegetation @ 2620.0-2620.0 m, 29 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 56
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0040 | VEG_PHW040 | RECORD ADDED |  | Vegetation @ 2710.0-2720.0 m, 43.3 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 57
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0041 | VEG_PHW041 | RECORD ADDED |  | Vegetation @ 2750.0-2750.0 m, 32.5 m2 TRIM | T2W - Tree Removal TakeOff (V.1).xlsx row 58
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0042 | VEG_PHW042 | RECORD ADDED |  | Vegetation @ 2770.0-2790.0 m, 86.4 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 59
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0043 | VEG_PHW043 | RECORD ADDED |  | Vegetation @ 2810.0-2810.0 m, 41.4 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 60
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0044 | VEG_PHW044 | RECORD ADDED |  | Vegetation @ 3930.0-3940.0 m, 283 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 61
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0045 | VEG_PHW045 | RECORD ADDED |  | Vegetation @ 3950.0-3960.0 m, 99 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 62
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0046 | VEG_PHW046 | RECORD ADDED |  | Vegetation @ 4900.0-4910.0 m, 309 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 63
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0047 | VEG_PHW047 | RECORD ADDED |  | Vegetation @ 5390.0-5410.0 m, 142 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 64
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0048 | VEG_PHW048 | RECORD ADDED |  | Vegetation @ 5840.0-5850.0 m, 85.2 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 65
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0049 | VEG_PHW049 | RECORD ADDED |  | Vegetation @ 5970.0-5990.0 m, 212 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 66
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0050 | VEG_PHW050 | RECORD ADDED |  | Vegetation @ 6620.0-6630.0 m, 27 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 67
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0051 | VEG_PHW051 | RECORD ADDED |  | Vegetation @ 8310.0-8320.0 m, 188 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 68
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0052 | VEG_PHW052 | RECORD ADDED |  | Vegetation @ 8350.0-8360.0 m, 54.8 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 69
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0053 | VEG_PHW053 | RECORD ADDED |  | Vegetation @ 8460.0-8470.0 m, 56 m2 TRIM | T2W - Tree Removal TakeOff (V.1).xlsx row 70
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0054 | VEG_PHW054 | RECORD ADDED |  | Vegetation @ 8950.0-8960.0 m, 88.8 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 71
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0055 | VEG_PHW055 | RECORD ADDED |  | Vegetation @ 8970.0-8980.0 m, 5 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 72
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0056 | VEG_PHW056 | RECORD ADDED |  | Vegetation @ 9140.0-9150.0 m, 164 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 73
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0057 | VEG_PHW057 | RECORD ADDED |  | Vegetation @ 9220.0-9230.0 m, 40 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 74
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0058 | VEG_PHW058 | RECORD ADDED |  | Vegetation @ 9460.0-9470.0 m, 48 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 75
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0059 | VEG_PHW059 | RECORD ADDED |  | Vegetation @ 9590.0-9600.0 m, 29 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 76
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0060 | VEG_PHW060 | RECORD ADDED |  | Vegetation @ 10320.0-10330.0 m, 65.7 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 77
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0061 | VEG_PHW061 | RECORD ADDED |  | Vegetation @ 11180.0-11190.0 m, 23.8 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 78
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0062 | VEG_PHW062 | RECORD ADDED |  | Vegetation @ 13590.0-13610.0 m, 90 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 79
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0063 | VEG_PHW063 | RECORD ADDED |  | Vegetation @ 13960.0-13980.0 m, 73 m2 TRIM | T2W - Tree Removal TakeOff (V.1).xlsx row 80
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0064 | VEG_PHW064 | RECORD ADDED |  | Vegetation @ 14250.0-14260.0 m, 21.5 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 81
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0065 | VEG_PHW065 | RECORD ADDED |  | Vegetation @ 14350.0-14360.0 m, 29 m2 TRIM | T2W - Tree Removal TakeOff (V.1).xlsx row 82
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0066 | VEG_PHW066 | RECORD ADDED |  | Vegetation @ 15760.0-15770.0 m, 43 m2 TRIM | T2W - Tree Removal TakeOff (V.1).xlsx row 83
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0067 | VEG_PHW067 | RECORD ADDED |  | Vegetation @ 18990.0-19000 m, 63.7 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 84
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0068 | VEG_PHW068 | RECORD ADDED |  | Vegetation @ 19010.0-19060.0 m, 593 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 85
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0069 | VEG_PHW069 | RECORD ADDED |  | Vegetation @ 19110.0-19120.0 m, 105 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 86
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PHW-VG-0070 | VEG_PHW070 | RECORD ADDED |  | Vegetation @ 19132.0-19132.0 m, 73 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 87
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-VG-0001 | VEG_PWG001 | RECORD ADDED |  | Vegetation @ 400.0-430.0 m, 234 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 88
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-VG-0002 | VEG_PWG002 | RECORD ADDED |  | Vegetation @ 440.0-450.0 m, 113 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 89
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-VG-0003 | VEG_PWG003 | RECORD ADDED |  | Vegetation @ 490.0-530.0 m, 273 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 90
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-VG-0004 | VEG_PWG004 | RECORD ADDED |  | Vegetation @ 590.0-740.0 m, 1550 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 91
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-VG-0005 | VEG_PWG005 | RECORD ADDED |  | Vegetation @ 760.0-880.0 m, 1520 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 92
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-VG-0006 | VEG_PWG006 | RECORD ADDED |  | Vegetation @ 990.0-1000 m, 56.6 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 93
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-VG-0007 | VEG_PWG007 | RECORD ADDED |  | Vegetation @ 1040.0-1050.0 m, 27 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 94
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-VG-0008 | VEG_PWG008 | RECORD ADDED |  | Vegetation @ 1430.0-1460.0 m, 215 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 95
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-VG-0009 | VEG_PWG009 | RECORD ADDED |  | Vegetation @ 2210.0-2220.0 m, 80 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 96
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-VG-0010 | VEG_PWG010 | RECORD ADDED |  | Vegetation @ 2370.0-2380.0 m, 50 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 97
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-VG-0011 | VEG_PWG011 | RECORD ADDED |  | Vegetation @ 3250.0-3260.0 m, 31.4 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 98
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-VG-0012 | VEG_PWG012 | RECORD ADDED |  | Vegetation @ 3540.0-3560.0 m, 145 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 99
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-VG-0013 | VEG_PWG013 | RECORD ADDED |  | Vegetation @ 3590.0-3600.0 m, 13.6 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 100
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-VG-0014 | VEG_PWG014 | RECORD ADDED |  | Vegetation @ 4080.0-4090.0 m, 46.6 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 101
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-VG-0015 | VEG_PWG015 | RECORD ADDED |  | Vegetation @ 10680.0-10690.0 m, 116 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 102
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-VG-0016 | VEG_PWG016 | RECORD ADDED |  | Vegetation @ 21580.0-21590.0 m, 74.8 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 103
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-VG-0017 | VEG_PWG017 | RECORD ADDED |  | Vegetation @ 24010.0-24020.0 m, 32.5 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 104
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-VG-0018 | VEG_PWG018 | RECORD ADDED |  | Vegetation @ 24830.0-24860.0 m, 176 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 105
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-VG-0019 | VEG_PWG019 | RECORD ADDED |  | Vegetation @ 26070.0-26080.0 m, 64.7 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 106
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-VG-0020 | VEG_PWG020 | RECORD ADDED |  | Vegetation @ 26290.0-26300.0 m, 23 m2 LIGHT | T2W - Tree Removal TakeOff (V.1).xlsx row 107
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | PWG-VG-0021 | VEG_PWG021 | RECORD ADDED |  | Vegetation @ 26430.0-26440.0 m, 79 m2 HEAVY | T2W - Tree Removal TakeOff (V.1).xlsx row 108
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | (source) |  | Src - Trench Stop & BH reloaded | 452 rows | 489 rows (source rev 2026-08-17) | Src - Trench Stop & BH
2026-08-24 09:54 | J. Krasnoff-Hnatjuk | (derived) |  | Chainage Index | ranges to row 1189, 6 registers | ranges to row 1317, 7 registers (Vegetation added) | Chainage Index
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | (schema) |  | new column |  | Thrust Block Category | Master Register!BK1
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-001 | PHW-TB-001 | Thrust Block Category |  | Bend | Master Register!BK5
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-002 | PHW-TB-002 | Thrust Block Category |  | Bend | Master Register!BK97
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-003 | PHW-TB-003 | Thrust Block Category |  | Bend | Master Register!BK104
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-004 | PHW-TB-004 | Thrust Block Category |  | Bend | Master Register!BK155
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-005 | PHW-TB-005 | Thrust Block Category |  | Bend | Master Register!BK161
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-006 | PHW-TB-006 | Thrust Block Category |  | Bend | Master Register!BK181
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-007 | PHW-TB-007 | Thrust Block Category |  | Bend | Master Register!BK182
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-008 | PHW-TB-008 | Thrust Block Category |  | Bend | Master Register!BK189
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-009 | PHW-TB-009 | Thrust Block Category |  | Bend | Master Register!BK192
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-010 | PHW-TB-010 | Thrust Block Category |  | Bend | Master Register!BK223
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-011 | PHW-TB-011 | Thrust Block Category |  | Bend | Master Register!BK226
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-012 | PHW-TB-012 | Thrust Block Category |  | Bend | Master Register!BK237
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-013 | PHW-TB-013 | Thrust Block Category |  | Bend | Master Register!BK243
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-014 | PHW-TB-014 | Thrust Block Category |  | Bend | Master Register!BK244
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-015 | PHW-TB-015 | Thrust Block Category |  | Bend | Master Register!BK248
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-016 | PHW-TB-016 | Thrust Block Category |  | Bend | Master Register!BK250
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-017 | PHW-TB-017 | Thrust Block Category |  | Bend | Master Register!BK282
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-018 | PHW-TB-018 | Thrust Block Category |  | Bend | Master Register!BK302
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-019 | PHW-TB-019 | Thrust Block Category |  | Bend | Master Register!BK307
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-020 | PHW-TB-020 | Thrust Block Category |  | Bend | Master Register!BK313
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-021 | PHW-TB-021 | Thrust Block Category |  | Bend | Master Register!BK314
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-022 | PHW-TB-022 | Thrust Block Category |  | Bend | Master Register!BK322
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-023 | PHW-TB-023 | Thrust Block Category |  | Bend | Master Register!BK324
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-024 | PHW-TB-024 | Thrust Block Category |  | Bend | Master Register!BK330
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-025 | PHW-TB-025 | Thrust Block Category |  | Bend | Master Register!BK360
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-026 | PHW-TB-026 | Thrust Block Category |  | Bend | Master Register!BK364
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-027 | PHW-TB-027 | Thrust Block Category |  | Bend | Master Register!BK373
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-028 | PHW-TB-028 | Thrust Block Category |  | Bend | Master Register!BK378
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-029 | PHW-TB-029 | Thrust Block Category |  | Bend | Master Register!BK381
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-030 | PHW-TB-030 | Thrust Block Category |  | Bend | Master Register!BK385
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-031 | PHW-TB-031 | Thrust Block Category |  | Bend | Master Register!BK393
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-032 | PHW-TB-032 | Thrust Block Category |  | Bend | Master Register!BK398
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-033 | PHW-TB-033 | Thrust Block Category |  | Bend | Master Register!BK399
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-034 | PHW-TB-034 | Thrust Block Category |  | Bend | Master Register!BK417
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-035 | PHW-TB-035 | Thrust Block Category |  | Bend | Master Register!BK434
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-036 | PHW-TB-036 | Thrust Block Category |  | Bend | Master Register!BK439
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-037 | PHW-TB-037 | Thrust Block Category |  | Bend | Master Register!BK454
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-038 | PHW-TB-038 | Thrust Block Category |  | Bend | Master Register!BK465
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-039 | PHW-TB-039 | Thrust Block Category |  | Bend | Master Register!BK471
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-040 | PHW-TB-040 | Thrust Block Category |  | Bend | Master Register!BK495
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-041 | PHW-TB-041 | Thrust Block Category |  | Bend | Master Register!BK500
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-042 | PHW-TB-042 | Thrust Block Category |  | Bend | Master Register!BK512
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-043 | PHW-TB-043 | Thrust Block Category |  | Bend | Master Register!BK539
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-044 | PHW-TB-044 | Thrust Block Category |  | Bend | Master Register!BK549
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-045 | PHW-TB-045 | Thrust Block Category |  | Bend | Master Register!BK618
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-046 | PHW-TB-046 | Thrust Block Category |  | Bend | Master Register!BK630
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-047 | PHW-TB-047 | Thrust Block Category |  | Bend | Master Register!BK647
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-048 | PHW-TB-048 | Thrust Block Category |  | Bend | Master Register!BK650
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-049 | PHW-TB-049 | Thrust Block Category |  | Bend | Master Register!BK654
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-050 | PHW-TB-050 | Thrust Block Category |  | Bend | Master Register!BK655
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-051 | PHW-TB-051 | Thrust Block Category |  | Bend | Master Register!BK658
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-052 | PHW-TB-052 | Thrust Block Category |  | Bend | Master Register!BK669
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-053 | PHW-TB-053 | Thrust Block Category |  | Bend | Master Register!BK685
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-054 | PHW-TB-054 | Thrust Block Category |  | Bend | Master Register!BK686
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-055 | PHW-TB-055 | Thrust Block Category |  | Bend | Master Register!BK704
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-056 | PHW-TB-056 | Thrust Block Category |  | Bend | Master Register!BK705
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-057 | PHW-TB-057 | Thrust Block Category |  | Bend | Master Register!BK707
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-058 | PHW-TB-058 | Thrust Block Category |  | Bend | Master Register!BK713
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-059 | PHW-TB-059 | Thrust Block Category |  | Bend | Master Register!BK714
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-060 | PHW-TB-060 | Thrust Block Category |  | Bend | Master Register!BK716
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-061 | PHW-TB-061 | Thrust Block Category |  | Bend | Master Register!BK721
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-062 | PHW-TB-062 | Thrust Block Category |  | Bend | Master Register!BK722
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-063 | PHW-TB-063 | Thrust Block Category |  | Bend | Master Register!BK739
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-064 | PHW-TB-064 | Thrust Block Category |  | Bend | Master Register!BK750
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-065 | PHW-TB-065 | Thrust Block Category |  | Bend | Master Register!BK752
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-066 | PHW-TB-066 | Thrust Block Category |  | Bend | Master Register!BK761
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-067 | PHW-TB-067 | Thrust Block Category |  | Bend | Master Register!BK783
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-068 | PHW-TB-068 | Thrust Block Category |  | Bend | Master Register!BK785
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-069 | PHW-TB-069 | Thrust Block Category |  | Bend | Master Register!BK806
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-070 | PHW-TB-070 | Thrust Block Category |  | Bend | Master Register!BK809
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-071 | PHW-TB-071 | Thrust Block Category |  | Bend | Master Register!BK812
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-072 | PHW-TB-072 | Thrust Block Category |  | Bend | Master Register!BK843
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-073 | PHW-TB-073 | Thrust Block Category |  | Bend | Master Register!BK848
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-074 | PHW-TB-074 | Thrust Block Category |  | Bend | Master Register!BK849
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-075 | PHW-TB-075 | Thrust Block Category |  | Bend | Master Register!BK857
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-076 | PHW-TB-076 | Thrust Block Category |  | Bend | Master Register!BK858
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-001 | PWG-TB-001 | Thrust Block Category |  | Bend | Master Register!BK892
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-002 | PWG-TB-002 | Thrust Block Category |  | Bend | Master Register!BK899
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-003 | PWG-TB-003 | Thrust Block Category |  | Bend | Master Register!BK902
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-004 | PWG-TB-004 | Thrust Block Category |  | Bend | Master Register!BK904
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-005 | PWG-TB-005 | Thrust Block Category |  | Bend | Master Register!BK905
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-006 | PWG-TB-006 | Thrust Block Category |  | Bend | Master Register!BK907
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-007 | PWG-TB-007 | Thrust Block Category |  | Bend | Master Register!BK911
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-008 | PWG-TB-008 | Thrust Block Category |  | Bend | Master Register!BK914
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-009 | PWG-TB-009 | Thrust Block Category |  | Bend | Master Register!BK923
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-010 | PWG-TB-010 | Thrust Block Category |  | Bend | Master Register!BK933
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-011 | PWG-TB-011 | Thrust Block Category |  | Bend | Master Register!BK937
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-012 | PWG-TB-012 | Thrust Block Category |  | Bend | Master Register!BK939
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-013 | PWG-TB-013 | Thrust Block Category |  | Bend | Master Register!BK940
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-014 | PWG-TB-014 | Thrust Block Category |  | Bend | Master Register!BK954
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-015 | PWG-TB-015 | Thrust Block Category |  | Bend | Master Register!BK972
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-016 | PWG-TB-016 | Thrust Block Category |  | Bend | Master Register!BK975
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-017 | PWG-TB-017 | Thrust Block Category |  | Bend | Master Register!BK1010
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-018 | PWG-TB-018 | Thrust Block Category |  | Bend | Master Register!BK1020
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-019 | PWG-TB-019 | Thrust Block Category |  | Bend | Master Register!BK1025
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-020 | PWG-TB-020 | Thrust Block Category |  | Bend | Master Register!BK1030
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-021 | PWG-TB-021 | Thrust Block Category |  | Bend | Master Register!BK1038
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-022 | PWG-TB-022 | Thrust Block Category |  | Bend | Master Register!BK1042
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-023 | PWG-TB-023 | Thrust Block Category |  | Bend | Master Register!BK1045
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-024 | PWG-TB-024 | Thrust Block Category |  | Bend | Master Register!BK1046
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-025 | PWG-TB-025 | Thrust Block Category |  | Bend | Master Register!BK1051
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PPH-TB-001 | PPH-TB-001 | Thrust Block Category |  | Bend | Master Register!BK1298
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PPH-TB-002 | PPH-TB-002 | Thrust Block Category |  | Bend | Master Register!BK1299
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PPH-TB-003 | PPH-TB-003 | Thrust Block Category |  | Bend | Master Register!BK1300
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PPH-TB-004 | PPH-TB-004 | Thrust Block Category |  | Bend | Master Register!BK1301
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PPH-TB-005 | PPH-TB-005 | Thrust Block Category |  | Bend | Master Register!BK1302
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PPH-TB-006 | PPH-TB-006 | Thrust Block Category |  | Bend | Master Register!BK1303
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PPH-TB-007 | PPH-TB-007 | Thrust Block Category |  | Bend | Master Register!BK1304
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | RHF-TB-001 | RHF-TB-001 | Thrust Block Category |  | Facility (RHF) - not in pipeline index | Master Register!BK1305
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | RHF-TB-002 | RHF-TB-002 | Thrust Block Category |  | Facility (RHF) - not in pipeline index | Master Register!BK1306
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | RHF-TB-003 | RHF-TB-003 | Thrust Block Category |  | Facility (RHF) - not in pipeline index | Master Register!BK1307
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | RHF-TB-004 | RHF-TB-004 | Thrust Block Category |  | Facility (RHF) - not in pipeline index | Master Register!BK1308
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | RHF-TB-005 | RHF-TB-005 | Thrust Block Category |  | Facility (RHF) - not in pipeline index | Master Register!BK1309
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | RHF-TB-006 | RHF-TB-006 | Thrust Block Category |  | Facility (RHF) - not in pipeline index | Master Register!BK1310
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | RHF-TB-007 | RHF-TB-007 | Thrust Block Category |  | Facility (RHF) - not in pipeline index | Master Register!BK1311
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | RHF-TB-008 | RHF-TB-008 | Thrust Block Category |  | Facility (RHF) - not in pipeline index | Master Register!BK1312
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | RHF-TB-009 | RHF-TB-009 | Thrust Block Category |  | Facility (RHF) - not in pipeline index | Master Register!BK1313
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | RHF-TB-010 | RHF-TB-010 | Thrust Block Category |  | Facility (RHF) - not in pipeline index | Master Register!BK1314
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | RHF-TB-011 | RHF-TB-011 | Thrust Block Category |  | Facility (RHF) - not in pipeline index | Master Register!BK1315
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | RHF-TB-012 | RHF-TB-012 | Thrust Block Category |  | Facility (RHF) - not in pipeline index | Master Register!BK1316
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | RHF-TB-013 | RHF-TB-013 | Thrust Block Category |  | Facility (RHF) - not in pipeline index | Master Register!BK1317
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-026 | PWG-TB-026 | RECORD ADDED |  | Thrust Block @ 7587.138 m, Type 6, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 127
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-027 | PWG-TB-027 | RECORD ADDED |  | Thrust Block @ 7618.704 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 128
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-028 | PWG-TB-028 | RECORD ADDED |  | Thrust Block @ 7619.979 m, Type 11, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 129
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-029 | PWG-TB-029 | RECORD ADDED |  | Thrust Block @ 7646.073 m, Type 11, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 130
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-030 | PWG-TB-030 | RECORD ADDED |  | Thrust Block @ 7862.684 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 131
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-031 | PWG-TB-031 | RECORD ADDED |  | Thrust Block @ 7910.66 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 132
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-032 | PWG-TB-032 | RECORD ADDED |  | Thrust Block @ 7957.939 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 133
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-033 | PWG-TB-033 | RECORD ADDED |  | Thrust Block @ 7973.15 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 134
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-034 | PWG-TB-034 | RECORD ADDED |  | Thrust Block @ 8109.465 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 135
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-035 | PWG-TB-035 | RECORD ADDED |  | Thrust Block @ 8202.694 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 136
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-036 | PWG-TB-036 | RECORD ADDED |  | Thrust Block @ 8245.381 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 137
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-037 | PWG-TB-037 | RECORD ADDED |  | Thrust Block @ 8288.124 m, Type 6, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 138
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-038 | PWG-TB-038 | RECORD ADDED |  | Thrust Block @ 8465.757 m, Type 9, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 139
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-039 | PWG-TB-039 | RECORD ADDED |  | Thrust Block @ 8481.865 m, Type 4, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 140
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-040 | PWG-TB-040 | RECORD ADDED |  | Thrust Block @ 8485.834 m, Type 6, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 141
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-041 | PWG-TB-041 | RECORD ADDED |  | Thrust Block @ 8545.354 m, Type 6, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 142
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-042 | PWG-TB-042 | RECORD ADDED |  | Thrust Block @ 8547.89 m, Type 6, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 143
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-043 | PWG-TB-043 | RECORD ADDED |  | Thrust Block @ 9455.661 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 144
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-044 | PWG-TB-044 | RECORD ADDED |  | Thrust Block @ 10741.055 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 145
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-045 | PWG-TB-045 | RECORD ADDED |  | Thrust Block @ 10780.713 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 146
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-046 | PWG-TB-046 | RECORD ADDED |  | Thrust Block @ 11468.159 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 147
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-047 | PWG-TB-047 | RECORD ADDED |  | Thrust Block @ 11759.158 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 148
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-048 | PWG-TB-048 | RECORD ADDED |  | Thrust Block @ 11768.094 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 149
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-049 | PWG-TB-049 | RECORD ADDED |  | Thrust Block @ 11773.094 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 150
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-050 | PWG-TB-050 | RECORD ADDED |  | Thrust Block @ 11782.037 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 151
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-051 | PWG-TB-051 | RECORD ADDED |  | Thrust Block @ 12099.939 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 152
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-052 | PWG-TB-052 | RECORD ADDED |  | Thrust Block @ 12694.713 m, Type 5, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 153
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-053 | PWG-TB-053 | RECORD ADDED |  | Thrust Block @ 12747.863 m, Type 5, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 154
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-054 | PWG-TB-054 | RECORD ADDED |  | Thrust Block @ 12782.914 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 155
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-055 | PWG-TB-055 | RECORD ADDED |  | Thrust Block @ 13394.686 m, Type 9, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 156
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-056 | PWG-TB-056 | RECORD ADDED |  | Thrust Block @ 13416.368 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 157
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-057 | PWG-TB-057 | RECORD ADDED |  | Thrust Block @ 14076.214 m, Type 11, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 158
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-058 | PWG-TB-058 | RECORD ADDED |  | Thrust Block @ 14139.442 m, Type 10, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 159
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-059 | PWG-TB-059 | RECORD ADDED |  | Thrust Block @ 14178.758 m, Type 10, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 160
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-060 | PWG-TB-060 | RECORD ADDED |  | Thrust Block @ 14883.12 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 161
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-061 | PWG-TB-061 | RECORD ADDED |  | Thrust Block @ 16429.262 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 162
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-062 | PWG-TB-062 | RECORD ADDED |  | Thrust Block @ 16975.581 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 163
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-063 | PWG-TB-063 | RECORD ADDED |  | Thrust Block @ 16982.79 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 164
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-064 | PWG-TB-064 | RECORD ADDED |  | Thrust Block @ 17433.278 m, Type 6, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 165
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-065 | PWG-TB-065 | RECORD ADDED |  | Thrust Block @ 17830.527 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 166
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-066 | PWG-TB-066 | RECORD ADDED |  | Thrust Block @ 18027.533 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 167
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-067 | PWG-TB-067 | RECORD ADDED |  | Thrust Block @ 18096.401 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 168
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-068 | PWG-TB-068 | RECORD ADDED |  | Thrust Block @ 18147.994 m, Type 5, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 169
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-069 | PWG-TB-069 | RECORD ADDED |  | Thrust Block @ 18150.734 m, Type 5, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 170
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-070 | PWG-TB-070 | RECORD ADDED |  | Thrust Block @ 18181.794 m, Type 6, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 171
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-071 | PWG-TB-071 | RECORD ADDED |  | Thrust Block @ 18190.097 m, Type 6, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 172
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-072 | PWG-TB-072 | RECORD ADDED |  | Thrust Block @ 18785.871 m, Type 9, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 173
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-073 | PWG-TB-073 | RECORD ADDED |  | Thrust Block @ 20066.024 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 174
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-074 | PWG-TB-074 | RECORD ADDED |  | Thrust Block @ 20282.529 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 175
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-075 | PWG-TB-075 | RECORD ADDED |  | Thrust Block @ 20818.272 m, Type 6, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 176
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-076 | PWG-TB-076 | RECORD ADDED |  | Thrust Block @ 20947.014 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 177
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-077 | PWG-TB-077 | RECORD ADDED |  | Thrust Block @ 21445.551 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 178
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-078 | PWG-TB-078 | RECORD ADDED |  | Thrust Block @ 21581.657 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 179
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-079 | PWG-TB-079 | RECORD ADDED |  | Thrust Block @ 21602.601 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 180
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-080 | PWG-TB-080 | RECORD ADDED |  | Thrust Block @ 21631.157 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 181
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-081 | PWG-TB-081 | RECORD ADDED |  | Thrust Block @ 22176.234 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 182
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-082 | PWG-TB-082 | RECORD ADDED |  | Thrust Block @ 22504.051 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 183
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-083 | PWG-TB-083 | RECORD ADDED |  | Thrust Block @ 22650.05 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 184
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-084 | PWG-TB-084 | RECORD ADDED |  | Thrust Block @ 23112.75 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 185
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-085 | PWG-TB-085 | RECORD ADDED |  | Thrust Block @ 23373.352 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 186
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-086 | PWG-TB-086 | RECORD ADDED |  | Thrust Block @ 23414.166 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 187
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-087 | PWG-TB-087 | RECORD ADDED |  | Thrust Block @ 23666.289 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 188
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-088 | PWG-TB-088 | RECORD ADDED |  | Thrust Block @ 23999.457 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 189
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-089 | PWG-TB-089 | RECORD ADDED |  | Thrust Block @ 24426.9 m, Type 5, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 190
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-090 | PWG-TB-090 | RECORD ADDED |  | Thrust Block @ 24713.951 m, Type 5, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 191
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-091 | PWG-TB-091 | RECORD ADDED |  | Thrust Block @ 24909.165 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 192
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-092 | PWG-TB-092 | RECORD ADDED |  | Thrust Block @ 25129.481 m, Type 5, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 193
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-093 | PWG-TB-093 | RECORD ADDED |  | Thrust Block @ 25162.559 m, Type 4, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 194
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-094 | PWG-TB-094 | RECORD ADDED |  | Thrust Block @ 25169.588 m, Type 5, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 195
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-095 | PWG-TB-095 | RECORD ADDED |  | Thrust Block @ 25391.145 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 196
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-096 | PWG-TB-096 | RECORD ADDED |  | Thrust Block @ 25800.795 m, Type 5, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 197
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-097 | PWG-TB-097 | RECORD ADDED |  | Thrust Block @ 25804.926 m, Type 5, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 198
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-098 | PWG-TB-098 | RECORD ADDED |  | Thrust Block @ 25817.226 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 199
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-099 | PWG-TB-099 | RECORD ADDED |  | Thrust Block @ 26038.676 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 200
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-100 | PWG-TB-100 | RECORD ADDED |  | Thrust Block @ 26195.427 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 201
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-101 | PWG-TB-101 | RECORD ADDED |  | Thrust Block @ 26560.798 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 202
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-102 | PWG-TB-102 | RECORD ADDED |  | Thrust Block @ 26662.937 m, Type 7, Bend | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 203
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-103 | PWG-TB-103 | RECORD ADDED |  | Thrust Block @ 230.031 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 204
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-104 | PWG-TB-104 | RECORD ADDED |  | Thrust Block @ 702.553 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 205
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-105 | PWG-TB-105 | RECORD ADDED |  | Thrust Block @ 7092.671 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 206
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-106 | PWG-TB-106 | RECORD ADDED |  | Thrust Block @ 8908.151 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 207
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-107 | PWG-TB-107 | RECORD ADDED |  | Thrust Block @ 9473.063 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 208
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-108 | PWG-TB-108 | RECORD ADDED |  | Thrust Block @ 10553.492 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 209
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-109 | PWG-TB-109 | RECORD ADDED |  | Thrust Block @ 12687.754 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 210
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-110 | PWG-TB-110 | RECORD ADDED |  | Thrust Block @ 13188.911 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 211
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-111 | PWG-TB-111 | RECORD ADDED |  | Thrust Block @ 14143.438 m, Type 6, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 212
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-112 | PWG-TB-112 | RECORD ADDED |  | Thrust Block @ 14224.068 m, Type 6, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 213
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-113 | PWG-TB-113 | RECORD ADDED |  | Thrust Block @ 15788.534 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 214
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-114 | PWG-TB-114 | RECORD ADDED |  | Thrust Block @ 18149.44 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 215
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-115 | PWG-TB-115 | RECORD ADDED |  | Thrust Block @ 18772.846 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 216
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-116 | PWG-TB-116 | RECORD ADDED |  | Thrust Block @ 19641.881 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 217
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-117 | PWG-TB-117 | RECORD ADDED |  | Thrust Block @ 20287.711 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 218
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-118 | PWG-TB-118 | RECORD ADDED |  | Thrust Block @ 21452.237 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 219
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-119 | PWG-TB-119 | RECORD ADDED |  | Thrust Block @ 22316.144 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 220
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-120 | PWG-TB-120 | RECORD ADDED |  | Thrust Block @ 22680.903 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 221
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-121 | PWG-TB-121 | RECORD ADDED |  | Thrust Block @ 23376.417 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 222
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-122 | PWG-TB-122 | RECORD ADDED |  | Thrust Block @ 24206.919 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 223
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-123 | PWG-TB-123 | RECORD ADDED |  | Thrust Block @ 25018.345 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 224
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-124 | PWG-TB-124 | RECORD ADDED |  | Thrust Block @ 25792.787 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 225
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-125 | PWG-TB-125 | RECORD ADDED |  | Thrust Block @ 26041.176 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 226
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-126 | PWG-TB-126 | RECORD ADDED |  | Thrust Block @ 4040.672 m, Type 12, Isolation Valve | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 227
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-127 | PWG-TB-127 | RECORD ADDED |  | Thrust Block @ 7536.828 m, Type 13, Isolation Valve | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 228
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-128 | PWG-TB-128 | RECORD ADDED |  | Thrust Block @ 8475.323 m, Type 13, Isolation Valve | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 229
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-129 | PWG-TB-129 | RECORD ADDED |  | Thrust Block @ 8562.951 m, Type 13, Isolation Valve | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 230
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-130 | PWG-TB-130 | RECORD ADDED |  | Thrust Block @ 13366.211 m, Type 13, Isolation Valve | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 231
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-131 | PWG-TB-131 | RECORD ADDED |  | Thrust Block @ 22075.201 m, Type 13, Isolation Valve | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 232
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-132 | PWG-TB-132 | RECORD ADDED |  | Thrust Block @ 99.181 m, 2 x Type 13, Pigging Station | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 233
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-133 | PWG-TB-133 | RECORD ADDED |  | Thrust Block @ 7595.718 m, 2 x Type 13, Pigging Station | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 234
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PWG-TB-134 | PWG-TB-134 | RECORD ADDED |  | Thrust Block @ 17865.623 m, 2 x Type 13, Pigging Station | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 235
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-077 | PHW-TB-077 | RECORD ADDED |  | Thrust Block @ 1261.832 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 236
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-078 | PHW-TB-078 | RECORD ADDED |  | Thrust Block @ 1727.817 m, Type 6, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 237
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-079 | PHW-TB-079 | RECORD ADDED |  | Thrust Block @ 2746.277 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 238
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-080 | PHW-TB-080 | RECORD ADDED |  | Thrust Block @ 3558.423 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 239
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-081 | PHW-TB-081 | RECORD ADDED |  | Thrust Block @ 4470 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 240
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-082 | PHW-TB-082 | RECORD ADDED |  | Thrust Block @ 4661.417 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 241
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-083 | PHW-TB-083 | RECORD ADDED |  | Thrust Block @ 4961.176 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 242
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-084 | PHW-TB-084 | RECORD ADDED |  | Thrust Block @ 6796.976 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 243
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-085 | PHW-TB-085 | RECORD ADDED |  | Thrust Block @ 8197.671 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 244
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-086 | PHW-TB-086 | RECORD ADDED |  | Thrust Block @ 10103.635 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 245
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-087 | PHW-TB-087 | RECORD ADDED |  | Thrust Block @ 11396.642 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 246
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-088 | PHW-TB-088 | RECORD ADDED |  | Thrust Block @ 11596.46 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 247
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-089 | PHW-TB-089 | RECORD ADDED |  | Thrust Block @ 13125.991 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 248
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-090 | PHW-TB-090 | RECORD ADDED |  | Thrust Block @ 15248.457 m, Type 7, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 249
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-091 | PHW-TB-091 | RECORD ADDED |  | Thrust Block @ 17038.094 m, Type 6, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 250
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-092 | PHW-TB-092 | RECORD ADDED |  | Thrust Block @ 17984.612 m, Type 6, Tee | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 251
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-093 | PHW-TB-093 | RECORD ADDED |  | Thrust Block @ 842.62 m, Type 12, Isolation Valve | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 252
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-094 | PHW-TB-094 | RECORD ADDED |  | Thrust Block @ 2019.495 m, Type 12, Isolation Valve | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 253
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-095 | PHW-TB-095 | RECORD ADDED |  | Thrust Block @ 2140.173 m, Type 12, Isolation Valve | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 254
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-096 | PHW-TB-096 | RECORD ADDED |  | Thrust Block @ 7335.153 m, Type 12, Isolation Valve | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 255
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-097 | PHW-TB-097 | RECORD ADDED |  | Thrust Block @ 14323.567 m, Type 12, Isolation Valve | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 256
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-098 | PHW-TB-098 | RECORD ADDED |  | Thrust Block @ 19120.153 m, Type 14, In-Line | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 257
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-099 | PHW-TB-099 | RECORD ADDED |  | Thrust Block @ 19155.385 m, Type 14, In-Line | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 258
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-100 | PHW-TB-100 | RECORD ADDED |  | Thrust Block @ 9801.143 m, 2 x Type 12, Pigging Station | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 259
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | PHW-TB-101 | PHW-TB-101 | RECORD ADDED |  | Thrust Block @ 19097.802 m, 2 x Type 12, Pigging Station | Thrust Block Register - T2W_PIPELINE 24-8.xlsm row 260
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | (source) |  | Src - Thrust Block reloaded | 121 rows | 255 rows, 42 columns (source 24-8) | Src - Thrust Block
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | (derived) |  | Chainage Index | ranges to row 1317 | ranges to row 1451 | Chainage Index
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | (control) |  | Current revision | Rev 2 | Rev 3 | Document Control!C10
2026-08-24 10:19 | J. Krasnoff-Hnatjuk | (control) |  | Records in Master Register | 1316 | 1450 | Document Control!C13
24/08/2026 12:11 | Jerry | PHW-TB-035 | PHW-TB-035 | Installed |  | Yes | Master Register!BL444
24/08/2026 12:11 | Jerry | PHW-TB-036 | PHW-TB-036 | Installed |  | Yes | Master Register!BL449
24/08/2026 12:11 | Jerry | PHW-TB-037 | PHW-TB-037 | Installed |  | Yes | Master Register!BL464
24/08/2026 12:11 | Jerry | PHW-TB-083 | PHW-TB-083 | Installed |  | Yes | Master Register!BL436
24/08/2026 12:14 | Jerry | PHW-TB-035 | PHW-TB-035 | Completion Date |  | 25/08/2026 | Master Register!BS444
24/08/2026 12:14 | Jerry | PHW-TB-036 | PHW-TB-036 | Completion Date |  | 25/08/2026 | Master Register!BS449
24/08/2026 12:14 | Jerry | PHW-TB-037 | PHW-TB-037 | Completion Date |  | 25/08/2026 | Master Register!BS464
24/08/2026 12:14 | Jerry | PHW-TB-083 | PHW-TB-083 | Completion Date |  | 25/08/2026 | Master Register!BS436
24/08/2026 12:14 | Jerry | PHW-TB-035 | PHW-TB-035 | Completion Date | 25/08/2026 |  | Master Register!BS444
24/08/2026 12:14 | Jerry | PHW-TB-036 | PHW-TB-036 | Completion Date | 25/08/2026 |  | Master Register!BS449
24/08/2026 12:14 | Jerry | PHW-TB-037 | PHW-TB-037 | Completion Date | 25/08/2026 |  | Master Register!BS464
24/08/2026 12:14 | Jerry | PHW-TB-083 | PHW-TB-083 | Completion Date | 25/08/2026 |  | Master Register!BS436
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | (schema) |  | new column |  | Unit Rate ($) | Master Register!BU1
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | (schema) |  | new column |  | Quantity | Master Register!BV1
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | (schema) |  | new column |  | Unit | Master Register!BW1
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | (schema) |  | new column |  | Total Cost ($) | Master Register!BX1
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0001 | PHW-TS-0001 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU9
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0002 | PHW-TS-0002 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU10
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0003 | PHW-TS-0003 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU11
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0004 | PHW-TS-0004 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU12
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0005 | PHW-TS-0005 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU13
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0006 | PHW-TS-0006 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU14
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0007 | PHW-TS-0007 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU15
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0008 | PHW-TS-0008 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU17
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0009 | PHW-TS-0009 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU18
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0010 | PHW-TS-0010 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU19
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0011 | PHW-TS-0011 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU20
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0012 | PHW-TS-0012 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU21
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0013 | PHW-TS-0013 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU22
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0014 | PHW-TS-0014 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU23
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0015 | PHW-TS-0015 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU24
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0016 | PHW-TS-0016 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU25
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0017 | PHW-TS-0017 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU26
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0018 | PHW-TS-0018 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU27
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0019 | PHW-TS-0019 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU36
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0020 | PHW-TS-0020 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU38
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0021 | PHW-TS-0021 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU39
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0022 | PHW-TS-0022 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU40
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0023 | PHW-TS-0023 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU41
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0001 | PHW-BS-0001 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU42
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0024 | PHW-TS-0024 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU43
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0025 | PHW-TS-0025 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU44
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0026 | PHW-TS-0026 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU46
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0002 | PHW-BS-0002 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU47
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0027 | PHW-TS-0027 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU48
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0028 | PHW-TS-0028 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU49
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0003 | PHW-BS-0003 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU50
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0029 | PHW-TS-0029 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU52
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0030 | PHW-TS-0030 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU53
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0031 | PHW-TS-0031 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU54
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0004 | PHW-BS-0004 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU55
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0032 | PHW-TS-0032 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU56
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0033 | PHW-TS-0033 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU57
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0034 | PHW-TS-0034 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU58
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0005 | PHW-BS-0005 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU59
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0035 | PHW-TS-0035 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU60
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0036 | PHW-TS-0036 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU61
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0037 | PHW-TS-0037 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU62
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0038 | PHW-TS-0038 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU63
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0039 | PHW-TS-0039 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU64
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0040 | PHW-TS-0040 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU65
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0041 | PHW-TS-0041 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU67
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0042 | PHW-TS-0042 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU68
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0043 | PHW-TS-0043 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU69
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0044 | PHW-TS-0044 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU70
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0045 | PHW-TS-0045 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU71
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0046 | PHW-TS-0046 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU72
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0006 | PHW-BS-0006 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU73
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0047 | PHW-TS-0047 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU75
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0048 | PHW-TS-0048 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU77
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0049 | PHW-TS-0049 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU78
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0007 | PHW-BS-0007 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU79
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0050 | PHW-TS-0050 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU80
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0051 | PHW-TS-0051 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU81
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0052 | PHW-TS-0052 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU82
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0053 | PHW-TS-0053 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU83
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0008 | PHW-BS-0008 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU84
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0054 | PHW-TS-0054 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU85
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0055 | PHW-TS-0055 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU86
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0056 | PHW-TS-0056 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU87
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0009 | PHW-BS-0009 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU88
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0057 | PHW-TS-0057 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU89
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0058 | PHW-TS-0058 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU90
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0010 | PHW-BS-0010 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU92
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0059 | PHW-TS-0059 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU93
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0060 | PHW-TS-0060 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU94
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0061 | PHW-TS-0061 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU95
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0062 | PHW-TS-0062 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU103
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0063 | PHW-TS-0063 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU104
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0064 | PHW-TS-0064 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU106
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0011 | PHW-BS-0011 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU107
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0065 | PHW-TS-0065 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU108
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0066 | PHW-TS-0066 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU109
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0067 | PHW-TS-0067 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU111
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0012 | PHW-BS-0012 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU112
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0068 | PHW-TS-0068 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU113
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0069 | PHW-TS-0069 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU114
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0070 | PHW-TS-0070 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU115
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0013 | PHW-BS-0013 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU116
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0071 | PHW-TS-0071 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU117
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0072 | PHW-TS-0072 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU119
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0073 | PHW-TS-0073 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU123
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0074 | PHW-TS-0074 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU124
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0014 | PHW-BS-0014 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU125
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0075 | PHW-TS-0075 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU126
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0076 | PHW-TS-0076 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU127
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0077 | PHW-TS-0077 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU128
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0015 | PHW-BS-0015 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU129
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0078 | PHW-TS-0078 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU130
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0079 | PHW-TS-0079 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU131
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0080 | PHW-TS-0080 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU133
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0081 | PHW-TS-0081 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU134
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0016 | PHW-BS-0016 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU135
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0082 | PHW-TS-0082 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU136
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0083 | PHW-TS-0083 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU138
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0084 | PHW-TS-0084 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU139
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0085 | PHW-TS-0085 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU140
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0017 | PHW-BS-0017 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU141
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0086 | PHW-TS-0086 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU142
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0087 | PHW-TS-0087 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU143
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0088 | PHW-TS-0088 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU145
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0018 | PHW-BS-0018 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU146
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0089 | PHW-TS-0089 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU147
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0090 | PHW-TS-0090 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU148
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0091 | PHW-TS-0091 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU149
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0019 | PHW-BS-0019 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU150
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0092 | PHW-TS-0092 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU151
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0093 | PHW-TS-0093 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU153
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0094 | PHW-TS-0094 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU154
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0020 | PHW-BS-0020 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU155
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0095 | PHW-TS-0095 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU167
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0096 | PHW-TS-0096 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU168
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0097 | PHW-TS-0097 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU169
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0098 | PHW-TS-0098 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU170
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0099 | PHW-TS-0099 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU172
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0021 | PHW-BS-0021 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU173
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0100 | PHW-TS-0100 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU174
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0101 | PHW-TS-0101 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU185
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0102 | PHW-TS-0102 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU186
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0103 | PHW-TS-0103 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU188
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0104 | PHW-TS-0104 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU189
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0105 | PHW-TS-0105 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU190
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0106 | PHW-TS-0106 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU195
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0107 | PHW-TS-0107 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU196
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0108 | PHW-TS-0108 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU197
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0109 | PHW-TS-0109 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU198
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0110 | PHW-TS-0110 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU199
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0111 | PHW-TS-0111 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU200
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0112 | PHW-TS-0112 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU201
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0113 | PHW-TS-0113 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU202
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0114 | PHW-TS-0114 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU203
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0115 | PHW-TS-0115 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU205
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0116 | PHW-TS-0116 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU206
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0117 | PHW-TS-0117 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU207
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0118 | PHW-TS-0118 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU208
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0119 | PHW-TS-0119 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU209
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0120 | PHW-TS-0120 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU210
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0121 | PHW-TS-0121 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU211
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0122 | PHW-TS-0122 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU212
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0123 | PHW-TS-0123 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU213
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0124 | PHW-TS-0124 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU214
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0125 | PHW-TS-0125 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU215
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0126 | PHW-TS-0126 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU216
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0127 | PHW-TS-0127 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU217
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0128 | PHW-TS-0128 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU218
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0022 | PHW-BS-0022 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU219
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0129 | PHW-TS-0129 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU220
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0130 | PHW-TS-0130 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU221
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0131 | PHW-TS-0131 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU222
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0023 | PHW-BS-0023 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU223
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0132 | PHW-TS-0132 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU224
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0133 | PHW-TS-0133 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU226
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0134 | PHW-TS-0134 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU227
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0135 | PHW-TS-0135 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU235
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0136 | PHW-TS-0136 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU236
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0024 | PHW-BS-0024 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU237
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0137 | PHW-TS-0137 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU238
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0138 | PHW-TS-0138 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU239
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0139 | PHW-TS-0139 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU241
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0140 | PHW-TS-0140 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU243
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0141 | PHW-TS-0141 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU266
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0142 | PHW-TS-0142 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU267
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0143 | PHW-TS-0143 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU269
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0144 | PHW-TS-0144 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU270
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0145 | PHW-TS-0145 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU271
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0146 | PHW-TS-0146 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU272
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0147 | PHW-TS-0147 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU273
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0148 | PHW-TS-0148 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU274
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0149 | PHW-TS-0149 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU275
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0150 | PHW-TS-0150 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU276
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0151 | PHW-TS-0151 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU277
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0152 | PHW-TS-0152 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU278
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0153 | PHW-TS-0153 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU279
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0154 | PHW-TS-0154 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU280
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0155 | PHW-TS-0155 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU281
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0156 | PHW-TS-0156 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU282
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0157 | PHW-TS-0157 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU283
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0158 | PHW-TS-0158 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU284
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0159 | PHW-TS-0159 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU286
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0160 | PHW-TS-0160 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU288
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0161 | PHW-TS-0161 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU290
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0162 | PHW-TS-0162 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU293
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0163 | PHW-TS-0163 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU294
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0164 | PHW-TS-0164 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU295
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0165 | PHW-TS-0165 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU296
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0166 | PHW-TS-0166 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU298
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0167 | PHW-TS-0167 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU299
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0168 | PHW-TS-0168 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU300
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0169 | PHW-TS-0169 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU301
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0170 | PHW-TS-0170 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU302
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0171 | PHW-TS-0171 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU311
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0172 | PHW-TS-0172 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU313
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0173 | PHW-TS-0173 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU314
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0174 | PHW-TS-0174 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU341
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0175 | PHW-TS-0175 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU342
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0176 | PHW-TS-0176 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU343
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0177 | PHW-TS-0177 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU344
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0178 | PHW-TS-0178 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU345
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0179 | PHW-TS-0179 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU347
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0180 | PHW-TS-0180 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU348
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0181 | PHW-TS-0181 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU349
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0182 | PHW-TS-0182 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU350
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0183 | PHW-TS-0183 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU351
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0184 | PHW-TS-0184 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU352
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0185 | PHW-TS-0185 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU353
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0186 | PHW-TS-0186 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU354
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0187 | PHW-TS-0187 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU355
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0188 | PHW-TS-0188 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU356
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0189 | PHW-TS-0189 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU357
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0190 | PHW-TS-0190 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU358
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0191 | PHW-TS-0191 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU359
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0192 | PHW-TS-0192 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU360
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0193 | PHW-TS-0193 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU361
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0194 | PHW-TS-0194 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU362
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0195 | PHW-TS-0195 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU363
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0196 | PHW-TS-0196 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU364
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0197 | PHW-TS-0197 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU367
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0198 | PHW-TS-0198 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU368
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0199 | PHW-TS-0199 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU386
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0200 | PHW-TS-0200 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU387
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0201 | PHW-TS-0201 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU396
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0202 | PHW-TS-0202 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU402
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0203 | PHW-TS-0203 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU403
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0204 | PHW-TS-0204 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU404
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0205 | PHW-TS-0205 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU417
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0206 | PHW-TS-0206 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU418
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0207 | PHW-TS-0207 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU425
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0208 | PHW-TS-0208 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU427
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0209 | PHW-TS-0209 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU428
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0210 | PHW-TS-0210 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU429
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0211 | PHW-TS-0211 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU430
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0212 | PHW-TS-0212 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU431
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0213 | PHW-TS-0213 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU433
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0214 | PHW-TS-0214 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU434
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0215 | PHW-TS-0215 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU435
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0216 | PHW-TS-0216 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU437
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0217 | PHW-TS-0217 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU438
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0218 | PHW-TS-0218 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU439
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0219 | PHW-TS-0219 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU440
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0220 | PHW-TS-0220 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU441
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0221 | PHW-TS-0221 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU442
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0222 | PHW-TS-0222 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU443
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0223 | PHW-TS-0223 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU445
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0224 | PHW-TS-0224 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU446
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0225 | PHW-TS-0225 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU447
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0226 | PHW-TS-0226 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU448
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0227 | PHW-TS-0227 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU451
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0228 | PHW-TS-0228 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU452
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0229 | PHW-TS-0229 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU453
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0230 | PHW-TS-0230 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU454
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0231 | PHW-TS-0231 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU455
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0232 | PHW-TS-0232 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU456
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0233 | PHW-TS-0233 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU457
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0234 | PHW-TS-0234 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU458
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0235 | PHW-TS-0235 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU459
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0236 | PHW-TS-0236 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU460
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0237 | PHW-TS-0237 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU461
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0238 | PHW-TS-0238 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU465
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0239 | PHW-TS-0239 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU466
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0240 | PHW-TS-0240 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU467
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0241 | PHW-TS-0241 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU468
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0242 | PHW-TS-0242 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU469
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0243 | PHW-TS-0243 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU470
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0244 | PHW-TS-0244 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU471
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0245 | PHW-TS-0245 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU472
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0246 | PHW-TS-0246 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU473
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0247 | PHW-TS-0247 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU474
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0248 | PHW-TS-0248 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU476
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0249 | PHW-TS-0249 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU477
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0250 | PHW-TS-0250 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU478
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0251 | PHW-TS-0251 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU479
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0252 | PHW-TS-0252 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU480
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0253 | PHW-TS-0253 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU482
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0025 | PHW-BS-0025 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU483
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0254 | PHW-TS-0254 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU484
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0026 | PHW-BS-0026 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU486
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0027 | PHW-BS-0027 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU487
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0028 | PHW-BS-0028 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU488
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0029 | PHW-BS-0029 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU489
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0030 | PHW-BS-0030 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU490
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0031 | PHW-BS-0031 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU491
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0032 | PHW-BS-0032 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU492
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0033 | PHW-BS-0033 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU493
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0255 | PHW-TS-0255 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU495
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0256 | PHW-TS-0256 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU496
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0257 | PHW-TS-0257 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU497
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0258 | PHW-TS-0258 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU498
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0259 | PHW-TS-0259 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU499
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0260 | PHW-TS-0260 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU500
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0261 | PHW-TS-0261 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU501
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0262 | PHW-TS-0262 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU502
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0263 | PHW-TS-0263 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU503
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0264 | PHW-TS-0264 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU504
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0265 | PHW-TS-0265 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU506
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0266 | PHW-TS-0266 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU507
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0267 | PHW-TS-0267 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU509
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0268 | PHW-TS-0268 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU511
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0269 | PHW-TS-0269 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU512
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0034 | PHW-BS-0034 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU513
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0270 | PHW-TS-0270 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU514
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0271 | PHW-TS-0271 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU515
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0272 | PHW-TS-0272 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU516
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0273 | PHW-TS-0273 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU517
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0035 | PHW-BS-0035 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU518
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0274 | PHW-TS-0274 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU519
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0275 | PHW-TS-0275 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU520
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0276 | PHW-TS-0276 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU521
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0277 | PHW-TS-0277 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU523
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0278 | PHW-TS-0278 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU524
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0279 | PHW-TS-0279 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU525
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0280 | PHW-TS-0280 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU526
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0281 | PHW-TS-0281 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU528
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0282 | PHW-TS-0282 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU529
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0283 | PHW-TS-0283 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU530
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0284 | PHW-TS-0284 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU531
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0285 | PHW-TS-0285 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU532
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0286 | PHW-TS-0286 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU533
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0287 | PHW-TS-0287 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU534
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0288 | PHW-TS-0288 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU535
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0289 | PHW-TS-0289 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU536
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0290 | PHW-TS-0290 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU537
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0291 | PHW-TS-0291 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU538
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0292 | PHW-TS-0292 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU539
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0036 | PHW-BS-0036 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU540
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0293 | PHW-TS-0293 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU541
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0294 | PHW-TS-0294 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU542
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0037 | PHW-BS-0037 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU543
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0295 | PHW-TS-0295 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU544
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0296 | PHW-TS-0296 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU545
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0038 | PHW-BS-0038 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU546
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0297 | PHW-TS-0297 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU547
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0298 | PHW-TS-0298 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU548
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0299 | PHW-TS-0299 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU550
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0300 | PHW-TS-0300 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU551
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0301 | PHW-TS-0301 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU555
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0302 | PHW-TS-0302 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU557
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0303 | PHW-TS-0303 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU558
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0304 | PHW-TS-0304 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU560
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0305 | PHW-TS-0305 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU562
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0306 | PHW-TS-0306 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU563
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0307 | PHW-TS-0307 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU564
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0308 | PHW-TS-0308 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU565
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0309 | PHW-TS-0309 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU566
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0310 | PHW-TS-0310 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU567
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0311 | PHW-TS-0311 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU569
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0312 | PHW-TS-0312 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU570
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0313 | PHW-TS-0313 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU571
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0314 | PHW-TS-0314 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU572
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0315 | PHW-TS-0315 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU573
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0316 | PHW-TS-0316 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU574
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0317 | PHW-TS-0317 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU575
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0318 | PHW-TS-0318 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU576
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0319 | PHW-TS-0319 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU577
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0320 | PHW-TS-0320 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU578
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0321 | PHW-TS-0321 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU581
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0322 | PHW-TS-0322 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU583
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0323 | PHW-TS-0323 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU584
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0324 | PHW-TS-0324 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU585
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0039 | PHW-BS-0039 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU586
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0325 | PHW-TS-0325 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU587
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0326 | PHW-TS-0326 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU588
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0327 | PHW-TS-0327 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU589
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0328 | PHW-TS-0328 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU590
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0040 | PHW-BS-0040 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU591
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0329 | PHW-TS-0329 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU597
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0330 | PHW-TS-0330 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU598
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0331 | PHW-TS-0331 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU599
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0332 | PHW-TS-0332 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU608
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0333 | PHW-TS-0333 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU609
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0334 | PHW-TS-0334 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU610
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0335 | PHW-TS-0335 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU611
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0336 | PHW-TS-0336 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU634
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0337 | PHW-TS-0337 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU635
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0338 | PHW-TS-0338 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU637
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0339 | PHW-TS-0339 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU639
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0340 | PHW-TS-0340 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU643
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0341 | PHW-TS-0341 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU644
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0342 | PHW-TS-0342 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU645
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0343 | PHW-TS-0343 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU646
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0344 | PHW-TS-0344 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU648
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0345 | PHW-TS-0345 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU651
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0346 | PHW-TS-0346 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU653
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0347 | PHW-TS-0347 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU654
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0348 | PHW-TS-0348 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU655
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0349 | PHW-TS-0349 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU657
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0350 | PHW-TS-0350 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU658
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0351 | PHW-TS-0351 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU659
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0352 | PHW-TS-0352 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU661
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0353 | PHW-TS-0353 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU664
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0354 | PHW-TS-0354 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU665
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0355 | PHW-TS-0355 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU672
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0356 | PHW-TS-0356 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU673
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0357 | PHW-TS-0357 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU675
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0358 | PHW-TS-0358 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU679
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0359 | PHW-TS-0359 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU680
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0360 | PHW-TS-0360 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU683
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0361 | PHW-TS-0361 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU684
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0362 | PHW-TS-0362 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU685
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0363 | PHW-TS-0363 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU686
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0364 | PHW-TS-0364 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU687
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0365 | PHW-TS-0365 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU688
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0366 | PHW-TS-0366 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU690
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0367 | PHW-TS-0367 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU691
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0368 | PHW-TS-0368 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU692
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0369 | PHW-TS-0369 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU693
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0370 | PHW-TS-0370 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU702
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0371 | PHW-TS-0371 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU704
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0372 | PHW-TS-0372 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU706
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0373 | PHW-TS-0373 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU707
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0374 | PHW-TS-0374 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU709
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0375 | PHW-TS-0375 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU710
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0376 | PHW-TS-0376 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU711
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0377 | PHW-TS-0377 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU716
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0378 | PHW-TS-0378 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU717
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0379 | PHW-TS-0379 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU720
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0380 | PHW-TS-0380 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU722
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0381 | PHW-TS-0381 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU723
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0382 | PHW-TS-0382 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU735
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0383 | PHW-TS-0383 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU762
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0384 | PHW-TS-0384 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU763
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0385 | PHW-TS-0385 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU764
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0386 | PHW-TS-0386 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU774
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0387 | PHW-TS-0387 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU775
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0388 | PHW-TS-0388 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU776
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0389 | PHW-TS-0389 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU788
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0390 | PHW-TS-0390 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU789
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0391 | PHW-TS-0391 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU796
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0392 | PHW-TS-0392 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU804
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0393 | PHW-TS-0393 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU806
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0394 | PHW-TS-0394 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU886
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0395 | PHW-TS-0395 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU888
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0396 | PHW-TS-0396 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU889
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0397 | PHW-TS-0397 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU890
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0398 | PHW-TS-0398 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU891
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0399 | PHW-TS-0399 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU892
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0400 | PHW-TS-0400 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU893
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0401 | PHW-TS-0401 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU894
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0402 | PHW-TS-0402 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU895
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0403 | PHW-TS-0403 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU896
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0404 | PHW-TS-0404 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU898
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0405 | PHW-TS-0405 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU899
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-TS-0406 | PHW-TS-0406 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU901
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0041 | PHW-BS-0041 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU907
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0042 | PHW-BS-0042 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU908
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0043 | PHW-BS-0043 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU909
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0044 | PHW-BS-0044 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU910
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0045 | PHW-BS-0045 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU911
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PHW-BS-0046 | PHW-BS-0046 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU912
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0001 | PWG-TS-0001 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU918
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-BS-0001 | PWG-BS-0001 | Unit Rate ($) |  | 20,507.00 per each | Master Register!BU921
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0002 | PWG-TS-0002 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU923
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0003 | PWG-TS-0003 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU956
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0004 | PWG-TS-0004 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU986
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0005 | PWG-TS-0005 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU987
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0006 | PWG-TS-0006 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1049
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0007 | PWG-TS-0007 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1055
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0008 | PWG-TS-0008 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1164
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0009 | PWG-TS-0009 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1165
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0010 | PWG-TS-0010 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1177
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0011 | PWG-TS-0011 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1178
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0012 | PWG-TS-0012 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1179
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0013 | PWG-TS-0013 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1187
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0014 | PWG-TS-0014 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1188
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0015 | PWG-TS-0015 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1189
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0016 | PWG-TS-0016 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1200
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0017 | PWG-TS-0017 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1201
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0018 | PWG-TS-0018 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1202
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0019 | PWG-TS-0019 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1204
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0020 | PWG-TS-0020 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1205
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0021 | PWG-TS-0021 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1206
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0022 | PWG-TS-0022 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1246
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0023 | PWG-TS-0023 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1248
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0024 | PWG-TS-0024 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1249
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0025 | PWG-TS-0025 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1270
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0026 | PWG-TS-0026 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1271
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0027 | PWG-TS-0027 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1280
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0028 | PWG-TS-0028 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1281
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0029 | PWG-TS-0029 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1282
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0030 | PWG-TS-0030 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1283
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0031 | PWG-TS-0031 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1284
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0032 | PWG-TS-0032 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1337
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0033 | PWG-TS-0033 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1396
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0034 | PWG-TS-0034 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1397
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0035 | PWG-TS-0035 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1399
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | PWG-TS-0036 | PWG-TS-0036 | Unit Rate ($) |  | 1,112.50 per each | Master Register!BU1400
2026-08-24 14:36 | J. Krasnoff-Hnatjuk | (control) |  | Current revision | Rev 3 | Rev 4 | Document Control!C10
27/08/2026 08:47 | Jerry | PHW-TT-0001 |  | Trench Complete (m) |  | 327.039 | Cost Tracker - Linear!K9
27/08/2026 08:47 | Jerry | PHW-TT-0001 |  | Pipe Laid (m) |  | 150 | Cost Tracker - Linear!Q9
27/08/2026 08:47 | Jerry | PHW-TT-0001 |  | Pipe Type |  | DICL | Cost Tracker - Linear!N9
27/08/2026 08:47 | Jerry | PHW-TT-0001 |  | As At Date |  | 46261 | Cost Tracker - Linear!X9
27/08/2026 08:47 | Jerry | PHW-TT-0001 |  | Updated By |  | Jerry | Cost Tracker - Linear!Y9
27/08/2026 08:47 | Jerry | PHW-TT-0002 |  | Trench Complete (m) |  | 77.823 | Cost Tracker - Linear!K10
27/08/2026 08:47 | Jerry | PHW-TT-0002 |  | As At Date |  | 46261 | Cost Tracker - Linear!X10
27/08/2026 08:47 | Jerry | PHW-TT-0002 |  | Updated By |  | Jerry | Cost Tracker - Linear!Y10
27/08/2026 08:47 | Jerry | PHW-TT-0003 |  | Trench Complete (m) |  | 0.1379999999999768 | Cost Tracker - Linear!K11
27/08/2026 08:47 | Jerry | PHW-TT-0003 |  | As At Date |  | 46261 | Cost Tracker - Linear!X11
27/08/2026 08:47 | Jerry | PHW-TT-0003 |  | Updated By |  | Jerry | Cost Tracker - Linear!Y11
27/08/2026 08:47 | Jerry | PHW-VG-0001 |  | Complete |  | Yes | Master Register!BR3
27/08/2026 08:47 | Jerry | PHW-VG-0001 |  | Completion Date |  | 46261 | Master Register!BS3
27/08/2026 08:47 | Jerry | PHW-TB-001 |  | Complete |  | Yes | Master Register!BR5
27/08/2026 08:47 | Jerry | PHW-TB-001 |  | Completion Date |  | 46261 | Master Register!BS5
27/08/2026 08:47 | Jerry | PHW-VG-0002 |  | Complete |  | Yes | Master Register!BR8
27/08/2026 08:47 | Jerry | PHW-VG-0002 |  | Completion Date |  | 46261 | Master Register!BS8
27/08/2026 08:47 | Jerry | PHW-TS-0001 |  | Complete |  | Yes | Master Register!BR9
27/08/2026 08:47 | Jerry | PHW-TS-0001 |  | Completion Date |  | 46261 | Master Register!BS9
27/08/2026 08:47 | Jerry | PHW-TS-0002 |  | Complete |  | Yes | Master Register!BR10
27/08/2026 08:47 | Jerry | PHW-TS-0002 |  | Completion Date |  | 46261 | Master Register!BS10
27/08/2026 08:47 | Jerry | PHW-TS-0003 |  | Complete |  | Yes | Master Register!BR11
27/08/2026 08:47 | Jerry | PHW-TS-0003 |  | Completion Date |  | 46261 | Master Register!BS11
27/08/2026 08:47 | Jerry | PHW-TS-0004 |  | Complete |  | Yes | Master Register!BR12
27/08/2026 08:47 | Jerry | PHW-TS-0004 |  | Completion Date |  | 46261 | Master Register!BS12
27/08/2026 08:47 | Jerry | PHW-TS-0005 |  | Complete |  | Yes | Master Register!BR13
27/08/2026 08:47 | Jerry | PHW-TS-0005 |  | Completion Date |  | 46261 | Master Register!BS13
27/08/2026 08:47 | Jerry | PHW-TS-0006 |  | Complete |  | Yes | Master Register!BR14
27/08/2026 08:47 | Jerry | PHW-TS-0006 |  | Completion Date |  | 46261 | Master Register!BS14
27/08/2026 08:47 | Jerry | PHW-TS-0007 |  | Complete |  | Yes | Master Register!BR15
27/08/2026 08:47 | Jerry | PHW-TS-0007 |  | Completion Date |  | 46261 | Master Register!BS15
27/08/2026 08:47 | Jerry | PHW-VG-0003 |  | Complete |  | Yes | Master Register!BR16
27/08/2026 08:47 | Jerry | PHW-VG-0003 |  | Completion Date |  | 46261 | Master Register!BS16
27/08/2026 08:47 | Jerry | PHW-TS-0008 |  | Complete |  | Yes | Master Register!BR17
27/08/2026 08:47 | Jerry | PHW-TS-0008 |  | Completion Date |  | 46261 | Master Register!BS17
27/08/2026 08:47 | Jerry | PHW-TS-0009 |  | Complete |  | Yes | Master Register!BR18
27/08/2026 08:47 | Jerry | PHW-TS-0009 |  | Completion Date |  | 46261 | Master Register!BS18
27/08/2026 08:47 | Jerry | PHW-TS-0010 |  | Complete |  | Yes | Master Register!BR19
27/08/2026 08:47 | Jerry | PHW-TS-0010 |  | Completion Date |  | 46261 | Master Register!BS19
27/08/2026 08:47 | Jerry | PHW-TS-0011 |  | Complete |  | Yes | Master Register!BR20
27/08/2026 08:47 | Jerry | PHW-TS-0011 |  | Completion Date |  | 46261 | Master Register!BS20
27/08/2026 08:47 | Jerry | PHW-TS-0012 |  | Complete |  | Yes | Master Register!BR21
27/08/2026 08:47 | Jerry | PHW-TS-0012 |  | Completion Date |  | 46261 | Master Register!BS21
27/08/2026 08:47 | Jerry | PHW-TS-0013 |  | Complete |  | Yes | Master Register!BR22
27/08/2026 08:47 | Jerry | PHW-TS-0013 |  | Completion Date |  | 46261 | Master Register!BS22
27/08/2026 08:47 | Jerry | PHW-TS-0014 |  | Complete |  | Yes | Master Register!BR23
27/08/2026 08:47 | Jerry | PHW-TS-0014 |  | Completion Date |  | 46261 | Master Register!BS23
27/08/2026 08:47 | Jerry | PHW-TS-0015 |  | Complete |  | Yes | Master Register!BR24
27/08/2026 08:47 | Jerry | PHW-TS-0015 |  | Completion Date |  | 46261 | Master Register!BS24
27/08/2026 08:47 | Jerry | PHW-TS-0016 |  | Complete |  | Yes | Master Register!BR25
27/08/2026 08:47 | Jerry | PHW-TS-0016 |  | Completion Date |  | 46261 | Master Register!BS25
27/08/2026 08:47 | Jerry | PHW-TS-0017 |  | Complete |  | Yes | Master Register!BR26
27/08/2026 08:47 | Jerry | PHW-TS-0017 |  | Completion Date |  | 46261 | Master Register!BS26
27/08/2026 08:47 | Jerry | PHW-TS-0018 |  | Complete |  | Yes | Master Register!BR27
27/08/2026 08:47 | Jerry | PHW-TS-0018 |  | Completion Date |  | 46261 | Master Register!BS27
27/08/2026 08:47 | Jerry | PHW-VG-0004 |  | Complete |  | Yes | Master Register!BR30
27/08/2026 08:47 | Jerry | PHW-VG-0004 |  | Completion Date |  | 46261 | Master Register!BS30
27/08/2026 08:47 | Jerry | PHW-VG-0005 |  | Complete |  | Yes | Master Register!BR33
27/08/2026 08:47 | Jerry | PHW-VG-0005 |  | Completion Date |  | 46261 | Master Register!BS33
27/08/2026 08:48 | Jerry | PHW-TT-0003 |  | Trench Complete (m) | 0.1379999999999768 | 21.528 | Cost Tracker - Linear!K11
27/08/2026 08:48 | Jerry | PHW-TT-0004 |  | Trench Complete (m) |  | 78.61000000000001 | Cost Tracker - Linear!K12
27/08/2026 08:48 | Jerry | PHW-TT-0004 |  | As At Date |  | 46261 | Cost Tracker - Linear!X12
27/08/2026 08:48 | Jerry | PHW-TT-0004 |  | Updated By |  | Jerry | Cost Tracker - Linear!Y12
27/08/2026 08:48 | Jerry | PHW-TS-0019 |  | Complete |  | Yes | Master Register!BR36
27/08/2026 08:48 | Jerry | PHW-TS-0019 |  | Completion Date |  | 46261 | Master Register!BS36
27/08/2026 08:48 | Jerry | PHW-TS-0020 |  | Complete |  | Yes | Master Register!BR38
27/08/2026 08:48 | Jerry | PHW-TS-0020 |  | Completion Date |  | 46261 | Master Register!BS38
27/08/2026 08:48 | Jerry | PHW-TS-0021 |  | Complete |  | Yes | Master Register!BR39
27/08/2026 08:48 | Jerry | PHW-TS-0021 |  | Completion Date |  | 46261 | Master Register!BS39
27/08/2026 08:48 | Jerry | PHW-TS-0022 |  | Complete |  | Yes | Master Register!BR40
27/08/2026 08:48 | Jerry | PHW-TS-0022 |  | Completion Date |  | 46261 | Master Register!BS40
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-001 |  | Utility Description (thrust block type) | Type 7 | Type 5 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-003 |  | Utility Description (thrust block type) | Type 6 | Type 7 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-005 |  | Utility Description (thrust block type) | Type 3 | Type 6 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-007 |  | Utility Description (thrust block type) | Type 1 | Type 3 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-009 |  | Utility Description (thrust block type) | Type 8 | Type 1 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-010 |  | Utility Description (thrust block type) | Type 10 | Type 8 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-012 |  | Utility Description (thrust block type) | Type 1 | Type 10 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-013 |  | Utility Description (thrust block type) | Type 2 | Type 1 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-014 |  | Utility Description (thrust block type) | Type 3 | Type 2 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-016 |  | Utility Description (thrust block type) | Type 2 | Type 3 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-018 |  | Utility Description (thrust block type) | Type 6 | Type 2 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-019 |  | Utility Description (thrust block type) | Type 5 | Type 6 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-020 |  | Utility Description (thrust block type) | Type 4 | Type 5 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-021 |  | Utility Description (thrust block type) | Type 7 | Type 4 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-022 |  | Utility Description (thrust block type) | Type 4 | Type 7 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-023 |  | Utility Description (thrust block type) | Type 5 | Type 4 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-024 |  | Utility Description (thrust block type) | Type 6 | Type 5 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-025 |  | Utility Description (thrust block type) | Type 3 | Type 6 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-026 |  | Utility Description (thrust block type) | Type 4 | Type 3 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-027 |  | Utility Description (thrust block type) | Type 5 | Type 4 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-028 |  | Utility Description (thrust block type) | Type 9 | Type 5 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-029 |  | Utility Description (thrust block type) | Type 5 | Type 9 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-030 |  | Utility Description (thrust block type) | Type 6 | Type 5 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-031 |  | Utility Description (thrust block type) | Type 7 | Type 6 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-032 |  | Utility Description (thrust block type) | Type 4 | Type 7 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-033 |  | Utility Description (thrust block type) | Type 9 | Type 4 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-034 |  | Utility Description (thrust block type) | Type 5 | Type 9 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-035 |  | Utility Description (thrust block type) | Type 7 | Type 5 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-036 |  | Utility Description (thrust block type) | Type 5 | Type 7 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-037 |  | Utility Description (thrust block type) | Type 7 | Type 5 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-038 |  | Utility Description (thrust block type) | Type 9 | Type 7 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-039 |  | Utility Description (thrust block type) | Type 7 | Type 9 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-040 |  | Utility Description (thrust block type) | Type 9 | Type 7 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-041 |  | Utility Description (thrust block type) | Type 7 | Type 9 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-042 |  | Utility Description (thrust block type) | Type 5 | Type 7 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-043 |  | Utility Description (thrust block type) | Type 7 | Type 5 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-046 |  | Utility Description (thrust block type) | Type 4 | Type 7 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-047 |  | Utility Description (thrust block type) | Type 7 | Type 4 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-048 |  | Utility Description (thrust block type) | Type 5 | Type 7 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-049 |  | Utility Description (thrust block type) | Type 7 | Type 5 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-050 |  | Utility Description (thrust block type) | Type 5 | Type 7 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-052 |  | Utility Description (thrust block type) | Type 7 | Type 5 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-054 |  | Utility Description (thrust block type) | Type 4 | Type 7 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-055 |  | Utility Description (thrust block type) | Type 10 | Type 4 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-056 |  | Utility Description (thrust block type) | Type 6 | Type 10 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-057 |  | Utility Description (thrust block type) | Type 4 | Type 6 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-060 |  | Utility Description (thrust block type) | Type 6 | Type 4 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-061 |  | Utility Description (thrust block type) | Type 4 | Type 6 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-062 |  | Utility Description (thrust block type) | Type 1 | Type 4 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-063 |  | Utility Description (thrust block type) | Type 3 | Type 1 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-064 |  | Utility Description (thrust block type) | Type 6 | Type 3 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-065 |  | Utility Description (thrust block type) | Type 4 | Type 6 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-068 |  | Utility Description (thrust block type) | Type 7 | Type 4 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-069 |  | Utility Description (thrust block type) | Type 1 | Type 7 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-071 |  | Utility Description (thrust block type) | Type 10 | Type 1 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-072 |  | Utility Description (thrust block type) | Type 1 | Type 10 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-074 |  | Utility Description (thrust block type) | Type 4 | Type 1 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PHW-TB-076 |  | Utility Description (thrust block type) | Type 11 | Type 4 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PWG-TB-001 |  | Utility Description (thrust block type) | Type 9 | Type 11 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PWG-TB-002 |  | Utility Description (thrust block type) | Type 5 | Type 9 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PWG-TB-003 |  | Utility Description (thrust block type) | Type 7 | Type 5 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PWG-TB-004 |  | Utility Description (thrust block type) | Type 6 | Type 7 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PWG-TB-006 |  | Utility Description (thrust block type) | Type 7 | Type 6 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PWG-TB-009 |  | Utility Description (thrust block type) | Type 5 | Type 7 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PWG-TB-011 |  | Utility Description (thrust block type) | Type 7 | Type 5 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PWG-TB-013 |  | Utility Description (thrust block type) | Type 5 | Type 7 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PWG-TB-014 |  | Utility Description (thrust block type) | Type 6 | Type 5 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PWG-TB-016 |  | Utility Description (thrust block type) | Type 7 | Type 6 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PWG-TB-017 |  | Utility Description (thrust block type) | Type 9 | Type 7 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PWG-TB-018 |  | Utility Description (thrust block type) | Type 11 | Type 9 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PWG-TB-020 |  | Utility Description (thrust block type) | Type 7 | Type 11 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
27/08/2026 09:00 | J. Krasnoff-Hnatjuk | PWG-TB-022 |  | Utility Description (thrust block type) | Type 6 | Type 7 | From thrust block index S-DWG-PTW-115/116/117/118 Rev 2/1, Issued for Construction
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | (schema) |  | new column |  | Bend Rate Class | Master Register!CJ1
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | (schema) |  | new column |  | Completion Driver | Master Register!CK1
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | (schema) |  | new column |  | Front Chainage (m) | Master Register!CL1
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | (schema) |  | new column |  | Auto Complete | Master Register!CM1
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | (schema) |  | new column |  | Auto Complete As At | Master Register!CN1
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | (schema) |  | new sheet |  | Progress Control | Progress Control
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | (schema) |  | new sheet |  | Cost Tracker - Pipe | Cost Tracker - Pipe
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | (schema) |  | new rate table |  | Rate Library Table 5 — Bends (10 lines) | Rate Library!B170
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | (schema) |  | new rate table |  | Rate Library Table 6 — Valves (20 lines) | Rate Library!B190
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | (schema) |  | new column |  | Trench Front (m) | Cost Tracker - Linear!AB8
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | (fix) |  | lookup range | Master Register rows 2:1638 | Master Register rows 2:2600 | Cost Tracker - Linear, Cost Dashboard, Thrust Block Costing — 2,973 formulas
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | (fix) |  | lookup range | Master Register rows 2:1451 | Master Register rows 2:2600 | Master Register!K — Drawing (Start), 690 array formulas, cleared 223 no-match errors
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-001 |  | Fitting Material |  | DICL | Master Register!CA7 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-001 |  | Fitting DN (mm) |  | 600 | Master Register!CB7 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-001 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU7:BW7
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-001 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU12:BW12
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-IV-001 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU109:BW109
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-002 |  | Fitting Material |  | DICL | Master Register!CA112 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-002 |  | Fitting DN (mm) |  | 600 | Master Register!CB112 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-002 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU112:BW112
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-002 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU113:BW113
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-003 |  | Fitting Material |  | DICL | Master Register!CA178 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-003 |  | Fitting DN (mm) |  | 600 | Master Register!CB178 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-003 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU178:BW178
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-004 |  | Fitting Material |  | DICL | Master Register!CA211 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-004 |  | Fitting DN (mm) |  | 600 | Master Register!CB211 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-004 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU211:BW211
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-SCV-001 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU213:BW213
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-005 |  | Fitting Material |  | DICL | Master Register!CA215 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-005 |  | Fitting DN (mm) |  | 600 | Master Register!CB215 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-005 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU215:BW215
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-003 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU225:BW225
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-006 |  | Fitting Material |  | DICL | Master Register!CA227 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-006 |  | Fitting DN (mm) |  | 600 | Master Register!CB227 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-006 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU227:BW227
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-007 |  | Fitting Material |  | DICL | Master Register!CA231 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-007 |  | Fitting DN (mm) |  | 600 | Master Register!CB231 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-007 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU231:BW231
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-008 |  | Fitting Material |  | DICL | Master Register!CA264 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-008 |  | Fitting DN (mm) |  | 600 | Master Register!CB264 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-008 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU264:BW264
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-SCV-002 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU268:BW268
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-004 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU269:BW269
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-009 |  | Fitting Material |  | MSCL | Master Register!CA272 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-009 |  | Fitting DN (mm) |  | 650 | Master Register!CB272 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-009 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU272:BW272
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-010 |  | Fitting Material |  | MSCL | Master Register!CA277 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-010 |  | Fitting DN (mm) |  | 650 | Master Register!CB277 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-010 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU277:BW277
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-011 |  | Fitting Material |  | MSCL | Master Register!CA278 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-011 |  | Fitting DN (mm) |  | 650 | Master Register!CB278 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-011 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU278:BW278
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-012 |  | Fitting Material |  | DICL | Master Register!CA287 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-012 |  | Fitting DN (mm) |  | 600 | Master Register!CB287 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-012 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU287:BW287
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-005 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU288:BW288
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-013 |  | Fitting Material |  | DICL | Master Register!CA296 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-013 |  | Fitting DN (mm) |  | 600 | Master Register!CB296 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-013 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU296:BW296
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-014 |  | Fitting Material |  | DICL | Master Register!CA298 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-014 |  | Fitting DN (mm) |  | 600 | Master Register!CB298 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-014 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU298:BW298
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-IV-002 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU302:BW302
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-006 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU303:BW303
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-015 |  | Fitting Material |  | DICL | Master Register!CA306 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-015 |  | Fitting DN (mm) |  | 600 | Master Register!CB306 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-015 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU306:BW306
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-016 |  | Fitting Material |  | MSCL | Master Register!CA310 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-016 |  | Fitting DN (mm) |  | 650 | Master Register!CB310 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-016 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU310:BW310
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-017 |  | Fitting Material |  | MSCL | Master Register!CA321 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-017 |  | Fitting DN (mm) |  | 650 | Master Register!CB321 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-017 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU321:BW321
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-IV-003 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU327:BW327
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-SCV-003 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU328:BW328
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-018 |  | Fitting Material |  | DICL | Master Register!CA349 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-018 |  | Fitting DN (mm) |  | 600 | Master Register!CB349 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-018 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU349:BW349
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-019 |  | Fitting Material |  | MSCL | Master Register!CA372 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-019 |  | Fitting DN (mm) |  | 650 | Master Register!CB372 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-019 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU372:BW372
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-020 |  | Fitting Material |  | DICL | Master Register!CA378 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-020 |  | Fitting DN (mm) |  | 600 | Master Register!CB378 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-020 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU378:BW378
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-007 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU384:BW384
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-021 |  | Fitting Material |  | DICL | Master Register!CA387 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-021 |  | Fitting DN (mm) |  | 600 | Master Register!CB387 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-021 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU387:BW387
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-022 |  | Fitting Material |  | DICL | Master Register!CA389 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-022 |  | Fitting DN (mm) |  | 600 | Master Register!CB389 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-022 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU389:BW389
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-SCV-004 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU391:BW391
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-023 |  | Fitting Material |  | MSCL | Master Register!CA401 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-023 |  | Fitting DN (mm) |  | 650 | Master Register!CB401 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-023 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU401:BW401
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-008 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU403:BW403
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-024 |  | Fitting Material |  | DICL | Master Register!CA412 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-024 |  | Fitting DN (mm) |  | 600 | Master Register!CB412 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-024 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU412:BW412
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-025 |  | Fitting Material |  | DICL | Master Register!CA445 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-025 |  | Fitting DN (mm) |  | 600 | Master Register!CB445 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-025 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU445:BW445
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-026 |  | Fitting Material |  | MSCL | Master Register!CA453 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-026 |  | Fitting DN (mm) |  | 650 | Master Register!CB453 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-026 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU453:BW453
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-027 |  | Fitting Material |  | DICL | Master Register!CA464 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-027 |  | Fitting DN (mm) |  | 600 | Master Register!CB464 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-027 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU464:BW464
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-SCV-005 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU465:BW465
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-009 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU469:BW469
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-028 |  | Fitting Material |  | DICL | Master Register!CA475 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-028 |  | Fitting DN (mm) |  | 600 | Master Register!CB475 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-028 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU475:BW475
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-029 |  | Fitting Material |  | DICL | Master Register!CA479 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-029 |  | Fitting DN (mm) |  | 600 | Master Register!CB479 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-029 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU479:BW479
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-030 |  | Fitting Material |  | DICL | Master Register!CA484 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-030 |  | Fitting DN (mm) |  | 600 | Master Register!CB484 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-030 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU484:BW484
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-010 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU496:BW496
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-031 |  | Fitting Material |  | DICL | Master Register!CA498 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-031 |  | Fitting DN (mm) |  | 600 | Master Register!CB498 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-031 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU498:BW498
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-032 |  | Fitting Material |  | DICL | Master Register!CA506 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-032 |  | Fitting DN (mm) |  | 600 | Master Register!CB506 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-032 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU506:BW506
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-033 |  | Fitting Material |  | DICL | Master Register!CA508 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-033 |  | Fitting DN (mm) |  | 600 | Master Register!CB508 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-033 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU508:BW508
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-SCV-006 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU520:BW520
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-034 |  | Fitting Material |  | DICL | Master Register!CA521 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-034 |  | Fitting DN (mm) |  | 600 | Master Register!CB521 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-034 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU521:BW521
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-011 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU524:BW524
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-SCV-007 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU527:BW527
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-035 |  | Fitting Material |  | MSCL | Master Register!CA532 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-035 |  | Fitting DN (mm) |  | 650 | Master Register!CB532 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-035 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU532:BW532
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-036 |  | Fitting Material |  | DICL | Master Register!CA541 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-036 |  | Fitting DN (mm) |  | 600 | Master Register!CB541 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-036 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU541:BW541
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-012 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU551:BW551
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-SCV -001 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU553:BW553
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-013 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU564:BW564
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-037 |  | Fitting Material |  | DICL | Master Register!CA566 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-037 |  | Fitting DN (mm) |  | 600 | Master Register!CB566 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-037 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU566:BW566
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-038 |  | Fitting Material |  | DICL | Master Register!CA573 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-038 |  | Fitting DN (mm) |  | 600 | Master Register!CB573 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-038 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU573:BW573
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-039 |  | Fitting Material |  | DICL | Master Register!CA589 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-039 |  | Fitting DN (mm) |  | 600 | Master Register!CB589 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-039 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU589:BW589
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-040 |  | Fitting Material |  | DICL | Master Register!CA602 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-040 |  | Fitting DN (mm) |  | 600 | Master Register!CB602 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-040 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU602:BW602
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-041 |  | Fitting Material |  | DICL | Master Register!CA609 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-041 |  | Fitting DN (mm) |  | 600 | Master Register!CB609 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-041 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU609:BW609
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-042 |  | Fitting Material |  | DICL | Master Register!CA635 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-042 |  | Fitting DN (mm) |  | 600 | Master Register!CB635 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-042 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU635:BW635
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-043 |  | Fitting Material |  | DICL | Master Register!CA641 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-043 |  | Fitting DN (mm) |  | 600 | Master Register!CB641 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-043 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU641:BW641
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-014 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU655:BW655
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-015 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU744:BW744
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-044 |  | Fitting Material |  | MSCL | Master Register!CA749 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-044 |  | Fitting DN (mm) |  | 650 | Master Register!CB749 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-044 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU749:BW749
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-SCV-008 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU753:BW753
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-016 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU757:BW757
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-IV-004 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU784:BW784
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-017 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU788:BW788
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-045 |  | Fitting Material |  | DICL | Master Register!CA790 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-045 |  | Fitting DN (mm) |  | 600 | Master Register!CB790 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-045 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU790:BW790
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-SCV-009 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU816:BW816
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-046 |  | Fitting Material |  | DICL | Master Register!CA827 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-046 |  | Fitting DN (mm) |  | 600 | Master Register!CB827 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-046 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU827:BW827
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-047 |  | Fitting Material |  | DICL | Master Register!CA837 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-047 |  | Fitting DN (mm) |  | 600 | Master Register!CB837 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-047 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU837:BW837
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-048 |  | Fitting Material |  | DICL | Master Register!CA839 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-048 |  | Fitting DN (mm) |  | 600 | Master Register!CB839 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-048 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU839:BW839
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-018 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU840:BW840
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-049 |  | Fitting Material |  | DICL | Master Register!CA845 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-049 |  | Fitting DN (mm) |  | 600 | Master Register!CB845 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-049 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU845:BW845
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-050 |  | Fitting Material |  | DICL | Master Register!CA861 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-050 |  | Fitting DN (mm) |  | 600 | Master Register!CB861 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-050 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU861:BW861
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-SCV-010 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU881:BW881
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-051 |  | Fitting Material |  | DICL | Master Register!CA901 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-051 |  | Fitting DN (mm) |  | 600 | Master Register!CB901 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-051 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU901:BW901
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-019 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU902:BW902
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-052 |  | Fitting Material |  | DICL | Master Register!CA904 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-052 |  | Fitting DN (mm) |  | 600 | Master Register!CB904 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-052 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU904:BW904
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-053 |  | Fitting Material |  | DICL | Master Register!CA906 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-053 |  | Fitting DN (mm) |  | 600 | Master Register!CB906 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-053 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU906:BW906
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-PIG-001 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU909:BW909
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-054 |  | Fitting Material |  | DICL | Master Register!CA915 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-054 |  | Fitting DN (mm) |  | 600 | Master Register!CB915 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-054 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU915:BW915
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-020 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU916:BW916
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-055 |  | Fitting Material |  | DICL | Master Register!CA919 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-055 |  | Fitting DN (mm) |  | 600 | Master Register!CB919 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-055 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU919:BW919
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-056 |  | Fitting Material |  | DICL | Master Register!CA922 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-056 |  | Fitting DN (mm) |  | 600 | Master Register!CB922 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-056 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU922:BW922
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-SCV-011 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU932:BW932
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-057 |  | Fitting Material |  | DICL | Master Register!CA934 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-057 |  | Fitting DN (mm) |  | 600 | Master Register!CB934 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-057 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU934:BW934
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-058 |  | Fitting Material |  | DICL | Master Register!CA936 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-058 |  | Fitting DN (mm) |  | 600 | Master Register!CB936 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-058 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU936:BW936
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-059 |  | Fitting Material |  | DICL | Master Register!CA939 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-059 |  | Fitting DN (mm) |  | 600 | Master Register!CB939 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-059 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU939:BW939
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-060 |  | Fitting Material |  | DICL | Master Register!CA947 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-060 |  | Fitting DN (mm) |  | 600 | Master Register!CB947 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-060 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU947:BW947
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-061 |  | Fitting Material |  | DICL | Master Register!CA950 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-061 |  | Fitting DN (mm) |  | 600 | Master Register!CB950 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-061 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU950:BW950
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-021 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU951:BW951
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-062 |  | Fitting Material |  | MSCL | Master Register!CA954 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-062 |  | Fitting DN (mm) |  | 650 | Master Register!CB954 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-062 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU954:BW954
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-063 |  | Fitting Material |  | MSCL | Master Register!CA968 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-063 |  | Fitting DN (mm) |  | 650 | Master Register!CB968 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-063 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU968:BW968
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-064 |  | Fitting Material |  | DICL | Master Register!CA975 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-064 |  | Fitting DN (mm) |  | 600 | Master Register!CB975 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-064 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU975:BW975
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-022 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU981:BW981
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-SCV-012 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1001:BW1001
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-065 |  | Fitting Material |  | DICL | Master Register!CA1007 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-065 |  | Fitting DN (mm) |  | 600 | Master Register!CB1007 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-065 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1007:BW1007
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-066 |  | Fitting Material |  | MSCL | Master Register!CA1008 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-066 |  | Fitting DN (mm) |  | 650 | Master Register!CB1008 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-066 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1008:BW1008
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-023 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1010:BW1010
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-067 |  | Fitting Material |  | MSCL | Master Register!CA1012 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-067 |  | Fitting DN (mm) |  | 650 | Master Register!CB1012 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-067 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1012:BW1012
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-068 |  | Fitting Material |  | MSCL | Master Register!CA1013 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-068 |  | Fitting DN (mm) |  | 650 | Master Register!CB1013 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-068 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1013:BW1013
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-069 |  | Fitting Material |  | MSCL | Master Register!CA1019 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-069 |  | Fitting DN (mm) |  | 650 | Master Register!CB1019 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-069 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1019:BW1019
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-024 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1021:BW1021
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-SCV-013 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1022:BW1022
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-070 |  | Fitting Material |  | MSCL | Master Register!CA1026 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-070 |  | Fitting DN (mm) |  | 650 | Master Register!CB1026 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-070 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1026:BW1026
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-025 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1031:BW1031
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-026 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1051:BW1051
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-SCV-014 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1056:BW1056
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-071 |  | Fitting Material |  | DICL | Master Register!CA1058 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-071 |  | Fitting DN (mm) |  | 600 | Master Register!CB1058 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-071 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1058:BW1058
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-072 |  | Fitting Material |  | DICL | Master Register!CA1062 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-072 |  | Fitting DN (mm) |  | 600 | Master Register!CB1062 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-072 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1062:BW1062
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-027 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1083:BW1083
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-073 |  | Fitting Material |  | DICL | Master Register!CA1097 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-073 |  | Fitting DN (mm) |  | 600 | Master Register!CB1097 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-073 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1097:BW1097
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-074 |  | Fitting Material |  | DICL | Master Register!CA1104 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-074 |  | Fitting DN (mm) |  | 600 | Master Register!CB1104 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-074 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1104:BW1104
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-075 |  | Fitting Material |  | DICL | Master Register!CA1108 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-075 |  | Fitting DN (mm) |  | 600 | Master Register!CB1108 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-075 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1108:BW1108
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-IV-005 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1114:BW1114
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-028 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1115:BW1115
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-076 |  | Fitting Material |  | MSCL | Master Register!CA1127 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-076 |  | Fitting DN (mm) |  | 650 | Master Register!CB1127 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-076 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1127:BW1127
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-077 |  | Fitting Material |  | MSCL | Master Register!CA1131 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-077 |  | Fitting DN (mm) |  | 650 | Master Register!CB1131 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-077 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1131:BW1131
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-029 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1140:BW1140
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-SCV-015 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1148:BW1148
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-030 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1151:BW1151
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-031 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1166:BW1166
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-078 |  | Fitting Material |  | MSCL | Master Register!CA1170 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-078 |  | Fitting DN (mm) |  | 650 | Master Register!CB1170 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-078 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1170:BW1170
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-079 |  | Fitting Material |  | MSCL | Master Register!CA1172 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-079 |  | Fitting DN (mm) |  | 650 | Master Register!CB1172 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-079 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1172:BW1172
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-080 |  | Fitting Material |  | MSCL | Master Register!CA1173 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-080 |  | Fitting DN (mm) |  | 650 | Master Register!CB1173 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-080 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1173:BW1173
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-081 |  | Fitting Material |  | MSCL | Master Register!CA1174 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-081 |  | Fitting DN (mm) |  | 650 | Master Register!CB1174 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-081 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1174:BW1174
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-SCV-016 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1177:BW1177
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-082 |  | Fitting Material |  | MSCL | Master Register!CA1179 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-082 |  | Fitting DN (mm) |  | 650 | Master Register!CB1179 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-082 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1179:BW1179
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-083 |  | Fitting Material |  | MSCL | Master Register!CA1182 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-083 |  | Fitting DN (mm) |  | 650 | Master Register!CB1182 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-083 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1182:BW1182
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-032 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1184:BW1184
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-SCV-017 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1189:BW1189
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-084 |  | Fitting Material |  | DICL | Master Register!CA1193 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-084 |  | Fitting DN (mm) |  | 600 | Master Register!CB1193 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-084 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1193:BW1193
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-085 |  | Fitting Material |  | DICL | Master Register!CA1195 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-085 |  | Fitting DN (mm) |  | 600 | Master Register!CB1195 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-085 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1195:BW1195
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-086 |  | Fitting Material |  | DICL | Master Register!CA1209 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-086 |  | Fitting DN (mm) |  | 600 | Master Register!CB1209 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-086 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1209:BW1209
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-087 |  | Fitting Material |  | DICL | Master Register!CA1211 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-087 |  | Fitting DN (mm) |  | 600 | Master Register!CB1211 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-087 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1211:BW1211
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-033 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1215:BW1215
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-PIG-002 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1239:BW1239
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-AV-034 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1244:BW1244
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-088 |  | Fitting Material |  | DICL | Master Register!CA1247 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-088 |  | Fitting DN (mm) |  | 600 | Master Register!CB1247 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-088 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1247:BW1247
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-089 |  | Fitting Material |  | MSCL | Master Register!CA1251 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-089 |  | Fitting DN (mm) |  | 650 | Master Register!CB1251 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-089 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1251:BW1251
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-090 |  | Fitting Material |  | MSCL | Master Register!CA1253 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-090 |  | Fitting DN (mm) |  | 650 | Master Register!CB1253 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-090 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1253:BW1253
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-091 |  | Fitting Material |  | MSCL | Master Register!CA1256 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-091 |  | Fitting DN (mm) |  | 650 | Master Register!CB1256 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-091 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1256:BW1256
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-092 |  | Fitting Material |  | MSCL | Master Register!CA1259 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-092 |  | Fitting DN (mm) |  | 650 | Master Register!CB1259 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-092 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1259:BW1259
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-093 |  | Fitting Material |  | MSCL | Master Register!CA1260 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-093 |  | Fitting DN (mm) |  | 650 | Master Register!CB1260 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-093 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1260:BW1260
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-094 |  | Fitting Material |  | MSCL | Master Register!CA1264 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-094 |  | Fitting DN (mm) |  | 650 | Master Register!CB1264 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PHW-BND-094 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1264:BW1264
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-001 |  | Fitting Material |  | DICL | Master Register!CA1289 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-001 |  | Fitting DN (mm) |  | 375 | Master Register!CB1289 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-001 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1289:BW1289
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-002 |  | Fitting Material |  | DICL | Master Register!CA1294 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-002 |  | Fitting DN (mm) |  | 375 | Master Register!CB1294 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-002 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1294:BW1294
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-PIG-001 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1297:BW1297
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-003 |  | Fitting Material |  | DICL | Master Register!CA1300 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-003 |  | Fitting DN (mm) |  | 375 | Master Register!CB1300 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-003 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1300:BW1300
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-001 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1302:BW1302
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-004 |  | Fitting Material |  | DICL | Master Register!CA1305 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-004 |  | Fitting DN (mm) |  | 375 | Master Register!CB1305 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-004 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1305:BW1305
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-005 |  | Fitting Material |  | DICL | Master Register!CA1308 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-005 |  | Fitting DN (mm) |  | 375 | Master Register!CB1308 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-005 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1308:BW1308
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-006 |  | Fitting Material |  | DICL | Master Register!CA1313 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-006 |  | Fitting DN (mm) |  | 375 | Master Register!CB1313 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-006 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1313:BW1313
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-001 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1315:BW1315
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-007 |  | Fitting Material |  | DICL | Master Register!CA1319 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-007 |  | Fitting DN (mm) |  | 375 | Master Register!CB1319 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-007 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1319:BW1319
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-002 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1321:BW1321
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-008 |  | Fitting Material |  | DICL | Master Register!CA1335 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-008 |  | Fitting DN (mm) |  | 375 | Master Register!CB1335 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-008 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1335:BW1335
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-009 |  | Fitting Material |  | DICL | Master Register!CA1353 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-009 |  | Fitting DN (mm) |  | 375 | Master Register!CB1353 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-009 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1353:BW1353
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-010 |  | Fitting Material |  | DICL | Master Register!CA1359 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-010 |  | Fitting DN (mm) |  | 375 | Master Register!CB1359 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-010 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1359:BW1359
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-002 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1361:BW1361
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-011 |  | Fitting Material |  | DICL | Master Register!CA1363 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-011 |  | Fitting DN (mm) |  | 375 | Master Register!CB1363 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-011 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1363:BW1363
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-012 |  | Fitting Material |  | DICL | Master Register!CA1367 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-012 |  | Fitting DN (mm) |  | 375 | Master Register!CB1367 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-012 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1367:BW1367
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-003 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1369:BW1369
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-013 |  | Fitting Material |  | DICL | Master Register!CA1379 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-013 |  | Fitting DN (mm) |  | 375 | Master Register!CB1379 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-013 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1379:BW1379
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-014 |  | Fitting Material |  | DICL | Master Register!CA1388 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-014 |  | Fitting DN (mm) |  | 375 | Master Register!CB1388 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-014 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1388:BW1388
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-015 |  | Fitting Material |  | MSCL | Master Register!CA1404 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-015 |  | Fitting DN (mm) |  | 450 | Master Register!CB1404 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-015 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1404:BW1404
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-016 |  | Fitting Material |  | MSCL | Master Register!CA1408 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-016 |  | Fitting DN (mm) |  | 450 | Master Register!CB1408 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-016 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1408:BW1408
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-017 |  | Fitting Material |  | DICL | Master Register!CA1415 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-017 |  | Fitting DN (mm) |  | 375 | Master Register!CB1415 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-017 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1415:BW1415
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-004 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1416:BW1416
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-018 |  | Fitting Material |  | DICL | Master Register!CA1423 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-018 |  | Fitting DN (mm) |  | 375 | Master Register!CB1423 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-018 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1423:BW1423
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-019 |  | Fitting Material |  | MSCL | Master Register!CA1444 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-019 |  | Fitting DN (mm) |  | 450 | Master Register!CB1444 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-019 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1444:BW1444
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-020 |  | Fitting Material |  | MSCL | Master Register!CA1453 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-020 |  | Fitting DN (mm) |  | 450 | Master Register!CB1453 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-020 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1453:BW1453
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-021 |  | Fitting Material |  | MSCL | Master Register!CA1459 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-021 |  | Fitting DN (mm) |  | 450 | Master Register!CB1459 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-021 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1459:BW1459
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-022 |  | Fitting Material |  | DICL | Master Register!CA1468 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-022 |  | Fitting DN (mm) |  | 375 | Master Register!CB1468 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-022 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1468:BW1468
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-003 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1473:BW1473
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-005 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1476:BW1476
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-004 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1481:BW1481
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-023 |  | Fitting Material |  | DICL | Master Register!CA1485 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-023 |  | Fitting DN (mm) |  | 375 | Master Register!CB1485 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-023 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1485:BW1485
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-IV-001 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1490:BW1490
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-005 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1493:BW1493
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-006 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1495:BW1495
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-006 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1496:BW1496
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-007 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1497:BW1497
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-024 |  | Fitting Material |  | DICL | Master Register!CA1499 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-024 |  | Fitting DN (mm) |  | 375 | Master Register!CB1499 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-024 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1499:BW1499
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-025 |  | Fitting Material |  | MSCL | Master Register!CA1505 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-025 |  | Fitting DN (mm) |  | 450 | Master Register!CB1505 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-025 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1505:BW1505
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-026 |  | Fitting Material |  | MSCL | Master Register!CA1506 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-026 |  | Fitting DN (mm) |  | 450 | Master Register!CB1506 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-026 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1506:BW1506
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-027 |  | Fitting Material |  | MSCL | Master Register!CA1509 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-027 |  | Fitting DN (mm) |  | 450 | Master Register!CB1509 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-027 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1509:BW1509
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-008 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1511:BW1511
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-007 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1512:BW1512
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-009 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1514:BW1514
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-008 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1521:BW1521
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-028 |  | Fitting Material |  | DICL | Master Register!CA1527 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-028 |  | Fitting DN (mm) |  | 375 | Master Register!CB1527 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-028 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1527:BW1527
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-029 |  | Fitting Material |  | DICL | Master Register!CA1534 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-029 |  | Fitting DN (mm) |  | 375 | Master Register!CB1534 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-029 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1534:BW1534
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-IV-002 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1537:BW1537
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-030 |  | Fitting Material |  | MSCL | Master Register!CA1541 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-030 |  | Fitting DN (mm) |  | 450 | Master Register!CB1541 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-030 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1541:BW1541
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-031 |  | Fitting Material |  | MSCL | Master Register!CA1543 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-031 |  | Fitting DN (mm) |  | 450 | Master Register!CB1543 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-031 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1543:BW1543
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-032 |  | Fitting Material |  | MSCL | Master Register!CA1546 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-032 |  | Fitting DN (mm) |  | 450 | Master Register!CB1546 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-032 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1546:BW1546
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-033 |  | Fitting Material |  | DICL | Master Register!CA1552 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-033 |  | Fitting DN (mm) |  | 375 | Master Register!CB1552 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-033 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1552:BW1552
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-034 |  | Fitting Material |  | DICL | Master Register!CA1554 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-034 |  | Fitting DN (mm) |  | 375 | Master Register!CB1554 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-034 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1554:BW1554
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-PIG-002 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1556:BW1556
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-010 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1559:BW1559
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-035 |  | Fitting Material |  | DICL | Master Register!CA1561 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-035 |  | Fitting DN (mm) |  | 375 | Master Register!CB1561 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-035 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1561:BW1561
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-036 |  | Fitting Material |  | DICL | Master Register!CA1563 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-036 |  | Fitting DN (mm) |  | 375 | Master Register!CB1563 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-036 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1563:BW1563
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-037 |  | Fitting Material |  | MSCL | Master Register!CA1566 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-037 |  | Fitting DN (mm) |  | 450 | Master Register!CB1566 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-037 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1566:BW1566
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-038 |  | Fitting Material |  | MSCL | Master Register!CA1568 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-038 |  | Fitting DN (mm) |  | 450 | Master Register!CB1568 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-038 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1568:BW1568
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-039 |  | Fitting Material |  | DICL | Master Register!CA1571 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-039 |  | Fitting DN (mm) |  | 375 | Master Register!CB1571 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-039 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1571:BW1571
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-011 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1572:BW1572
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-040 |  | Fitting Material |  | DICL | Master Register!CA1584 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-040 |  | Fitting DN (mm) |  | 375 | Master Register!CB1584 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-040 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1584:BW1584
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-041 |  | Fitting Material |  | DICL | Master Register!CA1593 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-041 |  | Fitting DN (mm) |  | 375 | Master Register!CB1593 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-041 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1593:BW1593
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-042 |  | Fitting Material |  | DICL | Master Register!CA1596 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-042 |  | Fitting DN (mm) |  | 375 | Master Register!CB1596 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-042 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1596:BW1596
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-043 |  | Fitting Material |  | DICL | Master Register!CA1603 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-043 |  | Fitting DN (mm) |  | 375 | Master Register!CB1603 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-043 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1603:BW1603
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-012 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1605:BW1605
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-044 |  | Fitting Material |  | DICL | Master Register!CA1607 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-044 |  | Fitting DN (mm) |  | 375 | Master Register!CB1607 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-044 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1607:BW1607
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-045 |  | Fitting Material |  | DICL | Master Register!CA1611 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-045 |  | Fitting DN (mm) |  | 375 | Master Register!CB1611 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-045 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1611:BW1611
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-046 |  | Fitting Material |  | DICL | Master Register!CA1617 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-046 |  | Fitting DN (mm) |  | 375 | Master Register!CB1617 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-046 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1617:BW1617
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-047 |  | Fitting Material |  | MSCL | Master Register!CA1628 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-047 |  | Fitting DN (mm) |  | 450 | Master Register!CB1628 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-047 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1628:BW1628
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-048 |  | Fitting Material |  | MSCL | Master Register!CA1639 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-048 |  | Fitting DN (mm) |  | 450 | Master Register!CB1639 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-048 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1639:BW1639
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-049 |  | Fitting Material |  | MSCL | Master Register!CA1641 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-049 |  | Fitting DN (mm) |  | 450 | Master Register!CB1641 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-049 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1641:BW1641
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-050 |  | Fitting Material |  | MSCL | Master Register!CA1644 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-050 |  | Fitting DN (mm) |  | 450 | Master Register!CB1644 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-050 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1644:BW1644
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-IV-003 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1647:BW1647
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-051 |  | Fitting Material |  | DICL | Master Register!CA1649 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-051 |  | Fitting DN (mm) |  | 375 | Master Register!CB1649 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-051 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1649:BW1649
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-052 |  | Fitting Material |  | DICL | Master Register!CA1651 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-052 |  | Fitting DN (mm) |  | 375 | Master Register!CB1651 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-052 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1651:BW1651
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-053 |  | Fitting Material |  | DICL | Master Register!CA1663 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-053 |  | Fitting DN (mm) |  | 375 | Master Register!CB1663 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-053 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1663:BW1663
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-054 |  | Fitting Material |  | DICL | Master Register!CA1666 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-054 |  | Fitting DN (mm) |  | 375 | Master Register!CB1666 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-054 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1666:BW1666
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-IV-004 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1668:BW1668
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-009 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1696:BW1696
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-013 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1697:BW1697
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-055 |  | Fitting Material |  | DICL | Master Register!CA1708 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-055 |  | Fitting DN (mm) |  | 375 | Master Register!CB1708 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-055 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1708:BW1708
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-010 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1711:BW1711
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-014 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1716:BW1716
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-015 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1726:BW1726
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-011 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1733:BW1733
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-056 |  | Fitting Material |  | DICL | Master Register!CA1737 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-056 |  | Fitting DN (mm) |  | 375 | Master Register!CB1737 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-056 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1737:BW1737
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-057 |  | Fitting Material |  | DICL | Master Register!CA1738 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-057 |  | Fitting DN (mm) |  | 375 | Master Register!CB1738 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-057 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1738:BW1738
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-016 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1740:BW1740
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-058 |  | Fitting Material |  | DICL | Master Register!CA1754 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-058 |  | Fitting DN (mm) |  | 375 | Master Register!CB1754 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-058 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1754:BW1754
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-059 |  | Fitting Material |  | DICL | Master Register!CA1762 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-059 |  | Fitting DN (mm) |  | 375 | Master Register!CB1762 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-059 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1762:BW1762
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-060 |  | Fitting Material |  | DICL | Master Register!CA1765 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-060 |  | Fitting DN (mm) |  | 375 | Master Register!CB1765 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-060 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1765:BW1765
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-061 |  | Fitting Material |  | DICL | Master Register!CA1769 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-061 |  | Fitting DN (mm) |  | 375 | Master Register!CB1769 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-061 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1769:BW1769
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-062 |  | Fitting Material |  | DICL | Master Register!CA1779 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-062 |  | Fitting DN (mm) |  | 375 | Master Register!CB1779 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-062 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1779:BW1779
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-017 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1780:BW1780
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-012 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1797:BW1797
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-063 |  | Fitting Material |  | DICL | Master Register!CA1799 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-063 |  | Fitting DN (mm) |  | 375 | Master Register!CB1799 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-063 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1799:BW1799
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-018 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1805:BW1805
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-064 |  | Fitting Material |  | DICL | Master Register!CA1807 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-064 |  | Fitting DN (mm) |  | 375 | Master Register!CB1807 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-064 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1807:BW1807
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-065 |  | Fitting Material |  | DICL | Master Register!CA1809 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-065 |  | Fitting DN (mm) |  | 375 | Master Register!CB1809 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-065 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1809:BW1809
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-013 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1811:BW1811
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-IV-005 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1821:BW1821
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-066 |  | Fitting Material |  | DICL | Master Register!CA1830 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-066 |  | Fitting DN (mm) |  | 375 | Master Register!CB1830 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-066 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1830:BW1830
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-067 |  | Fitting Material |  | DICL | Master Register!CA1832 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-067 |  | Fitting DN (mm) |  | 375 | Master Register!CB1832 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-067 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1832:BW1832
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-068 |  | Fitting Material |  | MSCL | Master Register!CA1844 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-068 |  | Fitting DN (mm) |  | 450 | Master Register!CB1844 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-068 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1844:BW1844
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-069 |  | Fitting Material |  | MSCL | Master Register!CA1847 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-069 |  | Fitting DN (mm) |  | 450 | Master Register!CB1847 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-069 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1847:BW1847
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-070 |  | Fitting Material |  | MSCL | Master Register!CA1848 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-070 |  | Fitting DN (mm) |  | 450 | Master Register!CB1848 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-070 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1848:BW1848
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-071 |  | Fitting Material |  | MSCL | Master Register!CA1850 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-071 |  | Fitting DN (mm) |  | 450 | Master Register!CB1850 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-071 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1850:BW1850
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-072 |  | Fitting Material |  | MSCL | Master Register!CA1853 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-072 |  | Fitting DN (mm) |  | 450 | Master Register!CB1853 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-072 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1853:BW1853
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-014 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1856:BW1856
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-019 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1857:BW1857
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-073 |  | Fitting Material |  | MSCL | Master Register!CA1860 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-073 |  | Fitting DN (mm) |  | 450 | Master Register!CB1860 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-073 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1860:BW1860
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-074 |  | Fitting Material |  | MSCL | Master Register!CA1863 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-074 |  | Fitting DN (mm) |  | 450 | Master Register!CB1863 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-074 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1863:BW1863
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-015 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1869:BW1869
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-075 |  | Fitting Material |  | DICL | Master Register!CA1898 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-075 |  | Fitting DN (mm) |  | 375 | Master Register!CB1898 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-075 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1898:BW1898
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-016 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1901:BW1901
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-020 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1913:BW1913
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-017 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1916:BW1916
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-021 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1919:BW1919
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-076 |  | Fitting Material |  | DICL | Master Register!CA1926 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-076 |  | Fitting DN (mm) |  | 375 | Master Register!CB1926 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-076 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1926:BW1926
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-077 |  | Fitting Material |  | DICL | Master Register!CA1934 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-077 |  | Fitting DN (mm) |  | 375 | Master Register!CB1934 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-077 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1934:BW1934
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-078 |  | Fitting Material |  | DICL | Master Register!CA1938 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-078 |  | Fitting DN (mm) |  | 375 | Master Register!CB1938 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-078 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1938:BW1938
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-022 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1941:BW1941
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-079 |  | Fitting Material |  | DICL | Master Register!CA1944 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-079 |  | Fitting DN (mm) |  | 375 | Master Register!CB1944 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-079 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1944:BW1944
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-080 |  | Fitting Material |  | DICL | Master Register!CA1946 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-080 |  | Fitting DN (mm) |  | 375 | Master Register!CB1946 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-080 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1946:BW1946
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-PIG-003 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1949:BW1949
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-023 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1950:BW1950
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-081 |  | Fitting Material |  | DICL | Master Register!CA1954 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-081 |  | Fitting DN (mm) |  | 375 | Master Register!CB1954 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-081 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1954:BW1954
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-082 |  | Fitting Material |  | DICL | Master Register!CA1958 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-082 |  | Fitting DN (mm) |  | 375 | Master Register!CB1958 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-082 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1958:BW1958
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-083 |  | Fitting Material |  | DICL | Master Register!CA1961 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-083 |  | Fitting DN (mm) |  | 375 | Master Register!CB1961 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-083 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1961:BW1961
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-018 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1963:BW1963
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-084 |  | Fitting Material |  | DICL | Master Register!CA1966 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-084 |  | Fitting DN (mm) |  | 375 | Master Register!CB1966 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-084 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1966:BW1966
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-085 |  | Fitting Material |  | DICL | Master Register!CA1970 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-085 |  | Fitting DN (mm) |  | 375 | Master Register!CB1970 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-085 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1970:BW1970
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-086 |  | Fitting Material |  | DICL | Master Register!CA1973 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-086 |  | Fitting DN (mm) |  | 375 | Master Register!CB1973 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-086 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1973:BW1973
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-024 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1976:BW1976
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-087 |  | Fitting Material |  | DICL | Master Register!CA1987 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-087 |  | Fitting DN (mm) |  | 375 | Master Register!CB1987 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-087 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1987:BW1987
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-025 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU1991:BW1991
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-088 |  | Fitting Material |  | DICL | Master Register!CA1998 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-088 |  | Fitting DN (mm) |  | 375 | Master Register!CB1998 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-088 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU1998:BW1998
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-026 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU2000:BW2000
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-089 |  | Fitting Material |  | DICL | Master Register!CA2003 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-089 |  | Fitting DN (mm) |  | 375 | Master Register!CB2003 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-089 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2003:BW2003
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-019 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU2005:BW2005
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-090 |  | Fitting Material |  | DICL | Master Register!CA2008 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-090 |  | Fitting DN (mm) |  | 375 | Master Register!CB2008 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-090 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2008:BW2008
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-091 |  | Fitting Material |  | DICL | Master Register!CA2011 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-091 |  | Fitting DN (mm) |  | 375 | Master Register!CB2011 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-091 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2011:BW2011
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-027 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU2013:BW2013
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-092 |  | Fitting Material |  | DICL | Master Register!CA2019 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-092 |  | Fitting DN (mm) |  | 375 | Master Register!CB2019 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-092 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2019:BW2019
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-020 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU2021:BW2021
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-093 |  | Fitting Material |  | DICL | Master Register!CA2026 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-093 |  | Fitting DN (mm) |  | 375 | Master Register!CB2026 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-093 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2026:BW2026
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-094 |  | Fitting Material |  | DICL | Master Register!CA2029 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-094 |  | Fitting DN (mm) |  | 375 | Master Register!CB2029 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-094 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2029:BW2029
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-095 |  | Fitting Material |  | DICL | Master Register!CA2031 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-095 |  | Fitting DN (mm) |  | 375 | Master Register!CB2031 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-095 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2031:BW2031
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-028 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU2032:BW2032
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-IV-006 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU2035:BW2035
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-096 |  | Fitting Material |  | DICL | Master Register!CA2038 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-096 |  | Fitting DN (mm) |  | 375 | Master Register!CB2038 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-096 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2038:BW2038
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-021 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU2041:BW2041
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-097 |  | Fitting Material |  | MSCL | Master Register!CA2044 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-097 |  | Fitting DN (mm) |  | 450 | Master Register!CB2044 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-097 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2044:BW2044
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-098 |  | Fitting Material |  | DICL | Master Register!CA2052 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-098 |  | Fitting DN (mm) |  | 375 | Master Register!CB2052 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-098 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2052:BW2052
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-029 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU2053:BW2053
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-099 |  | Fitting Material |  | DICL | Master Register!CA2056 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-099 |  | Fitting DN (mm) |  | 375 | Master Register!CB2056 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-099 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2056:BW2056
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-022 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU2058:BW2058
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-030 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU2059:BW2059
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-100 |  | Fitting Material |  | DICL | Master Register!CA2061 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-100 |  | Fitting DN (mm) |  | 375 | Master Register!CB2061 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-100 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2061:BW2061
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-101 |  | Fitting Material |  | DICL | Master Register!CA2063 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-101 |  | Fitting DN (mm) |  | 375 | Master Register!CB2063 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-101 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2063:BW2063
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-023 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU2066:BW2066
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-031 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU2067:BW2067
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-102 |  | Fitting Material |  | DICL | Master Register!CA2069 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-102 |  | Fitting DN (mm) |  | 375 | Master Register!CB2069 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-102 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2069:BW2069
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-103 |  | Fitting Material |  | DICL | Master Register!CA2071 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-103 |  | Fitting DN (mm) |  | 375 | Master Register!CB2071 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-103 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2071:BW2071
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-024 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU2077:BW2077
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-104 |  | Fitting Material |  | DICL | Master Register!CA2081 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-104 |  | Fitting DN (mm) |  | 375 | Master Register!CB2081 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-104 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2081:BW2081
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-105 |  | Fitting Material |  | DICL | Master Register!CA2087 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-105 |  | Fitting DN (mm) |  | 375 | Master Register!CB2087 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-105 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2087:BW2087
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-106 |  | Fitting Material |  | DICL | Master Register!CA2092 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-106 |  | Fitting DN (mm) |  | 375 | Master Register!CB2092 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-106 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2092:BW2092
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-032 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU2094:BW2094
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-107 |  | Fitting Material |  | MSCL | Master Register!CA2099 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-107 |  | Fitting DN (mm) |  | 450 | Master Register!CB2099 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-107 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2099:BW2099
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-108 |  | Fitting Material |  | DICL | Master Register!CA2111 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-108 |  | Fitting DN (mm) |  | 375 | Master Register!CB2111 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-108 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2111:BW2111
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-109 |  | Fitting Material |  | DICL | Master Register!CA2113 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-109 |  | Fitting DN (mm) |  | 375 | Master Register!CB2113 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-109 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2113:BW2113
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-110 |  | Fitting Material |  | DICL | Master Register!CA2119 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-110 |  | Fitting DN (mm) |  | 375 | Master Register!CB2119 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-110 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2119:BW2119
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-033 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU2128:BW2128
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-025 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU2133:BW2133
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-111 |  | Fitting Material |  | DICL | Master Register!CA2135 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-111 |  | Fitting DN (mm) |  | 375 | Master Register!CB2135 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-111 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2135:BW2135
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-112 |  | Fitting Material |  | DICL | Master Register!CA2137 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-112 |  | Fitting DN (mm) |  | 375 | Master Register!CB2137 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-112 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2137:BW2137
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-113 |  | Fitting Material |  | DICL | Master Register!CA2139 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-113 |  | Fitting DN (mm) |  | 375 | Master Register!CB2139 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-113 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2139:BW2139
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-034 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU2143:BW2143
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-114 |  | Fitting Material |  | DICL | Master Register!CA2155 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-114 |  | Fitting DN (mm) |  | 375 | Master Register!CB2155 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-114 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2155:BW2155
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-SCV-026 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU2157:BW2157
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-115 |  | Fitting Material |  | DICL | Master Register!CA2165 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-115 |  | Fitting DN (mm) |  | 375 | Master Register!CB2165 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-115 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2165:BW2165
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-116 |  | Fitting Material |  | DICL | Master Register!CA2179 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-116 |  | Fitting DN (mm) |  | 375 | Master Register!CB2179 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-116 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2179:BW2179
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-117 |  | Fitting Material |  | DICL | Master Register!CA2181 — derived from bend angle, rule on Rate Library Table 5
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-117 |  | Fitting DN (mm) |  | 375 | Master Register!CB2181 — derived from pipeline section and material
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-BND-117 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 5 | Master Register!BU2181:BW2181
2026-08-28 09:00 | J. Krasnoff-Hnatjuk | PWG-AV-035 |  | Unit Rate ($) / Quantity / Unit |  | formula reading Rate Library Table 6 | Master Register!BU2182:BW2182
28/08/2026 11:40 | Jerry KH | PHW-TB-001 |  | Complete |  | Yes | Master Register!BR6
28/08/2026 11:40 | Jerry KH | PHW-TB-001 |  | Completion Date |  | 46262 | Master Register!BS6
28/08/2026 11:40 | Jerry KH | PHW-BND-001 |  | Complete |  | Yes | Master Register!BR7
28/08/2026 11:40 | Jerry KH | PHW-BND-001 |  | Completion Date |  | 46262 | Master Register!BS7
28/08/2026 11:40 | Jerry KH | PHW-TT-0001 |  | Trench Complete (m) |  | 125 | Cost Tracker - Linear!K9
28/08/2026 11:40 | Jerry KH | PHW-TT-0001 |  | Pipe Laid (m) | 0 |  | Cost Tracker - Linear!Q9
28/08/2026 11:40 | Jerry KH | PHW-TT-0001 |  | As At Date | 46261 | 46262 | Cost Tracker - Linear!X9
28/08/2026 11:40 | Jerry KH | PHW-TT-0001 |  | Updated By | Jerry | Jerry KH | Cost Tracker - Linear!Y9
28/08/2026 11:40 | Jerry KH | Recorded By |  | Settings |  | Jerry KH | Settings!C8
28/08/2026 11:40 | Jerry KH | Project Folder (last used) |  | Settings |  | t2w-asset-register_rev2 | Settings!C14
28/08/2026 11:40 | Jerry KH | PHW |  | Daily Progress |  | 28/08/2026 · +25.0 m trench, +10.0 m pipe, 0 item(s) | Daily Progress!B9
28/08/2026 11:40 | Jerry KH | Supervisor |  | Daily Plant and Labour |  | 28/08/2026 · Supervisor x1 · 10.0 h | Daily Plant and Labour!B9
28/08/2026 11:40 | Jerry KH | Pipe crew |  | Daily Plant and Labour |  | 28/08/2026 · Pipe crew x6 · 10.0 h | Daily Plant and Labour!B10
28/08/2026 11:40 | Jerry KH | Excavator 30t |  | Daily Plant and Labour |  | 28/08/2026 · Excavator 30t x1 · 9.0 h | Daily Plant and Labour!B11
28/08/2026 11:40 | Jerry KH | Sideboom |  | Daily Plant and Labour |  | 28/08/2026 · Sideboom x1 · 9.0 h | Daily Plant and Labour!B12
28/08/2026 11:40 | Jerry KH |  |  | Daily Safety |  | 28/08/2026 · toolbox Yes · 7 on site · Nil | Daily Safety!B9
28/08/2026 11:40 | Jerry KH | 16074.25 |  | Daily Profit |  | 28/08/2026 · earned $16,074, cost $16,684, profit -$610 | Daily Profit!B9
28/08/2026 11:42 | Jerry KH | PHW-TS-0001 |  | Complete |  | Yes | Master Register!BR13
28/08/2026 11:42 | Jerry KH | PHW-TS-0001 |  | Completion Date |  | 46262 | Master Register!BS13
28/08/2026 11:42 | Jerry KH | PHW-TS-0002 |  | Complete |  | Yes | Master Register!BR14
28/08/2026 11:42 | Jerry KH | PHW-TS-0002 |  | Completion Date |  | 46262 | Master Register!BS14
28/08/2026 11:42 | Jerry KH | PHW-TT-0001 |  | Trench Complete (m) | 125 | 325 | Cost Tracker - Linear!K9
28/08/2026 11:42 | Jerry KH | PHW-TT-0001 |  | Pipe Laid (m) |  | 150 | Cost Tracker - Linear!Q9
28/08/2026 11:42 | Jerry KH | PHW |  | Daily Progress |  | 29/08/2026 · +200.0 m trench, +150.0 m pipe, 2 item(s) | Daily Progress!B10
28/08/2026 11:42 | Jerry KH | Supervisor |  | Daily Plant and Labour |  | 29/08/2026 · Supervisor x1 · 10.0 h | Daily Plant and Labour!B13
28/08/2026 11:42 | Jerry KH | Pipe crew |  | Daily Plant and Labour |  | 29/08/2026 · Pipe crew x6 · 10.0 h | Daily Plant and Labour!B14
28/08/2026 11:42 | Jerry KH | Excavator 30t |  | Daily Plant and Labour |  | 29/08/2026 · Excavator 30t x1 · 9.0 h | Daily Plant and Labour!B15
28/08/2026 11:42 | Jerry KH | Sideboom |  | Daily Plant and Labour |  | 29/08/2026 · Sideboom x1 · 9.0 h | Daily Plant and Labour!B16
28/08/2026 11:42 | Jerry KH |  |  | Daily Safety |  | 29/08/2026 · toolbox Yes · 7 on site · Nil | Daily Safety!B10
28/08/2026 11:42 | Jerry KH | 164800.5 |  | Daily Profit |  | 29/08/2026 · earned $164,801, cost $78,526, profit $86,275 | Daily Profit!B10
28/08/2026 11:48 | Jerry KH | PHW-AV-001 |  | Complete |  | Yes | Master Register!BR12
28/08/2026 11:48 | Jerry KH | PHW-AV-001 |  | Completion Date |  | 46262 | Master Register!BS12
28/08/2026 11:48 | Jerry KH | PHW-TS-0018 |  | Complete |  | Yes | Master Register!BR34
28/08/2026 11:48 | Jerry KH | PHW-TS-0018 |  | Completion Date |  | 46262 | Master Register!BS34
28/08/2026 11:48 | Jerry KH | PHW-VG-0004 |  | Complete |  | Yes | Master Register!BR38
28/08/2026 11:48 | Jerry KH | PHW-VG-0004 |  | Completion Date |  | 46262 | Master Register!BS38
28/08/2026 11:48 | Jerry KH | PHW-VG-0005 |  | Complete |  | Yes | Master Register!BR41
28/08/2026 11:48 | Jerry KH | PHW-VG-0005 |  | Completion Date |  | 46262 | Master Register!BS41
28/08/2026 11:48 | Jerry KH | PHW-TT-0001 |  | Trench Complete (m) | 325 | 327.039 | Cost Tracker - Linear!K9
28/08/2026 11:48 | Jerry KH | PHW-TT-0001 |  | Pipe Laid (m) | 150 | 250 | Cost Tracker - Linear!Q9
28/08/2026 11:48 | Jerry KH | PHW-TT-0002 |  | Trench Complete (m) |  | 77.823 | Cost Tracker - Linear!K10
28/08/2026 11:48 | Jerry KH | PHW-TT-0002 |  | As At Date | 46261 | 46262 | Cost Tracker - Linear!X10
28/08/2026 11:48 | Jerry KH | PHW-TT-0002 |  | Updated By | Jerry | Jerry KH | Cost Tracker - Linear!Y10
28/08/2026 11:48 | Jerry KH | PHW-TT-0003 |  | Trench Complete (m) |  | 21.528 | Cost Tracker - Linear!K11
28/08/2026 11:48 | Jerry KH | PHW-TT-0003 |  | As At Date | 46261 | 46262 | Cost Tracker - Linear!X11
28/08/2026 11:48 | Jerry KH | PHW-TT-0003 |  | Updated By | Jerry | Jerry KH | Cost Tracker - Linear!Y11
28/08/2026 11:48 | Jerry KH | PHW-TT-0004 |  | Trench Complete (m) |  | 23.610000000000014 | Cost Tracker - Linear!K12
28/08/2026 11:48 | Jerry KH | PHW-TT-0004 |  | As At Date | 46261 | 46262 | Cost Tracker - Linear!X12
28/08/2026 11:48 | Jerry KH | PHW-TT-0004 |  | Updated By | Jerry | Jerry KH | Cost Tracker - Linear!Y12
28/08/2026 11:48 | Jerry KH | PHW |  | Daily Progress |  | 30/08/2026 · +125.0 m trench, +100.0 m pipe, 4 item(s) | Daily Progress!B11
28/08/2026 11:48 | Jerry KH | Supervisor |  | Daily Plant and Labour |  | 30/08/2026 · Supervisor x1 · 10.0 h | Daily Plant and Labour!B17
28/08/2026 11:48 | Jerry KH | Pipe crew |  | Daily Plant and Labour |  | 30/08/2026 · Pipe crew x8 · 10.0 h | Daily Plant and Labour!B18
28/08/2026 11:48 | Jerry KH | Excavator 30t |  | Daily Plant and Labour |  | 30/08/2026 · Excavator 30t x1 · 9.0 h | Daily Plant and Labour!B19
28/08/2026 11:48 | Jerry KH | Sideboom |  | Daily Plant and Labour |  | 30/08/2026 · Sideboom x1 · 9.0 h | Daily Plant and Labour!B20
28/08/2026 11:48 | Jerry KH |  |  | Daily Safety |  | 30/08/2026 · toolbox Yes · 9 on site · Nil | Daily Safety!B11
28/08/2026 11:48 | Jerry KH | 85964.46510999996 |  | Daily Profit |  | 30/08/2026 · earned $85,964, cost $37,738, profit $48,226 | Daily Profit!B11
28/08/2026 11:51 | Jerry KH | PHW-IV-001 | PHW-IV-001 | Progress Notes |  | Supplied | Master Register!BT109
28/08/2026 11:51 | Jerry KH | PHW-IV-002 | PHW-IV-002 | Progress Notes |  | Supplied | Master Register!BT302
28/08/2026 11:51 | Jerry KH | PHW-IV-003 | PHW-IV-003 | Progress Notes |  | Supplied | Master Register!BT327
28/08/2026 11:51 | Jerry KH | PHW-IV-004 | PHW-IV-004 | Progress Notes |  | Supplied | Master Register!BT784
28/08/2026 11:51 | Jerry KH | PHW-IV-005 | PHW-IV-005 | Progress Notes |  | Supplied | Master Register!BT1114
28/08/2026 11:51 | Jerry KH | PWG-IV-001 | PWG-IV-001 | Progress Notes |  | Supplied | Master Register!BT1490
28/08/2026 11:51 | Jerry KH | PWG-IV-002 | PWG-IV-002 | Progress Notes |  | Supplied | Master Register!BT1537
28/08/2026 11:51 | Jerry KH | PWG-IV-003 | PWG-IV-003 | Progress Notes |  | Supplied | Master Register!BT1647
28/08/2026 11:51 | Jerry KH | PWG-IV-004 | PWG-IV-004 | Progress Notes |  | Supplied | Master Register!BT1668
28/08/2026 11:51 | Jerry KH | PWG-IV-005 | PWG-IV-005 | Progress Notes |  | Supplied | Master Register!BT1821
28/08/2026 11:51 | Jerry KH | PWG-IV-006 | PWG-IV-006 | Progress Notes |  | Supplied | Master Register!BT2035
28/08/2026 12:02 | Jerry KH | PHW-VG-0001 |  | Complete |  | Yes | Master Register!BR4
28/08/2026 12:02 | Jerry KH | PHW-VG-0001 |  | Completion Date |  | 46262 | Master Register!BS4
28/08/2026 12:02 | Jerry KH | PHW-VG-0002 |  | Complete |  | Yes | Master Register!BR10
28/08/2026 12:02 | Jerry KH | PHW-VG-0002 |  | Completion Date |  | 46262 | Master Register!BS10
28/08/2026 12:02 | Jerry KH | PHW-TS-0003 |  | Complete |  | Yes | Master Register!BR15
28/08/2026 12:02 | Jerry KH | PHW-TS-0003 |  | Completion Date |  | 46262 | Master Register!BS15
28/08/2026 12:02 | Jerry KH | PHW-TS-0004 |  | Complete |  | Yes | Master Register!BR16
28/08/2026 12:02 | Jerry KH | PHW-TS-0004 |  | Completion Date |  | 46262 | Master Register!BS16
28/08/2026 12:02 | Jerry KH | PHW-TS-0005 |  | Complete |  | Yes | Master Register!BR18
28/08/2026 12:02 | Jerry KH | PHW-TS-0005 |  | Completion Date |  | 46262 | Master Register!BS18
28/08/2026 12:02 | Jerry KH | PHW-TS-0006 |  | Complete |  | Yes | Master Register!BR19
28/08/2026 12:02 | Jerry KH | PHW-TS-0006 |  | Completion Date |  | 46262 | Master Register!BS19
28/08/2026 12:02 | Jerry KH | PHW-TS-0007 |  | Complete |  | Yes | Master Register!BR21
28/08/2026 12:02 | Jerry KH | PHW-TS-0007 |  | Completion Date |  | 46262 | Master Register!BS21
28/08/2026 12:02 | Jerry KH | PHW-VG-0003 |  | Complete |  | Yes | Master Register!BR22
28/08/2026 12:02 | Jerry KH | PHW-VG-0003 |  | Completion Date |  | 46262 | Master Register!BS22
28/08/2026 12:02 | Jerry KH | PHW-TS-0008 |  | Complete |  | Yes | Master Register!BR23
28/08/2026 12:02 | Jerry KH | PHW-TS-0008 |  | Completion Date |  | 46262 | Master Register!BS23
28/08/2026 12:02 | Jerry KH | PHW-TS-0009 |  | Complete |  | Yes | Master Register!BR24
28/08/2026 12:02 | Jerry KH | PHW-TS-0009 |  | Completion Date |  | 46262 | Master Register!BS24
28/08/2026 12:02 | Jerry KH | PHW-TS-0010 |  | Complete |  | Yes | Master Register!BR25
28/08/2026 12:02 | Jerry KH | PHW-TS-0010 |  | Completion Date |  | 46262 | Master Register!BS25
28/08/2026 12:02 | Jerry KH | PHW-TS-0011 |  | Complete |  | Yes | Master Register!BR26
28/08/2026 12:02 | Jerry KH | PHW-TS-0011 |  | Completion Date |  | 46262 | Master Register!BS26
28/08/2026 12:02 | Jerry KH | PHW-TS-0012 |  | Complete |  | Yes | Master Register!BR27
28/08/2026 12:02 | Jerry KH | PHW-TS-0012 |  | Completion Date |  | 46262 | Master Register!BS27
28/08/2026 12:02 | Jerry KH | PHW-TS-0013 |  | Complete |  | Yes | Master Register!BR28
28/08/2026 12:02 | Jerry KH | PHW-TS-0013 |  | Completion Date |  | 46262 | Master Register!BS28
28/08/2026 12:02 | Jerry KH | PHW-VG-0006 |  | Complete |  | Yes | Master Register!BR47
28/08/2026 12:02 | Jerry KH | PHW-VG-0006 |  | Completion Date |  | 46262 | Master Register!BS47
28/08/2026 12:02 | Jerry KH | PHW-TT-0001 |  | Pipe Laid (m) | 250 | 327.039 | Cost Tracker - Linear!Q9
28/08/2026 12:02 | Jerry KH | PHW-TT-0002 |  | Pipe Laid (m) |  | 77.823 | Cost Tracker - Linear!Q10
28/08/2026 12:02 | Jerry KH | PHW-TT-0002 |  | Pipe Type |  | DICL | Cost Tracker - Linear!N10
28/08/2026 12:02 | Jerry KH | PHW-TT-0003 |  | Pipe Laid (m) |  | 15.137999999999977 | Cost Tracker - Linear!Q11
28/08/2026 12:02 | Jerry KH | PHW-TT-0003 |  | Pipe Type |  | DICL | Cost Tracker - Linear!N11
28/08/2026 12:02 | Jerry KH | PHW-TT-0004 |  | Trench Complete (m) | 23.610000000000014 | 33.610000000000014 | Cost Tracker - Linear!K12
28/08/2026 12:02 | Jerry KH | PHW |  | Daily Progress |  | 31/08/2026 · +10.0 m trench, +170.0 m pipe, 1 item(s) | Daily Progress!B12
28/08/2026 12:02 | Jerry KH | Supervisor |  | Daily Plant and Labour |  | 31/08/2026 · Supervisor x1 · 10.0 h | Daily Plant and Labour!B21
28/08/2026 12:02 | Jerry KH | Pipe crew |  | Daily Plant and Labour |  | 31/08/2026 · Pipe crew x8 · 10.0 h | Daily Plant and Labour!B22
28/08/2026 12:02 | Jerry KH | Excavator 30t |  | Daily Plant and Labour |  | 31/08/2026 · Excavator 30t x1 · 9.0 h | Daily Plant and Labour!B23
28/08/2026 12:02 | Jerry KH | Sideboom |  | Daily Plant and Labour |  | 31/08/2026 · Sideboom x1 · 9.0 h | Daily Plant and Labour!B24
28/08/2026 12:02 | Jerry KH |  |  | Daily Safety |  | 31/08/2026 · toolbox Yes · 9 on site · Nil | Daily Safety!B12
28/08/2026 12:02 | Jerry KH | 87014.4 |  | Daily Profit |  | 31/08/2026 · earned $87,014, cost $12,684, profit $74,331 | Daily Profit!B12